## sheet 1
|  |  | Inspection and Test Plan - Cycle Railing (Supply & Installation) | [8 empty] | Document # 1145-C200-FUL-QAC-ITP-0020
[12 empty] | Revision: | 00
Client: MRPV |  |  | Construction Process: Cycle Railing (Supply & Installation) |  |  | Prepared by: |  |  | Reviewed by: |  | Approved by:
Project: Craigieburn Road Upgrade |  |  | Standards: AS5100.2, AGRD, Part 6A, BTN 006 January 2018, BTN 008 June 2018 |  |  | Name: Mike Freeman |  |  | Name: Mike Freeman |  | Name: Dirk Slabbert
Contract No.: 1145 |  |  | Structure / Component: Bridges & Culverts |  |  | Position: Special Projects Manager |  |  | Position: Special Projects Manager |  | Position: Completions Manager
|  |  | Location: Site-wide |  |  | Date: 31.05.2024 |  |  | Date: 31.05.2024 |  | Date:3.06.2024
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
ConQA Team Notes:
Document Title: |  | ITP-STR-Bicycle Railing (Supply & Installation)
ITP Description: |  | Bicycle Railing (Supply & Installation)
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 00
Revision Date: |  | 31.05.2024
ITP created by: |  | Mike Freeman
ITP approved for use by:
Special Notes to ConQA Team : |  | ITP to be visible for all sites
Inspection & Test Plan - Cycle Railing (Supply & Installation)
|  |  | Document No.: | 1145-C200-FUL-QAC-ITP-0020 |  |  |  |  | Revision: | 00
|  |  | Specification: | [5 empty] | Date: | 2024-06-05
|  |  | Other Referenced Documentation: | AS5100.2-2017, BTN 006 January 2018, BTN 008 June 2018
Austroads Guide to Road Design, Part 6A: Paths for Walking & Cycling
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Preliminaries - Materials
1.1 | Railing Components | IFC Drawings Manufacturer's Drawings & Installation Recommendations AS5100.2 AGRD, Part 6A, Clause 5.5.3 Fulton Hogan Quality Management Plan | Where applicable, product to be selected based on the following criteria: Mounted on SUPs and veloways: i. height to rail between 1.2m & 1.4m Mounted on bridges and culverts: ii. able to withstand the load conditions iii. height to rail 1.4m minimum (on bridges and culverts) Details of the nominated proprietary system to be submitted for review to the Superintendent. Enter: Teambinder Material Approval number [free text box] | Document Review | Each component | IP | PE/SE/SPE | This ITP
1.2 | Fixing Detail | IFC Drawings BTN 006, Clause 2.3 BTN 008, Clauses 2.4.3 & 2.4.4 Manufacturer's Drawings & Installation Recommendations | Fixing detail to be either positive connection via cast-in ferrules or similar. Bonded anchors are subject to approval from the Superintendent on new structures. Changes to the above shall be accompanied with a PE Certificate. Note: Mechanical anchors shall not be used as they will be subject to tensile loads. Enter: Teambinder Approval number [free text box] or Attach: PE Certificate of Compliance | Document Review | Each component | IP | PE/SE/SPE | This ITP
1.3 | Base Plate Bedding (non-structural) Grout or Mortar | IFC Drawings Manufacturer's Drawings & Installation Recommendations | Where applicable, product to be selected based on the following criteria: i. have a trowelable consistency ii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of product | IP | Superintendent | This ITP
2 | Preliminaries - Procedures
2.1 | Certification of Installers | BTN 006, Clause 3 680.06 | Where applicable, all bonded anchor installation crews and direct supervisory personnel shall either be: i. listed on the "AEFAC Certified List of Installers"; or ii. trained by the Supplier of the bonded anchor system. Evidence of either is to be submitted to the Superintendent. Enter: Teambinder Approval number [free text box] | Document Review | Where applicable, once, prior to commencement of Works | WP | Superintendent | This ITP
3 | Pre-installation Activities
3.1 | IFC Drawings | Fulton Hogan Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
3.2 | Materials Inspection Checklist | IFC Drawings Fulton Hogan Quality Management Plan | General inspection of railing components for defects including cracks, handling and storage damage & distortion. Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues. Complete: Materials Inspection Checklist in ConQA | Measure Visual | Each component | IP | SE/PE/SPE | This ITP
4 | Installation Activities
4.1 | Bearing / Mounting Surface Preparation | Manufacturer's Drawings & Installation Recommendations | As a minimum, ensure that the bearing surface is clean and free from loose particles and laitance. | Visual | Each post location | IP | SE/PE/SPE | This ITP
4.2 | Railing Handling | Manufacturer's Drawings & Installation Recommendations | The method of handling and erection of the steel railing shall ensure that the components are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings. | Visual | Each component | IP | SE/PE/SPE | This ITP
4.3 | Railing Erection | Manufacturer's Drawings & Installation Recommendations | Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown on the IFC drawings or Manufacturer's Drawings and installation recommendations. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely. Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs. Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia | Measure Visual | Each component | IP | SE/PE/SPE | This ITP
4 | Installation Activities (Continued)
4.4 | Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S) | IFC Drawings Manufacturer's Drawings & Installation Recommendations | Place bolts, washers and nuts as detailed on the drawings. Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm. | Measure Visual | Where applicable, each bolted connection | IP | SE/PE/SPE | This ITP
5 | Post-installation Activities
5.1 | Inspection of Coating | IFC Drawings Manufacturer's Drawings & Installation Recommendations | After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure. | Visual | Each component | IP | SE/PE/SPE | This ITP
5.2 | As-built Survey | IFC Drawings Manufacturer's Drawings & Installation Recommendations AS5100.2 AGRD, Part 6A, Clause 5.5.3 Fulton Hogan Quality Management Plan | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: Mounted on SUPs and veloways: i. height to rail between 1.2m & 1.4m Mounted on bridges and culverts: ii. height to rail 1.4m minimum (on bridges and culverts) Attach: Survey As-builts / Survey Report | Document Review | Each component | IP | Surveyor SE/PE/SPE | This ITP
5.3 | Non-conformance Report (NCR) Closure | Fulton Hogan Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /