## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-020-A2-LOT-XXX - Desc | itp |  |  |  |  | ITP 0020 - Cycle Railing (Supply & Installation)
section | 1 - Preliminaries - Materials
checkpoint | 1.1 - Railing Components
label | Reference:
label | IFC Drawings
label | Manufacturer's Drawings & Installation Recommendations
label | AS5100.2
label | AGRD, Part 6A, Clause 5.5.3
label | Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Acceptance Criteria: Where applicable, product to be selected based on the following criteria:
label | Mounted on SUPs and veloways:
label | i. height to rail between 1.2m & 1.4m
label | Mounted on bridges and culverts:
label | ii. able to withstand the load conditions
label | iii. height to rail 1.4m minimum (on bridges and culverts)
label | Details of the nominated proprietary system to be submitted for review to the Superintendent.
textbox | Enter: Teambinder Material Approval number
label | - - - - - - - - -
label | Method: Document Review
label | - - - - - - - - -
label | Frequency: Each component
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: PE/SE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
checkpoint | 1.2 - Fixing Detail
label | Reference:
label | IFC Drawings
label | BTN 006, Clause 2.3
label | BTN 008, Clauses 2.4.3 & 2.4.4
label | Manufacturer's Drawings & Installation Recommendations
label | - - - - - - - - -
label | Acceptance Criteria: Fixing detail to be either positive connection via cast-in ferrules or similar.
label | Bonded anchors are subject to approval from the Superintendent on new structures.
label | Changes to the above shall be accompanied with a PE Certificate.
label | Note: Mechanical anchors shall not be used as they will be subject to tensile loads.
textbox | Enter: Teambinder Approval number
label | or
label | Attach: PE Certificate of Compliance
label | - - - - - - - - -
label | Method: Document Review
label | - - - - - - - - -
label | Frequency: Each component
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: PE/SE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
checkpoint | 1.3 - Base Plate Bedding (non-structural) Grout or Mortar
label | Reference:
label | IFC Drawings
label | Manufacturer's Drawings & Installation Recommendations
label | - - - - - - - - -
label | Acceptance Criteria: Where applicable, product to be selected based on the following criteria:
label | i. have a trowelable consistency
label | ii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
textbox | Enter: Teambinder Material Approval number
label | - - - - - - - - -
label | Method: Document Review
label | - - - - - - - - -
label | Frequency: Once, for each product, prior to placement of product
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Superintendent
label | - - - - - - - - -
label | Verifying Documents: This ITP
section | 2 - Preliminaries - Procedures
checkpoint | 2.1 - Certification of Installers
label | Reference:
label | BTN 006, Clause 3
label | 680.06
label | - - - - - - - - -
label | Acceptance Criteria: Where applicable, all bonded anchor installation crews and direct supervisory personnel shall either be:
label | i. listed on the "AEFAC Certified List of Installers"; or
label | ii. trained by the Supplier of the bonded anchor system.
label | Evidence of either is to be submitted to the Superintendent.
textbox | Enter: Teambinder Approval number
label | - - - - - - - - -
label | Method: Document Review
label | - - - - - - - - -
label | Frequency: Where applicable, once, prior to commencement of Works
label | - - - - - - - - -
label | WP
label | - - - - - - - - -
label | Responsibility: Superintendent
label | - - - - - - - - -
label | Verifying Documents: This ITP
section | 3 - Pre-installation Activities
checkpoint | 3.1 - IFC Drawings
label | Reference:
label | Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Acceptance Criteria: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | - - - - - - - - -
label | Method: Document Review
label | - - - - - - - - -
label | Frequency: Prior to starting Works and at regular intervals
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: All
label | - - - - - - - - -
label | Verifying Documents: This ITP
checkpoint | 3.2 - Materials Inspection Checklist
label | Reference:
label | IFC Drawings
label | Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Acceptance Criteria: General inspection of railing components for defects including cracks, handling and storage damage & distortion.
label | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | Complete: Materials Inspection Checklist in ConQA
label | - - - - - - - - -
label | Method: Measure, Visual
label | - - - - - - - - -
label | Frequency: Each component
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
section | 4 - Installation Activities
checkpoint | 4.1 - Bearing / Mounting Surface Preparation
label | Reference:
label | Manufacturer's Drawings & Installation Recommendations
label | - - - - - - - - -
label | Acceptance Criteria: As a minimum, ensure that the bearing surface is clean and free from loose particles and laitance.
label | - - - - - - - - -
label | Method: Visual
label | - - - - - - - - -
label | Frequency: Each post location
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
checkpoint | 4.2 - Railing Handling
label | Reference:
label | Manufacturer's Drawings & Installation Recommendations
label | - - - - - - - - -
label | Acceptance Criteria: The method of handling and erection of the steel railing shall ensure that the components are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
label | - - - - - - - - -
label | Method: Visual
label | - - - - - - - - -
label | Frequency: Each component
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
checkpoint | 4.3 - Railing Erection
label | Reference:
label | Manufacturer's Drawings & Installation Recommendations
label | - - - - - - - - -
label | Acceptance Criteria: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown on the IFC drawings or Manufacturer's Drawings and installation recommendations.
label | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
label | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
label | Holes shall not exceed the greater of:
label | 1.25 x bolt dia. OR bolt dia. + 8mm
label | Slots shall not exceed the greater of:
label | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | - - - - - - - - -
label | Method: Measure, Visual
label | - - - - - - - - -
label | Frequency: Each component
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
checkpoint | 4.4 - Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | Reference:
label | IFC Drawings
label | Manufacturer's Drawings & Installation Recommendations
label | - - - - - - - - -
label | Acceptance Criteria: Place bolts, washers and nuts as detailed on the drawings.
label | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | - - - - - - - - -
label | Method: Measure, Visual
label | - - - - - - - - -
label | Frequency: Where applicable, each bolted connection
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
section | 5 - Post-installation Activities
checkpoint | 5.1 - Inspection of Coating
label | Reference:
label | IFC Drawings
label | Manufacturer's Drawings & Installation Recommendations
label | - - - - - - - - -
label | Acceptance Criteria: After installation Works are complete, inspect the steel element for damage to the coatings.
label | Where damage exists, it shall be repaired using an approved repair procedure.
label | - - - - - - - - -
label | Method: Visual
label | - - - - - - - - -
label | Frequency: Each component
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
checkpoint | 5.2 - As-built Survey
label | Reference:
label | IFC Drawings
label | Manufacturer's Drawings & Installation Recommendations
label | AS5100.2
label | AGRD, Part 6A, Clause 5.5.3
label | Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Acceptance Criteria: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | Mounted on SUPs and veloways:
label | i. height to rail between 1.2m & 1.4m
label | Mounted on bridges and culverts:
label | ii. height to rail 1.4m minimum (on bridges and culverts)
label | Attach: Survey As-builts / Survey Report
label | - - - - - - - - -
label | Method: Document Review
label | - - - - - - - - -
label | Frequency: Each component
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Surveyor, SE/PE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
checkpoint | 5.3 - Non-conformance Report (NCR) Closure
label | Reference:
label | Fulton Hogan Quality Management Plan
label | - - - - - - - - -
label | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | - - - - - - - - -
label | Method: Document Review
label | - - - - - - - - -
label | Frequency: Once, prior to closure of this lot / element / Work area
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
label | - - - - - - - - -
label | Verifying Documents: This ITP
checkpoint | Final Inspection
note | On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Date:
date | Work Completed On