## Resources
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | FH-ZU2-QU-ITP019 - Spray Seal Placement - Rev 0 | itp | ITP019 - Spray Seal Placement | 022de526-11af-4f7e-8005-bc5dfa939fcb
| section | 1.0 - Preliminary Works
| checkpoint | 1.1 - Check for Correct Documentation
0338091b-6849-5e91-ab24-288d05799d5a | note | Frequency - Prior to commencing works
f1c4bcfa-15fd-5082-b518-2f6bfe1a3c25 | note | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors. Current revisions of these documents to be obtained via Aconex or ACC.
56761984-8b52-53a8-8822-50c863d43498 | note | Reference Documents - Current Revisions in Aconex or ACC
099c6cc3-ecd8-5d83-943e-4562fd5208bb | note | Inspection/Test Method - Verify
ade0a277-7020-5d2a-94b7-a292ef5478ea | note | Record of conformity - This ITP signed
341e8386-6719-57f2-9a54-37739b8f945d | note | HP*
19df1e36-01d3-55c7-becc-a83a2fa2c7cd | note | Responsibility - Project / Site Engineer
9349017d-0618-575c-bdb4-e285fd401f19 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
d1bf2877-da5f-5876-b9fc-c31847f95bea | note | Frequency - Prior to commencing works
4e20f32d-dc92-5a56-b3c1-2592d032165b | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS.
f0514b64-ef11-5406-929d-d307acb2e68d | note | Reference Documents - PSP, EMP, TMP, SWMS, WMS
c5f9c362-259a-5a8a-bbd2-7ebdb8121eac | note | Inspection/Test Method - Visual Inspection
33394019-6e12-5d23-b044-82b76ee325ec | note | Record of conformity - This ITP signed
8b086da5-1a28-55e3-9f11-214f144f4571 | note | HP*
07c91057-9fde-53ba-8f80-73b73e39e6df | note | Responsibility - Project / Site Engineer
da1eeaf7-6b98-5193-a3b1-5f6458c1cc1d | date | Date Completed:
| checkpoint | 1.3 - Plant & Equipment Check
52451bc8-8fa5-5227-98c8-d3d0deb939fb | note | Frequency - Prior to commencing works
24b5ade8-68a9-5ac8-8c5c-b3ad20d181d6 | note | Acceptance Criteria - All equipment shall comply with VicRoads Section 408 and VicRoads Bituminous Sprayed Surfacing Manual.
83e8ea0d-fb35-5495-bcd6-9dca4a47221c | note | Reference Documents - Beca Spec 002 - 12.3
89d0dc0a-2ecd-5b17-a449-754396782cf9 | note | Inspection/Test Method - Verify
cb9e460a-9837-53ce-8921-e8afd339d828 | note | Record of conformity - This ITP signed
62f23a0d-83b7-5f21-9d28-1247cadf1ffe | note | HP*
0383f368-68bb-55dd-bbec-c764949d16a5 | note | Responsibility - Project / Site Engineer
db217685-0cc4-532c-8d74-629561e88330 | date | Date Completed:
| section | 2.0 - Materials
| checkpoint | 2.3 - Material Approval
36048218-ebba-5b75-bc93-16bd0d21a04b | note | Frequency - Prior to Works
9588d36e-1d96-5a41-8af8-fd13ad0ea4f6 | note | Acceptance Criteria - The binder used shall be class 170 residual bitumen complying with AS 2008.
9938bcd9-e8ca-5533-953c-1bc2616e5baa | note | ○ All aggregates used shall comply with VicRoads section 801 and 831. Material and Test Reports to be submitted to the Principal’s Representative prior to commencement of works.
c3abd480-94e4-5797-ab62-34fda3bddc67 | note | Reference Documents - Beca Spec 002 - 12.6.1.1 to 12.6.1.3
03b20b15-37cb-53e4-96e6-3c6595c4898c | note | Inspection/Test Method - Verify
6ad33181-3bc4-5705-a55a-b1b9497ff0a0 | note | Record of conformity - Test Reports, This ITP signed
cf0e6f2b-dc71-5d10-a3eb-9f65f11eeb28 | note | HP
53ae5648-9273-5cc6-ac92-b31bb6c24af3 | note | Responsibility - Project / Site Engineer, Principal’s Representative
6440aab1-856c-57ff-bc25-7f7131fba383 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 - Construction
| checkpoint | 3.1 - Underlying Surface
3eebee34-1fbe-5403-8c42-4d4010c12a81 | note | Frequency - Prior to works
c419e70b-0b7b-5980-bce7-7cf2a80ae7fa | note | Acceptance Criteria - The pavement surface should be cleaned to remove all mud, carried on material, dirt and dust.
12e9e198-9b63-5054-8528-6b47f4eeeb04 | note | ○ After cleaning the surface should be swept with a suction sweeper, supplemented by hand brooms where required. Seal coat should only be applied to a sound clean dry surface.
35b9ca1f-8b6b-5878-9d6f-9221cb439ce7 | note | ○ Preparation of the underlying surface shall be approved by the Principal’s Representative.
0ac039db-423e-5f23-9e6f-c0268094e410 | note | Reference Documents - Beca Spec 002 - 12.4.1 to 12.4.5
3f8554d4-dc75-5643-8404-1463684c4e6c | note | Inspection/Test Method - Verify
f0ceec3a-c604-532f-871e-a530b25eb790 | note | Record of conformity - This ITP signed
c1d1704e-a365-5d2e-b5db-817215969479 | note | HP
416e0906-13a6-5ba4-b20b-b4087b73c12d | note | Responsibility - Project / Site Engineer, Principal’s Representative
f8a2683b-6a39-5341-9d92-90c14da8a1d5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Binder and Aggregate Application
46d85ea1-c304-5100-9c87-246ff6a83c14 | note | Frequency - During works
6a161514-f2d1-5174-9d98-2c10b3b48112 | note | Acceptance Criteria - Application rates shall be:
fe593034-64be-54d4-90d4-5c3eaaf31146 | note | ○ Binder: 0.8 – 1.0 L/m2
9d2c2fa6-d5e5-5f58-ae4b-3ff7166eb06f | note | ○ Aggregate: 8 – 10 kg/m2
a9f893e6-e430-59e5-8f3d-4782d9c75631 | note | Reference Documents - Beca Spec 002 - 12.6.2
e608d166-4c9c-5617-8ef6-8875835087e6 | note | Inspection/Test Method - Verify
c53d96b2-ca83-5b49-8488-179c251e1ddf | note | Record of conformity - This ITP signed
80c1be45-e4cd-5346-88de-53cd36ff02be | note | IP
087e4ab6-8a1e-5869-bdab-146f2b456660 | note | Responsibility - Project / Site Engineer
2c140901-e263-550e-8106-6da5f1b5b88f | date | Date Completed:
| checkpoint | 3.4 - Aggregate Spreading
360de500-a0c3-58ae-9e44-5cf64aec2ab6 | note | Frequency - During works
da6cba42-dc9a-5cc3-9313-f781c145627d | note | Acceptance Criteria - All aggregate spreading shall be undertaken using forward aggregate spreading and discharge plant.
361fa8c1-eba4-54dd-a451-62c80444a098 | note | Reference Documents - VicRoads Section 408 – 408.13(e) to 408.13(f)
19f40917-c682-5fb4-9902-726e9cfce912 | note | Inspection/Test Method - Verify
010672fc-b6b3-55d1-b9b5-768da0e2f368 | note | Record of conformity - This ITP signed
66a42d9e-9912-5e72-9f9f-47009903b973 | note | IP
6215b40e-1dbd-5998-b4df-ae2088f5401c | note | Responsibility - Project / Site Engineer
aa9fb1ce-a68d-5e5f-a943-677b79c35632 | date | Date Completed:
| checkpoint | 3.4 - Rolling of Aggregate
a43d4bb9-7058-5eea-ac7b-e5e628da8ef4 | note | Frequency - During Works
4518b789-9bf4-5581-beaa-0a0d4b093079 | note | Acceptance Criteria - Rolling of aggregate shall be undertaken over the full width of the pavement being sealed. Works to be undertaken by static rubber tyred rollers or otherwise approved by the Principal’s Representative.
7c58c4b2-29ab-5815-beca-47873a10793e | note | Reference Documents - VicRoads Section 408 – 408.13(g)
45fabd6d-a208-5ad3-8128-0653884c352b | note | Inspection/Test Method - Verify
8c9decdd-5dac-55ef-848f-12c23e105859 | note | Record of conformity - This ITP signed
9cea5468-74c7-5703-8b8e-8c1e4381a91e | note | IP
e6d83783-27c5-5256-8396-4ffbb37c539d | note | Responsibility - Project / Site Engineer
c3225380-19dd-5012-9895-f56263b181d2 | date | Date Completed:
| checkpoint | 3.5 - Removal of Loose Aggregate
df14e7ab-bcbd-5004-af25-98c10d4ea0bf | note | Frequency - During Works
2a630df0-8c56-5d37-b998-cda5d3b73777 | note | Acceptance Criteria - At completion of sprayed seal treatment, the Contractor shall remove and dispose of all loose aggregate.
5abe8ced-7041-5092-9364-153adfb962f6 | note | Reference Documents - VicRoads Section 408 – 408.14
3cf93853-d5c7-5a59-9fb3-9c10d57b585d | note | Inspection/Test Method - Verify
a991d669-89b6-58dd-8128-79458c7a112b | note | Record of conformity - This ITP signed
c943f80d-44fc-5e60-b513-0646f5af80fd | note | IP
ce475f64-84c9-5d22-8531-52ebc44d3971 | note | Responsibility - Project / Site Engineer
ce7b8f6e-0579-5c75-980b-5f694f011b25 | date | Date Completed:
| checkpoint | Final Inspection
32497480-f3b1-5c2f-8a18-88a7a7a743b6 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
7628e703-c3b0-571d-b220-426fddfe55fc | textbox | Print Name:
90716a2d-8ead-50b9-91c7-b9f6ab0813d3 | textbox | Position:
d8ed759e-5f16-58e0-9e77-a58513e6c30d | date | Work Completed On:
bcae2680-09f7-5058-abb3-53df76875256 | date | Date:
| checklist | FH-ZU2-QU-ITP007 - Precast Drainage Structures - Rev 0 | itp | ITP007 - Precast Drainage Structures | 402839a9-e811-488c-99cd-5670e095de16
| section | 1.0 - Preliminaries
| checkpoint | 1.1 - Check for correct documentation
5db1b43a-1481-53e1-8de3-6d2f2dc31855 | note | Frequency - Prior to commencing activity
1a76d17f-abc3-50a3-b63a-504f13b3a613 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
0d8d158f-73f0-5a63-b5b1-81123ed6bfe9 | note | ○ using the correct and complete set of drawings.
bbdc7d62-c614-531d-9e87-93061dcfdf4b | note | ○ all drawings are the latest revision.
2cceb0a1-7ceb-5f46-90ba-44ce40a286b7 | note | Reference Documents - IFC Drawings
57e73c5b-8753-5f96-9e6b-7503760b523e | note | Inspection/Test Method - Document Review
3453148d-86f9-55d1-9874-e84456f23411 | note | Record of conformity - This ITP Signed
f2aebf2b-e43a-5cb6-b55f-8253f262294f | note | HP*
31f3edd6-0a74-5ffd-994f-63f47528d216 | note | Responsibility - Project/Site Engineer
9b90ffe2-5c62-5bad-b57d-2238a6456e16 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
7db392a2-fa21-5236-8c16-e9900da3e150 | note | Frequency - Prior to commencing activity
f4083910-855f-57c0-9147-6a80de365aa0 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS & WP.
06f95c10-fae3-5fe3-ab27-fe120bb891db | note | Reference Documents - CEMP, TMP, SWMS & WP
8a3feeb6-5bce-57be-b8e7-c3078292fad6 | note | Inspection/Test Method - Visual Inspection
016a468e-f575-5630-a16d-5dfbd4f4075a | note | Record of conformity - Site and Office Inspection
a0e8ae7d-3b8c-58c4-9d58-ac3382dc190e | note | HP*
bb752f86-d03a-511d-84ff-723e46cdeb21 | note | Responsibility - Project/Site Engineer/Supervisor
dba43527-ddff-57f6-bb82-05b51bf52559 | date | Date Completed:
| checkpoint | 1.3 - Excavation Permit
b22648d9-7d02-580d-85cd-cdbdcad4c8ac | note | Frequency - Prior to commencing activity
191cd235-416b-56c4-ae45-ba847c9b457a | note | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
3fd46ef3-909e-574d-bc0a-517872f8ebd0 | note | Reference Documents - Approved Permits
aed208a1-ac7a-596e-9042-0a061c81d802 | note | Inspection/Test Method - Verify
83a18917-fc0f-5b77-80ab-116c9821c0b8 | note | Record of conformity - Proof of permit & ITP signed
5d722d91-8a36-5933-b731-3c1675a16b46 | note | HP*
2368bad9-cb75-5cf3-a8ba-657e6c725e1b | note | Responsibility - Project/Site Engineer
70234546-ef16-5344-83b2-265b140986d3 | date | Date Completed:
| section | 2.0 - Material Approvals
| checkpoint | 2.1 - Precast Structures
ab58fa24-f116-51e1-bb56-2a5a9c8ec0a2 | note | Frequency - Prior to commencing activity
cf5ed991-6585-57b3-b911-3d0f86fa22e2 | note | Acceptance Criteria - Details of the proposed precast drainage pits, headwalls, and culverts to be as specified on the IFC Drawings.
bdd411b2-4986-53fb-b73b-7e7c7000d1e2 | note | ○ Approval of the shop drawings constitutes a Hold Point.
dc249841-c08f-5a5f-af73-76dbf53cd354 | note | – Outline of sampling and test program
fed5492d-1da5-53b7-a7cf-795b5d8a04cc | note | Reference Documents - Cl16.6.1 & Manufacturer's documents
1301e68d-a0a5-5b05-bcea-f42d62c4a43f | note | Inspection/Test Method - Document Review
727e61f8-7fd4-50b5-a15d-86daf5052d56 | note | Record of conformity - Aconex Correspond ence
0599f0ff-d4c6-5ff8-8896-4d09cc6f8ea3 | note | HP
60e01000-b791-57e5-bb2f-4f7d4d1ff2ac | note | Responsibility - Project/Site Engineer
2794c579-9153-5731-8224-ae2a4141554f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Access Cover and Grates
ee79c773-1a56-5fe8-899f-c58377ade254 | note | Frequency - Prior to commencing activity
738d9405-acdd-56c8-ba83-7a8e734ab43c | note | Acceptance Criteria - All Pit covers to conform to AS 3996 and the applicable load class to be as noted on the Drawings.
fa10de75-6a4c-5fb4-a5fb-5874320a4794 | note | ○ For all drainage pits, pit lids are to be Class D.
e579fe7a-accd-5bed-91df-d69f754eb26c | note | Reference Documents - Cl16.5.7.1 & IFC Drawings
ec5278a1-6e0e-5f5b-b066-f574f2cc1a35 | note | Inspection/Test Method - Verify
26f47815-84b6-555e-8d46-79bb5eaf571e | note | Record of conformity - This ITP Signed
01dc8e7e-e7f0-55ad-8db3-4ececbf30b27 | note | HP*
bd40906a-f0ca-51cc-ad66-83ab99c6018f | note | Responsibility - Project/Site Engineer
bb342a11-5224-5e4d-95e4-d782fb070f5c | date | Date Completed:
| checkpoint | 2.3 - Box Culverts Bedding, Side, Overlay and Backfill Zone Materials.
688061a6-81b0-559a-8250-397751cc1678 | note | Frequency - Prior to commencing activity
f4a418bf-6ffb-5a9d-aba5-c09c320a74ba | note | Acceptance Criteria - Materials are to be compliant with the requirements detailed in Cl.16.5.6.
38053ff1-cd39-5fdf-8ce8-f5930d7b639e | note | ○ Material submission approval.
16451f44-84f4-5e7c-9a14-7a0da0f8e1d3 | note | Reference Documents - Cl16.5.6 & 16.6.2.2
30b99241-d916-525a-bfc3-2d08052484b7 | note | Inspection/Test Method - Document Review
2eb85dda-ae6a-50fa-bbfb-e924fb5d65de | note | Record of conformity - Aconex Correspond ence
bb4d22c6-594e-5e4e-a331-0681ccdd570c | note | HP
7fcdd18b-5de0-57e4-9b71-aaa4a4660761 | note | Responsibility - Project/Site Engineer, Beca
08680424-9ec9-592b-8546-d45754dd8cba | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Blinding for Drainage Pits and Headwalls
2cdc4b40-de5a-5ded-8076-77119d0265f3 | note | Frequency - Prior to commencing activity
a24482b1-7c81-59d4-a748-46579e1d29c8 | note | Acceptance Criteria - Approved bedding material as per IFC Drawings.
783bb8e2-be87-5037-9220-8c38c2c4dd3c | note | Reference Documents - IFC Drawings
f44ffccd-5943-5302-aed5-53db29ae97ce | note | Inspection/Test Method - Document Review
63f4a899-fbd9-5678-a97e-10b5d6ed1165 | note | Record of conformity - Aconex Correspond ence
e90d6749-9565-5df0-b4c1-b94133094ae9 | note | HP*
930504cd-e750-5cfb-b16e-1becd7073c2d | note | Responsibility - Project/Site Engineer
11bca55f-d813-5454-a26b-d1954d7f4432 | date | Date Completed:
| checkpoint | 2.5 - Geotextile Fabric
0951a30d-bcd5-5f82-bef2-ba9a2aad8644 | note | Frequency - Prior to commencing work
f891fcef-102e-5a05-8555-ad08670e8ccb | note | Acceptance Criteria - Non-woven type complying with the requirements of VicRoads for first stage filter.
24b2885c-192f-549e-802c-228765e85054 | note | Reference Documents - Cl.16.5.8 & VicRoads Section 702
c630faca-13d4-560f-830e-3f4aa85bed97 | note | Inspection/Test Method - Verify
1294c6fe-f4d9-590b-9f86-0f6f852ba88a | note | Record of conformity - Visual Inspection & Delivery Docket
c0d53522-9130-5af2-a8d7-de0dc81e3b98 | note | IP
4dba0165-a49b-5344-86bc-0d5dd9ac3264 | note | Responsibility - Project/Site Engineer
b2b17873-ad3d-59da-a630-c012a3d50118 | date | Date Completed:
| section | 3.0 - Material Receival
| checkpoint | 3.1 - Precast Structure Delivery
510d066f-aaad-521c-acd0-6ab33d93d77d | note | Frequency - Each Lot
dd9eb527-123d-5ff3-8a1d-3dc9615eb7ee | note | Acceptance Criteria - Ensure each precast component is inspected upon arrival ensuring:
07b2c205-7888-5b47-92a6-db01e80e6c1d | note | ○ Dimensions are as shown on manufacturer drawings.
7cc21e09-88cc-50a3-9e6f-0ca3fb4973b0 | note | ○ All blockouts in correct positions and to dimensions.
135c1ef7-713d-5cc5-ba69-8ad6e14a1ce1 | note | ○ No damage to any precast structure component to the satisfaction of FH Engineer
8d9ffef1-ea02-531e-8f73-963f781550bf | note | ○ No modifications to the pits are to be made without written approval from manufacturer.
5074dbb4-fe4f-5a86-8c38-d55d527c200c | note | ○ Manufacturer’s conformance report
6d2e38b7-5e7a-579b-98aa-27efa490fb76 | note | Reference Documents - Cl16.6.1 & IFC Drawings
16726ebd-142c-5e2d-94c3-c144f08e5ef2 | note | Inspection/Test Method - Visual Inspection
315da72d-1ceb-58aa-8eff-c1fd0d60823b | note | Record of conformity - Order Acceptance Form
59a9abc0-badd-59c7-8e34-ca95cacf72b3 | note | HP*
0f267815-5dc3-5586-9e6c-2588f0be04e8 | note | Responsibility - Project/Site Engineer
9b599835-4289-5d69-b59b-6d98ad2786ab | date | Date Completed:
| section | 4.0 - Drainage Pit, Headwall and Culvert Installation
| checkpoint | 4.1 - Survey Setout
96f73f4c-1ddb-5ecf-8655-9ec86c40c259 | note | Frequency - Prior to construction and each lot
80120edb-cad5-57b6-b432-a9dfba621b6a | note | Acceptance Criteria - Set out the drainage structures as shown on the Drawings to identify the locations, lengths and levels:
eaaa0d90-e5de-575a-bd91-aeb0a7373072 | note | – All pits, and inlet and outlet structures.
c40a009b-6410-5c62-97aa-7dbe26d35a79 | note | – Ends of wing walls and headwalls.
15456013-b6fe-5a16-8b34-9444a9a3f601 | note | – At outlets and inlets of box culvert structures.
739131ea-764e-5029-b752-a70fa5c75714 | note | ○ Setout of each drainage system to constitute a Hold Point.
6c41b77b-65df-5b8e-9a67-f535ee05e9e9 | note | Reference Documents - Cl16.7.1
1f07cdb5-abfd-522c-b9e8-564f84f66c66 | note | Inspection/Test Method - Survey
16a01d25-681e-5993-bc13-59adf1d5e086 | note | Record of conformity - This ITP Signed
219b5388-f45e-56f4-a1df-a87748de4426 | note | HP
14944d7e-92c0-52a4-bacf-e90676402f30 | note | Responsibility - Project/Site Engineer, Beca
fa7a906f-cd3c-519d-84f4-67963423f62e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Excavation
1176e267-a531-5cdd-b74e-306ee86a5a72 | note | Frequency - Each Lot
e374136f-55f7-5a35-86e5-f75d59b8c3a4 | note | Acceptance Criteria - Excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material.
1a9ec8b6-abbe-5c22-9433-db8811c2a6dd | note | ○ Inspection of completed excavation works to constitute a Hold Point.
d8d48fdc-af48-5f58-80f8-c3a8dd8d7a41 | note | ○ Pits: The shape of the excavation to be as required and the size sufficient to enable construction of the structure.
dde9fb29-d00c-5e0f-80d9-470fd164b600 | note | ○ Box Culverts: The width of trench to be not less than the exterior width of the culvert plus 400mm, and not greater than that required for satisfactory backfilling.
ccdb8dbb-6936-568e-baa8-372a04b9834d | note | Reference Documents - Cl16.8 & Cl 16.6.2.2
c5d4529e-db4c-5d84-959d-20a5f2f5efb7 | note | Inspection/Test Method - Verify
d9f522df-c5ed-5ac9-9d83-0fa5b613c708 | note | Record of conformity - This ITP Signed
571c1da6-a91a-5fa3-a70c-66ec3ae68a74 | note | HP
c6c80ad7-00a7-5073-908c-c069c67ae74c | note | Responsibility - Project/Site Engineer, Beca
94484256-bf2c-5fd8-b6dc-a6317e71bd2a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Confirm Ground Conditions
b8d350c1-8ff5-5b96-973a-67f22efdb856 | note | Frequency - Each Structure
20e25821-d580-5c2e-b669-b1ad3bb75e5f | note | Acceptance Criteria - Min. 1 x DCP test to be undertaken per drainage line / structure to confirm ground conditions. If the first DCP is inconclusive or fails, additional DCP to be taken as needed based on on-site assessment of the ground.
36164437-c5cf-56ae-9d48-c40a20b3ed9a | note | ○ Contractor to notify the Contract Administrator of any area of the foundation with inadequate material to support the proposed drainage structure. Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, as per note 4 on drawing ZULU-BECA-012- DWG-07102.
2f1f7b49-708c-5f8c-a252-fe31b08cae2d | note | ○ Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent.
2350b2d8-7113-5a27-a640-aeecc9cfcaee | note | Reference Documents - Cl16.8.2 & Tender Clarification #38
ea4ce89e-4f55-53c5-bd51-7609dc2a8f82 | note | Inspection/Test Method - Site Inspection
2423809a-6b01-53b2-8e5b-8dd890b86fdd | note | Record of conformity - DCP, Test Results
06e8b35d-cbaa-523b-9400-83dc0bda6785 | note | TP
6c53e3f2-cb75-566e-aa85-9477e2f68835 | note | Responsibility - Project/Site Engineer
0414f3d0-9444-5ffb-b0fa-d989cc17b6be | date | Date Completed:
| checkpoint | 4.4 - Blinding for Drainage Pits and Headwalls
bcad1afe-016b-5246-927e-c5f03a90f683 | note | Frequency - Each Lot
b55575d8-14b3-5e3f-8751-50467135ca28 | note | Acceptance Criteria - Blinding to be installed as per the depths and widths shown on the Drawings.
45ac2b98-d9a1-5003-b229-0a8f31ab2df2 | note | ○ Pits: 50mm Crushed Rock bedding
89a61e11-443b-50b1-8d5a-9700e1abaa68 | note | ○ Headwalls: 100mm 15MPa Concrete blinding and 600x150mm apron cut off wall
ebd7362e-49bf-5a7b-9ffb-9e0d8661adbc | note | Reference Documents - IFC Drawings & VicRoads SD
0e10937e-f79f-5a21-a6a5-a510f354efb2 | note | Inspection/Test Method - Verify and Visual Inspection
7f27ad83-67f0-59e9-b805-d75ab259c9b1 | note | Record of conformity - Delivery Docket & This ITP Signed
dc4048a4-91fe-5f55-ada0-70be55bd2a52 | note | HP*
d9ac6299-f974-558c-b572-02ef9cc116d3 | note | Responsibility - Project/Site Engineer
f8ec5fdd-ff5b-5701-9419-f7ff43c7b7ef | date | Date Completed:
| checkpoint | 4.5 - Bedding for Box Culverts
f6104982-9dea-5959-98f6-70237c3d3dd8 | note | Frequency - Each Lot
4fa34d6c-f014-5a38-beb1-1c3e335ffd31 | note | Acceptance Criteria - Bedding material to comprise of approved select fill and to be placed for the full width of the trench.
42c26375-9a6c-569e-9359-fb0c5cfd5717 | note | ○ Upon completion, the bedding is to provide a uniform firm foundation with the top surface of the bedding shaped to the details shown on the drawings. This to constitute a Witness Point.
14025ba8-9afd-54e8-be08-4d2e8e8a27af | note | Reference Documents - CL16.5.6. 1
20d97cde-028a-5067-846d-c4bcc652d396 | note | Inspection/Test Method - Verify and Visual Inspection
18606999-4387-52e4-a1c1-37ccd808471b | note | Record of conformity - Delivery Docket & This ITP Signed
f52e261e-1bef-5aa7-8741-0bb3dabc2c2b | note | WP
61c2e6db-e12f-5367-ad8e-43d826fcc22d | note | Responsibility - Project/Site Engineer Beca
34b4a718-4ed3-563b-bec5-2a949aab05dd | date | Date Completed:
| checkpoint | 4.6 - Positioning of Precast Structures
11f1ce0f-933d-5c66-b10d-8ca75e1a0230 | note | Frequency - Each Lot
cc95c182-f51a-5dd3-8794-6c3a70be63aa | note | Acceptance Criteria - Precast structures installed as per survey set out points marked on blinding / bedding layer
df1710e5-23d8-5ac6-b0a9-32a51a5dfb01 | note | Reference Documents - Cl.16.8.1 & IFC Drawings
52618993-76b4-5fe0-b5ec-760dd3780ed4 | note | Inspection/Test Method - Verify
d0e4ca64-9106-55b0-a47a-48a846c16bf7 | note | Record of conformity - This ITP Signed
62ffd668-108d-5f05-a822-06fac03094e8 | note | IP
5ef51f22-b49d-5375-87c3-b02487c59eac | note | Responsibility - Project/Site Engineer
ac26066b-3fa6-50e3-bf9c-b1f302782640 | date | Date Completed:
| checkpoint | 4.7 - Backfill Materials for Box Culverts
f797f376-3caa-58b0-bd53-dfce5ebb7902 | note | Frequency - Each Lot
4fa89b10-99b2-50e1-818a-1cb940c0473e | note | Acceptance Criteria - Side Zone, Overlay Zone and Backfill Zone Subject to Vehicle Loads
d2e1e579-fd48-5bdc-aee0-64eb6b1073a6 | note | ○ Approved Select fill material.
068414fc-e61e-512c-b7b3-bd93288de40b | note | ○ Completed in layers with maximum thickness of Cl200mm loose material.
29ef28c6-caad-5e95-a851-4720cb916273 | note | Overlay and Backfill Zone – Not Subject to Vehicle Loads
39bc908f-7787-552e-9edc-bcd4afe87479 | note | ○ Ordinary fill material compliant with Cl.16.5.6.3 of Beca’s specification
5f59707d-fbdf-5d92-aa4c-011a03990d19 | note | Reference Documents - Cl.16.5.6 & IFC Drawings
04391806-868e-55c2-967c-a5a34dd0621a | note | Inspection/Test Method - Verify and Site Inspection
f87b33fe-04c5-5d60-8d00-8d73cafd1cb8 | note | Record of conformity - This ITP Signed
32827412-ef03-5eae-97ff-c2b0e931a375 | note | IP
23df4aec-6efa-5a2b-bcf0-63d5419c08b5 | note | Responsibility - Project/Site Engineer
3d43666e-c673-5375-aaad-1c98ed6901b8 | date | Date Completed:
| checkpoint | 4.8 - Compaction Requirements (Box Culvert)
98400f66-d4ff-57da-81dd-2aa44bd1cdbf | note | Frequency - 1 test per lot.
e82ad8bb-5d63-55ba-b493-617779f660fa | note | ○ "1 test per layer of bedding for bedding materials and every 2nd layer for side, overlay and backfill zone materials."
6505258c-50fe-5498-909a-6ec23215c323 | note | Acceptance Criteria - Bed Zone – Minimum 90% SMDD
cdbf78aa-742b-5d44-acd4-73ad8c9d8c0a | note | ○ Side Zone Not Subject to Vehicle Loads – Minimum RD of 95% SMDD
224642d9-8551-5dfa-9f37-38db447150ec | note | ○ Side Zone Subject to Vehicle Loads – Minimum of 95% SMDD
7185abd0-f6b6-5e6d-9992-fe193d868633 | note | ○ Overlay Not Subject to Vehicle Loads – Minimum RD of 90% SMDD
20b777a5-0948-5cab-a93d-a92f0a9be3d4 | note | ○ Backfill Zone Not Subject to Vehicle Loads – Minimum RD of 90% SMDD
a6406e74-85d9-50e7-bb1f-e5c15ddfa32d | note | ○ Overlay and Backfill Zone Subject to Vehicle Loads – Minimum 95% SMDD. Top 300mm under pavement to a minimum of 98% SMDD.
c3136cf7-8b38-5165-872c-2c5d937abe76 | note | Reference Documents - Cl.16.5.6. 1 (b) (iv)
db9b4411-efa6-5856-af78-2ea2b9335782 | note | Inspection/Test Method - Site Inspection
f82995cc-38b0-5b15-a358-a96ca9566be0 | note | Record of conformity - Test Records
473aac9c-b16d-5edb-bb4d-33375d1f8a79 | note | TP
d5d91f95-4800-5240-bfec-fc3ad1f31973 | note | Responsibility - Project/Site Engineer
af50add4-63eb-5738-b5a5-38eb32e83ab0 | date | Date Completed:
| checkpoint | Final Inspection
4bfba408-c2c7-5b13-a5b6-2aac8afb6c80 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
bd8aa650-6082-5eb0-9fb1-0784fb190a53 | textbox | Print Name:
07933e25-3d1e-5871-b20e-a61376c04a4e | textbox | Position:
94923ded-cd73-539a-81ee-c1c46804e037 | date | Work Completed On:
9c06ea5a-c74f-5bfa-9993-ce5fe6ee7f38 | date | Date:
| checklist | FH-ZU2-QU-ITP003 - Stripping Topsoil and Bulk Excavation - Rev 0 | itp | ITP003 - Stripping Top Soil and Bulk Excavation | 5645e9f5-3660-4c90-a71c-b1ba3bd279a6
| section | 1.0 - Preliminary Activities
| checkpoint | 1.1 - Check for correct documentation
b0bf35cf-bf6c-5dcc-bc41-0235c9052364 | note | Frequency - Prior to works
e04509c7-936f-53e0-8fb6-f7bcc1a327ea | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
fdc5d8e3-669e-5553-b761-b07e1a397496 | note | ○ Using the correct and complete set of drawings.
48eb929d-4aad-5b25-ae8d-1d7116fe3a1a | note | ○ All drawings are the latest revision
6ca6d629-4784-5861-a79c-4c0ba3d6f4eb | note | Reference Documents - Aconex
dd16b1cc-ab12-505c-a2b7-7bb53fe3bd1d | note | Inspection/Test Method - Visual inspection
2d9a6b90-f30a-5624-8211-191e8989370d | note | Record of conformity - This ITP signed
cc09c387-0c2f-5dda-adea-a8ef80176672 | note | IP
ea4975d0-50ea-5d69-bb76-c1968543b9ce | note | Responsibility - Project/Site Engineer
cf4ecca4-eaeb-5bec-9d03-95e47a4cca08 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
a1c6b7af-0051-5b47-adee-2ba83b1e11a9 | note | Frequency - Prior to works
0fbcefe2-64ad-51a3-9613-d315fef28308 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP.
e4c9d16e-a953-5b9b-9a45-8877156edfba | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
7d8cb712-2e8a-5a0d-a8b0-c44a5c45ec04 | note | Inspection/Test Method - Visual inspection
d25d94ff-7601-53b0-919b-c613f70f2323 | note | Record of conformity - This ITP signed
b7a0ec80-5f8e-587f-834b-1d098369588f | note | IP
0a63dfdf-bbf5-580e-a8d0-ae9bf172ca29 | note | Responsibility - Project/Site Engineer
72eda7e5-1afb-5c67-acd8-196c3e10781d | date | Date Completed:
| checkpoint | 1.3 - Survey
b28ddb15-dca5-55f8-87fa-e72f19e92a7a | note | Frequency - Prior to works
8f6fc471-c5ab-56c6-92c3-cdc17da61ba1 | note | Acceptance Criteria - Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone).
895ea11a-326a-5b69-9652-f24fcd91fd48 | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
d8337aa2-37fe-515d-b4f3-1bacfc84dc3c | note | Inspection/Test Method - Visual inspection
7717e169-d754-5552-bb9d-d4f6f8d10b45 | note | Record of conformity - This ITP signed
eb0c37fb-eed5-5944-85a7-b335db33ccc5 | note | IP
fd3a1bf8-2181-59f0-ac7e-d79f06a26e54 | note | Responsibility - Project/Site Engineer Surveyor
bf4564b4-0f61-503c-bcf3-02eccb92fc4f | date | Date Completed:
| checkpoint | 1.4 - APAM permits
f25c9f2a-2ac1-560f-9017-7b5a7084fae8 | note | Frequency - Prior to works
24dd5cb6-1f04-5f82-a4dd-46e652983d3d | note | Acceptance Criteria - Excavation permit issued. If working near HV electrical, an Electricity supply Isolation form and cabling permit has been issued from Melbourne Airport.
9212205d-6ac3-54ab-8fc9-fee1a896df2e | note | Reference Documents - Excavation permit
c8d42d6b-eab7-5cb6-8755-e20453f295ab | note | Inspection/Test Method - Approved permits
cd6b0421-3dd9-5c4c-b73a-de6b1c4ef85c | note | Record of conformity - This ITP signed
8c0fd384-a553-5a21-86d2-9c2ae1ecfe59 | note | HP*
d444af54-ebc2-5cb7-8451-2ffc6d07021f | note | Responsibility - Project/Site Engineer
8be9d07d-a5ae-5841-b757-795c9b56f251 | date | Date Completed:
| checkpoint | 1.5 - Fulton Hogan Permits
46947f88-5c71-5c7e-b717-22cd2b1a7fc2 | note | Frequency - Prior to works
71e0ef47-8be4-5ac0-962e-604e87161e84 | note | Acceptance Criteria - Fulton Hogan Excavation permit issued to plant operators prior to excavation works. Native Grass heatmap issued and boundary of working area has been set out.
6f1796c9-4d05-53e0-bdde-821c5592e2a9 | note | Reference Documents - Excavation permit
d8325656-3f12-56e1-b210-0d4b6ceac6e5 | note | Inspection/Test Method - Approved permits
4967b778-ff83-52d9-ba59-8cdfef0f275f | note | Record of conformity - This ITP signed
286d6d2b-0311-53eb-ab23-9f4d05737f61 | note | HP*
e52bf27e-db56-57ab-bf83-dafe2c698d6d | note | Responsibility - Project/Site Engineer
eee46c57-60e0-571e-a3f7-97999f76db52 | date | Date Completed:
| checkpoint | 1.8 - Plant and Equipment
725e528d-8b52-5ff5-85fb-0ada1e94e3c8 | note | Frequency - Prior to works
85884f2f-55a6-5be8-9305-0ab219e520c7 | note | Acceptance Criteria - Plant and Equipment used in the works are appropriate to achieve specifications requirements. All plant inducted and inspected as per Fulton Hogan’s plant safety guidelines.
0c019c51-0614-53a0-a154-a2497f8f1c0a | note | Reference Documents - WMS - 003
49aa4a47-fa8b-5fc8-9e34-53bd8059363b | note | Inspection/Test Method - Visual Inspection
6f0ef1fb-f190-53d8-bb13-c894ce09a267 | note | Record of conformity - This ITP signed
1200834b-44a9-5646-b802-8fb932cef07a | note | HP*
acb14978-a615-5ab1-b64f-c6ca52037d13 | note | Responsibility - Project/Site Engineer
d2181fa4-4cd9-5c12-8779-31f6d7c56cc6 | date | Date Completed:
| section | 2.0 - Stripping / Bulk Excavation
| checkpoint | 2.1 - Site Preparation
e27a247b-1e88-5f51-a280-e8299a920aef | note | Frequency - Each lot
0a25fe0f-b005-5d68-9994-e63d04d72117 | note | Acceptance Criteria - All excavation and filling will be free draining to low points clear of the Works. Sufficient pumps, well-points or other equipment for work area de-watered during the works shall be provided where required. Existing drainage lines and water mains found to be traversing the site must be removed as shown on drawings. Contractor must provide temporary pollution control devices or ponds in existing drainage systems and receiving waters.
fb794ab0-50c9-5a06-9d65-96021ddcebff | note | Reference Documents - ZULU- BECA-001- DWG-00001 to ZULU- BECA-005- DWG-01119
57f65844-de94-507d-8927-bfcd2dc9e32f | note | Inspection/Test Method - Visual Inspection
de7135f9-ef45-53c4-a19f-d3aee6734303 | note | Record of conformity - This signed ITP
1e268370-06e4-51b0-93f7-5fe806d0e603 | note | IP
fdf1cd7f-ee62-5ff2-92da-3766f85b1d48 | note | Responsibility - Project/Site Engineer
a585c59e-e787-55aa-92e0-4d29ff87e6d7 | date | Date Completed:
| checkpoint | 2.2 - Dust & FOD control
4d67a5f8-2cd4-5cd9-9125-ce8a13c6a8e4 | note | Frequency - Each Lot
9d8de3bf-fc2b-5dc9-a674-f8c8cc422829 | note | Acceptance Criteria - Prevention of dust during earthworks and subgrade preparation. Sweeper onsite at all times to manage dust / FOD.
4ad3cfa1-c539-5aed-8a56-1a9ecdfb9de9 | note | Reference Documents - Site ECP
c801db41-4373-5367-9606-050abb383544 | note | Inspection/Test Method - Visual Inspection
ffd00528-9efe-5abc-885c-e0a0693ef0cd | note | Record of conformity - This signed ITP
191ac37f-fb65-59aa-9cf7-0486937f3484 | note | IP
8e80ef2a-479d-5ee0-bfd4-90df9d4824b1 | note | Responsibility - Project/Site Engineer
58934db1-aab0-59e1-af23-b9571dc42add | date | Date Completed:
| checkpoint | 2.3 - Stripping Top Soil
a2cb99da-1e4a-5761-888c-818826c7f6f0 | note | Frequency - Each Lot
795111e8-641b-57d4-817c-253a3653277c | note | Acceptance Criteria - Prior to bulk excavation, site shall be stripped of all topsoil and organic matter as shown on the drawings. Spoil to be taken to Gate 11.
e90c0149-9f06-5f8a-befe-fb458a02b66b | note | Reference Documents - WMS - 003
58244c20-c81e-55b3-810d-ca191ccd8952 | note | Inspection/Test Method - Inspection Point
544ed1e8-6d34-59ab-93b7-0c67e29edcbe | note | Record of conformity - This signed ITP
b8aec92e-8e8a-5dac-95b4-9a205065a43a | note | IP
b77161e9-7ad9-5ed9-bb01-df12fda98a3b | note | Responsibility - Project/Site Engineer
f8d6de4d-e30d-5464-bfc8-fdf096736fcf | date | Date Completed:
| checkpoint | 2.4 - Excavation
655ef21e-d583-540b-b0e8-1ae4f87f9ef6 | note | Frequency - Each Lot
fd71f423-e2b8-53ba-bbee-19f9db30e125 | note | Acceptance Criteria - Bulk out subgrade to 100mm of subgrade. If rain is imminent, ensure subgrade is left 100mm high prior to trimming.
c7cc11d3-553d-5d81-b8f0-0f6f1407a670 | note | ○ Rocks Under <800mm can be taken as mixed fill to Gate 11
623c6037-b637-5187-982a-aec791a42130 | note | ○ Rocks >800mm to be sorted and taken to Vic Civil
00c8d2f8-9d2e-5735-9cec-8d01d06b07aa | note | Reference Documents - WMS – 003 Spec 001 - Cl8.5.3
14dccc02-a646-50f9-8f6d-32f24959c516 | note | Inspection/Test Method - Inspection Point
5d396ef6-eb80-5b2a-b64b-d36b8ef0cd6f | note | Record of conformity - This signed ITP
f0aa852a-6306-543b-81bf-7bb4fe5f8563 | note | IP
5d0cec04-02dc-5c0f-8bfd-6084f48216a9 | note | Responsibility - Project/Site Engineer
55143d0a-4292-5671-8588-0096dd2b279b | date | Date Completed:
| checkpoint | 2.5 - Batters & Temporary Support
0078066f-7ff2-5a7e-8bd0-f096e2d634ee | note | Frequency - Each Lot
a9d660c2-8e06-58b0-819c-137e62261509 | note | Acceptance Criteria - All batters to be kept at 1:1. If not, temporary support will need to be designed, engineer and approved for use. Temporary support will remain in place until it is no longer required.
29b426b8-1462-5593-8f23-9614a99f34eb | note | Reference Documents - WMS – 003 Spec 001 - Cl8.5.3
126bb257-8287-5830-aac8-804f9eb9a3ce | note | Inspection/Test Method - Inspection Point
2c813702-c8eb-5da1-a4cc-6123c2135816 | note | Record of conformity - This signed ITP
087bd442-d3ce-5bd3-a28d-e96e359893d3 | note | IP / HP* (if required)
391bd648-17fe-558b-a9e4-f3742978176b | note | Responsibility - Project/Site Engineer
5b4b410e-8682-530d-bb89-ffc8cee3cc2a | date | Date Completed:
| checkpoint | 2.6 - Excavation – Detailed Trim
409c906c-8df3-5ce5-baed-d2848aa53b27 | note | Frequency - Each Lot
6c4e7036-00b5-55de-ae66-e0e7d66c0a00 | note | Acceptance Criteria - Detail trim Subgrade with excavator / dozer
261f738f-711f-58c1-9b34-cd5f799091d7 | note | Reference Documents - WMS - 003
c48ff060-151e-56f8-8dbd-337de1a3b9d6 | note | Inspection/Test Method - Inspection Point
857f60cb-c4f5-52c7-a914-3d2c5f25ef5e | note | Record of conformity - This signed ITP
d00655ce-58a8-571d-a4f0-17a5c069092c | note | IP
2e518698-e4ba-51be-a036-130fbe55bbbe | note | Responsibility - Project/Site Engineer
b7c1f4d5-948f-56cc-8b7f-1d61781f5e30 | date | Date Completed:
| checkpoint | 2.6 - Contaminated Materials (if found)
67d60ac1-c767-5cea-b33a-9c957fe6607c | note | Frequency - Each Lot
7449cf1a-8fdd-5cbe-ae73-f35efccbcd1c | note | Acceptance Criteria - If contaminated or hazardous materials are found, immediate notice is to be given to the Principal’s Representative. These include the following;
18a1b02f-fa5f-5c4b-b29e-8f690d0c20a9 | note | ○ Asbestos or material containing asbestos;
0e601b8e-85e3-5a48-a95a-ce16b3c42b43 | note | ○ Flammable or explosive liquids or gases;
2ffaae20-313d-56b8-af17-0013db1ffe64 | note | ○ Toxic, infective or contaminated materials;
62627aff-bf7a-5503-aaa0-559e22ae8235 | note | ○ Radiation or radioactive materials;
07a861b9-fcc3-52fa-867a-fdd1a56a7642 | note | ○ Noxious or explosive chemicals; and
ea990217-0df6-564d-b132-aaf6c7ce482c | note | ○ Tanks or other containers which have been used for storage of explosive, toxic, infective or contaminated substances.
37992f1d-ea50-5adf-8ffe-baa1ff457dd3 | note | ○ High levels of PFAS
2b53e1b2-cddd-5f0b-ad08-820e0dc38a18 | note | – Agreed removal location to be confirmed with Principles Representative.
9480a3e7-6a36-5ce4-ae96-c773283c46a8 | note | Reference Documents - WMS - 003
c114f601-e3b3-5150-891f-fd79140ee62f | note | Inspection/Test Method - Inspection Point
544d69e3-e333-556a-a981-ea4bfb155186 | note | Record of conformity - This signed ITP
a5480ed3-09c5-55d5-9668-ff3b1e52ce26 | note | HP*
1ec73940-2fe9-55e5-ae19-877a013ce1a4 | note | Responsibility - Project/Site Engineer
cae0531d-97c9-55cc-8a76-caf2995f702c | date | Date Completed:
| checkpoint | Final Inspection
b663b21c-3dfa-536b-b178-91b4f1c37e18 | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
ee31d79b-0f59-5a23-82d1-8fe5dd6ec31c | textbox | Print Name:
664f83e7-742d-544a-9d95-9b5f459e4f81 | textbox | Position:
b8ae34f3-9bd9-5e79-9bd4-5cef927f9b58 | date | Work Completed On:
3fe6fc4e-f7a1-5d0e-aa19-8fd21eac62dd | date | Date:
| checklist | FH-ZU2-QU-ITP008 - Lime Stabilisation / Subgrade Improvement - Rev 0 | itp | ITP008 - Lime Stabilisation Works | 5944a9b8-0892-4aee-a2d9-d710cab1086d
| section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Materials and Trials
| checkpoint | 1.1 - Check for correct documentation
f80ad63e-e054-58a6-a576-5a5156f8f8f3 | note | Frequency - Prior to commencing works
34372137-72c1-5b78-8857-0f4f56117113 | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex.
580de26a-94ed-5a77-9d34-68c0de8454b4 | note | Reference Documents - Aconex
5884289d-b391-508f-8f26-6eb97aee0dc9 | note | Inspection/Test Method - Visual Inspection
2221d813-5b0e-555c-b17a-b06903a82588 | note | Record of conformity - This signed ITP
1641ee97-6204-5c83-9048-3a8b6c09dcc5 | note | HP*
0916181f-7bd9-570f-ba06-450763029d6b | note | Responsibility - Project/Site Engineer
3a82f130-c2e3-5900-9703-54d723e73696 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
2c1d7258-8000-5b31-8f79-226a154efb79 | note | Frequency - Prior to commencing works
417cbc72-d3c4-5e70-9d6b-6d7fd9543fa3 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
f58b910f-8b97-58b0-9ec4-8d835fad21a5 | note | Reference Documents - PSP, EMP, TMP, WP SWMS
16c2ed29-62a0-56d2-a6bd-dcc04d5066c9 | note | Inspection/Test Method - Visual Inspection
c098280e-eab5-5450-82a7-3064d0f70f3f | note | Record of conformity - This signed ITP
4a2d40a3-38c1-5039-a5f4-dd646da1fe9c | note | HP*
cc8e0828-610c-5047-af96-86a758dd60ef | note | Responsibility - Project/Site Supervisor
17c04995-8757-5c6f-82eb-4b3d59be076c | date | Date Completed:
| checkpoint | 1.3 - Current excavation permit
48755452-95f8-5c14-a233-f2e1cf26d6fc | note | Frequency - Prior to commencing works
b01f95de-178b-54ed-aeb7-b45562fdd472 | note | Acceptance Criteria - An Excavation Permit and an Isolation permit issued by Melbourne Airport. Fulton Hogan Excavation permit issued to plant operators.
fbbb0ee7-a34f-5610-bf1a-f5a488b2f235 | note | Reference Documents - Excavation Permit
d7fb0750-fc55-58dc-9eed-a9c56f8dc487 | note | Inspection/Test Method - Visual Inspection
4d53328b-f3e0-5e07-9229-c4368426e0b3 | note | Record of conformity - Permits
a28cb457-3300-5049-a9dc-6df79138d9f1 | note | HP*
16159f6c-a4d3-5c8a-9ff3-26033da1286f | note | Responsibility - Project/Site Foreman
b1e6b55d-eb1d-59ed-94ef-517a38151dd1 | date | Date Completed:
| checkpoint | 1.4 - Preceding Lots Satisfactory
7b4d2be7-586c-5c08-92ec-a97afa14a7d4 | note | Frequency - Prior to commencing works
5a0cab34-2cd9-5151-83c4-bffc7a581e96 | note | Acceptance Criteria - Review ITP004 (Select Fill placement) and ITP003 (Stripping and bulk out) has been completed to a satisfactory level
d8e0fc77-3146-5441-a683-eca1b40121a0 | note | Reference Documents - ITP004, ITP003
11225a67-461e-574a-a52e-67f98e2149e9 | note | Inspection/Test Method - Visual Inspection
a50494c7-dc42-5d61-9716-1ad5c838a926 | note | Record of conformity - This signed ITP
c01588dc-e681-5eb9-ac50-cf96b17b44ea | note | HP*
947156b6-065d-5acf-b73c-792903b506a4 | note | Responsibility - Project/Site Engineer
2a7c5747-5127-549f-967b-707955a736f5 | date | Date Completed:
| checkpoint | 1.5 - Test Pits
7c8519cf-ff0c-5c02-aa96-9b158f5e6e29 | note | Frequency - Prior to commencing works
41a79849-3252-57fd-b30f-d4a68214ffbb | note | Acceptance Criteria - Test Pits have taken for the works area and suitable lime content parameters have been established. Test Pits should be taken at least one month prior to works beginning.
71daa2cc-6103-565b-b46c-98841bbca874 | note | Reference Documents - WMS003 – cl3.1.9
57acbe24-3046-54bd-bb53-a17a9127cecb | note | Inspection/Test Method - Visual Inspection
64134581-a21c-506b-99a9-d0d1c880f2a9 | note | Record of conformity - This signed ITP
ea9433d0-78af-51f7-94a0-b0b613798d59 | note | HP*
f22378cc-3fca-5bf0-b859-26e4d26a13d4 | note | Responsibility - Project/Site Engineer
545db90f-ab5b-53d7-bea8-b422883bd1d6 | date | Date Completed:
| checkpoint | 1.6 - Stabilised Lime Content
f2f31c7f-52ce-57ee-9395-40c354934c6f | note | Frequency - Prior to commencing
0e307209-0378-5981-9057-c4b66b6e204d | note | Acceptance Criteria - Stabilised Lime subgrade material shall have a minimum of lime content of 4% and a specified minimum strength of 20% CBR after 7 days of curing.
0ad1c593-f993-5554-b867-61a4f26394a8 | note | Reference Documents - Spec cl. 3.3
dfe53d81-bbca-5d9e-8f62-4e024c45e26c | note | Inspection/Test Method - Testing
21a7fda0-7769-5e6f-9181-6b849c545dfd | note | Record of conformity - Test results & This ITP signed
083f471c-d4f2-5af5-aaf9-70e82188470f | note | HP
cea4568a-f969-58c2-b43b-f9e846f19f75 | note | Responsibility - Project/Site Engineer, Principal’s Representative
d0ac1f16-ef5b-5c04-b294-6e28176e1e57 | date | Date Completed:
a36502c5-adb9-560d-a70d-678505437c86 | textbox | Principles Rep - Aconex Ref:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.7 - Stabilised Soil Trial
e3d0b6f7-6262-5ae7-a116-cdf8203cc42b | note | Frequency - Prior to commencing
2e2fcecc-d65e-5881-8a0f-c4e3d62082c6 | note | Acceptance Criteria - Trial of the Lime Stabilised Subgrade is greater than 500m2 to demonstrate that the Subgrade is able to meet the required specification.
d9320f77-f9cf-5415-aeee-ad3e50d4eeb0 | note | ○ If trial is approved and accepted by Principal’s Representative. Trial of Lime Stabilised Subgrade will form the completed Works.
764a3254-a6cd-5bb3-8d96-1553077c9681 | note | ○ Principal’s Representative to approve trial before commencing Lime Stabilised Subgrade placing.
c74c4ef1-a31a-5983-b31f-08be016efe25 | note | Reference Documents - Spec cl. 3.6
ee59310b-da9b-5b45-944b-c2caf07af9ba | note | Inspection/Test Method - Verify
97a2130d-f4a2-5239-b27e-9e5f00e946b7 | note | Record of conformity - This ITP signed
f0486ae8-36d6-593f-af18-abc1300c6ef1 | note | HP
f78d5313-a3c9-5c16-9805-4ae05ace1554 | note | Responsibility - Project/Site Engineer Principal’s Representative
8f783d79-6766-59c1-bb70-a94fb669fd07 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 - Subgrade Preparation & Replacement
| checkpoint | 2.0 - Pre-treatment of earthworks
62101956-cfd2-56c5-a143-4fcaba515afd | note | Frequency - Each Lot
ca2ab39e-38b8-5645-8e8e-460eeec59cf4 | note | Acceptance Criteria - Inspect subgrade that will require lime stabilisation.
f7698896-93d5-5474-af2c-25a6768a2d96 | note | ○ Subgrade that is excessively wet and/or contains rocks greater than 60mm to 100mm, subgrade will need to be removed and replaced with site won material.
449ef220-c86c-57a5-9b93-86589310e7a8 | note | ○ No testing or proof rolls required on replaced subgrade
e925ddb6-f95f-555d-bd8a-84e3a6919e3e | note | ○ Survey to for any excessive high and/or low spots. Fill / excavate spots as required.
6574d0fc-589f-501c-b9e6-d4e591f900c9 | note | Reference Documents - WMS008 – cl 3.2.1
d934765e-d9f6-599e-85ab-b2db351f6738 | note | Inspection/Test Method - Verify
2d74c1c7-55a6-5095-a646-e3a7e197179d | note | Record of conformity - This signed ITP
9c64b3e9-bc04-5d0a-b882-244b2a0eb039 | note | IP
6198c2fc-43cc-59eb-be6f-1ed67fefda31 | note | Responsibility - Project/Site Engineer
fc7a943e-af06-5ce0-ad19-febd7032786d | date | Date Completed:
| checkpoint | 2.1 - Rip Subgrade
0ed5f65f-3dd4-572f-b3f2-fc4a6da3a75f | note | Frequency - Each Lot
289ff85d-0e0f-52af-a6c4-b533252d1c95 | note | Acceptance Criteria - Prior to spreading lime, the subgrade is to be ripped and pulverised to at least 400mm
78a69a18-ef9f-5a5f-b19f-44f9a9e27cfa | note | Reference Documents - Cl3.7
07a86b6f-2f5c-53df-9cd7-e2343a34de4f | note | Inspection/Test Method - Verify
8ebee48c-0faa-5a95-8e7a-c814d37c73e5 | note | Record of conformity - This signed ITP
8987659c-3dd4-56df-8cee-3eafa73c79e0 | note | IP
0978e5f5-b066-569d-8337-01eadd85b626 | note | Responsibility - Project/Site Engineer
e412f8a9-a9a1-5572-a8f5-fca294ade8de | date | Date Completed:
| section | 3.0 - Layer Placement
| checkpoint | 3.1 - Layer Parameters
99e44411-a4ad-5fcb-830f-e0d514ee55f7 | note | Frequency - Each Lot
9668753c-07fd-5ae3-9a2d-500b9dad8b2d | note | Acceptance Criteria - Summary of Layer Parameters:
e7987681-aecf-5adf-9e89-02b191d8bde4 | note | ○ A Lot is defined as one days production
fddf2ea4-53ad-52e6-9b97-31c9a6cd1f6a | note | ○ Min depth of 300mm for PT01, PT03, PT08
0b2f3865-99cd-5ea6-a77a-5b4f53aada8e | note | ○ Min Depth of 400mm PT02
a12d4f6f-4b99-52bd-a159-699b10b67c91 | note | ○ Shape: <12mm over a 3.5m straight edge
042cf666-81dc-5ef0-a900-b9ebf2205b1a | note | ○ Surface Level: -25mm to +0mm
d55ac57e-4ef5-53a8-a429-8559b87327f8 | note | Reference Documents - Cl 3.16, Cl. 3.14.3
f37964be-4804-592f-8472-6ac8abb7c365 | note | Inspection/Test Method - Verify
b6018f76-a667-5ba2-857f-b65ce20ea6e5 | note | Record of conformity - This signed ITP
4244dc42-aa65-5ad0-b98b-0e643ce23f76 | note | IP
ee8912da-58a6-5c54-a045-2dcd5397f24e | note | Responsibility - Project/Site Engineer
70f4e856-2faf-59ca-9345-bdf1a240d1f2 | date | Date Completed:
| checkpoint | 3.2 - Prior to Works Starting
f09b7eeb-84a5-5d2c-a892-80da7ab3a55c | note | Frequency - Each Lot
8c0af34f-fa40-554b-af73-418ad7d50957 | note | Acceptance Criteria - Check weather forecast for rain and wind. Works to not beginning if rain is imminent. Works must not start or cease if wind increase over 15 knots.
e886f363-b2b7-5d65-a0d3-74b740221ef7 | note | Reference Documents - Cl3.7
428c7c0b-bcd8-5ef4-b124-ab659e25d26b | note | Inspection/Test Method - Verify
edea983b-1021-5459-87af-07fad8ad33ea | note | Record of conformity - This signed ITP
40298fdd-eece-5a4d-bf52-24aa79d1721d | note | IP
840a110e-9bae-54b5-b7b6-7aa8312005d7 | note | Responsibility - Project/Site Engineer
2097ba3d-a9c1-5756-a462-013f70a97ea0 | date | Date Completed:
| checkpoint | 3.3 - Spreading of Lime
78e2769e-331f-565f-ac61-b2172501c3a3 | note | Frequency - Each Lot
ee78259e-b187-553c-a8f8-a39f8b65891d | note | Acceptance Criteria - Lime to be spread uniformly over the prepared surface at the Lime spreading rate calculated.
33187a45-846e-52b6-ab6a-5d438b34c101 | note | Reference Documents - Cl3.7
ca0f43a1-fc2a-5041-9c08-4906d7047af9 | note | Inspection/Test Method - Verify
d8bc3daf-9fff-5d39-a2f3-3270cfd3f663 | note | Record of conformity - This signed ITP
0976379c-eeb2-55c7-91f8-d74f1929eb49 | note | IP
4ee44097-ec15-5b67-b8c6-59ed3780f975 | note | Responsibility - Project/Site Engineer
420033b4-467d-50e9-a35e-c3d53789f22b | date | Date Completed:
| checkpoint | 3.4 - Spreading of Lime
a75badb0-eb77-5a41-8fd7-57d54ba88ce7 | note | Frequency - Once Per Hour
b74e3e83-f0f3-54a3-affc-686b1d414fcc | note | Acceptance Criteria - Lime spread to be checked every hour and shall be with +/- 5% of the specified amount. An area to be checked is required to be not less than 1x1m2.
3390d410-7f7c-5242-8e9f-d6a14c96a9d9 | note | Reference Documents - Cl3.7
94907931-d99d-5f4a-9ed1-72a7bd40a53c | note | Inspection/Test Method - Verify
1d6bc099-7de6-521e-a53b-c1dc33af1031 | note | Record of conformity - TP
6bce729d-7697-5a49-bed7-d09bba0b0fdb | note | IP
ad236bae-a6ed-5aed-89d2-cbd80ce624e7 | note | Responsibility - Project/Site Engineer
704bcd53-dd10-5f8e-abf6-1d85f6e1e264 | date | Date Completed:
| checkpoint | 3.5 - Mixing
342dc891-c403-5f90-b824-bbf8f7a88c87 | note | Frequency - Each Lot
390ce6f2-6e8b-5b9c-af40-e7318e0b4f9e | note | Acceptance Criteria - All lime to be mixed to the specified depth within 8 hours of spreading. Mixing passes to overlap to ensure subgrade is mixed twice as a minimum.
cc5e43e5-aeea-5ebe-89e0-150f5c893321 | note | ○ Where possible, adjacent material will be placed within 1.5 hours of initial placement to avoid joints from forming.
1dffa4ef-977c-5200-9704-d4057650e30f | note | Reference Documents - Cl3.8
6bfe17ce-16bc-52bb-a1c0-3e907940d531 | note | Inspection/Test Method - Verify
e0aabdf2-0f0c-51bd-855e-f54daab64e09 | note | Record of conformity - This signed ITP
d0540783-c182-5522-b955-56420d6d484a | note | IP
994e21c9-ca3a-5509-a5a3-0cf0d1059d7e | note | Responsibility - Project/Site Engineer
9a5228ee-ec2b-5d18-8311-95a576bf01a8 | date | Date Completed:
| checkpoint | 3.6 - Mixing
c562766c-54bc-512f-8f72-d70eadefc4f0 | note | Frequency - Once Per Hour
c1f928cf-02bb-562e-8be8-3b04caaf0ac3 | note | Acceptance Criteria - Approximately every hour, mixing plant will record the depth of application to check compliance with the specification (300mm or 400mm).
ce08e854-5a2e-5f75-a0ce-ee62a04c30b8 | note | Reference Documents - Cl3.8
fddc46ec-5c36-548c-9341-af9ba77c9e32 | note | Inspection/Test Method - Verify
3718af78-1a8b-57a9-a532-0dea2ad1f0fc | note | Record of conformity - TP
6e7b5fd0-bb87-52f0-8aa3-de05d6a89a6a | note | IP
604b6d97-13ba-5a6c-a11c-15e0afee918b | note | Responsibility - Project/Site Engineer
9911afd3-d0e0-521b-bea9-867e1aa90967 | date | Date Completed:
| checkpoint | 3.7 - Joints
d260d097-aab9-5437-a478-470276285dfb | note | Frequency - Each Lot
87275da8-6c25-52f9-a6f7-98b66d093217 | note | Acceptance Criteria - Construction Joints when required, will be placed to ensure no single plane of weakness. Construction joints of adjacent lots will:
56b137d2-41f8-5edb-9b14-5cb2bf5b70bf | note | ○ Longitudinal Joints – Will be avoided by overlapping adjacent lime stabilisation mixing runs.
3ff60da7-8cef-5b45-aac3-88eb76284fb9 | note | ○ Traverse Joints – Will be staggered to avoid forming a single joint.
09fc5b76-e89a-55e9-91a1-304745c6f012 | note | Reference Documents - Cl3.13
4f5cf043-d1a6-5402-9422-ec3286759824 | note | Inspection/Test Method - Verify
0f8796f9-0f68-5d9d-911c-4dd0df554f39 | note | Record of conformity - This signed ITP
91fc4eb7-572e-5e1d-b5bb-73b2d8d06491 | note | IP
59a162e2-9def-5e63-800f-f58f1cd41a8f | note | Responsibility - Project/Site Engineer Foreman
71be9b34-2f3f-51e8-96e1-c87052da0403 | date | Date Completed:
| checkpoint | 3.8 - Compaction
98edc022-ce50-597f-a49e-fd5f9cd8f64f | note | Frequency - Each Lot
a802c0d7-976b-507a-82ab-78328487457b | note | Acceptance Criteria - After satisfactory mixing, compaction shall commence within two hours and be finished within eight hours of mixing completion. Additional moisture may be added if required.
4c8d3682-ad1a-5729-9c6f-2e04e34da9f8 | note | Reference Documents - Cl3.11
e5693786-39f2-5aae-81e9-a3617205b081 | note | Inspection/Test Method - Verify
e15bc505-3a49-52dd-9b7c-9ed1054f2c30 | note | Record of conformity - This signed ITP
43fc5fae-6188-59b1-82a8-c5d0d4f56eeb | note | IP
a7256504-2d31-5e6a-bb32-f6b1487cad93 | note | Responsibility - Project/Site Engineer
813850de-8025-5607-84f0-7cdf4c1621ec | date | Date Completed:
| checkpoint | 3.9 - Trimming
b2c11689-93f9-520e-b751-4b92349a7772 | note | Frequency - Each Lot
70ccdfdc-aa8b-545f-9f9d-36c5789170e9 | note | Acceptance Criteria - Surface to be trimmed to +0mm, -25mm
a4867d15-b3ab-57ac-b389-76f5f082326a | note | Reference Documents - Cl3.11
2c8e1993-e02f-5023-82c6-ff4971f7b99f | note | Inspection/Test Method - Verify
21f15f9a-1bae-52d8-9b6c-b7f6cf06e552 | note | Record of conformity - This signed ITP
e4704b06-5569-5e33-a586-8cc50ab7f1c9 | note | IP
1357d1c2-2430-5df4-85a6-b9c7d2652ddd | note | Responsibility - Project/Site Engineer
e44933a5-f7c7-5f2c-a310-b86a294811e4 | date | Date Completed:
| checkpoint | 3.10 - Protection
3a917592-6749-5df9-b2e0-1e85c23e2f6f | note | Frequency - Each Lot
e2b99457-d65b-54d8-8fef-e7c361627566 | note | Acceptance Criteria - As soon as lime stabilisation activities start, no construction plant to travel across works zone (other than those involved in the operation for 48 hours minimum.
2dd506ec-22c9-5e37-a1bf-fc4acf1eedc7 | note | Reference Documents - Cl3.15
17f9f7c3-91cc-5b6c-8462-621aa1bfd5a8 | note | Inspection/Test Method - Verify
a3d5d5de-4b52-5924-9d24-2c0b71b05c48 | note | Record of conformity - This signed ITP
e7639432-5a5f-5ccc-88ff-b79580bbf1c5 | note | IP
7e023d29-6b28-5d62-b994-407b63ef41fd | note | Responsibility - Project/Site Engineer
eb4df604-5d71-5666-8157-65e62f99e767 | date | Date Completed:
| checkpoint | 3.11 - Curing
f5d664e1-3302-5239-b31b-bb3d32877dae | note | Frequency - Each Lot
3634ecf6-60c9-5eb9-9428-1f7e010dcc54 | note | Acceptance Criteria - Curing shall commence as soon as practical. The curing period is 48 hours or until the succeeding layer is placed.
61592bc7-ee26-52a2-a062-6e051423a52d | note | Reference Documents - Cl3.15
7180bd48-55d1-52eb-bc1a-3e79860497ec | note | Inspection/Test Method - Verify
17d9e9eb-a333-5f92-a309-9d214f33daa2 | note | Record of conformity - This signed ITP
2ec1438f-9013-52d1-822b-308c154d145f | note | IP
02640a26-aa0f-5092-8fb2-64afa27ad078 | note | Responsibility - Project/Site Engineer
77d43f30-4dbf-58d2-86f2-a8ea53be2978 | date | Date Completed:
| section | 4.0 - Acceptance – Lime Stabilisation
| checkpoint | 4.1 - Proof Roll
2f9353b6-e54c-554e-8c1b-d099c954ad0a | note | Frequency - Each Lot
36368a93-d957-5fdf-89b4-f9e013b6bb09 | note | Acceptance Criteria - Following completion of the curing period, detailed trim and survey conformance, the Principle’s Representative will be invited to a proof roll (24 hours notice). Proof roll will be accepted if no rutting greater than 25mm is observed. Proof roll will involve using a heavy vibrating roller (in static mode)
c68d0f35-ea92-50b2-a8f9-67e617c28a42 | note | ○ Proof rolling of the subgrade will be approval to place Sub-basecourse or Basecourse. If rain falls on subgrade prior to placing next layer, a further inspection will be required.
01c1e634-186b-5a82-a4b8-b45d73df62b1 | note | Reference Documents - Cl3.12 Cl4.6
87be2623-dfbd-595f-891c-8be21e24dbf4 | note | Inspection/Test Method - Verify
18dcd2dc-0dc5-50c3-9665-7cd0923ebd3a | note | Record of conformity - This signed ITP
6fc411fb-3ae7-5906-8a89-562298867e11 | note | HP WP HP HP
d1fa4d52-e8b4-590a-968e-cf95e9142cce | note | Responsibility - Project/Site Engineer Principle’s Representative
66401dcd-82fa-5286-aead-1904100de9e2 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Surface Smoothness
837b0e22-2d8b-5699-84c5-515f36d75e55 | note | Frequency - Each Lot every 10m
de08aee8-f886-5796-a501-5eabd7247879 | note | Acceptance Criteria - Long straight edge surface not to deviate by more than 12mm over a 3.5m long straight edge, following subgrade treatment
55319a9f-9797-5e69-859e-50134128725b | note | Reference Documents - Cl3.16
16184e99-8bbd-5666-ad3a-1593c7749c5b | note | Inspection/Test Method - Verify
b9fa94eb-211f-52da-8503-97c347b9b63e | note | Record of conformity - This signed ITP, Results Attached
badb7c5b-c62c-5b51-9f76-70912fae58ac | note | TP
0789e41b-dcac-5f88-996d-89e182908747 | note | Responsibility - Project/Site Engineer
b79112a3-6ced-57fa-b89d-fddd9e664d09 | date | Date Completed:
| checkpoint | 4.3 - Strength Testing (CBR)
d85a453c-5089-51ed-954f-8e86db541710 | note | Frequency - Each Lot – Once per 1500m2
f5a104ee-3f30-5158-8fbb-ace6a4d16cbf | note | Acceptance Criteria - To exceed 20% CBR after 7 days.
dcfc4b1e-0919-542f-b37d-11d9d298b83c | note | Reference Documents - Cl3.16
9aafccc7-b587-5e41-9e41-508f824c8f8e | note | Inspection/Test Method - Verify
7d77674a-c72a-53e8-8a83-e1b6063b07ef | note | Record of conformity - This signed ITP, Results Attached
da13dbcc-c9e4-57d0-8957-1788082fb56b | note | TP
d639452d-ccd1-5669-8883-d3a580538630 | note | Responsibility - Project/Site Engineer
a45fc774-3ef6-57c2-b1f7-690c9bddcf71 | date | Date Completed:
| checkpoint | 4.4 - Field Dry Density
5b50c56a-2fb2-56de-a1a9-589bcd9b2868 | note | Frequency - Each Lot – Once per 500m2
13f56cac-10c3-5539-9859-e527e2da735f | note | Acceptance Criteria - Maximum Dry Density used is lime stabilised subgrade 100% using standard compaction.
f62b5305-d129-5dbc-bf9c-8ff4bafc6a11 | note | Reference Documents - Cl3.11 Cl3.16
92188a49-9e45-5703-b6e1-72394050c8e9 | note | Inspection/Test Method - Verify
458eb129-b3d5-54be-9309-1a51f9e67403 | note | Record of conformity - This signed ITP, Results Attached
f5b3e371-e308-5ab0-b6ae-b1becb453e47 | note | TP
a6ee8b2b-41ec-5e59-a54f-86f1f31451df | note | Responsibility - Project/Site Engineer
7fb847a3-e1dd-5c9b-871a-e52592ada559 | date | Date Completed:
| checkpoint | 4.5 - Surface Level
f264f4f4-7d4f-54d0-8b2f-52a809c0980a | note | Frequency - Each Lot
a9239d3b-556d-58a1-9f60-bb446b8a5ee5 | note | Acceptance Criteria - Stabilised and compacted subgrade surface layer to comply within -25mm to +0mm from specified levels.
dd91c709-302e-59a4-9b57-787abfb44091 | note | Reference Documents - Cl3.16
5c788dd4-2a4d-591d-bc3d-cf3bd5319e8d | note | Inspection/Test Method - Verify, Report
03035fda-fbdf-5aca-9ea7-6a19bf79a240 | note | Record of conformity - This signed ITP, Results Attached
a3606e88-472f-5d9d-8a9b-d3aa27803cec | note | SCP
22446a72-33e9-53a1-a9d8-daa4db972c79 | note | Responsibility - Project/Site Engineer
8536f0c4-4dcf-5494-a569-c3e75eed94ca | date | Date Completed:
| checkpoint | Final Inspection
77834e6f-6574-54f0-b03c-6bcabe6cb4dc | note | On behalf of Fulton Hogan, it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
e9b4af31-26aa-5a17-b1c7-baaf6919ffd1 | textbox | Print Name:
a304cf96-b429-5255-a2df-662eb05d02a4 | textbox | Position:
7de9a745-74e3-5528-8e04-9e99c94961b2 | date | Work Completed On:
fb9de0d3-dd9f-5aff-9a96-ab452a1610b2 | date | Date:
| checklist | FH-ZU2-QU-ITP006 - Subsoil Drainage - Rev 0 | itp | ITP006 - Subsoil Drainage | 620efb2d-bb1e-4b7c-bce3-9de8780204a5
| section | 1.0 - Preliminary Activities
| checkpoint | 1.1 - Check for correct documentation
b203efa7-9a22-5926-bd73-8de13b415a22 | note | Frequency - Prior to commencing activity
bbc090e4-5691-53ff-8630-4771d69f82b0 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
0bd51d55-9b65-50b8-b133-094970bffa42 | note | ○ using the correct and complete set of drawings.
2796cb7c-8938-5ce3-864e-aed637875e7b | note | ○ all drawings are the latest revision.
46916086-2b53-5d88-ad5d-4ec4e0b35143 | note | Reference Documents - IFC Drawings
2331c893-c1ca-5edd-a5bc-32cd368b8062 | note | Inspection/Test Method - Document Review
0c7059cd-7c8d-5927-b2a6-53aeda36e7f6 | note | Record of conformity - This ITP Signed
2a4ea12c-0fc8-5bf2-8321-e0e60a39e82b | note | HP*
62a43976-e7ef-5bb6-b3c4-d0f251e5ed9b | note | Responsibility - Project/Site Engineer
babe2d24-e642-593a-b977-cfdd507e634e | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
941dc993-a111-5574-9200-06146195396a | note | Frequency - Prior to commencing activity
40f86d52-0a66-57a8-890a-0408cd16eb95 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS & WP.
2e4953e3-5ca0-5ad7-8b53-475ec0eb0254 | note | Reference Documents - CEMP, TMP, SWMS & WP
c9883755-8c08-5007-a533-cc805d703693 | note | Inspection/Test Method - Verify
9f40c57f-8d81-5fbc-97cc-5cc438a222b3 | note | Record of conformity - Site and Office Inspection
d456838d-d521-5f5e-9814-6ebab7e168ba | note | HP*
13a3a736-2da8-5338-9439-c66cf07d0f9e | note | Responsibility - Project/Site Engineer/Supervisor
8d3617a0-ff7a-589c-97a6-7746d94759b0 | date | Date Completed:
| checkpoint | 1.3 - Excavation Permit
4621e442-d233-5395-83bc-ce811358abeb | note | Frequency - Prior to commencing activity
c10cec44-4414-5d8f-adad-794206ee4cef | note | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
6a9c7f96-9941-5267-b05e-e17eaf8ad66d | note | Reference Documents - Approved Permits
b7759b67-f929-5676-a29c-9f2d90988101 | note | Inspection/Test Method - Verify
f39f1bfc-9cd3-5716-a541-b40dbc723cf1 | note | Record of conformity - Proof of permit & ITP signed
7a6a615a-ed94-53da-aa6d-817b63f120c6 | note | HP*
178bd2a1-3ba0-50c6-afce-5996683f0817 | note | Responsibility - Project/Site Engineer
99112c83-d7a5-59d9-aef3-fc94599fd70f | date | Date Completed:
| section | 2.0 - Subsoil Materials
| checkpoint | 2.1 - Subsoil Drainage Pipes
5b646d98-aa7a-5836-ae73-381d8ebf1b62 | note | Frequency - Prior to commencing work
bcaec0c9-9031-5295-9942-dbf72084364d | note | Acceptance Criteria - Pavement Subsoils:
b7359a8d-0550-508d-8b02-ed66b1b36fc1 | note | ○ 100mm Dia slotted with filter fabric (sock) CL1000 SN20.
d5a93f8c-7cf5-5dd9-ac9b-3357d03174ae | note | Subsoil Collector Pipes:
b092e40d-b547-5be0-99d7-08a0a40cc028 | note | ○ AGL Carrier Pipe: 80mm Dia PN12 uPVC Non-Perforated Pipe.
c71454fc-b17e-5349-9e45-7aa67f16c22d | note | ○ SSD Carrier Pipe: 150mm Dia PN12 uPVC Non-Perforated Pipe.
0fe68566-15e7-5f87-ac33-ea7c86b3cb4d | note | Reference Documents - Cl.16.5.3, Cl.16.5.4 & IFC Drawings
7db0c490-ad5b-577f-af6c-8253694d2b26 | note | Inspection/Test Method - Verify
7b19fdb1-45b4-5c3e-8438-1738fb265c3e | note | Record of conformity - Order Inspection Checklist
5a52b1f3-475b-5840-a3fe-5ad3d836fb4e | note | IP
6a41afaf-d4b0-56ae-9cde-29297e7b2dbc | note | Responsibility - Project/Site Engineer
7e10c348-b168-547c-b344-2948e99a3363 | date | Date Completed:
| checkpoint | 2.2 - Bedding and Backfill
0a65b798-f2a0-50d4-8a54-048370d7f9e6 | note | Frequency - Prior to commencing work
65490841-89f8-52b9-a6c8-0e6ade8c75c5 | note | Acceptance Criteria - Subsoil Drain Pipes Under Pavement
8d673ba2-f482-50d9-8e8d-01e35ea81db5 | note | ○ Holcim’s 5mm Moriac Sand or approved equivalent.
ea074592-f6e0-5276-8ecf-09e2aa464e5e | note | Subsoil Collector Pipes – Under Pavement
90d57a37-66c0-5a63-9a00-37a0d5ea31cb | note | ○ Approved 5MPa lean mix.
0a750720-2d3c-5829-b0b1-43f7a714381f | note | Subsoil Collector Pipes In Grass
f6feccc3-2a5b-5c58-8c91-7bc66bc2ac4e | note | ○ Holcim’s 5mm Moriac Sand or approved equivalent.
a375508d-7a04-5b79-a062-dd33308b9ec0 | note | ○ Excavated Soil
0be3036b-e5c3-5cd3-94d1-82069d58357c | note | Reference Documents - IFC Drawings & VicRoads Section 702
192a4443-013d-5350-bee7-1ced123affd2 | note | Inspection/Test Method - Verify
04805040-cf54-5fbd-ab74-74d27943c596 | note | Record of conformity - Visual Inspection & Delivery Docket
12a91005-a1ce-5115-9639-3ff57f494a39 | note | IP
75b3b35e-138d-55f3-86be-0386538781c7 | note | Responsibility - Project/Site Engineer
977a00fc-306d-59b1-9a0a-2ac71d410998 | date | Date Completed:
| checkpoint | 2.3 - Geotextile Fabric
1f00f2b1-23ff-5d29-ad30-843835eca1db | note | Frequency - Prior to commencing work
3654a3b6-f2a4-5ef2-a001-4d0b5aca6d9b | note | Acceptance Criteria - Non-woven type complying with the requirements of VicRoads for first stage filter.
e7938520-5e9f-54bc-91a5-5d8faeca7148 | note | Reference Documents - Cl.16.5.8 & VicRoads Section 702
cbdc78d0-0722-54da-8205-b90cc9af3622 | note | Inspection/Test Method - Verify
447ec906-7210-5a3a-a5f3-6f908f3d604c | note | Record of conformity - Visual Inspection & Delivery Docket
0c6a5fea-3afd-512c-8368-a5417aef9492 | note | IP
f8fe6ab3-b47f-56cd-a396-18119f9ec08b | note | Responsibility - Project/Site Engineer
d3362b11-23dc-5195-9144-10052d55416a | date | Date Completed:
| section | 3.0 - Excavation and Installation
| checkpoint | 3.1 - Trench Excavation
93bdb9fc-556e-5244-9d83-f6783c956641 | note | Frequency - Each Lot
8c640fb9-21ba-520b-a95f-471abad2330d | note | Acceptance Criteria - Trenches shall be excavated to the minimum depths, widths and batter slopes as shown on the drawings.
56f6e280-b7f1-5fd9-a677-7c644276b746 | note | Minimum Trench Widths:
43759727-e5da-57a1-af50-b01cf3d394bb | note | ○ Subsoil Drain Pipes
43e28dc1-5a6a-5792-b73e-e85f01e8c46f | note | – 300mm total width for the subsoil drain pipe (DN100).
af2bffd1-df6b-5b82-83e6-861c7441d94c | note | ○ Subsoil Collector Pipes
02934fcd-64ef-573a-95a1-a5782919ad2c | note | – Horizontal clearance from the outside of the pipe to the wall of the trench to be minimum of 150mm for all collector pipes (DN80 & DN150 both under pavement and in grassed areas).
c83e1bc1-a23f-50ea-a791-ee6fee052881 | note | ○ Excavated material disposed per approved CEMP.
d35269e0-0384-5008-8156-7ca76583fce3 | note | ○ Completed excavation works shall constitute a Hold Point.
30c8a41b-bf2d-5399-81fb-af8d6620b1df | note | Reference Documents - Cl.16.8.1 & IFC Drawings
84ef1c63-e86c-5e80-8a4a-3617827e4c3e | note | Inspection/Test Method - Verify
20ae350c-40fc-5b50-9d8f-19f392727a14 | note | Record of conformity - This ITP Signed
2579ceae-223e-5bc5-813e-452564241e37 | note | HP
bc954475-f8de-599e-8749-faa5b05ffb8a | note | Responsibility - Project/Site Engineer Beca
6efe9634-1020-5184-b917-5d6940c41288 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Geotextile Placement
ef9802b5-3e5f-5715-a88b-5cb5dc0ff26f | note | Frequency - Each Lot
deb9c76e-c3ed-54e6-b14d-4668eeb6639b | note | Acceptance Criteria - Geotextiles in trench drains shall be placed to conform loosely to the shape of the trenches. The approved geotextile must fully envelope the drainage material in the trench with a minimum 150mm lap. Cover the placed geotextile with 50mm sand after wrapping. The geotextile placed must not have punctures or tears and, if these occur, they must be rectified prior to covering over.
21d2eb47-3873-541e-b2c9-79d7673f0a3e | note | ○ Site trial to be undertaken to evaluate the proposed construction process and compaction method, Hold Point.
dab879b0-1f17-5774-8e0f-6117afa132ea | note | Reference Documents - Cl.16.9.4.2, Cl.16.9.4.5 & IFC Drawings
82e70949-388e-58e4-a299-eb94ab7b8933 | note | Inspection/Test Method - Visual Inspection
71db4eed-f250-532a-bb94-bd3a828c4158 | note | Record of conformity - This ITP Signed
e5f82998-cc61-5ce3-93b0-24d850879a9b | note | HP
705d94a8-4029-58fe-a8b9-780793c31bca | note | Responsibility - Project/Site Engineer Beca
860b8d14-7b9e-506a-a000-6954dab63e0c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Bedding
edf8c917-c28c-5c70-b565-3e2d432fd2dd | note | Frequency - Each Lot
62421231-2c6d-5eca-9810-3473afb30050 | note | Acceptance Criteria - Bedding for Subsoil Drain Pipes Under Pavement and Subsoil Collector Pipes in Grass
bc12892a-da80-540e-8469-0dfa293e3156 | note | ○ Bedding of granular filter material:
9ef781b3-6406-5d7a-b1e3-c4c4d0ffd4bb | note | – 100mm for subsoil drain pipes.
8739fd5d-84f9-595e-bd56-eb792fcc829d | note | – 75mm for subsoil collector pipes
4a1d56be-0e72-559e-8a13-4adfe3968569 | note | ○ Filter material shall be placed and compacted with minimum disturbance to pipes and in layers no greater than 200mm uncompacted.
f7bbff52-7368-5ad4-ac3a-16b9fd15f9eb | note | Reference Documents - Cl.16.9.2 & IFC Drawings
a1ff3c14-5b58-56dd-9b30-9a770d99dedc | note | Inspection/Test Method - Visual Inspection
edbf6be4-9c0b-5c1e-8e98-001ed939039e | note | Record of conformity - This ITP Signed
11b14a64-c51f-50ef-a675-66ea99711356 | note | IP
60facb07-3d1a-5dc6-9896-76c918e4279c | note | Responsibility - Project/Site Engineer
b6e19c2b-861b-5e35-aa57-f3dfa61fcc93 | date | Date Completed:
| checkpoint | 3.4 - Laying and Jointing of Pipes
acc63919-1859-5956-accd-4338e7a69607 | note | Frequency - Each Lot
982dab69-d0d8-5ee3-9b07-5a9200f9ad52 | note | Acceptance Criteria - Pipes laid at the depths and lines indicated on the drawings. Where grades are not specified, the bottom of the trenches shall be trimmed to provide no less than 0.5% longitudinal fall.
43ca6168-124c-5106-916f-7f05a8f1181f | note | Reference Documents - Cl.16.9.2 & VicRoads Section 702.03, 702.09
f30b24eb-069d-52f8-9c80-00edf093fa0c | note | Inspection/Test Method - Visual Inspection
8d17080c-d48d-5c25-8294-368a7b2b11f5 | note | Record of conformity - This ITP Signed
12ccdfeb-6447-5b5f-9c90-89d12c8e5783 | note | IP
5af6caf2-1f5c-55ba-9bda-dd7a686406ea | note | Responsibility - Project/Site Engineer
5fed5454-4550-5138-823f-625274cf1e2e | date | Date Completed:
| checkpoint | 3.5 - Backfill
82e0d72f-b673-55f3-a373-a8ea5a346c9c | note | Frequency - Each Lot
782fda5e-a891-560b-a090-0d895cc5246e | note | Acceptance Criteria - Backfill for Subsoil Drain Pipe (⌀100mm pipe)
16f6de95-850c-54e9-9cda-8db3e3234d8a | note | – Granular filter material backfill is to be placed to the underside of the CTB layer.
c65b7a80-90b6-58d2-b607-783ba0e61707 | note | ○ Backfill for Subsoil Collector pipe ⌀150mm Under Pavement
db90f132-f0d7-53d9-8eae-ea8a81b12ea0 | note | – 5MPa lean mix backfill is to be placed to a minimum of 150mm above the pipe crown to underside of pavement formation.
7815479a-a64b-514a-a8ac-c710635bff3e | note | – Backfill to be completed in two stages to avoid pipe floatation.
52e3cb2e-51b0-5ed2-a80d-117db9ebcc0a | note | ○ Backfill for Subsoil Collector pipe ⌀150mm In Grassed Areas
e01eaf9d-2a64-523d-b88e-eaba57882e10 | note | – Granular filter material is to be placed to a minimum of 150mm above the pipe crown.
04f9a45d-67aa-5f3a-9cf6-d80049db9353 | note | – Excavated soil recompacted in layers not exceeding 200mm loose thickness to underside of topsoil.
7a5f02a3-76eb-5822-a496-80137de680ef | note | ○ Backfill for Subsoil Collector pipe ⌀80mm
3d708b91-b862-571a-bd20-879a1ca722a2 | note | – 5MPa lean mix backfill to be placed to be placed to top of 150mm FCR subbase layer
d63fb179-d759-5832-859e-dff393f317ce | note | – Backfill to be completed in two stages to avoid pipe floatation.
e2f44423-fabd-5fc4-a2bd-d2019986ed13 | note | Reference Documents - Cl.16.9.2, IFC Drawings & Tender Clarification #38
2c3a2b19-1ecf-55da-b4cc-23359d952d5d | note | Inspection/Test Method - Visual Inspection
c359ccd0-b0bf-56ed-9d34-2103b9b83abc | note | Record of conformity - This ITP Signed
89d9dfb0-fe82-54a4-b618-7d17b9f3ecf1 | note | Project/Site Engineer
5a6ddc48-3b75-5b34-a0cc-51ff2e6bbcdb | date | Date Completed:
| checkpoint | 3.6 - Subsoil Drain Outlet
2729af9d-76e7-5b4f-b482-22072c7b5378 | note | Frequency - Each Lot
93d4d9f0-a715-5621-902f-6b616213da84 | note | Acceptance Criteria - Subsoil outlet point to be located at a drainage pit, pipe end wall or outlet in a fill batter or drain. All subsoil drain outlets shall be fitted with Vermin Guards.
43351c17-7eda-5104-ba99-610b06d2a88b | note | Reference Documents - IFC Drawings
f54cbdc1-b074-5ceb-b237-b304e63b3eca | note | Inspection/Test Method - Verify
118f5f81-1efc-52a1-88c9-a445cb2c84c2 | note | Record of conformity - This ITP Signed
dc0e6d00-83df-50ea-81de-bb9fbdfead91 | note | IP
02300ae5-d391-51c9-a516-b20c5ddd137f | note | Responsibility - Project/Site Engineer
cc3b74dc-e10e-501a-a4f7-2f5006fa8096 | date | Date Completed:
| checkpoint | 3.7 - Flushout Risers
4ce793d0-4b56-55ae-bbda-0be872c461e9 | note | Frequency - As applicable
160fda7a-f329-55cf-b8ba-fdf84ab370a6 | note | Acceptance Criteria - Cleanouts shall be located at the heads of all subsoil drains and as specified on the Drawings.
59bd5fb0-e432-5242-b273-7bf5b9e311ed | note | Reference Documents - Cl.16.9.2 & IFC Drawings
7b40b719-15b4-5402-93d8-59527c560432 | note | Inspection/Test Method - Visual Inspection
f3ef272f-cdec-523a-903c-f3f96bd94df1 | note | Record of conformity - This ITP Signed
4717fb7b-5e44-5540-b72d-1c7a289ab715 | note | IP
c6899f67-80fc-5df1-80cf-fe23901deb0d | note | Responsibility - Project/Site Engineer
47d5459c-6674-578c-9823-3add99fab108 | date | Date Completed:
| section | 4.0 - Post Construction
| checkpoint | 4.1 - Flushing Test
ac2cde80-3d01-529a-812e-aef469bf814a | note | Frequency - Each Lot
33817df8-516a-506f-bf30-2f709891d88f | note | Acceptance Criteria - Flushing test to be carried out for subsoil pipes to remove material that has entered the pipes during construction and to ensure that the drainage line is free from obstruction. This constitutes a Witness Point.
9b875275-a4ca-5915-bdf5-2499e12fbd6d | note | Reference Documents - Tender Clarificati on #33
eee59dc7-f9c7-5a81-8506-01615d50d95b | note | Inspection/Test Method - Visual Inspection
02293552-747a-5fd4-866a-94f45d6e5a3e | note | Record of conformity - This ITP Signed
62c6cda1-4101-52c8-9adf-97edc1fddbc1 | note | WP
67f67238-bbbc-5e97-b0ec-911c93b51479 | note | Responsibility - Project/Site Engineer
c6604951-a6da-5fa5-a47e-d47d5f6087bd | date | Date Completed:
| checkpoint | 4.2 - Records
265d3813-d435-55c9-8a25-0b3901c43330 | note | Frequency - Each Lot
a5ebcd79-d827-530b-81ad-26bce792df85 | note | Acceptance Criteria - Levels and alignment recorded in as built documentation.
5a5215f2-64c1-573e-ae61-0cbce602f745 | note | Reference Documents - As built Data
4c686766-1525-5f55-bbeb-013432f0beb7 | note | Inspection/Test Method - Verify
0d197c67-89f3-5a1e-b1ae-c8ebc5c7e02f | note | Record of conformity - Aconex Correspondence / Asbuilts
287c6857-e310-5e63-8b19-69f7316bccd1 | note | SCP
5b6a66e7-a082-5f5d-b2a2-fea9a80aa612 | note | Responsibility - Project/Site Engineer
5ebdc4ef-343c-5375-8a19-e6b25236d540 | date | Date Completed:
| checkpoint | Final Inspection
61331d75-b3c7-5352-8079-414b603e3db6 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
5572ef30-e932-5a08-a991-e4f08674c94b | textbox | Print Name:
f6667217-4fcf-50bd-b2bf-6f44ca637a42 | textbox | Position:
f259472e-32a8-5470-b3b9-9487c05a4eb7 | date | Work Completed On:
933ef43f-f06a-5888-ba35-78c4fb61c965 | date | Date:
| checklist | FH-ZU2-QU-ITP001 - Demolition of Existing Pavements - Rev 0 | itp | ITP001 - Demolition of Existing Pavements | 6c81ad99-728e-449a-9e5f-10150372d498
| section | 1.0 - Preliminary Activities
| checkpoint | 1.1 - Check for correct documentation
de6ba418-2f03-5955-aff5-5e2c470d39b5 | note | Frequency - Prior to works
bb451165-5268-54e3-b4b3-8cbe6e9d37fa | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
6ed2bb77-45d4-5333-a0a1-cce4e1527cc8 | note | ○ Using the correct and complete set of drawings.
cff6e110-a38b-51b6-a6e5-0e28d19fe499 | note | ○ All drawings are the latest revision
33fc753a-477a-5f83-a6b1-be5cbddefd25 | note | Reference Documents - Aconex
869252e6-5f03-5a03-a27c-06d6aa13de5b | note | Inspection/Test Method - Visual inspection
e10801c6-67d0-59d2-a960-52a5b2a6237d | note | Record of conformity - This ITP signed
98e00363-1acd-579f-aa9e-b465cfc1d60d | note | IP
2e60b1e9-7e3d-5aca-850f-c29ad54093ee | note | Responsibility - Project/Site Engineer
a181c36b-ae14-5c86-a20a-ba915d3c521c | date | Date Completed:
| checkpoint | 1.2 - Demolition Work Plan
bb0d47e1-b70f-5be4-86bc-6d0d37693a4d | note | Frequency - 2-weeks prior to start of works
e1c9a3bf-226c-5123-9338-2edf778f750e | note | Acceptance Criteria - Prepared and submit Demolition Work Plan in accordance with AS 2601 to Contract Administrator two weeks prior to start of works.
c758a3bb-d8ed-5e95-a947-289dfedf1fac | note | Reference Documents - Spec cl. 8.4 AS2601 WMS-001
4ca45db9-8b0c-593f-854a-70f9c91cca6c | note | Inspection/Test Method - Verify
c8cd80e1-5dc0-5e39-a4bd-8395ab627af1 | note | Record of conformity - This ITP signed
e2077523-4d37-50e2-a1f7-236a89c4a6fb | note | HP
7d84c665-a967-530f-8433-c484bfb0d278 | note | Responsibility - Project/Site Engineer, Principal’s Representative
5db4d83c-29fd-5cdf-960c-ed9c12482e50 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Dilapidation Report
7bd5b0c6-ba17-5187-adc3-e6a326a32eb2 | note | Frequency - Prior to works
35695348-166d-5426-94a1-37f22be6a12e | note | Acceptance Criteria - A dilapidation report is to be completed and submitted prior to works on site. Dilapidation report to include photos and recordings of the condition of the pavement prior to demolition works.
218d6988-09da-5982-a2e4-909d172da817 | note | Reference Documents - Dilapidation Report
0b41a501-7016-5af3-988e-a6311d817726 | note | Inspection/Test Method - Visual inspection & Verify
405be92c-0e43-50e6-8944-d5e211f5759f | note | Record of conformity - Aconex & This ITP signed
74a7bfa7-7423-5826-abb8-adebfeae7f9a | note | HP*
023533ff-1616-5d33-a2b8-30bef7b7486b | note | Responsibility - Project/Site Engineer
c2e3814f-1ccd-534b-a013-4d4f743f21dd | date | Date Completed:
| checkpoint | 1.4 - Existing Service Identification & Protection
45f1702d-5b43-575b-9667-75048355810b | note | Frequency - Prior to works
4522f48d-9bdf-5866-8d04-f661277673a2 | note | Acceptance Criteria - Existing services information gathered from APAM prior to works. Area to be demolished has current BYD plans, service scanned, and existing services has been proved. Services have been identified and protected prior to demolition.
58dd54e3-03e1-5fb7-849e-d8f22fa07fbe | note | Reference Documents - Spec cl. 8.5.1 Drawings, BYDA, Survey Maps
97297616-c88e-5eb6-99ed-b539126ae022 | note | Inspection/Test Method - Verify
e5c985f5-f458-58aa-a10f-f5e7346a67d4 | note | Record of conformity - This ITP signed
f276c259-8c21-5cca-a78f-49100e7c9402 | note | IP
5907faef-fe05-5530-81d6-24ed30a1b715 | note | Responsibility - Surveyor, Project/Site Engineer
4f9c2daa-fa7b-5ede-9e45-eefa43fd675d | date | Date Completed:
| checkpoint | 1.5 - Execution of Demolition works
b9f49108-0177-5ea0-a0db-0e2301b5389a | note | Frequency - 2-weeks prior to start of works
e6729bde-b9d0-5217-9282-8cc785387ff1 | note | Acceptance Criteria - If working within the existing vicinity of AGL services, Fulton Hogan to give APAM a two-week written notice to work in the vicinity of existing AGL cables and transformers, to provide notice for APAM to assist in isolating services.
8c4ca2a2-bc2a-51a5-89eb-197856cb2a8e | note | Reference Documents - Spec cl. 8.5.1
2705b2d5-423f-5299-9b17-ff18479d6236 | note | Inspection/Test Method - Verify
f6a5a2d9-aa00-55c5-af5b-02517ffb42e5 | note | Record of conformity - This ITP signed
9b05a6b9-21b7-5a6d-94f2-aac152dfdcfe | note | IP
6769e4c8-2210-5634-bd56-691fabf8e714 | note | Responsibility - Project/Site Engineer
2ec735ad-f8dd-51ad-a7d0-bdab91a4efac | date | Date Completed:
| checkpoint | 1.6 - Implementation of all measures and controls
0288d473-5da7-580d-bb77-dd34ac13a7f6 | note | Frequency - Prior to works
5b133118-4d35-573b-806b-23778d780fd9 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, ECP, TMP, SWMS and WP. Existing areas that are not part of the demolition will be delineated with bollards or similar to ensure that it is not disturbed during demolition.
34224c36-7f04-5aef-8886-f22b446426a1 | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
f22f7a72-5027-5553-b48d-c50f459710fb | note | Inspection/Test Method - Visual Inspection
00819a04-f5a1-5f8f-a38e-4a4f6fa7092b | note | Record of conformity - This ITP signed
a3cd1da0-3c74-5829-81b8-79d9cb39a0f3 | note | IP
b88747a5-0950-5069-8d91-33c9885de087 | note | Responsibility - Project/Site Engineer
05a68ad6-76b3-58df-93c1-dd9252a94a11 | date | Date Completed:
| checkpoint | 1.7 - Testing of Demolition Materials
d7fd890f-720a-5d4d-9d5e-fff65772b3c3 | note | Frequency - Prior to works
eb55cd7b-dcfa-5434-8639-c55e87603b0a | note | Acceptance Criteria - Ensure PFAS testing has been completed. The results of the testing will be used to determine the appropriate disposal or re-use of the demolished materials. Offsite disposal of material has been approved by APAM and comply with regulatory requirements.
e07c9c66-19b8-53e8-ae70-ef8968bfec0a | note | Reference Documents - Spec cl. 8.5.5
50f7461a-2b7e-5d7d-9c84-ffedd2400d90 | note | Inspection/Test Method - Verify
8bdecf34-d91f-5805-b803-d4e50f3f66b2 | note | Record of conformity - This ITP signed
de5775e5-cd56-550e-8333-79a2f2215f3f | note | HP*
c9bfbcd4-75a8-59e6-8fe8-974782b93305 | note | Responsibility - Project/Site Engineer
9f4b5e74-2c21-5070-a5c6-40e28d21b6bd | date | Date Completed:
| checkpoint | 1.8 - Excavation Permits
be982e0d-451d-5990-b371-14bd6a185547 | note | Frequency - Prior to works
31b23bba-6ec6-56fd-a149-0b62d29a0b33 | note | Acceptance Criteria - Prior to works, check that excavation permit has been gathered from APAM prior to any demolition works. Internal Fulton Hogan permit has been issues to excavation works and plant operators.
b7c27170-a1ca-5d0d-b0b8-cb64a43d841e | note | Reference Documents - APAM Excavation permit, FH Permit, Go- Cards
10f5a5af-1690-5b5a-9bda-dee7d4bdb2d8 | note | Inspection/Test Method - Verify
1b9c1d85-945d-5cd5-87df-b56aa0eeb97e | note | Record of conformity - Excavation Permit
2e86c833-d897-5663-8392-742befa2a4f6 | note | HP*
08f2e4dd-49c9-5a1d-b705-b46fe3ed0ad2 | note | Responsibility - Project/Site Engineer
f80a5894-3af3-507f-a3c4-605e3111fde8 | date | Date Completed:
| section | 2.0 - Demolition of Existing Pavement Works
| checkpoint | 2.1 - Definition of a works area (survey)
aae52969-45d2-503e-adc2-d30ba1dd9d2d | note | Frequency - Each Lot
b4adfc7f-599d-5b8d-8cd3-e661d18ab14f | note | Acceptance Criteria - Work area has been cleaned and surveyed (marked on site). Limits of demolition are clearly marked.
ef12fdfe-1564-5ea2-b5f6-2d7d56fe5e0c | note | Reference Documents - Drawings
e867c56c-9d76-5a56-bb23-b85897312423 | note | Inspection/Test Method - Verify
17d31cd7-172a-5a27-b550-5cef99ad77ce | note | Record of conformity - This ITP signed
4d590bf8-5081-5894-a2b4-5b161ed967fb | note | IP
53d97e94-87e1-5ed2-b6ab-66f519b380ae | note | Responsibility - Project/Site Engineer, Surveyor
9dfd43f7-e8ef-503e-bd0b-4685d0cc6190 | date | Date Completed:
| checkpoint | 2.2 - Temporary Supports
284bf415-c66d-52fc-87f8-f1d3317cd3e5 | note | Frequency - Each Lot
c5a0bfd9-acef-5e79-9960-d1bba05f5585 | note | Acceptance Criteria - Check demolition will not affect any structural or service supports, if so, temporary supports will be provided until it is no longer required.
25fd1501-6624-532a-8618-4460e259eb3a | note | Reference Documents - Spec cl. 8.5.3
4527299f-b244-5799-ba2a-31ec22a6e6f8 | note | Inspection/Test Method - Verify
bff6d09d-e026-51bf-8796-48ecd81b755d | note | Record of conformity - This ITP signed
26408a23-98a8-529a-8c69-e60a9c256fc1 | note | IP
9cb94ee1-978c-577c-a441-c9a96ac698b7 | note | Responsibility - Project/Site Engineer, Superintendent, Foreman
c6fd8ad7-c9a7-519e-bb7f-7215c1ca0594 | date | Date Completed:
| checkpoint | 2.3 - Disposal of Material
edeeb9de-8f1d-5408-948d-f170556aefb9 | note | Frequency - Each Lot
62348367-a089-5ff2-965a-d5b97f1490d5 | note | Acceptance Criteria - Demolished clean concrete material will be taken to Vic Civils at Gate 8, for concrete recycling. Contaminated or PFAS material are to be taken to Gate 11 to be stockpiled into their dedicated category and contaminant. Any discovered contaminated material found on site, that are not already known, will be notified to the client immediately.
d51bfb7b-fb2b-5e85-bb31-102f96a844ab | note | Reference Documents - Spec cl. 8.5.5
628bdfa2-776a-56b3-ad7f-2c6f15db31a7 | note | Inspection/Test Method - Verify
34eb3d96-c6e2-5c48-a27e-e66ecd8623f7 | note | Record of conformity - This ITP signed
eab19740-24a5-5057-b0a7-4656c968481d | note | IP
6ef59242-739d-584c-9780-6332e3011149 | note | Responsibility - Project/Site Engineer, Foreman
4d348c96-f5be-5a9b-a86f-4c97db7f50b6 | date | Date Completed:
| checkpoint | 2.4 - Asbestos Materials
4973ee8e-e824-5621-8769-1660434f041c | note | Frequency - Each Lot
50401d4f-5850-55fc-867d-33e4e17c44a6 | note | Acceptance Criteria - If asbestos material is identified, works are to be stopped until test is conducted to verify the asbestos. If asbestos is confirmed, licensed subcontractors are to remove and dispose the asbestos out of site.
c8338bbf-c5cd-5c6d-8560-17ec9a11dcf2 | note | Reference Documents - Spec cl. 8.5.6
63eac01c-1285-511f-9009-807a05066da4 | note | Inspection/Test Method - Verify
deb03700-7275-57e9-8b52-ec1baaf14c47 | note | Record of conformity - This ITP signed
1919a9ee-a3fc-5a1d-a43f-206f21f2ed84 | note | HP*
2660f46f-ffde-5d8d-ba2b-1fe0c70f3c7f | note | Responsibility - Project/Site Engineer, Foreman
f9a21230-85e8-5c8a-8766-654ec65b288f | date | Date Completed:
| checkpoint | 2.5 - Made Good
2e649beb-1249-56e7-bdf6-b2a3358aed94 | note | Frequency - Each Lot
72cb9da6-7592-566c-a0c5-7bad14187df7 | note | Acceptance Criteria - Removed and demolished pits and/or cavities are backfilled and compacted. Backfilled areas match adjacent existing surfaces.
a122d8df-a5a6-5039-abe3-45ddf042b566 | note | Reference Documents - Spec Cl. 8.5.7
032378c0-9e5f-5fe6-9c7c-a7a25c0cc35f | note | Inspection/Test Method - Verify
de1d9087-ec08-57fa-9c3b-a8e2f082dd8a | note | Record of conformity - This ITP signed
753bd93d-d588-5243-bb18-80ffc50e8cb1 | note | HP*
95172b46-6943-5d2b-b5b9-60aef6f9cecb | note | Responsibility - Project/Site Engineer, Foreman
0d69e2a8-438f-5fbd-be52-ebd47e1cc6e7 | date | Date Completed:
| checkpoint | Final Inspection
2e649beb-1249-56e7-bdf6-b2a3358aed94 | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
72cb9da6-7592-566c-a0c5-7bad14187df7 | textbox | Print Name:
a122d8df-a5a6-5039-abe3-45ddf042b566 | textbox | Position:
032378c0-9e5f-5fe6-9c7c-a7a25c0cc35f | date | Work Completed On:
de1d9087-ec08-57fa-9c3b-a8e2f082dd8a | date | Date:
| checklist | FH-ZU2-QU-ITP004 - Select Fill Placement - Rev 0 | itp | ITP004 - Select Fill Placement | 7b74922b-d98b-4973-8d9b-f42b3f6a3132
| section | 1.0 - Preliminary Activities
| checkpoint | 1.1 - Check for correct documentation
08c4b17e-a29e-56a5-be50-2ab69afd4d71 | note | Frequency - Prior to works
ec07a3cb-c1f0-5188-bcf9-00a8a0a7c914 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
0afb9d20-3984-59f9-afad-cbce551ff055 | note | ○ Using the correct and complete set of drawings.
9934483f-2306-58cc-9494-554d12355379 | note | ○ All drawings are the latest revision
ffc9abf8-4d0f-5d97-bd9f-25c82ca3379e | note | Reference Documents - Aconex
ab0c1193-80ea-588b-943d-7498f0b43bae | note | Inspection/Test Method - Verify
9190310b-61ff-55e1-b585-7c6deddfd16d | note | Record of conformity - This ITP signed
d5d4dd88-73b5-5173-aa38-2d4c061b361e | note | IP
f1a09c02-c144-573f-9bf1-fc6e921e59dc | note | Responsibility - Project/Site Engineer
5582b486-373d-5a50-a97b-1b17f5be5c85 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
b26f041a-9e1a-53f5-a2a7-ae357fb1b158 | note | Frequency - Prior to works
5f736424-2c68-5813-9f3e-9938bc60e9e0 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP.
f2c2258a-099b-5a2d-bbb8-405e99612b87 | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
2a982293-b48a-53b5-9ab5-3e0ad4ffa560 | note | Inspection/Test Method - Visual inspection
4651ff39-7b00-5362-9150-e2db58cfff0d | note | Record of conformity - This ITP signed
2f29ce51-e199-555a-98f0-058275729f9f | note | IP
2f332fd5-58f8-54ee-b8b4-6bcfbdb45e3b | note | Responsibility - Project/Site Engineer
847d413e-f5a2-5801-bdce-d489bf57302a | date | Date Completed:
| checkpoint | 1.3 - Survey
b94c6f79-9487-5050-adc7-6028f0f7816c | note | Frequency - Prior to works
bb4e26e8-aa42-5610-aa37-25d1a70889db | note | Acceptance Criteria - Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone).
d71e8c39-5636-59d4-aeb9-34f2bc826c1b | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
a5158671-8dd3-51d0-8cea-a932a5e0b6ce | note | Inspection/Test Method - Visual inspection
5e36ac1e-3494-5b2b-8bbe-78c39bdf135f | note | Record of conformity - This ITP signed
09f23b99-26a6-52f7-a317-f1e4add963d3 | note | IP
2bb97587-0580-57bc-8c47-320a24478bc9 | note | Responsibility - Project/Site Engineer Surveyor
43a2c40b-d1a0-5c47-a992-6064ca6125ff | date | Date Completed:
| checkpoint | 1.4 - Select Fill Material Source (Under Pavements, Imported)
daaba572-1025-5653-afd5-9bf625b59ef9 | note | Frequency - Prior to works
cbb4fed3-7ecd-5ef1-9d34-d585415b842c | note | Acceptance Criteria - Material to meet the following the properties:
be36a13f-2979-5221-b8a4-81124970ae9a | note | – – – – – – – – –
00897eec-50ef-56f5-b303-a4a67d250bfb | note | Wet strength ¦¦ Not less than 125 kN wet/dry strength variation less than 40%
49dcfc3f-2abb-5459-8068-e575a930b0fe | note | – – – – – – – – –
2c356531-e24e-5bfe-a5ed-558c7e48cfbf | note | Linear Shrinkage ¦¦ < 6%
1e1a2f50-b31b-599f-b1b8-b6cedf70dba4 | note | Organic Matter Content ¦¦ < 0.2%
4dec1663-fb29-55bd-95db-83504927c099 | note | Maximum Particle Size ¦¦ 75 mm
28ecf767-cd52-5370-a3ff-72d6443e29f1 | note | % Passing 0.075 mm sieve ¦¦ 0-12%
476e4531-4980-5b57-a950-4372438293d5 | note | Soaked CBR ¦¦ > 20%
b265c9d2-38af-59c4-8e30-d0393ed05e4d | note | CBR swell % ¦¦ ≤ 1.5%
c9074b6f-1d34-594b-b824-102bd68533e0 | note | Permeability ¦¦ < 5 x 10-9 m/s
d8ecc50e-bce7-5f79-8a5c-a4b2dc1bfc3f | note | – – – – – – – – –
d8e6513b-c0b9-52ee-bf6c-8f331b0195b6 | note | Material Property:
814c752b-bb60-50f1-96f9-edf0e7c737d7 | note | – – – – – – – – –
c0a6959d-2e3d-5fb8-ac12-ff1d57863ae2 | note | Material Property ¦¦ Requirement
f2a02c5d-7e16-43b5-bb11-24639f86353b | note | Liquid limit ¦¦ < 35%
6023c1d1-dc64-42b9-b566-66672555818b | note | Plasticity Index ¦¦ < 12%
cf82e18b-2dd1-4b6c-af80-f76a73ba9eb2 | note | Wet Strength ¦¦ Not less than 125 kN Wet/dry strength variation of less than 40%
a6256b04-31e1-4c46-bb8b-be1963b43002 | note | Linear Shrinkage ¦¦ < 6%
c25f9859-1f75-4146-8214-12162e402f21 | note | Organic Matter Content ¦¦ < 0.2%
28a6fc05-a96f-400f-9a83-f665e36487fe | note | Maximum Particle Size ¦¦ 75 mm
18e70ce3-cd41-4e80-b2e7-cdecd621e86f | note | % Passing 0.075 mm sieve ¦¦ 0-12%
426ddf19-4a19-428c-81d9-a0976b6ba863 | note | Soaked CBR ¦¦ > 20%
56b31f61-ec77-4a26-9c02-193aec6fd96f | note | CBR Swell % ¦¦ ≤ 1.5%
3c76cdd8-3729-43ea-9684-809f18ec2000 | note | Permeability ¦¦ < 5 x 10^-9 m/s
279ea369-5031-4f1b-91e8-626b863153c5 | note | – – – – – – – – –
d5283e63-ac96-4ffb-8466-b3b6a9038e9a | note | Gradings:
c2e5e53a-5d01-4f32-a8cb-c9d3eec343f1 | note | – – – – – – – – –
e962e5c9-1583-517a-8479-ab3ac3cd2746 | note | AS1152 Sieve Size (mm) ¦¦ Percentage of mass passing sieve size
cfe1cd19-1284-5aa2-9cf8-91fea8545b4f | note | – – – – – – – – –
bed041fd-d001-5108-af09-ef0e9711b9e0 | note | 75.0 ¦¦ 100 to 100
f320a33c-f6e6-5e94-99ea-c648d595de8b | note | 37.5 ¦¦ 67 to 100
2f304236-d42e-550f-bb74-14664bc6880a | note | 26.5 ¦¦ 54 to 100
1c1acd2b-5d4c-5220-9478-f62ad2876162 | note | 19.0 ¦¦ 44 to 85
6d8636bc-a42b-5f14-9b5f-c72cb8ab9d44 | note | 9.5 ¦¦ 31 to 65
31e3bec9-ba20-56cd-8c5a-6f576fda8073 | note | 4.75 ¦¦ 21 to 50
0faee927-3dcf-5944-91aa-5c5917c5dccd | note | 2.36 ¦¦ 13 to 38
c568518d-b7e3-533f-a9a7-bc6383d1fb15 | note | 1.18 ¦¦ 9 to 30
b3f56a11-f6f1-5983-937f-1d114c23c723 | note | 0.425 ¦¦ 4 to 23
0d6d1251-8dbd-5410-b46f-a3b6e67d4b61 | note | 0.075 ¦¦ 0 to 12
d6ae7631-afe6-5798-9b1a-d28144e937a3 | note | – – – – – – – – –
040eeceb-01be-5cb7-acbf-c3f57fee68c1 | note | ○ Production testing if supplied select fill will be: 1 per 1,000t for first 5,000t, increase to 1 per 2,000t following conforming 5,000t of conforming results. If material source changes, testing to be re-conducted from start.
04ffc556-268c-52b6-b721-d92339b742b2 | note | Reference Documents - Spec 002 – CL2.5 Cl2.7.5
3ca23b7d-514d-5470-97a3-39d41093fa60 | note | Inspection/Test Method - Test Report
9c5f393c-f175-51db-9434-fda4147480d2 | note | Record of conformity - This ITP signed
8a63c909-49de-5436-b4b5-575aefd813ac | note | HP
02927e97-19f7-5fbe-a3b4-eee1b7c62d58 | note | Responsibility - Project/Site Engineer Principles Rep
da34b4ca-7a9f-578d-9c02-d4fabb27fd31 | textbox | Checked by: Principles Representative - Aconex:
071c1a9c-2607-5e67-a29d-6a65f01f5cb8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Select Fill Material Source (Other Locations, Site Won)
063b6ae1-0810-55a7-b6a7-6b5db22bfcbb | note | Frequency - Prior to works
258f4ebc-f34d-5d30-bd3f-22d86510d714 | note | Acceptance Criteria - Each source of select fill shall be approved by the Principles Representative.
ac6389cc-17e2-595b-b34b-dd88ffe8864e | note | Reference Documents - Spec Cl 2.6.2
719895c5-7f3e-5091-ba15-8a37bcc0b054 | note | Inspection/Test Method - Test Report
b178ae95-a6a8-5f30-a71e-77c3180b179a | note | Record of conformity - This ITP signed
5fea5191-b455-5379-a562-341e47f23a5c | note | HP
1b1175c9-563b-5f66-9a51-8150698498ab | note | Responsibility - Project/Site Engineer Principles Rep
e3e36edf-af24-4dfa-9403-05f346394d44 | textbox | Checked by: Principles Representative - Aconex:
51923049-c02d-5ec6-b16f-c5aea6323641 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Submission of Select Fill Methodology Plan
d005a128-0585-5c5f-a4ed-dc6cd7fed680 | note | Frequency - 14-days Prior to works
7f0a4f4d-b378-5a12-b0e4-f56352981a2f | note | Acceptance Criteria - Principal Contractor to submit a Select Fill Methodology addressing the criteria listed in Spec cl. 2.3.1. Hold Point to be released by Principal’s Representative after acceptance of Select Fill Methodology.
9669e478-dd97-5343-81cd-5199ba8b11fb | note | Reference Documents - Spec cl. 2.3.2
9a4f811b-2c81-59e0-bc06-90aeeca2bea8 | note | Inspection/Test Method - Select Fill methodology & verify
7ee34b39-a2d3-5e3b-b6b4-d71bab0d7184 | note | Record of conformity - Select Fill methodolog y & this ITP signed
ab118804-4cfd-581c-a8b2-4173b3f62ba2 | note | HP
c427744c-00ec-5244-95ee-1968a0a0506d | note | Responsibility - Project/Site Engineer Principal’s Rep
3ff59667-9db9-5e0f-af41-a6422fa1c607 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.7 - Starting Works
191a663e-328f-5ce5-a946-a8d013cca794 | note | Frequency - Prior to works
6988de33-b3cc-59d5-ab8d-79735df2e94a | note | Acceptance Criteria - Principles Representative to approve works starting in each Separable Portion
d953518c-4665-5be5-9df4-3b5706752e35 | note | Reference Documents - Spec cl. 2.3.1
8da07ef4-0244-55ed-84cb-82af9c176d0f | note | Inspection/Test Method - Verify
9c0d8931-832c-56ec-b854-27402cac329e | note | Record of conformity - This ITP signed
01cc9dd3-f181-5d4e-b595-c5bddced1061 | note | HP
1c0dfe50-17e6-5aec-a644-70f7bd58cd85 | note | Responsibility - Project/Site Engineer, Principal’s Rep
f8c8d075-b3c2-428c-b172-8159d39d679b | textbox | Checked by: Principles Representative - SP8 Aconex:
b154fc99-0a6d-550d-b606-cf95d0f9bece | textbox | Checked by: Principles Representative - SP9 Aconex:
5e843dd3-b3d2-5eb4-9338-9d3baeddc93d | textbox | Checked by: Principles Representative - SP10 Aconex:
ed099b5c-abd0-5fc3-bf77-6287326c1569 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.8 - Preparation of Underlying Surface Layer
3fd33117-7eb2-586f-aa85-c38c3a5e3e4e | note | Frequency - Each lot
d49700fe-80cf-52d1-b05b-5a9dd1b1a079 | note | Acceptance Criteria - All excavation and filling are free draining to low points clear of the working area. Sufficient pumps, well-points, or other equipment for work area are de-watered as required.
29337356-89d0-56e5-9ce6-bb65769f6fa6 | note | Reference Documents - Spec cl. 2.8.2 ITP003
be289948-f406-5e5d-aa09-44a86a08572d | note | Inspection/Test Method - Verify
6554c8ee-bac9-53ad-8ac4-0c6a0f9b9336 | note | Record of conformity - This ITP signed
509f5b45-e354-5884-871e-a14c5219f88e | note | IP
a8de60f0-59c1-5c31-8c97-7ab7c45d6531 | note | Responsibility - Project/Site Engineer Foreman
843759f7-5dbd-5c16-aced-bd975265065d | date | Date Completed:
| checkpoint | 1.9 - Cut Floor Level
6c8d8f56-6505-5557-a082-4e1a61cb67ac | note | Frequency - Prior to works
e41bf1b5-9786-5635-8da4-452b93549516 | note | Acceptance Criteria - Cut floor to be inspected for suitability - compacted, firm and dry
b5ec83c9-941c-5393-a618-6317d028adb3 | note | Reference Documents - WMS003 cl 3.3.3
4d0e6c39-2d95-58d1-8054-9ff4a0c20dc4 | note | Inspection/Test Method - Verify
1357443b-4fe8-50f2-bc24-5754a41f44d2 | note | Record of conformity - This ITP signed
8ca3c972-2063-5790-8b54-d410a0ba7407 | note | HP*
47799b55-8c62-5420-b582-d3bfe6e9728d | note | Responsibility - Project/Site Engineer Foreman
a61bf0fe-c74c-5468-8b07-734f781a523f | date | Date Completed:
| section | 2.0 - Select Fill Works – Imported Material - Under Pavements
| checkpoint | 2.1 - Select Fill Placement
a285683c-8b89-5d00-8ee5-7dd4aed4cce1 | note | Frequency - Each Lot
1088eff9-1f90-59a7-b41b-14d0f0ad1908 | note | Acceptance Criteria - Each Lot of fill must:
76abb573-0b41-5839-8ab6-8f3a78d19147 | note | ○ Not be greater than 200mm in thickness
c7e45ad8-2f77-5838-8b90-c5dfcf3d6e79 | note | ○ Material is to maintain within 1% of the optimum moisture content during all steps of placement, compaction, and finishing
678a7288-b1b6-53dc-b1f4-3c67e7ce5832 | note | ○ Placement of material to commence at the crown or the highest side of the pavement, with each lane spread adjacent to the previously placed lane
ae18ee55-133d-4030-a099-fa46d32f59f9 | textbox | ○ The first layer of placed material is dropped and spread using a dozer, grader, or similar plant to prevent trafficking 7mm seal
af09624f-e3c1-5797-9314-8274a1c59ed7 | note | ○ Material to not be contaminated by foreign materials and other contaminants
90c3fdc8-a923-4e70-8403-04a9ffc41923 | textbox | ○ Plant and equipment does not traffic 7mm Aggregate Seal
3dbc7cb7-6509-580f-91f9-e9a368e88d35 | note | Reference Documents - Spec cl. 2.8.4
f4e6e6d0-2488-542e-a580-ab6ff313a746 | note | Inspection/Test Method - Verify
255c8a3e-d31e-5112-864d-8f0b1a95a4c9 | note | Record of conformity - This ITP signed
cbb35942-afe0-5989-8175-5db882b1f056 | note | HP*
5f20e431-67c6-5049-94d6-bf6ddc20f219 | note | Responsibility - Project/Site Engineer Foreman
d8351717-5829-52da-9630-21fa92547fd8 | date | Date Completed:
| checkpoint | 2.2 - Proof Rolling & Compaction
f6bcdc13-2b29-5e73-a520-feffb5a5ff4c | note | Frequency - Each Lot
e256642d-13d3-5932-b4a9-3a0ded3bfdae | note | Acceptance Criteria - Each layer of select fill under pavements is to be inspected with the Principles Representative.
d7d39b8c-6eb2-537e-8c6f-760b58edb6fe | note | ○ A medium size vibrating roller (or larger) is to be used for all proof rolls.
ba9f68a4-a645-56b1-abbe-2ce5f7244fd2 | note | ○ At least 5m of longitudinal Select Fill and 500mm of lateral overlap of proof rolling between adjacent areas is needed.
4f3eb4f4-7107-5840-9dee-53fc6614bbc9 | note | ○ At least one working days’ notice is to be provided to schedule the presence of the Principles Representative.
24ebd48e-de5b-5a02-b3d8-bd75dd473447 | note | ○ Maximum allowable rutting of 25mm.
8400133a-8770-5d5c-aa61-6afb25a99e31 | note | ○ No heaving to be observed.
d47c6d07-a0d7-4b4c-a959-37094aa81598 | note | ○ Proof rolling of the select fill will be approval to place Sub-basecourse or Basecourse. If rain falls on select fill prior to placing next layer, a further inspection will be required.
aa8ce4a4-dfad-50ae-9679-f4a320171abc | note | Reference Documents - Spec cl. 2.10, Spec Cl 4.6
43d9517b-b833-59e1-a928-f0e9191db911 | note | Inspection/Test Method - Visual Inspection & Verify
007a5866-30c6-5e94-9f7b-eda3d6be2915 | note | Record of conformity - This ITP signed
75d45070-7e38-5e90-be33-a40b6c4d25f9 | note | WP, HP, HP
1035b6bc-5313-55a3-89f8-247dc8516c36 | note | Responsibility - Project/Site Engineer Principal's Rep
e74b8669-4382-5781-a35f-13ab9e7a638b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Final Trimming and Surface Finishing
b969e5f6-98cc-5976-a1db-96e747fccfd0 | note | Frequency - Per lot (final layer only)
c5073318-1d2b-5d22-8b0a-7bfc85218377 | note | Acceptance Criteria - Final layer of Select Fill surface to the required level, grade, and shape with a tolerance of +0mm and -25mm. Intermediate layers of select fill do not require a Survey Conformance Report
bbcd9e54-00b8-5001-8b05-4da4db95e2bb | note | Reference Documents - Spec cl 2.11 WMS003 – cl3.4.5
cb48011c-a1e9-5dfd-ae7d-68851eeacc67 | note | Inspection/Test Method - SCP
61bdba24-af61-5bcf-8e88-65004e5e2603 | note | Record of conformity - This ITP signed
cbc322f2-a319-54e9-95bd-9652bfb5dd3d | note | HP
d843fe42-ddf3-58e3-b760-959cd61a1cff | note | Responsibility - Surveyor, Project/Site Engineer
5f10bc1c-6362-5c7f-b1df-be0007331eb8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 - Select Fill Works – Site Won Material – Other Areas (Not Under Pavements)
| checkpoint | 3.1 - Select Fill Placement
dd600633-1855-5efb-aa7a-b22b1a16b9ad | note | Frequency - Each Lot
6cf86ae2-1ebf-5597-a601-ce96a64e12c9 | note | Acceptance Criteria - Each Lot of fill must:
5c46b0da-a8eb-525b-805d-7a15fe1ddb17 | note | ○ Not be greater than 200mm in thickness.
ff7b2559-af03-547a-9188-aff61a7ed3ad | note | ○ If required, material to be lightly watered to aid in compaction.
164428fd-9f41-5a84-989b-371e5ef907e5 | note | ○ Placement to start on the high side.
606c0f40-6a0a-5a36-a25b-d94b5802f1b9 | note | ○ Material to not be contaminated by foreign materials and other contaminants.
595e330f-84d7-5d07-bdd1-f36f30d40394 | note | Reference Documents - Spec cl. 2.8.4
261751eb-649e-54fc-858d-2c38f03f9163 | note | Inspection/Test Method - Verify
6a4957a0-b9ab-5808-9006-ec62b9ccf935 | note | Record of conformity - This ITP signed
84c8b8d1-03dd-59e6-9d99-6c4ff276b04f | note | IP
2a1f2666-ba88-513c-b479-bda9af6ebe9e | note | Responsibility - Project/Site Engineer Foreman
3cd2359e-478d-5a7c-937b-723ea792aa09 | date | Date Completed:
| checkpoint | 3.2 - Proof Rolling & Compaction
61716091-7ff1-53da-be97-6525d3ab0d02 | note | Frequency - Each Lot – intermediate layers
0e621325-bc78-538e-9d1c-ad5c898e2500 | note | Acceptance Criteria - Intermediate Layers
7eb80e75-eeda-5830-bbf2-877aa402d695 | note | ○ Each intermediate layer will be visually inspected for conformance to the specification following compaction.
16d757da-361e-5a78-a738-deaa432d1861 | note | ○ No rutting greater than 25mm observed
de4e646d-a05c-5dcd-bdaf-e12065b7296b | note | Reference Documents - WMS003 – cl3.4.4.1
1121916d-79fd-5972-b23d-a650ab4d24a8 | note | Inspection/Test Method - Verify
1c5f4405-0f62-5fb5-8c5f-310627cbe0fb | note | Record of conformity - This ITP signed
554a3ed7-20f7-5e35-83f7-6728a552da00 | note | HP*
e63bbe64-3698-541a-9ae4-d8da7237141a | note | Responsibility - Project/Site Engineer Foreman
ccaaa446-44ab-5a1a-af6f-eff82876dee0 | date | Date Completed:
| checkpoint | 3.2 - Proof Rolling & Compaction
c08bae98-5572-5c0f-bc54-6c2e4e967af5 | note | Frequency - Each Lot (final layer only)
c5d002ec-66be-5b68-8f97-eae95a2aed15 | note | Acceptance Criteria - Final layer
546f7143-3279-5d94-9daf-380e3a1eaf5c | note | ○ Principles Representative to be invited to visually inspect final layer of Select Fill not under pavements.
333ff332-9e8b-5a29-a97a-d2e1c8e1531e | note | ○ At least 5m of longitudinal Select Fill and 500mm of lateral overlap of proof rolling between adjacent areas is needed.
5d380afc-eb96-5670-9bfd-668848f80509 | note | ○ If requested, Proof rolling is carried out in the presence of the Principles Representative
d960ea35-51db-573f-89d1-ce44c75a5cac | note | ○ If requested, at least one working days’ notice is to be provided to schedule the presence of the Contract Administrator.
b49298b2-d1ef-5f42-8be4-cf51205e8922 | note | ○ Maximum allowable rutting is 25mm.
af69c2c0-630e-5064-96fa-814131dd5fee | note | ○ No heaving to be observed.
b59bcabf-c714-52e2-92ff-fa9244039adc | note | Reference Documents - Spec cl. 2.10 WMS003 – cl3.4.4.1
381fbbab-cc3c-5605-9803-bee173c2d21b | note | Inspection/Test Method - Visual Inspection & Verify
716b97f9-32ec-58ce-8d4f-8e536b454e40 | note | Record of conformity - This ITP signed
93ca3368-b935-5713-9776-0469b8471dbd | note | WP, HP, HP
5c34c3a5-4097-5295-a686-eb8106c9fb84 | note | Responsibility - Project/Site Engineer Principal's Rep
40dbf905-4676-5e94-ae72-655a8ae24718 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 - Testing & Acceptance
| checkpoint | 4.1 - Classification and Testing (imported material, under pavements only)
497bfaa0-6206-5775-81af-233539a11d92 | note | Frequency - Each Lot
271fc17f-30a4-59e8-bbca-65edc4f02acc | note | Acceptance Criteria - Imported Material Under Pavements
27355161-24bb-5967-93e9-dda843f4ba98 | note | – Dry Density as per AS1289.5.3.1
3179e986-b82b-5056-98ff-4aabbe83c0dc | note | ○ 4 test per lot to achieve average
e64042f7-dd1c-50be-926d-7c64a5cbf840 | note | ○ Minimum average standard dry density ratio of no less than 98.0%.
fdb3a14a-9a9e-55d1-ab92-eb781d5eda6f | note | ○ No single standard dry density ratio test result being less than 97.0%.
4dfaf25b-ec5f-5a98-b76f-018000e525bb | note | Reference Documents - Spec cl. 2.9 AS1289 5.3.1, AS1289 5.4.1, AS1289 5.8.1, Spec tab. 2-3
cde87d4d-e124-5808-9805-530b6d47ec39 | note | Inspection/Test Method - Verify
20e31860-c7e0-59f1-bbe5-e62b5343e90b | note | Record of conformity - Test results & This ITP signed
fec63964-1ec3-5c2e-b894-f48a5a9eee1d | note | HP
befcf3c6-d0dd-5b27-b626-a9a33bf6131f | note | Responsibility - Project/Site Engineer, Principles Rep Foreman
57cd6c31-ace6-54db-9b2e-2802c5fd7311 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Lot Acceptance
fd6d64c3-6ffb-527d-8b4b-bcb152ea8af2 | note | Frequency - Each Lot
6094e51b-56c8-55be-81e7-ccc9388928af | note | Acceptance Criteria - Principles Representative to review acceptance of lot according to table 2-3. Acceptance of lot will not hold up placing succeeding layer of subbase.
2da0f362-8c08-58fe-9a83-451b169eb89d | note | Reference Documents - Spec Table 2-3 Cl2.12
5cadbf22-2e7d-5c0b-8f81-bb24150c0f16 | note | Inspection/Test Method - Verify
5317b649-84e5-5a25-8ad7-23504448e577 | note | Record of conformity - Test results & This ITP signed
565abba3-17d0-5afd-9e87-56fb95d8fbf4 | note | HP
c23be552-5ce0-5137-bd63-cde77864010b | note | Responsibility - Project/Site Engineer, Principles Rep
f8286b5b-50b2-5dec-af24-fffc837e80cd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
c99016f3-cb40-5a62-aebc-b4d7bb465048 | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f2bc87cb-c91c-5291-95da-3deaa91d47f1 | textbox | Print Name:
997fdfdb-a196-5436-9205-97836b076b0c | textbox | Position:
68dcca9c-d28c-529d-b4b1-3ceac23b94e3 | date | Work Completed On:
2181d0aa-ae54-5dfc-8386-981fe6cd1902 | date | Date:
| checklist | FH-ZU2-QU-ITP042 - AGL Shallow Base Cans - Rev 0 | itp | ITP042 - AGL Shallow Base Cans | 82c5f217-7e84-4803-a45b-201bc3470762
| section | 1.0 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
c2322c0b-6788-5c16-a6b2-b5f52c3f4b1a | note | Frequency - Prior to commencing any activity
582e3dce-a077-5116-bcb1-896a02192280 | note | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
e3466404-cd66-5ad3-816f-0b07f2710d0a | note | Reference Documents - IFC Drawings
e0254087-d69f-5d9e-b0cb-32aaaa397665 | note | Inspection/Test Method - Verify
9672afbb-f6c7-55d5-be1c-0648961a7f7f | note | Record of conformity - Drawings
1f7997ad-9e29-5091-99ce-a1541b6d5d23 | note | IP
0f48af26-3a1b-5468-b326-e04676008e08 | note | Responsibility - Project Engineer
17a5140c-a227-53b6-bb1b-930c20c4a914 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
b1c8abe8-5e01-5fce-ba7d-ae2080b43e87 | note | Frequency - Prior to commencing any activities
d13eb50d-6a5b-516e-8197-610276251445 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
75185538-73d0-5990-9d9d-4de1b0ad90f3 | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
abf06095-7bf1-5c21-bbc7-171952b56fb6 | note | Inspection/Test Method - Verify
f78c7b91-f167-5da4-979c-0d175be305cc | note | Record of conformity - Site and office Inspection
dea835b8-8a32-59f0-beb9-f1d6afb64e7c | note | HP*
492d3161-69b5-5d5c-b5c3-3b0b54bb4fda | note | Responsibility - Project Engineer / Site Supervisor
1a761cb6-1739-5231-a304-1740c04bfc65 | date | Date Completed:
| checkpoint | 1.3 - Material/equipment approvals
f50cddb5-c152-5829-b45b-46febd125cd2 | note | Frequency - Prior to start
9b9f59a6-e8f0-53ee-84c8-344032349d0a | note | Acceptance Criteria - Materials and equipment that shall be used in the construction of the works as nominated on the Drawings.
d3e7a9b1-4753-514a-acdc-719b7b8baabd | note | Reference Documents - ZULU-BECA-001-SPC-00003 cl 2.3
deaae5fc-d4fd-5b67-b374-f50cda576d3e | note | Inspection/Test Method - Verify
60f0ecfc-7eda-5125-9186-7f4484e139e7 | note | Record of conformity - Aconex reference(s)
afb90af9-7b48-57f7-97f4-dfe8a2d92a0c | note | HP*
45e049bc-b21a-55b3-85f9-28c9957fe7d6 | note | Responsibility - Project Engineer
13a07e97-e873-5875-8467-feebff81f3cb | date | Date Completed:
| checkpoint | 1.4 - Setting out for airfield luminaires
05c67439-9b8e-527d-aa6f-d013651a46bf | note | Frequency - Each Lot
05e3861b-0b08-51b9-9b46-9486ebf45c5c | note | Acceptance Criteria - HOLD POINT
77631a20-328d-56ae-ac12-a64728a96660 | note | ○ The Contractor shall survey the proposed light locations in conjunction with the new and existing line-marking to set out the proposed lights. A schedule of the proposed lights shall be produced and submitted to the Contract Administrator.
0a596d91-2dfe-5bc6-8fe7-22f2ae1fd00b | note | Reference Documents - ZULU- BECA-001-SPC-00003 cl 5.4
5a1db113-abf6-5054-9267-2175089641f7 | note | Inspection/Test Method - Verify
273ff0cc-a6d6-5d2b-a98f-307add13e94d | note | Record of conformity - Aconex reference
f2c6079f-dc6c-5b72-b54e-628f8ee13d59 | note | HP
126f27ca-e90c-5898-937b-a1d6cec09c28 | note | Responsibility - Project Engineer / Beca
29a46fe9-1a00-5314-8e2a-9ffc79f66e50 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 - Removal of Existing Can
| checkpoint | 2.1 - Removal of existing AGL can
430c3dec-bc91-534f-a831-530fce96f995 | note | Frequency - Each lot
7a4bcd73-9144-5287-9688-89bdb8158b09 | note | Acceptance Criteria -
09135dc2-cdfa-5033-bc59-d13b78cad3e4 | note | Reference Documents - ZULU-BECA-024-DWG-07513
d45ff866-c0a6-5483-91bf-ae3aeca5db68 | note | Inspection/Test Method - Visual Inspection
a3ae43c8-d83d-5aa1-b568-4ffd04218050 | note | Record of conformity - This ITP signed, Avionics Removal of Existing Can checklist
09d4764e-d758-55da-92a6-c02dd52b601e | note | IP
cf42774b-72d0-56f3-aaac-ec33b6793345 | note | Responsibility - Project Engineer
9753c511-dbf4-5b88-a085-a690b4c87e47 | date | Date Completed:
| section | 3.0 - Installation of Shallow Base Can
| checkpoint | 3.1 - Inset luminaire base can
07f4f2fd-e8ed-5279-8e03-7dc69393e65c | note | Frequency - Each lot
ba6cec38-004d-54e3-81b3-9f937287b7f2 | note | Acceptance Criteria -
756cd43f-e403-5130-92bd-300646fcb8bd | note | Reference Documents - ZULU-BECA-024-DWG-07501, ZULU-BECA-024-DWG-07506-8
4648c9d7-554a-5a50-81a0-f4f9d000642d | note | Inspection/Test Method - Visual Inspection
f49a4d2f-8208-586d-ab8d-d784a61594c7 | note | Record of conformity - This ITP signed, Avionics Shallow Canister Installation checklist
eb7f1abb-7df6-5b5f-af4c-4a31f7d1d498 | note | IP
d81b5b99-8c22-5f87-8dc3-7e2b103720a5 | note | Responsibility - Project Engineer
abf7e728-7c3b-5bc4-93ab-576a1813ccd6 | date | Date Completed:
| checkpoint | Final Inspection
59e9a41a-9eca-5958-a226-24d2700db36c | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
e1bf6fce-a9da-5ac8-a650-36374942bd25 | textbox | Print Name:
acbb9cd2-1435-5789-a7ee-fbc848bcf068 | textbox | Position:
24ac43bf-4f9d-5dd1-9a2e-d681c5f24931 | date | Work Completed On:
86ff4a10-6933-5b1a-9f8b-9d3c47bd350b | date | Date:
| checklist | FH-ZU2-QU-ITP005 - Stormwater Drainage - Rev 0 | itp | ITP005 - Stormwater Drainage | 83f202df-0ed7-499d-abd2-6f7b84d31412
| section | 1.0 - Preliminary Activities
| checkpoint | 1.1 - Check for correct documentation
54e098fd-2875-533c-ae63-868a90e30081 | note | Frequency - Prior to commencing activity
3a9488af-ceef-526d-a9e6-e8a30e966b9f | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
471f36d6-b4b4-5388-a9d2-5ae7ece93b5f | note | ○ using the correct and complete set of drawings
8f7a1599-66cb-573c-9016-a55fbc589bc8 | note | ○ all drawings are the latest revision.
c2e5a589-5901-5b02-9701-76e4ce132a9a | note | Reference Documents - Drawings and Aconex Register
a2ee1067-eb31-532d-8b47-6005b527fbc3 | note | Inspection/Test Method - Visual Inspection
bfafb1b0-e9c1-591c-b5de-dc2927d5d9b0 | note | Record of conformity - Up to date drawing sets & ITP
839ea919-c7d7-547f-a4c5-a127348d8a0e | note | HP*
95bf2957-8d71-57ca-98d9-f701505fe279 | note | Responsibility - Project/Site Engineer
16f17a8f-429d-5221-b86f-2a3ff34b50bc | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
2b1c2541-a2e3-53ee-acdf-59d7d816963e | note | Frequency - Prior to commencing activity
56e020d7-7c16-5716-9b87-daa768345924 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: CEMP, TMP, SWMS & WP.
bc2543d4-aa2d-54cf-a7b6-1c651c7eef89 | note | Reference Documents - CEMP, TMP, SWMS & WP
b2945d35-791b-5282-9eab-f1096aae2e5c | note | Inspection/Test Method - Verify
6743976f-a864-5448-8b47-d3bd43ab57a1 | note | Record of conformity - Site and Office Inspection
f3bde6b2-9eeb-5f16-a6fd-7ab73df5c502 | note | HP*
7247c46e-49a4-5101-afd6-c19f89422b74 | note | Responsibility - Project/Site Engineer/Supervisor
a959ad58-ba7b-515e-934e-cfe533042728 | date | Date Completed:
| checkpoint | 1.3 - Excavation Permit
67c58622-d040-5817-8e40-c14ba3c81201 | note | Frequency - Prior to commencing activity
858c6e33-5f6d-5f36-b9be-131e6512679b | note | Acceptance Criteria - Excavation Permit issued by APAM obtained prior to any excavation on site.
d89748f0-3fe4-5f6e-bd16-db487ca14c10 | note | Reference Documents - Excavation Permit
5ac316e1-5683-5604-bf46-2f6aa45e1fe3 | note | Inspection/Test Method - Verify
2a3b06da-8a9d-55ae-a1b3-00d7413308e1 | note | Record of conformity - Proof of signed permit
62992194-6156-50b2-81f9-ef93471b5596 | note | HP*
11702d77-2c52-5332-81a8-f6e2b636d283 | note | Responsibility - Project/Site Engineer
5da7027f-4163-53a4-8cf3-0db8251e49d5 | date | Date Completed:
| section | 2.0 - Stormwater Products and Materials
| checkpoint | 2.1 - Drainage Pipes (RCPs)
41d9fad8-a375-534c-a828-f397d7515358 | note | Frequency - Prior to commencem ent of works
6f00cc3b-c4a0-5f15-b5f6-bf98b9efe43f | note | Acceptance Criteria - Drainage pipes supplied in accordance with AS4058.
bb56e26e-19e7-566c-ba5d-74cdce66240b | note | ○ Material submission approval.
b162d0c8-25a1-5911-b3f4-0422cfa98d99 | note | Reference Documents - CL16.6.1
8228597f-c73b-526f-af9d-351be9066490 | note | Aconex ref: DCWC Mgt-GCOR-009281
25943020-9f4e-5ca1-bb79-37472b1edede | note | Inspection/Test Method - Document Review
ad6d63b5-fe57-5348-bd57-1d841f377ee4 | note | Record of conformity - Aconex
d8eba816-e46c-541d-aec8-fefd40c15961 | note | HP
57487e94-4c41-5a5e-8e96-638ad350df34 | note | Responsibility - Project/Site Engineer, Beca
179683db-9a8d-5462-955f-c7ee24fced30 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Pipe Support Cradles
8d618c69-5b5e-5645-817f-836c8e834b02 | note | Frequency - Prior to commencem ent of works
9c03adc9-e7de-52a6-993c-ccf61071cfe7 | note | Acceptance Criteria - Pipe to sit on firm foundation with pipe support cradles.
cea46deb-31cf-5803-af12-5fe92b2db20f | note | ○ Material submission/ Shop drawing submission.
b213bf5e-eb9c-5753-b606-7d40d87cd7e4 | note | Reference Documents - Cl16.5.6.1
a40cf2e5-0db3-51ea-b1c4-75fbd7cbc6d1 | note | Aconex ref: DCWC Mgt-GCOR-009496
076afd1f-35a5-5927-a7fc-edd5de7cec1e | note | Inspection/Test Method - Document Review
3a0220cb-cceb-5803-a539-4a7b71938cac | note | Record of conformity - Aconex
5acb6203-0f4b-5ceb-886a-84cdc070e164 | note | HP*
ec6daf90-e504-55df-a72d-5737e28ea03c | note | Responsibility - Project/Site Engineer
ee87f83a-c632-507e-9a14-1ea8ce2dcacd | date | Date Completed:
| checkpoint | 2.3 - Encasement Material
046121b9-b4f0-54f0-8a63-31d5a43a9243 | note | Frequency - Prior to commencem ent of works
cfed6de3-a0e4-56e6-a0f6-bd5a01012fcb | note | Acceptance Criteria - Encasement Material to be 5Mpa lean mix concrete for all RCP’s.
75304e44-4159-53f3-9435-58d198c06a7b | note | ○ Material submission approval.
549db1d7-fd4a-5eab-b6d1-07156f91fe49 | note | Reference Documents - Cl16.5.6.1 & 16.6.2.2 & Tender Clarifications #36
eb1080aa-021d-5be6-b979-d353ecb13764 | note | Aconex ref: BecaCPL-RTRFI-000089
1ed1078f-fff6-57f8-b1e1-0cf5460b2dd8 | note | Inspection/Test Method - Document Review
42d9471f-bd13-5359-b02c-cf38eb141023 | note | Record of conformity - Aconex
be559595-6804-5b57-ac83-af45fe1f80c8 | note | HP
2e927600-b0f8-50f9-b5ef-90d1180e4339 | note | Responsibility - Project/Site Engineer, Beca
378e34be-3bd9-5bee-b76f-f57c9a9a2a99 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Backfill Material
fa1e2509-551b-53e2-b3e4-40cc2b17a126 | note | Frequency - Prior to commencem ent of works
00ce685d-1629-5606-af60-85e42324d169 | note | Acceptance Criteria - Backfill material to be 6% cement stabilised sand to pavement formation level.
b7edf96b-f4dc-56ba-a385-62c46425914d | note | ○ Material submission approval.
1269190a-dcff-5390-9084-4e405c70093c | note | Reference Documents - Cl16.5.6, 16.5.6.3 (a)(i) & 16.6.2.2.
f4389ac0-ef80-594f-bf52-856b6d8aa05b | note | Aconex ref: BecaCPL-GCOR-000802
62c05dc6-f5a7-5245-b8ba-0b49ce5d172c | note | Inspection/Test Method - Document Review
1449f01c-c4aa-5c77-aa84-5af40b4e64e8 | note | Record of conformity - Aconex Ref
affd4a93-a921-5aa2-8cd0-44c441e6648d | note | HP
fd9f3fa5-4bfc-54a0-8e72-7bffd8a90810 | note | Responsibility - Project/Site Engineer, Beca
c7981258-9841-5a6b-88cc-4a9f38a7f6e3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 - Stormwater Delivery
| checkpoint | 3.1 - RCP Delivery
88e5903e-8133-58e3-8e64-8e8887c3b17a | note | Frequency - Each Delivery
9ab65ed4-0c52-5684-b951-353241be59b1 | note | Acceptance Criteria - Drainage pipes supplied and delivered as per approved Material submission.
041fa456-d7d6-5468-88a3-8afbf07b794a | note | ○ Manufacturer’s conformance report.
325517ec-3131-5c6c-8485-ad1ddfe7f2ff | note | Reference Documents - CL16.6.1 & AS4058
4f86dc35-1ead-595a-963f-52d63f59fb27 | note | Inspection/Test Method - Verify
6c5cabb9-9f3b-5c37-b5c0-8304d309bcb3 | note | Record of conformity - Order Acceptance Form
5f4e3bae-bc6b-59ba-969b-1387a4915c0c | note | IP
fdf5360e-5800-577c-ad9f-ffc483d77ba0 | note | Responsibility - Project/Site Engineer
67bc3511-85af-51e9-a897-ae6d65695009 | date | Date Completed:
| section | 4.0 - Construction Activities
| checkpoint | 4.1 - Survey Setout
184b7804-94df-5c10-9503-064b7e236985 | note | Frequency - Prior to construction and each lot
74e80b21-7b41-5c14-8fd1-0aaea06ed169 | note | Acceptance Criteria - Set out the stormwater drainage as shown on the Drawings to identify the locations, lengths and levels at outlets and inlets of pipes.
c997444a-d4ec-5293-9985-137593984628 | note | ○ This constitutes a Hold Point.
45c2e80c-419c-5521-b8b4-d3401d87004b | note | Reference Documents - Cl16.7.1
f12f3715-d50d-5ab2-ae65-f56d39c25ae4 | note | Inspection/Test Method - Survey
572ef53e-e8d6-50be-be91-ee3ee56e43f0 | note | Record of conformity - ITP Signed
39a0f67d-1725-5c40-9a71-dcb48f857a75 | note | HP
54ba654f-6272-5c0d-b9e1-ea03ebe60ed6 | note | Responsibility - Project/Site Engineer, Beca
fa4a235e-3294-560d-8789-a3d08c871e5a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Excavation
ae9b32ec-7fff-5d0a-9424-24163091f7a9 | note | Frequency - Each Lot
4d6accd7-8604-53a9-ba80-22e6de486899 | note | Acceptance Criteria - All excavation to be performed to the minimum depths, widths and batter slopes as shown on the Drawings, regardless of the type of material.
923600d7-e22b-5c6b-b9b3-98e96bec5038 | note | ○ Trench excavation is to commence at the downstream end, where practical.
c06bac9c-d541-57f4-9632-d0d3b38d1659 | note | ○ The width of trench to be such that the horizontal clearance from the outside of the pipe to wall of the trench to be minimum 300mm when under the runway and taxiway graded strip. Trench width outside of the runway and taxiway graded strip to be the greater of 150mm and D/6.
f20b6792-e317-56ec-9aab-88b5226f314c | note | ○ Subgrade Inspection to constitute a Hold Point.
107547f8-aa65-500c-ae0e-13c46097e260 | note | Reference Documents - Cl16.8.1 & Cl16.6.2.2
b4c9308b-6d7f-54c9-bb86-94b073803c26 | note | Inspection/Test Method - Verify
e4767b4c-5011-58e6-aed5-79760c673c48 | note | Record of conformity - ITP Signed
2ed83b9e-e250-51d5-9d5f-c97d45d2ec14 | note | HP
68cabd5c-0e9e-5d91-acd3-bdee66617bbb | note | Responsibility - Project/Site Engineer, Beca
a9d66231-9287-5067-8242-cbb0f31407c8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Site Dewatering
e99776f6-6cf4-5503-9c98-dd1a53bdacac | note | Frequency - Each Lot
389dad6e-d921-5c6e-84c1-f0e86313a748 | note | Acceptance Criteria - Excavations are to be kept free from water during construction and backfilling and provide pumps, well-points or other equipment as necessary.
b278c28b-7740-546c-9834-724a125c10a8 | note | ○ Any temporary works to be designed such that flooding upstream of the diversion does not occur. This constitutes a Hold Point.
c55d97ae-880c-5161-913e-dea6114660c2 | note | Reference Documents - Cl16.8.4
da00b571-a482-5590-8ee3-bbb311c60c04 | note | Inspection/Test Method - Site Inspection
93d02277-da10-5973-8a27-3ffba730c5a5 | note | Record of conformity - Aconex Ref
a7d77778-30f4-570c-a3f4-92e9ce0195a3 | note | HP
c829d6c5-3da0-555f-99f8-f98c7d2adf74 | note | Responsibility - Project/Site Engineer, Beca
8e733820-540c-5f3f-ba59-1d720e847f55 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Confirm Ground Conditions
c24d7f4c-211d-512c-8f62-fb8c74c5f909 | note | Frequency - Each Drainage Line
1f1e2149-09a6-5a8a-bf8e-05bcf9343e0e | note | Acceptance Criteria - Min. 1 x DCP test to be undertaken per drainage line / structure to confirm ground conditions. If the first DCP is inconclusive or fails, additional DCP to be taken as needed based on on-site assessment of the ground.
03f1408a-fcfa-59d9-9794-c463a54760c7 | note | ○ Contractor to notify the Contract Administrator of any area of the foundation which contains material that is inadequate to support the proposed drainage structure.
21488094-6570-5bb8-b7d2-27530887acab | note | ○ Inadequate material is deemed to have a bearing pressure less than 130kPa, equivalent to 4 DCP blows per 100mm, per note 4 on drawing ZULU-BECA-012-DWG-07102.
242cba19-a3d8-5f42-88f9-69b17170d46f | note | ○ Inadequate foundation material is to be replaced with a layer of coarse crushed aggregate compacted to 95% relative standard compaction to AS1289 Section 5.5.1 over a geotextile Bidim A29 or approved equivalent.
a504a46e-b0eb-5c9d-97d2-012af669a2a0 | note | Reference Documents - Cl16.8.2 & Tender Clarification 179
b45513b3-79a1-56a5-ad23-95b269d572e3 | note | Inspection/Test Method - Site Inspection
920754ad-5496-5649-ac23-cc159d334d41 | note | Record of conformity - DCP, Test Results
19a4ccca-6f42-515d-a026-65b358677d48 | note | TP
e0837cd8-3bb2-5877-86de-a5278106923e | note | Responsibility - Project/Site Engineer/ Beca
a252e786-e6c8-54d0-8b34-75422fb024b4 | date | Date Completed:
| checkpoint | 4.5 - Bedding
61b37c59-fb70-5d0e-a698-20adcac2ec80 | note | Frequency - Each Lot
af9fe81b-be0f-51af-9fc1-0aa0674506f3 | note | Acceptance Criteria - Bedding material/subgrade to be prepared for laying the pipes. Pipe support cradles to be placed on firm bedding. This constitutes a Witness Point.
a494ec9f-64b2-5c1a-adbb-3d56b1681edc | note | Reference Documents - Cl.16.6.2.1
3dbef3ef-2cbd-5041-8907-f8b8307af3a2 | note | Inspection/Test Method - Visual Inspection
1956b3b1-4e04-5e3e-9732-44247b2e39cf | note | Record of conformity - ITP Signed
b97739b7-6d89-55a2-b679-4865132d3009 | note | WP
092f1bf4-ab52-5aea-8233-0f976053f229 | note | Responsibility - Project/Site Engineer, Beca
d2238a42-f78c-584c-9962-043e884ad5b2 | date | Date Completed:
| checkpoint | 4.6 - Laying of Pipes (Sample)
b0f015fc-6552-5b29-bc8d-4109aaefe0fa | note | Frequency - First Lot
fdcea21a-b0f1-5a9e-9488-f4881b37681d | note | Acceptance Criteria - Initial sample 20m length of concrete pipeline to be laid and approved by the Contract Administrator for line and level before continuing construction of pipe network, Hold Point.
8154e474-aae9-522a-bb86-a36adaf49a47 | note | Reference Documents - Cl.16.9.1.6
ff430c75-267d-5dc4-9bb9-27ba336032d5 | note | Inspection/Test Method - Verify & Visual Inspection
c912703c-040e-512b-9f93-f947c2067b52 | note | Record of conformity - ITP Signed
0a819ca1-a073-554e-b852-5981530c427d | note | HP
45418fb0-ad6f-55e9-bb76-4c331754f30c | note | Responsibility - Project/Site Engineer, Beca
364dcce2-0e59-5280-b67b-e0c39dfd3bbe | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.7 - Laying and Jointing of Pipes
55ab6429-192d-55db-90d1-e22d55d14f86 | note | Frequency - Each Lot
7ff6eaa5-759b-58da-bcda-b470e99c9620 | note | Acceptance Criteria - Concrete Pipes to be rigidly supported by approved steel pipe cradle during laying.
1ab0c57c-d867-51c9-805d-1cfba53d82cb | note | ○ Pipes to be placed with spigot end facing downstream.
6fe829fb-2d02-5890-ba73-92b42ff58f96 | note | ○ Pipes to be laid with the word ‘TOP’ and or lifting holes uppermost. Lifting holes to be plugged after installation.
3f96e12c-a485-5858-aabe-f2cf56590f05 | note | ○ All Concrete Pipes to be checked and subject to the approval of the Contract Administrator prior to commencement of backfilling, Hold Point.
2fcb497d-7650-53d4-a543-98138cafc299 | note | Reference Documents - Cl.16.9.1.6
eaf88d90-0d84-5b9d-9e63-fcd1e3dd790c | note | Inspection/Test Method - Verify & Visual Inspection
4ad99015-63ff-5ef0-baa5-e0c2fe2c7d66 | note | Record of conformity - ITP Signed
6a597174-ca65-5552-882a-99ff143fd83e | note | HP
c92309d5-ae3a-50f4-9998-027105030665 | note | Responsibility - Project/Site Engineer, Beca
e2eaa18f-509d-5079-a636-1319ae775611 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.8 - Survey
19ba0200-7d70-5c1c-9869-0b767944f1c9 | note | Frequency - Each Lot
ba84b8bd-9cfc-5c75-8319-359bfbd60ead | note | Acceptance Criteria - The alignment, level and grade to be checked on the obvert of every third concrete pipe unit.
051e0e72-b396-5bac-8001-2c429bd84e51 | note | ○ Pipes shall be laid to the lines, grades and invert levels shown on the Drawings. No deviation shall be made without the prior approval of the Contract Administrator.
3bcbb87d-38bc-50b8-854c-b22cd0532cd9 | note | Deviation from Invert Level
9cfa4cdb-4a32-599c-897b-a0be107b8529 | note | ○ Maximum deviation from design invert level to not exceed 20mm and not result in zero grade or reversal of grade in any length of concrete pipe.
b404e9c4-7ff7-5ee3-9781-a07bfd70a889 | note | ○ Where the design pipe grade is less than 1%, maximum deviation from pipe socket to pipe socket does not exceed 20 mm.
bf35ce05-4c92-599f-848f-79c69bdded2a | note | ○ Maximum deviation from design invert level between upstream and downstream structures to not exceed 20mm and not result in zero grade or reversal of grade in any length of concrete pipe.
8ab47876-2624-553a-a091-f979dbe03713 | note | Deviation from Alignment
8746020d-7933-5d0a-94d6-715b8f5b708e | note | ○ Maximum deviation of the concrete pipe from the alignment shown on the Drawings to not exceed 25mm.
00bf8704-8b53-5f6d-90eb-dbeac1b3f060 | note | Reference Documents - Cl.16.7 & 16.9.1.6
98e36215-0999-5d5f-b355-ee54b245c97c | note | Inspection/Test Method - Survey
45d4783a-a78e-5de2-a1e9-a5aaae115305 | note | Record of conformity - Survey Report
e8c5c51b-7c73-5362-bbab-5bc699b81f75 | note | SCP
ec49249a-59ed-5f71-bd09-36378a6def97 | note | Responsibility - Project/Site Engineer
29281e2a-c5e9-596e-a91c-3ba3578fbc68 | date | Date Completed:
| checkpoint | 4.9 - Backfill Materials
d330036d-185e-5e46-8366-c2c7f4b375fe | note | Frequency - Each Lot
c465880e-2673-5fe3-a924-adb7d7121a49 | note | Acceptance Criteria - RCP’s under Runway and Taxiway Graded Strip
0ff8ca7d-6a9b-587d-82b3-ae0b80d2a9c6 | note | ○ 5MPa wet lean mix to 200mm above pipe obvert
b7a47116-f844-5054-8ea5-77a8929a72a8 | note | ○ 6% Cement Stabilised Sand to pavement formation level
2b325fbd-334e-55c4-a31c-ad9693321040 | note | RCP’s outside Runway and Taxiway Graded Strip
8e1d4e99-575a-5cb3-a0db-2ff00c22e48e | note | ○ 5MPa wet lean mix 150mm above pipe overt completed in stages
a2be7076-28f2-5a0b-989c-7dd7e1330b73 | note | ○ Site won material completed in 200mm loose layer thickness (maximum) to pavement formation level or 6% stabilised sand
be32f9d6-757b-5617-af9f-340f9192925c | note | Reference Documents - Cl.16.5.6 & IFC Drawings & Tender Clarification #164
599b4af8-1dfc-5861-8e5c-a43813aff579 | note | Inspection/Test Method - Verify and Site Inspection
c8ab4ca6-dd7b-503d-a5d1-861f531aca8e | note | Record of conformity - Delivery Docket and ITP Signed
0d893b32-e969-5749-b54c-411d59d73362 | note | IP
ada9dd1b-ddca-5e6e-b385-6d121df1925c | note | Responsibility - Project/Site Engineer
5b8512f3-b805-5670-9e2b-46b008eb4aa1 | date | Date Completed:
| section | 5.0 - Testing and Inspection
| checkpoint | 5.1 - Compaction Requirements (RCPs)
20cf176f-a6b7-5c20-a15f-3a00128219f6 | note | Frequency - 1 test per lot.
130a3c59-641f-510a-aa7a-32754c96dced | note | Acceptance Criteria - Concrete Backfill Under Runway and Taxiway Graded Strip
d7323c0b-d2a3-52ba-b3c3-bdbbc0c3869a | note | ○ 1 compressive strength test for each 50m3 of backfill
b81c3dbe-96d4-5cad-8aaa-3c074b3ed218 | note | Concrete Backfill Outside Runway and Taxiway Graded Strip
13116915-82ef-58ce-a250-2e687f1b84fa | note | ○ 1 compressive strength test for each 100m3 of backfill
5b0edd3d-8dc9-5638-81b6-d2af923ddc36 | note | Backfill Zone - Outside the Runway and Taxiway Graded Strip
28818352-ac85-59f9-9890-d6dc2ad38044 | note | ○ Minimum RD of 95% SMDD (1 lot consists of every 50m3 for concrete backfill and every 2nd layer of backfill zone material every 40m.)
50268ddf-4832-5a04-b762-7344556c95dc | note | Reference Documents - Cl.16.5.6.3 (c), Cl.16.9.6 & AS3798.1 Table 8.1
e4e7c828-7985-5b35-9867-0ed080422016 | note | Inspection/Test Method - Site Inspection
7c2f5a42-9f8d-5f65-b4c2-8ab18d53ae71 | note | Record of conformity - Test Records
c98f2819-da3f-5a3b-9606-d21d1a15883d | note | TP
f5adbcf0-2707-52f6-844c-97e15c83e568 | note | Responsibility - Project/Site Engineer
49e3653e-dbb4-598c-928a-a15de17bcc47 | date | Date Completed:
| checkpoint | 5.2 - Inspection of drainage lines
dc0e3d4b-5cd4-5d5d-a0ed-7e2dd2a289ab | note | Frequency - Prior to constructing pavement
6dd1734b-9742-579c-9bb6-cb16e9c5a269 | note | Acceptance Criteria - CCTV inspection of RCPs required at the completion of the works.
65d7ac9b-b970-5c02-bb61-569d311577b3 | note | ○ Submission of CCTV footage to the Contract Administrator for review is a Hold Point.
21589f61-502d-5693-b289-8a8c5369d97a | note | Reference Documents - Cl.16.10.1
bd1cb358-993c-50bd-b162-888a5e2fe05e | note | Inspection/Test Method - Verify
5bfc6948-2c78-54c6-8b42-5e86765dbe38 | note | Record of conformity - Aconex Ref
5125a29a-784c-58df-bca6-136d172fd69d | note | HP
0a750240-ecff-52c8-9832-f0ad5e348793 | note | Responsibility - Project/Site Engineer, Beca
84fa9f99-d2e5-53e8-991a-df278960a6a1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
07843a40-ad75-597b-8d27-a2d33627f1bb | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
74bea63c-2144-54cf-8d9c-2c5d0a5c32bb | textbox | Print Name:
ceef9121-eb7a-57ad-9b81-0ff6d16629d8 | textbox | Position:
93d9e161-3a8c-5069-bbc8-466eab8fc03c | date | Work Completed On:
4ad221ca-63b8-5fac-8d71-1d492ee82fa6 | date | Date:
| checklist | FH-ZU2-QU-ITP038 - Native Grass Protection - Rev 0 | itp | ITP038 - Native Grass Protection | 89ecd1f5-7610-456b-acae-3bd03e903aaa
| section | 1.0 - Preliminary Activities
| checkpoint | 1.1 - Check for correct documentation
216f13c0-631a-5de2-b0e8-fa6c90d79a55 | note | Frequency - Prior to site establishment
4865a96d-3c1c-56af-ac3c-5e4505e5a0ca | note | Acceptance Criteria - Review whether a preliminary report has been completed for the project which will outline where the Significant native grasses are and what protection has been specified.
a8a796cf-5317-54bd-91f0-127b840b229c | note | Reference Documents - Consultant reports
dfc0e17f-a7fb-5399-964b-061ad1ddcade | note | Inspection/Test Method - Visual inspection
b60740c1-039b-5ee9-ad44-5eb87146d68c | note | Record of conformity - This Signed ITP
a12a05ea-f6c1-5ec7-90cf-9d30a6834ce0 | note | HP*
d8df4a35-931a-583d-9715-e1beb93e2b7d | note | Responsibility - FH Project Engineer
46867ecf-e671-59a9-882b-a222ccf7f921 | date | Date Completed:
| checkpoint | 1.2 - Check the Google Earth Mapping
7d49b9ed-235a-52ce-a8f4-2de6272b0539 | note | Frequency - During site establishment
0935c216-bfa9-53fa-aa5e-6a24aadf877e | note | Acceptance Criteria - Review the Google Earth / GIS mapping which outlines the boundary of the native grasses at the time they were mapped.
890b0dca-2ad6-57f6-a256-cfbac6c3fd1e | note | Reference Documents - Google Earth Mapping
e828aed7-b6b9-5af5-b39a-7cfd2ba13139 | note | Inspection/Test Method - Visual inspection
4c63015d-0410-5dfe-84b1-0f2a44f6494f | note | Record of conformity - This Signed ITP
3f02a3d8-03b7-52b6-bcef-69cc7373f799 | note | HP*
5fa5b223-a8d4-5c5f-a979-66255446357f | note | Responsibility - FH Project Engineer
66c722a9-7fb1-53a7-a3c3-49221e73ac68 | date | Date Completed:
| section | 3.0 - Implementation of Controls to Protect the Native Grasses
| checkpoint | 3.1 - Mark out the exact Significant Native Grass Boundary area
7b9cc617-651f-548d-84f2-c5bfa7195818 | note | Frequency - Prior to commencing any activity
9e5247df-1849-5d0a-ac94-738ed0a240e9 | note | Acceptance Criteria - Work with the surveyor to mark out the Significant Native grass boundary. FH Project Engineer must verify the set out survey data file matches the ECP and GIS.
cd48b603-4e2c-5241-977e-2b838e386106 | note | Reference Documents - CEMP & ECP
f03b23f5-4e4f-5063-9515-445644e52b43 | note | Inspection/Test Method - Inspect
9c11c12f-352e-5db0-92c6-9953921e13eb | note | Record of conformity - This Signed ITP
604250c5-a2c0-5718-be33-25a53ed49fc6 | note | HP*
9405f436-a806-556a-ba3b-73cb5cfa7103 | note | Responsibility - FH Project Engineer
9d3efbad-6c9d-5657-8277-15af080be725 | date | Date Completed:
| checkpoint | 3.2 - Use temporary fencing/bollards and signage to block access to the Significant native grasses where we are working in close proximity.
55b2ead0-5305-5d1f-ba70-df0cc5ef6528 | note | Frequency - Prior to commencing any activity
d56d6f01-1109-59d9-a58c-202e8297dc02 | note | Acceptance Criteria - For works in close proximity to the native grasses, use temporary fencing or purple bollards to block access with signage stating “NO GO ZONE NATIVE GRASSES”. Where possible, this fencing will be installed at a distance (1-2m) away from the actual native grass boundary to act as a ‘buffer zone’ but still allows works to progress.
231e9034-3722-5440-abdd-2a691a73f168 | note | Reference Documents - CEMP & ECP
a6e5d715-ee40-54cb-b489-1074dc6ab1ef | note | Inspection/Test Method - Inspect
684fa277-9e04-5df0-973b-bd4fabbba96d | note | Record of conformity - This Signed ITP
de894924-de20-55a4-b2fe-e3e9090e645a | note | HP*
6518d271-ff9d-52a6-968d-1aad7fb2d35d | note | Responsibility - FH Project Engineer
2ecb63d8-d93a-5324-8656-94f77f649fcc | date | Date Completed:
| checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
ce3ec308-c40b-5654-b01b-fa9c462bc99b | note | Frequency - Prior to commencing any activity
70eb4d5a-2c35-533f-ba80-b2090e69c2d5 | note | Acceptance Criteria - Inspected and validate native grass delineation has been installed correctly using GPS mapping and against the design drawings.
8c06eace-458d-5889-9803-a0bfb7305238 | note | Reference Documents - CEMP & EMP
2ce81219-11a7-53b2-a7c1-08a4a9fa3dff | note | Inspection/Test Method - Inspect
57032812-6950-579e-9bdf-0d3204896163 | note | Record of conformity - This signed ITP
15f24092-ef40-59e0-ab53-bbc888e9c3b8 | note | HP
590151ac-7781-5df5-aa78-61f32f38673c | note | Responsibility - FH Project Engineer
62376a53-799c-5c5d-8b46-8a01aacbcda3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 - APAM Hold Point Release - Second Inspection
| checkpoint | 4.1 - Release of Hold Point for Native grass Protection
1514a478-e8a2-5956-97af-5aac277f7c60 | note | Frequency - Prior to commencing construction
16698acc-f712-57d3-b446-36cc47b8d676 | note | Acceptance Criteria - Arrange an APAM inspection to confirm that the native grasses are protected with the required temporary fencing or bollards and correct signage where required.
aaf09a0d-10a7-5d7f-a40f-7880b7f29fff | note | ○ All parties are to sign off on this Hold Point
a554ba14-e259-5b74-b82d-e33ccc278e93 | note | ○ Release document
67135554-3eb0-59e4-a017-9fb6cf9b2ec2 | note | Reference Documents - CEMP and ECP
caa3d8fb-e362-53c7-9629-09e294870f5e | note | Inspection/Test Method - Visual
ed9995a5-92ad-5c82-9a71-76ef981f15f0 | note | Record of conformity - This Signed ITP
1d5a99cf-1eba-516a-bf5d-b9c2d13d1c2a | note | HP
bfc9749e-effb-5925-9977-03a5ebc89408 | note | Responsibility - APAM, Fulton Hogan Environmental Manager or Project Manager
848286a1-04f4-5425-ba4c-0c33c6fc3015 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
c1cfe4e5-b9a8-5a77-804a-a216757322c9 | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
e2acd868-285d-5070-b4a5-44cdc9e52994 | textbox | Print Name:
359709b0-92ea-5762-b403-eb9708784de7 | textbox | Position:
a0ff56c3-768f-5bb6-8989-1c9828e97505 | date | Work Completed On:
c839de23-6ced-54fe-91ad-70b2eca78835 | date | Date:
| checklist | FH-ZU2-QU-ITP002 - Site Establishment - Rev 0 | itp | ITP002 - Site Establishment | 8beded60-2c75-4e81-b432-c4a0e26e2509
| section | 1.0 - Preliminary Activities
| checkpoint | 1.1 - Check for correct documentation
3cfc1515-1fe7-5182-8110-095e2a556c32 | note | Frequency - Prior to works
5f979054-727e-54aa-8645-fb79302086c9 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
7a7b835a-87b9-5819-b24a-054c8dcd3994 | note | – Using the correct and complete set of drawings.
f8079544-3881-5620-98b8-59beb27370c3 | note | – All drawings are the latest revision
a8475448-f144-5495-b5fc-6993900571fa | note | Reference Documents - Work Pack
bf8a3dd4-0e62-571f-98da-683c260cb359 | note | Inspection/Test Method - Verify
958ce004-234e-5e71-88fd-6fa4b18a21bd | note | Record of conformity - This ITP signed
90469bb2-d27a-536c-acea-5544ec8976bb | note | IP
8ce14f19-a51e-55f3-81ea-0f8a06940dd7 | note | Responsibility - Project/Site Engineer
0f7b1605-06d9-53a7-9a06-c33e112dd6ee | date | Date Completed:
| checkpoint | 1.2 - Dilapidation Report
c2bcdd88-d14e-5d6b-a936-b84cdcbd0466 | note | Frequency - Prior to works
c26ff740-c231-52ba-b06c-8c6efda807a6 | note | Acceptance Criteria - A dilapidation report is to be completed and submitted prior to works on site. Dilapidation report to include photos and recordings of the condition of the site compounds areas prior to start.
e5b19e94-a206-5ae9-b7b5-3bebbc124d70 | note | Reference Documents - Dilapidation Report
abf9fb6f-e6bd-5b84-9c6c-bbb1fc04293c | note | Inspection/Test Method - Verify
61cbd3d1-e908-5933-b041-d38e71e0f6e0 | note | Record of conformity - Aconex & This ITP signed
ec2200f5-4a02-51e7-88e8-2ba60278d73c | note | HP*
87eb43cf-d3bc-5448-a56b-f2b3d9588de5 | note | Responsibility - Project/Site Engineer
8170464f-1e89-5ae7-a7f9-ea5bf1cb95d9 | date | Date Completed:
| checkpoint | 1.3 - Existing Service Identification & Protection
c91f897a-bbb9-557f-b0d6-b68cad614832 | note | Frequency - Prior to works
a5f8e5b3-8e44-5306-a72b-ed5465d53ee9 | note | Acceptance Criteria - Hardstand area has current BYD plans, service scanned, and existing services has been proved. Services have been identified and protected prior to demolition.
dabcbcc8-a24c-5a75-8c79-37a520ffe796 | note | Reference Documents - BYDA, Survey Maps
db005276-8c78-56db-84ad-8194afcea8e2 | note | Inspection/Test Method - Verify
1f97c349-d1c4-5349-ab1c-9fbb364f8e06 | note | Record of conformity - This ITP signed
761d0319-0a04-56dc-82fc-3e7a37a2af9a | note | IP
4d9a8f6a-9164-5dfa-9de7-9b1576639340 | note | Responsibility - Surveyor, Project/Site Engineer
3a1c9c80-0467-5605-9459-fd9cf9a7a741 | date | Date Completed:
| checkpoint | 1.4 - Implementation of control measures
2102382c-98b4-55ec-b64f-c362f5d93de1 | note | Frequency - Prior to works
82f3d642-92cf-5365-a9d8-ac7a7ad9079a | note | Acceptance Criteria - All necessary control measures are being implemented, which include PSP, ECP, TMP, SWMS and WP
1106c405-6435-545f-8e0c-fbce99609408 | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
c8f203b8-de9d-538c-9fa8-de265c221722 | note | Inspection/Test Method - Verify
2e4e799e-1a58-58cc-8183-e0c31531b986 | note | Record of conformity - This ITP signed
ad65f495-a215-5c46-b32d-c93fd03a6710 | note | IP
9624af7e-36c8-5a93-8425-4efbc949557c | note | Responsibility - Project/Site Engineer
b6171726-97ec-5f08-9180-4fb7cb54bb40 | date | Date Completed:
| checkpoint | 1.5 - Testing
56b0609c-3136-5adb-99e7-6dcebb30eb90 | note | Frequency - Prior to works
0fa57451-1e5c-5b06-ab1c-28c81e6b2bc7 | note | Acceptance Criteria - Ensure PFAS testing has been completed. The results of the testing will be used to determine the appropriate disposal or re-use of the demolished materials.
1ccf6cf2-b3af-5025-8e17-a48c645c1d2a | note | Reference Documents - Aconex
efded1df-a4f6-5702-8cfc-40a516be814f | note | Inspection/Test Method - Verify
875c58e8-5650-55dd-98e5-667a9fad9d8d | note | Record of conformity - This ITP signed and test report
88f43a90-dbaa-55a4-813d-f7e661c27c40 | note | HP*
121c1f21-fd9f-58f7-bf2a-77c8dcf0392c | note | Responsibility - Project/Site Engineer
ede39bc6-21e6-5577-89e6-4f486939a620 | date | Date Completed:
| checkpoint | 1.6 - Excavation Permits
438f0943-5177-502b-8329-f1c93846ee19 | note | Frequency - Prior to works
626de8fa-07e5-5ee3-8890-a365da489a19 | note | Acceptance Criteria - Prior to works, check that excavation permit has been obtained from APAM prior to any ground penetrating works. Internal Fulton Hogan permit has been issued for excavation works and plant operators have a Go-Card.
a54e3c31-8e56-52bd-bb6a-6e561a515ea8 | note | Reference Documents - APAM Excavation permit, FH Permit, Go-Cards
acb02066-1e9f-5d4e-a02b-3524ecf65518 | note | Inspection/Test Method - Verify
8e9c8bd5-f7ac-5969-a618-e51bcce70ad7 | note | Record of conformity - Excavation Permit
3f36bc56-a1ae-5524-a1b5-203eb3437f1b | note | HP*
2ea25830-60bd-5a21-9281-8bb933f3dddb | note | Responsibility - Project/Site Engineer
53bb5044-b0c6-587d-96c6-ef4f3c40ef13 | date | Date Completed:
| checkpoint | 1.7 - Geotechnical Testing
a4717674-a002-501b-becd-3542952ad92d | note | Frequency - Prior to works
1a27f139-cfa4-5855-b846-c7ceca0c45fc | note | Acceptance Criteria - Ensure testing is carried out to obtain a Hardstand design that meets the requirements and suitable for use.
aa6eaba6-6550-5320-bc28-5704f826047b | note | Reference Documents - APAM Excavation permit, FH Permit, Go-Cards, FH spec
d1e480aa-8ca8-59b1-b0d9-8911b71b7fb2 | note | Inspection/Test Method - Verify
7a3e9e1d-e818-5582-a74a-5742912a6702 | note | Record of conformity - Excavation Permit
55237742-d7d0-5ba3-aae7-197b754af9e0 | note | HP*
f6691999-63d4-5007-a230-0e782e5acee6 | note | Responsibility - Project/Site Engineer
7bea0aba-af66-5129-8dfa-567546d0a78d | date | Date Completed:
| section | 2.0 - Building Hardstands
| checkpoint | 2.1 - Definition of a works area (survey)
1495f105-79ac-5ae6-958c-b8af2f0917fd | note | Frequency - Each Hardstand
01e59542-55ff-56a7-aa8c-3bd66f93bf12 | note | Acceptance Criteria - Work area has been cleaned and surveyed (marked on site). Limits of hardstands are clearly marked.
d24c548c-733b-5b2f-abf7-fb8acbda0a0a | note | Reference Documents - Site Markups, Survey layouts
b3aeb841-330e-5fb0-bc8f-0c972c71cd39 | note | Inspection/Test Method - Verify
6a1d4755-e820-59c7-877f-a8267b2a731b | note | Record of conformity - This ITP signed
8b048cc1-d142-5981-852a-346e271051c3 | note | IP
263c11bc-6929-5a56-9e2b-d67036efd2c1 | note | Responsibility - Project/Site Engineer, Surveyor
f2fb3fe2-53a4-5a0c-a34d-21a5c29f3c5d | date | Date Completed:
| checkpoint | 2.2 - Preparing subgrade
0500d3f1-331d-53cf-92e7-71e3c5882841 | note | Frequency - Each Hardstand
2056ded0-8e4b-5e8a-97af-bb9d5e1849f8 | note | Acceptance Criteria - Ensure topsoil stripped as per hardstand temp design and subgrade compacted to meet design requirements from Geotechnical Engineer.
b9d6dd20-7633-5fc9-934b-2e738cabf5b7 | note | Reference Documents - Geotechnical temp design
cff19e40-fcb9-544a-94e4-101c985beb63 | note | Inspection/Test Method - Verify
4ef23d7c-8ee6-5f4f-93d3-276683bfb7d0 | note | Record of conformity - This ITP signed
7ca16b4b-c013-5661-866b-649b18a4799c | note | IP
adf3bda5-8f3a-5328-aa10-88d2359ad0e5 | note | Responsibility - Project/Site Engineer, Foreman
2ed9a8c6-51e9-55d1-ab26-0b8d28996d2a | date | Date Completed:
| checkpoint | 2.3 - Disposal of Material
5a4695fc-fed9-5d39-993b-510f73c26ba4 | note | Frequency - As Required
3647b628-1080-5ac0-b783-d8115721a752 | note | Acceptance Criteria - Contaminated or PFAS materials are to be taken to Gate 11 to be stockpiled into their dedicated category and contaminant.
663f3cad-596d-5600-ac40-ce55a7eb5859 | note | Reference Documents - Negri PFAS Permit
21926fa3-6a6b-5ba1-b5a7-04ec5295ffab | note | Inspection/Test Method - Verify
1051b69c-784e-5baa-821a-685cf463f56f | note | Record of conformity - This ITP signed and Negri Permit
14b22d9f-12b9-54c5-baf2-d886cd44341f | note | IP
8c75014e-8b2e-599f-8b71-9df089d86128 | note | Responsibility - Project/Site Engineer, Foreman
a38167de-9652-580c-b90b-bc2a92606021 | date | Date Completed:
| checkpoint | 2.4 - Building Hardstand
00812335-82b0-5f82-a978-d66410fe7bbb | note | Frequency - Each Hardstand
948565d6-733a-5129-949a-6d6626132e7b | note | Acceptance Criteria - Make sure hardstand is built according to the geotechnical temp design, no soft spots existing after proof rolling.
13626329-6635-5e4f-ab0d-9320cbea65c8 | note | Reference Documents - Geotechnical temp design
3ba010e5-4f98-50ab-9f06-1e842ade4b3a | note | Inspection/Test Method - Verify
e55312eb-1212-5945-b08d-29d1795a93f1 | note | Record of conformity - This ITP signed
fac0995c-3df7-564b-88ba-c6ef256d86c6 | note | HP*
07acc568-4d34-5e61-80ba-8d566d18a14a | note | Responsibility - Project/Site Engineer, Foreman, Geotechnical Engineer
033a81d7-b825-5c67-807e-e2a45faea285 | date | Date Completed:
| checkpoint | 2.5 - Building Crossways
24afd2cf-7314-5d7d-8524-bb6e52f39473 | note | Frequency - As Required
6951fa49-1dc5-561e-a19a-05594f2f1e53 | note | Acceptance Criteria - Construct culvert crossing/driveway access where required as per the temporary design.
7af45202-667f-5d7d-844b-376be1ae9dce | note | Reference Documents - Temporary Design
9993275a-e295-5c89-8fea-488eed4ed7d0 | note | Inspection/Test Method - Verify
555f84ed-9ffb-5bac-94b6-eed048703976 | note | Record of conformity - This ITP signed
09403b2b-f310-53d7-9b6d-107cf6c40f3e | note | HP*
bc825d6d-54af-53f1-896d-cdcd4437350a | note | Responsibility - Project/Site Engineer, Foreman
4fae311f-986e-5084-9887-13b447c20d07 | date | Date Completed:
| checkpoint | 2.6 - Installing Fencing
2d642617-6f94-57c4-a8cb-79d6413ad8e3 | note | Frequency - As Required
6a4b3d31-c75a-5a35-ab95-c6707a983f3f | note | Acceptance Criteria - Fencing installation is done as per the temp design or Australian standards AS4687
cee0728a-ca97-52b3-9931-596a16407ea8 | note | Reference Documents - Temporary Design
70d40084-dc8c-5ebd-859a-3361fde9f881 | note | Inspection/Test Method - Visual inspection & verify
ad67a3d9-bcff-53d7-b960-693d887c30a7 | note | Record of conformity - This ITP signed
ae9c735d-ac9d-533c-9799-f4cd5f930588 | note | HP*
e81d5045-3b97-50c8-a580-ffe7680ddca9 | note | Responsibility - Project/Site Engineer, Foreman
613c1904-3c34-59be-aff9-6aabec9d5697 | date | Date Completed:
| section | 3.0 - Mobilization and Set Up
| checkpoint | 3.1 - Landing and Levelling Sheds
7df20ce7-1bce-5bad-b012-07f31c438756 | note | Frequency - Each Hardstand
16d6c691-10b3-547e-bf53-e42c8b13e516 | note | Acceptance Criteria - Sheds are level and as per the site management plan.
e01217b5-9153-58bc-bbdc-18783838db10 | note | Reference Documents - Manufacturers specification
797168ac-a472-531f-9cd6-fe49616e8dd9 | note | Inspection/Test Method - Visual Inspection
1c18e28a-aeb6-56af-8b04-09385f08da47 | note | Record of conformity - This ITP signed
6b27caa2-19ff-5478-9a42-982c2b053420 | note | HP*
ed054c00-a465-57f1-9e8d-e2841ca4ef42 | note | Responsibility - Project/Site Engineer, Foreman
8bae08db-8d08-599d-add9-df806f7f6e72 | date | Date Completed:
| checkpoint | 3.2 - Erecting Hayshed
57049837-e6ce-58e4-848a-828da521ef1f | note | Frequency - Each Hardstand
bd1ac969-30a5-59cf-948e-d25e80e4213c | note | Acceptance Criteria - Hayshed has been constructed as per the verified temporary design provided by OPT
d818c8d1-37c4-5d90-9795-51b1448746f6 | note | Reference Documents - Temporary Design
c2c6e331-eebf-5ab1-b63d-5dae1c5edf6e | note | Inspection/Test Method - Verify
a79d71dd-7cce-52a7-a077-d8d34fef6462 | note | Record of conformity - This ITP signed
07272eac-048d-54b3-a9a7-324c54f19912 | note | HP*
475e6078-bd4f-58d3-9584-8dfbbf0e0133 | note | Responsibility - Project/Site Engineer, Foreman
791c8721-250c-51ba-9c7a-873b0d6eb072 | date | Date Completed:
| checkpoint | 3.3 - Connecting electrical and plumbing services and appliances
52c6b1ec-caa5-507b-b7ee-81561729edb9 | note | Frequency - Each Hardstand
74ee067a-3644-5bd6-bc78-7023ae184444 | note | Acceptance Criteria - All appliances and connections are functional and tested and tagged
37ddfe63-6932-5aa1-be1b-260df3edf73c | note | Inspection/Test Method - Verify
f9f078d4-88a9-532e-9806-4bd6abf31f24 | note | Record of conformity - This ITP signed
f4e10d7d-947f-5f4c-80e2-bcf1d06ffc36 | note | HP*
d84d564b-45d2-566a-bd7f-4d5be6c4422a | note | Responsibility - Project/Site Engineer, Foreman
2bee9357-f1c3-5394-87f1-7515da434d13 | date | Date Completed:
| checkpoint | Final Inspection
26cc0429-e587-5450-b454-1ebe89d0daf6 | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
383b649f-0c48-5212-8c94-fd8b492b7fc4 | textbox | Print Name:
0cf105b1-a508-5f4b-aa82-8acee5a17fd9 | textbox | Position:
2e5731f2-7afe-535e-97ba-f3610e5d15c5 | date | Work Completed On:
2c9bcd1c-9204-524f-9d2e-3f7b651761c8 | date | Date:
| checklist | FH-ZU2-QU-ITP028 - AGL MAG Signs - Rev 0 | itp | ITP028 - AGL MAG Signs | 998e41cf-f4a0-4879-9b7e-910b1b9f86b1
| section | 1.0 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
8ddc60c2-52d6-5ba3-bb5f-c822692ca78e | note | Frequency - Prior to commencing any activity
6df18c19-7c6f-50f9-b677-3f2b959531f8 | note | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
f9da8ea9-89b7-5f0e-b989-84b6a8b80b8e | note | Reference Documents - IFC Drawings
4683521a-f900-5473-98f3-a67b4f6ea1e5 | note | Inspection/Test Method - Verify
674379bd-c284-5e3d-873f-ce09bf739c70 | note | Record of conformity - Drawings
d8eb3e01-fda0-5c31-856a-83c759b25a3e | note | IP
175b6b71-cc52-516e-8e9f-846a379cfcc0 | note | Responsibility - Project Engineer
dfc620fd-985a-53d1-b486-992f4c1d8362 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
260a7c4b-a99c-5a02-adad-d000ceabfd8b | note | Frequency - Prior to commencing any activities
813e3056-3b3e-51c9-8d23-d749416004b0 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
c9605aa4-86a1-52a6-83ce-2ee4605031fa | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
b313f28e-2438-582e-ab7c-e25ba2da9340 | note | Inspection/Test Method - Verify
2224f6d5-342a-592e-9d5c-41029967a1a7 | note | Record of conformity - Site and office Inspection
d87775a1-ef24-51a6-a318-1ccc0adeec75 | note | HP*
cf72e15b-9c45-5942-92d3-14461509a1d6 | note | Responsibility - Project Engineer / Site Supervisor
0b8b7bbc-9c92-59c0-8160-fb26bad4aa5b | date | Date Completed:
| checkpoint | 1.3 - Material/Equipment Approvals
48893bdb-4389-5907-9976-dd6ddf0f8c56 | note | Frequency - Prior to start
34c061f0-7aee-5109-a88b-625ab5d38f62 | note | Acceptance Criteria - All materials shall be proven to meet contractual requirements prior to acceptance.
5fe73daf-9af6-5110-a145-b770a0022e1e | note | ○ MAGS shall be from ATG Airfield guidance signs range.
a6532fa3-d5e3-5a41-b2ab-395352d6acc5 | note | ○ Any deviation from the above suppliers shall be submitted to the Contract Administrator for approval prior to ordering.
13379fa6-158f-5a66-95b5-84d65aff3b24 | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl 2.3
cb7f38e8-7634-5cc9-9ed5-70723d66218a | note | Inspection/Test Method - Verify
e44fdd8a-7997-5917-bd17-07bd45a39200 | note | Record of conformity - Aconex reference(s)
919a5e4d-2e49-546d-8fa5-373dcb126d7d | note | HP*
d445324b-b5cb-5add-a93b-5fb130ce1c55 | note | Responsibility - Project Engineer
bd170232-4df1-5bea-aee7-01b489ce921c | date | Date Completed:
| section | 2.0 - Installation of MAG Sign Footing
| checkpoint | 2.1 - MAG Sign Base
b5e75d4b-ba5e-512f-b305-af4a72153d70 | note | Frequency - Each lot
54b5f099-4b4e-5e08-8742-199530135d52 | note | Acceptance Criteria - Position of rectangular base to be as per set out coordinated listed in MAG schedule.
68a3f16a-00de-5635-ac38-c10fc7eb2b48 | note | ○ 150mm thick class 2 crushed rock base layer compacted to 98% STD on prepared subgrade.
efcf5c26-7fbd-57b8-b37e-3b3bbed3a269 | note | ○ Subgrade Bearing strength of 130kPA confirmed by a qualified geotechnical engineer on behalf of the contractor before placing membrane, reinforcement or concrete.
26c34011-20fb-5b2b-9342-d03d93dab5ec | note | ○ 50mm blinding concrete between subgrade and foundation.
1361518f-7030-5a8b-a82c-5bf3e706f9a8 | note | ○ Slab thickness to be 300mm for all H<900mm signs, min. 32 MPa concrete.
28cefa2c-b332-5be7-8348-f7c0639fcf1a | note | ○ Footing to be placed flush with FSL when placed in pavement surfaced areas.
d3bc008f-5ac3-5001-965d-721918b27030 | note | ○ N12-200 top and bottom reinforcing bars with minimum 50mm cover from edge of concrete.
0e9e1085-36c9-552e-a6f2-0803bba1b4aa | note | ○ Sign mounting brackets and frangible coupling as per manufacturers guidelines
99b4b9d2-8f6f-5b2c-bbe0-ca5e4ef81b1a | note | Reference Documents - ZULU-BECA-023-DWG-07502
2c46142e-8c92-580a-b15c-8143787bd00b | note | Inspection/Test Method - Visual Inspection
fa5695c3-bc1c-5393-a2dd-5c2d327be5c6 | note | Record of conformity - This ITP signed, DCP test result, Concrete test certificate, Avionics Installation of New MAG Slab and Sign checklist
fbd2220d-bd86-5e38-a782-43c2d0712fe1 | note | IP
17c8bcb1-6358-5a68-826b-72b35e9e546e | note | Responsibility - Project Engineer
1661ae28-e9c6-53cb-88e0-dcd5b3024934 | date | Date Completed:
| section | 3.0 - Installation of MAG Sign
| checkpoint | 3.1 - Luminaire Circuit
649045eb-7b83-5714-8fcd-5679b6a48f55 | note | Frequency - Each lot
35f7888b-a995-585d-ba71-3d5588cae03a | note | Acceptance Criteria - Each luminaire fitting shall be installed on the appropriate circuit as specified in the AGL schedule.
c4f8306d-842a-546b-83a0-de6e924ee263 | note | Reference Documents - ZULU-BECA-024-DWG-09001-16
4736f50d-ba8b-5e52-8973-cfffbf02d65d | note | Inspection/Test Method - Verify
b74f2399-6413-5405-8088-8793ec0d8281 | note | Record of conformity - This ITP signed, As-Built Documentation
f7953965-0b65-517b-aa70-b79462b51b48 | note | IP
3b31a614-8e8a-556a-b653-a0225400d8e5 | note | Responsibility - Project Engineer
0b78267f-d355-55de-877f-46da63527d4b | date | Date Completed:
| checkpoint | 3.2 - MAG Sign Face
e271b798-8392-52fa-bbc9-fcc5c50d9445 | note | Frequency - Each lot
65e89ebe-45e9-5dfe-9fb5-16068bb9c2a4 | note | Acceptance Criteria - All MAGS that are to be mounted on frangible couplings. The provision of internal illumination of the MAGS shall be as detailed on the Drawings.
2418b2c0-d908-590e-a501-656146b5875f | note | ○ Bird spikes provided with MAGS Chain tether installed on side further from taxiway and installed as per manufacturer’s recommendations
aae51f8e-af26-5831-b4e5-ee1b4d57ac58 | note | ○ Where multiple panels are required, the inscription shall appear continuous over any joint and shall only include a bar if the bar is part of the inscription.
9d39b429-0499-5f89-8c13-88ff7fa8ee14 | note | Reference Documents - ZULU-BECA-001-SPC-00003 cl 4.7.1
ddb0b542-b302-5082-8da0-213b3846b37f | note | Inspection/Test Method - Verify
bc671c39-5ef8-5b06-bc94-7c327ca06502 | note | Record of conformity - This ITP signed, Avionics Installation of New MAG Slab and Sign checklist
807e5a06-a1dc-5e4c-8900-cab92739b26f | note | IP
f1ab977d-08e0-5a56-bc90-8394e3858bd3 | note | Responsibility - Project Engineer
41095d3a-5d75-5593-927e-01d84d3868f8 | date | Date Completed:
| section | 4.0 - Post Construction
| checkpoint | 4.1 - As-Built
d2db8983-8962-5251-8907-3a1af8d4868b | note | Frequency - Each lot
d40e1033-e6a3-5a67-ba70-c917adff63e0 | note | Acceptance Criteria - Submission of surveyed luminaire position to superintendent prior to practical completion
13b6ec89-5610-5d0c-bab6-59a273075fdd | note | Reference Documents - WP-001-09
887bebae-c0ad-58b6-85b9-cd2ff8c8f678 | note | Inspection/Test Method - Verify
61623fca-ce75-5d91-8d5d-d6ab18564d4d | note | Record of conformity - SCP
a5c81aff-54c0-5186-b766-f50c3760b787 | note | IP
f9903796-9cf8-5ea2-b162-9e3f120f9827 | note | Responsibility - Project Engineer
bb1d6c76-c8ea-5a38-b46f-92638b522829 | date | Date Completed:
| checkpoint | Final Inspection
c44b9953-a27c-53c7-86a8-3482ecbc51a0 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
dadff64c-aa37-5bda-834d-acbbc2fccf63 | textbox | Print Name:
b3256f93-fe30-5261-ba15-c2ca5080105d | textbox | Position:
22333328-1ec8-5b1f-b442-2c4df6d45cbc | date | Work Completed On:
915032fe-efc9-5633-8c63-2d8aa5994c45 | date | Date:
| checklist | Order Acceptance Certificate |  | Order Acceptance Certificate - Lot: | d9fa5533-4678-44db-ad39-7d61dd04ee01
| section | Details
| checkpoint | Order Acceptance Certificate -- Details:
12a7c1e5-72a9-5807-befc-b9efc424750a | textbox | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
5af93389-f25c-5d80-b77f-39a4818315e4 | textbox | Order No.:
4133d23c-5515-5362-b530-be47a6518f52 | textbox | Delivery Site/Location:
cd8c425f-9f53-5c2d-ad08-4b2c599e8049 | date | Date on which materials delivered:
c0097141-a841-55bf-8ae3-c53f2873beca | dropdown | Inspecting Engineer: | Abdallah Saidan, Abdul Saad, Alex Soo, Angela Julianto, Brad Carroll, Chris Cappelleri, Cristin Swar, Fadi Hanna, Faiyaaz Ahmed, Giuliano Follacchio, Jamal Khodr, Jasman Singh, Jihad Barbar, John Kakoliris, Jonathon Rock, Jordan Nicolaou, Marianne Sales, Michael Natalizio, Owen Tieu, Patrick Croagh, Tirrell Slaney
45e3f212-8d1c-543b-9a35-0358266c0e47 | textbox | Inspecting Engineer (if not included above)
4966c6cb-3e3d-5752-bb82-0a115d0656d6 | textbox | Subcontractor's delivery personnel (full name)
6b811dd6-6dc3-548c-b57f-0364a98d27a7 | textbox | Delivery vehicle registration number
| checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
| section | Packaging Inspection
| checkpoint | Inspection Result ID:
5af37914-7f8a-57ac-b8eb-af8f32f81e30 | button | Special Storage/ Handling Requirements? | Yes, No, N/A
d472a224-2992-568f-9627-b4deeee5931a | textbox | If yes, provide details
5c6b6948-bc83-52c5-9b75-ea98613e1ad4 | note | The following is for completion by Fulton Hogan
6d4bcd5e-6127-574d-a9b9-fb512def9611 | button | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.] | Yes, No, N/A
70fd54d0-3acd-5341-b686-5705578dd7c0 | button | QA/Compliance Docs Delivered? | Yes, No, N/A
49ff98bb-f0fa-5156-a58c-e12bcb2510f0 | button | Defective? | Yes, No, N/A
| checkpoint | 1)
14fbd31c-3ed8-50d5-8bdf-b1544e387fea | textbox | Item ID:
2994839b-a721-5165-ac58-c135d99c2709 | textbox | Item description:
65816c8d-705e-5e01-a0e3-31d06a01fe72 | textbox | Units ordered:
2a8a3e58-1dff-56b1-9a34-9c5d3d05d8c9 | textbox | Units delivered:
d727198e-a11c-508d-b0e2-c3d4c1563815 | textbox | Number Accepted
d0755175-ee3f-501a-a373-48d612f07c5b | textbox | Number Rejected
111ddf99-8375-57e2-92b4-62eb39931b6b | note | Inspection Result ID (select below)
eb186f37-07fd-507f-a68b-4eba6d0d570c | tickbox | OK = Meets all criteria
d18323b2-c7d1-5115-a09c-544c7bdfcd3b | tickbox | QI = Quantity incorrect
0d812c22-f0a3-5d0c-9055-d001df447d3f | tickbox | IN = Item incomplete
bd28b41a-6ae4-5899-b676-258553c470b5 | tickbox | MI = Make or type incorrect
aab47e5e-1a43-5442-b958-df4ebb9be7ee | tickbox | TD = Damaged in transit
98d6ddf2-47e8-59a0-9158-0dbdfaa17086 | tickbox | NI = Not properly Identified
d6144275-4bd2-5780-83d0-a0e828e846d1 | tickbox | CD = Compliance docs not provided
| checkpoint | 2)
bcb8a80c-62a2-5601-8016-580bbc87704f | textbox | Item ID:
1b8dc746-448e-5455-895a-f55bcd8ebb83 | textbox | Item description:
4c97d56b-02c8-5d15-b1b2-77fb99e0d5ec | textbox | Units ordered:
a7fc8070-6e1b-5dba-bf70-313ca170f523 | textbox | Units delivered:
932ae001-ff39-554d-9551-288cb472e167 | textbox | Number Accepted
415e27e9-065d-5622-b00d-a2681ed2da3d | textbox | Number Rejected
f9f13e5f-856f-534d-a759-79009afd7c7c | note | Inspection Result ID (select below)
29b66bee-d998-50b8-bc4b-51bcc0a4b891 | tickbox | OK = Meets all criteria
4df1d900-41f1-5892-9255-6196f48f45b2 | tickbox | QI = Quantity incorrect
b6316236-2594-55a7-8f43-05628dd24ba8 | tickbox | IN = Item incomplete
0260be27-5d9c-5126-9cd6-2bdb101cfedc | tickbox | MI = Make or type incorrect
99b072dd-aa0b-5134-90bb-cb8ce550164e | tickbox | TD = Damaged in transit
53310f68-ca19-5463-a84e-fbb01226322e | tickbox | NI = Not properly Identified
3d1740fb-d64a-5717-8671-52a78e10fb91 | tickbox | CD = Compliance docs not provided
| checkpoint | 3)
7d0b2e97-16e6-5457-98d3-76cd64b0f7e4 | textbox | Item ID:
eaca7272-0657-5d88-ba36-14ecc6e4f300 | textbox | Item description:
bfcf3a2f-2700-522c-82fe-c8b1bfd41064 | textbox | Units ordered:
c85741be-5e1d-508b-9596-988eabaa0f2a | textbox | Units delivered:
edd2e7e2-63ef-5942-ac19-b879a6054401 | textbox | Number Accepted
ba9cf8c6-51f0-5fea-a9af-e267a9c2954d | textbox | Number Rejected
1a5019de-b026-5684-bb61-9054252a1b79 | note | Inspection Result ID (select below)
18eb4d14-d9f2-5767-bd57-95ef30adb9af | tickbox | OK = Meets all criteria
a5db3abf-a7d9-5d87-ba79-115540460781 | tickbox | QI = Quantity incorrect
e3505139-cebb-5419-a051-7ef94dd7113c | tickbox | IN = Item incomplete
b2ff2970-0289-502b-bad3-211bbc4fd855 | tickbox | MI = Make or type incorrect
592bbd0c-4513-567e-b6bd-330459126e7d | tickbox | TD = Damaged in transit
9f04d024-b4de-5d63-9de0-e34bb90ecf2e | tickbox | NI = Not properly Identified
4278a3d3-eb65-553f-b192-ad44788bbdf1 | tickbox | CD = Compliance docs not provided
| checkpoint | 4)
02030a4a-e9f9-5de5-b134-e3c68ff5647b | textbox | Item ID:
0adef97f-9057-5939-ac0e-36f39d8591bf | textbox | Item description:
f1deff30-74cc-527b-97ac-ca8758e545bb | textbox | Units ordered:
bad31414-c790-55f1-94df-e9b3e7db8d0c | textbox | Units delivered:
6126b4ab-c1a1-5e47-803d-d37b5714cefb | textbox | Number Accepted
2608bb75-8749-5221-b1ae-e7e03b904cf1 | textbox | Number Rejected
cb797cad-1ab2-5fa4-93b8-5639b0145c17 | note | Inspection Result ID (select below)
485a4c56-ea86-5699-a275-6085cba522d1 | tickbox | OK = Meets all criteria
3657c271-31a4-5827-b9be-83ccb17cfea9 | tickbox | QI = Quantity incorrect
aea79501-99ea-5d7c-a344-23456988306a | tickbox | IN = Item incomplete
375a4393-fb27-5712-85d2-a3d39c6bea58 | tickbox | MI = Make or type incorrect
014225a6-fd62-55e4-a7fc-248b025fa0b5 | tickbox | TD = Damaged in transit
9e770ae4-cb01-5510-8737-fa33711c1bfb | tickbox | NI = Not properly Identified
dabc3c4d-271a-52e4-848a-b6f31b0f5dd6 | tickbox | CD = Compliance docs not provided
| checkpoint | 5)
ee3e5da8-de72-531e-95b5-9d20e807142c | textbox | Item ID:
8e7052af-a398-5e46-92b7-a2e49a4d9b3d | textbox | Item description:
89b51c1b-da9e-5489-8e93-95759094bd01 | textbox | Units ordered:
839dbb10-e1dd-5507-befe-477e8984beed | textbox | Units delivered:
b255ed66-3db3-518b-9402-6788fc4751b1 | textbox | Number Accepted
9ca98e0a-965c-5b4a-931b-555565640b79 | textbox | Number Rejected
2b9365df-3a69-5e77-9670-c4c1643e71dd | note | Inspection Result ID (select below)
83b4e2c3-6d8a-5719-a07a-3f29a40bd4c0 | tickbox | OK = Meets all criteria
0f572fc2-39e3-5ccd-a238-48068a967c0f | tickbox | QI = Quantity incorrect
1b0d93e3-fbf6-56d6-9ebd-234da000b0a4 | tickbox | IN = Item incomplete
9d4ab8e8-64d7-51e9-bceb-3aa3845370a1 | tickbox | MI = Make or type incorrect
b81b70ef-1498-5b95-afa1-955a18d41376 | tickbox | TD = Damaged in transit
880ad6fd-7a04-5537-8145-e9ec30b0af67 | tickbox | NI = Not properly Identified
5947b083-7280-51a0-bbba-ef46a1b46c3d | tickbox | CD = Compliance docs not provided
| checkpoint | 6)
f5213d94-b80a-58ad-9e02-f4c55d406424 | textbox | Item ID:
edd20faa-cb86-5256-bc0a-01f72d478ff4 | textbox | Item description:
777534c3-f873-5c72-b8bc-84a8652d31c5 | textbox | Units ordered:
c70ed69f-7b0f-51a7-9ebc-8e8780ed4eba | textbox | Units delivered:
bf72f1f5-fd8a-5f81-bfa7-30ec85b2b7b4 | textbox | Number Accepted
c066d4e0-a8b8-55e3-80b1-95163a7f00d9 | textbox | Number Rejected
f4a433b9-bedb-535f-afb2-38b96236e638 | note | Inspection Result ID (select below)
78f4fb22-5dd4-53c8-ae6f-45f0e5bbec26 | tickbox | OK = Meets all criteria
76a89976-b7bb-58ec-9dd9-5273687c8bb7 | tickbox | QI = Quantity incorrect
e3057735-dba9-579a-883b-f54c31d4dda4 | tickbox | IN = Item incomplete
b1e39859-58b0-57c7-a46f-b8dcece44ae6 | tickbox | MI = Make or type incorrect
317c7343-d44b-5e6f-ac4d-14777d996856 | tickbox | TD = Damaged in transit
22d1c960-40b1-5717-a111-2733e94a093b | tickbox | NI = Not properly Identified
5627b1ca-a2cb-569b-b8d7-4b4fdf5390e5 | tickbox | CD = Compliance docs not provided
| checkpoint | 7)
24420331-8897-5df8-8e20-28850ce6820b | textbox | Item ID:
050f2298-60e1-597c-ba41-19f372d6f9ea | textbox | Item description:
4aed13e8-5b70-5ac5-b063-27682e4b1e7d | textbox | Units ordered:
a8455a7c-3e34-5fe2-9484-44265dbc6270 | textbox | Units delivered:
c96e5370-3e8a-546d-b3ba-30efbbacacd3 | textbox | Number Accepted
2ef35f51-cea1-59a0-a464-7b59d63adaef | textbox | Number Rejected
8d6998f0-ae2a-550b-9a35-ce9a90bcd907 | note | Inspection Result ID (select below)
38731218-084d-5300-8ed7-2fa488172541 | tickbox | OK = Meets all criteria
f5fab120-e143-55d9-98b3-47b141326437 | tickbox | QI = Quantity incorrect
1bbc596b-6778-5be7-be40-a3679ec04117 | tickbox | IN = Item incomplete
59d81aa0-cf54-5156-96b1-253b1feaf6aa | tickbox | MI = Make or type incorrect
a2040892-0694-53d0-bcd2-55ecc0661f89 | tickbox | TD = Damaged in transit
5ff1772d-def4-5790-807b-814328b8894d | tickbox | NI = Not properly Identified
4aee0408-6d70-5ad6-a317-4bbc96d33a65 | tickbox | CD = Compliance docs not provided
| checkpoint | 8)
0a389b74-9f90-525d-8b0c-2552b759cf12 | textbox | Item ID:
da5d972b-2633-569a-ac0d-39ab45185063 | textbox | Item description:
5225212b-ed5d-5287-97df-f33b1afb8849 | textbox | Units ordered:
93ccb08d-1a0e-5bbd-b3fe-401d00e9b93f | textbox | Units delivered:
efe49955-ccdf-5024-a811-8666f33136b1 | textbox | Number Accepted
ded9f1eb-3668-56ca-b5a9-a52244bb2ade | textbox | Number Rejected
ae08ee64-0f14-5936-97e7-b66bc37e6886 | note | Inspection Result ID (select below)
369bd422-e8d4-5e79-93e2-fec34f9dcbe0 | tickbox | OK = Meets all criteria
36c62b89-9687-5b3e-8bae-397801b4f57c | tickbox | QI = Quantity incorrect
db8728c7-e9ea-5d6b-b0e6-ebd0d5eb6d8d | tickbox | IN = Item incomplete
ed22784c-94c4-5299-b9ac-d91e57c69287 | tickbox | MI = Make or type incorrect
5a8fff9f-6801-5421-98eb-2215df843cbe | tickbox | TD = Damaged in transit
676893f2-c88c-51b8-80f3-69b2dc890cfc | tickbox | NI = Not properly Identified
67c8e16c-c8f8-588a-9ee8-31eb20893fad | tickbox | CD = Compliance docs not provided
| checkpoint | 9)
65eae4e7-939c-5ce5-9db2-eece6a4a649f | textbox | Item ID:
974acc2a-4b50-5eee-9e15-9ba65a782a7c | textbox | Item description:
21e915b9-fedf-5b73-a47d-be5243581d53 | textbox | Units ordered:
0cced952-00de-55ce-8584-6be8030a25ee | textbox | Units delivered:
f3a96a9e-67cf-55a6-8f0d-bf09c6d85ef8 | textbox | Number Accepted
d3a1489b-5278-579a-9a15-15c1cea2f994 | textbox | Number Rejected
f383bbb4-9354-50cb-b763-6b692204c157 | note | Inspection Result ID (select below)
05656c8c-a056-5d75-971d-973831c209d5 | tickbox | OK = Meets all criteria
aee89344-f771-5ce8-8c50-075d95882fce | tickbox | QI = Quantity incorrect
377a752a-da2e-5870-83e8-7d570544216a | tickbox | IN = Item incomplete
8158ea5b-dcb3-5a4a-970a-029eebc1a66c | tickbox | MI = Make or type incorrect
9fe0fffb-3708-50b7-a9ce-0792b5913c20 | tickbox | TD = Damaged in transit
f81eae3f-8b92-5308-9e64-456dbeb343cb | tickbox | NI = Not properly Identified
6857182b-1b54-522a-a5d4-8dbdcedde131 | tickbox | CD = Compliance docs not provided
| checkpoint | 10)
f31045c7-1532-5996-9539-a059c44e9143 | textbox | Item ID:
bf14bf6a-0c22-5298-acce-1b1e76efa58b | textbox | Item description:
275633ff-23c0-509e-994c-a32a2affc4d8 | textbox | Units ordered:
f4f913e7-857f-587d-853a-582fc5c6cea6 | textbox | Units delivered:
0ad7f80a-763c-56c2-a5d0-fccc379240e3 | textbox | Number Accepted
728face4-b70a-51ba-9372-5306f854b124 | textbox | Number Rejected
09e54c31-f69e-559c-9836-3041d059feb5 | note | Inspection Result ID (select below)
f83dc770-5925-5f78-8f97-99ada5109ef4 | tickbox | OK = Meets all criteria
24966949-b70a-5c70-8b17-e0f2631cc6df | tickbox | QI = Quantity incorrect
4f31970c-fe9c-5c41-b197-736cf33848ba | tickbox | IN = Item incomplete
26817fea-ad8e-5d03-ab40-a2308c1e1b90 | tickbox | MI = Make or type incorrect
aa968b3c-f799-56e7-b410-ef29880b0530 | tickbox | TD = Damaged in transit
a7e94359-1c7f-51d6-b0c8-688f94b72d28 | tickbox | NI = Not properly Identified
945ea484-67de-5837-a72f-5e3f7a05d714 | tickbox | CD = Compliance docs not provided
| section | Sign Off
| checkpoint | Accepted by Fulton Hogan
| signoff | Sign Off
| checklist | FH-ZU2-QU-ITP025 - AGL Conduit and Boring Installation - Rev 0 | itp | ITP025 - AGL Conduit and Boring Installation | e5c4ed83-6e8c-4060-ab4e-866cf668ad0e
| section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
| checkpoint | 1.1 - Check for correct documentation
b8a32079-1aa5-57e6-8a66-15d046efe9a4 | note | Frequency - Prior to commencing activity
dca089ff-fabe-5dfd-9155-fd95e5e738e2 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
dba1a5c0-d0de-5d6d-b571-cae043ee78fd | note | – using the correct and complete set of drawings.
99e63a8b-aa25-5791-87ed-2128adff683e | note | – all drawings are the latest revision.
0d37360b-f68e-5e84-8b12-8e39c9daf073 | note | Reference Documents - Drawings / Aconex Register
e1eaf8d7-ca21-5f67-8a56-b4657842d17c | note | Inspection/Test Method - Verify
8d9414de-68d1-5128-86de-09bf100caffa | note | Record of conformity - Drawings and drawing registers
cac2c81a-95d7-527f-ba64-e416799584f2 | note | HP*
7f726786-8251-5e46-83af-455cd1302016 | note | Responsibility - Project Engineer
10a06d2c-0727-5f35-9bdc-3e4672b3a79c | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
9e830bc9-6113-5cb4-9a34-eba9ba021b42 | note | Frequency - Prior to commencing activity
9418b1c8-716b-5ea0-a719-ba1ccd42d304 | note | Acceptance Criteria - All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP.
81fa21ec-76e9-5833-816a-8d4f88d14f18 | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
5b75c70f-9e38-5946-9d65-a6a3204df160 | note | Inspection/Test Method - Visual inspection
1deda285-60ca-5351-b3d3-e42caadce55e | note | Record of conformity - This ITP signed
3767b002-064d-5f2b-a08e-c974d9b21578 | note | HP*
4cbb564b-8fa9-59a0-893a-1706d763fe3f | note | Responsibility - Project Engineer
343fa595-a04c-5db6-b296-f79f8b91a9a9 | date | Date Completed:
| checkpoint | 1.3 - Definition of the work area (survey)
2a01ebfc-039d-5ba5-a171-e3056faf5778 | note | Frequency - Prior to commencing activity
ff5b4170-c852-50d2-86d7-a1bfe1389ea8 | note | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of excavation clearly defined.
2360f750-b416-5fe2-bb88-558bdaeec326 | note | Reference Documents - Drawings
d84c98fa-fcb1-575a-a417-1f8ecf6ca0a3 | note | Inspection/Test Method - Visual inspection
79ded8b4-2e16-52fe-b9f2-cb72048a09e9 | note | Record of conformity - This ITP signed
3de3e26d-10d8-5785-bd23-f9c04341127d | note | HP*
bf9859db-19aa-5d27-9a66-8544815d825c | note | Responsibility - Project Engineer / Surveyor
b31fbb3b-c423-5d91-a5ab-4207c71c863d | date | Date Completed:
| checkpoint | 1.4 - Check conduit compliance
ca75f7e2-9fe0-5872-8553-2e25ec68ebeb | note | Frequency - Prior to commencing activity
bda3bffd-140a-5c53-a9d5-ed07bf6460c2 | note | Acceptance Criteria - Ensure that uPVC conduits comply with AS 1477 or equivalent AS 2053. Shall be heavy duty, orange for electrical services and white for communication services.
0a9b4a58-a26a-5475-97ba-dfaf945b9ef1 | note | ○ Ensure that pipe diameter is correct as per the drawings.
2228e221-89bc-5623-96c3-d7daf7b13c94 | note | Reference Documents - ZULU-BECA- 001-SPC-00004 cl. 3.4 AS 1477, AS 2053
cf302bda-01b5-536e-9688-e3b16a7a9c35 | note | Inspection/Test Method - Verify
86110fe3-7368-5cab-a456-dd3623a8f731 | note | Record of conformity - Aconex reference This ITP signed
5af08d7a-b984-5b02-9978-fc0db3cb6214 | note | IP
593f0f5e-a639-5aa7-b8c4-36cdafa92cab | note | Responsibility - Project Engineer
cec57df8-208a-5528-9608-2e86de3bf819 | date | Date Completed:
| checkpoint | 1.5 - Check bedding material compliance
5f2c1b92-3599-5a8a-834a-427ad7a18190 | note | Frequency - Prior to commencing activity
6fb6c1f2-9d81-5b59-b99f-e5f49ee6ddb5 | note | Acceptance Criteria - HOLD POINT
020b801f-5412-5d77-9d2a-2145dfd4cc60 | note | ○ Ensure that conduit bedding material is non- plastic granitic sand complying with Table 3-1 and 3-2 under cl. 3.8.3.3 of the Works Specification.
8727225b-c976-525a-8b39-a8a70dd7c5b2 | note | Reference Documents - ZULU-BECA- 001-SPC-00004 cl. 3.8.3.3
7636d754-0604-5df7-9841-02fb51f9bc27 | note | Inspection/Test Method - Verify
c4bc2b8d-464c-5b8b-a1ce-34e10567a9a9 | note | Record of conformity - Aconex reference
c202e6eb-af88-5ad4-b192-43b7eadbf787 | note | TP / HP
c7e23314-96b2-5d4f-95ae-b805ad0bb910 | note | Responsibility - Project Engineer / Principal’s Representative
f52f6ef1-99d5-583b-9def-0012f8fe7415 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Locate and prove existing services
b481a873-1b9b-587c-bb85-6db6664f6e12 | note | Frequency - Prior to commencing activity
079fe04c-e0fd-5abd-89d5-2beade7873ef | note | Acceptance Criteria - Location of services to be found and marked on the ground within the works;
cab71392-4f1d-5730-b896-8dc966adc310 | note | ○ Contractor to obtain excavation permit from APAM prior to any demolition works.
c12281a4-c363-5678-af29-17485de6279a | note | ○ Services located within the works area to be exposed/proven, recorded as survey data and also on a service plan which is to be attached to the Excavation Permit.
e3f2e297-de92-5390-a29a-e6ecffaa0e1b | note | Reference Documents - ZULU-BECA- 001-SPC-00004 cl. 3.15
f37db078-ea05-5781-947a-5141c960d86d | note | Inspection/Test Method - Verify
47c50d96-5b10-547a-b164-c366eded8ae3 | note | Record of conformity - Melbourne Airport Excavation Permit
6ae7ada3-828e-5efa-b02d-1f97814f83c4 | note | HP*
21f800ce-67b2-55b4-b05d-59bd92905a1b | note | Responsibility - Project Engineer / Surveyor
22b782f4-e33b-586a-9f54-a5ccbadb9f8b | date | Date Completed:
| section | 2.0 - Construction
| checkpoint | 2.1 - Excavate trenches for conduits
5bd4a899-f778-5d8c-b992-335b43cabe80 | note | Frequency - Each lot
47fee060-3be0-5cd5-92ff-7cc2ecafb650 | note | Acceptance Criteria - - Trenches for conduits shall be excavated to the width and depth required enabling construction of the conduits to the requirements specified on the drawings.
08811dd7-8796-5bb3-8ac0-cdca7c1dae5f | note | ○ The level at the bottom of the trench shall not be above the required level at any point.
6b0450c6-a3f2-5f66-89e7-7f3673de58ad | note | ○ Any over excavation under pavements shall be restored using 5MPa lean mix concrete in conjunction with the embedment.
80e258da-eebe-5947-af44-4382d2235a85 | note | Reference Documents - Drawings ZULU-BECA- 001-SPC-00004 cl. 3.6
6ef7be7b-a588-5265-ac5d-3cdc2601cbf3 | note | Inspection/Test Method - Visual inspection
8be7f315-2c5e-5326-8ad1-19ab81608184 | note | Record of conformity - This ITP signed
4c8ef0f8-c97d-5915-a9db-4f39a711b06a | note | IP
01d592f3-fdb5-502b-82ac-c60be15407cf | note | Responsibility - Project Engineer / Foreman
21de2358-3437-5033-a795-74e2bc6a791b | date | Date Completed:
| checkpoint | 2.2 - Existing services crossing new conduits
ad540ad0-90dd-5cfe-b7b4-cd38d1129a8b | note | Frequency - Each lot
8610695a-f5b6-5cde-aede-10dd232465a0 | note | Acceptance Criteria - Only approved methods of excavation that has been approved by the Principal’s Representative shall be used.
15c7adb2-452b-5f6f-903e-0b6b2d59e030 | note | ○ Location, level and configuration of existing service crossing to be recorded in as built documentation prior to backfill (including CAD model file)
8c691458-22ee-56c5-8d0c-e75f284652b2 | note | Reference Documents - WMS002 – Working Near Existing Services
c4d3d455-51a3-5cf5-bc75-56a0a78aa1bc | note | Inspection/Test Method - Visual inspection
62d0f4e4-b8ea-51a3-badf-52674410f43c | note | Record of conformity - As-built survey report
cb8ad14c-84af-5a07-9bcf-1568b1c7441e | note | SCP
8a014a96-019e-5793-8c6b-9d9a6c7f2a18 | note | Responsibility - Project Engineer / Surveyor
b9cd8c33-d715-597c-b3a2-9debd806dc21 | date | Date Completed:
| checkpoint | 2.3 - Laying and jointing of conduits
a6d44dc9-0037-5d39-8d4a-0172eede369a | note | Frequency - Each lot
f32cb045-a292-5246-87d4-d27f7f190010 | note | Acceptance Criteria - - All conduits shall be rigidly supported and positioned by concrete or plastic spacer blocks so that no displacement occurs during backfill.
a339ad4c-3e9f-59ea-b9f1-185bbda9515c | note | ○ Where conduit ends are not open to a pit, UPVC end caps shall be temporarily fitted to each end.
cff3ddce-2f19-59ad-b7ba-f60ad7f88809 | note | ○ Number of conduits and duct route to be confirmed for conformity with design.
a0edff87-a828-5c1e-8c99-46f0d6a2a643 | note | Reference Documents - ZULU-BECA- 001-SPC-00004 cl. 3.7
9101403f-eeba-575d-82b0-a0702d54a132 | note | Inspection/Test Method - Visual inspection
df67a876-f59e-5da8-97cb-148c5ebf4c95 | note | Record of conformity - This ITP signed
2aeb0379-0633-5c03-af97-8446cd0ed6ba | note | IP
8e72718a-8e55-528f-8731-d5c59ffe18f2 | note | Responsibility - Project Engineer / Foreman
e4395f7c-9b90-5450-bc92-c1e031fe526d | date | Date Completed:
| checkpoint | 2.4 - Survey as-built
8ae894e3-637b-5fdf-a08c-96583d56b234 | note | Frequency - Prior to backfilling each lot
7d523446-7f0c-5c9e-839a-bcbb7c6c5b79 | note | Acceptance Criteria - Surveyor to pick up completed conduit runs before backfill
b3ba4b9a-ccd1-531e-96fd-fd243d60682e | note | Reference Documents - FH QMP
4d18d776-ce5e-598f-81ad-04054ca2922a | note | Inspection/Test Method - Verify / Inspection
3f74a3af-7a35-51d7-bdae-fd3f196f6863 | note | Record of conformity - Survey report
83f3fdd7-21a2-5f4a-b12e-2487dac36cee | note | SCP / IP
99848c36-7396-5e20-b1bc-49bfd1f61ff2 | note | Responsibility - Project Engineer / Surveyor
69571608-498b-5acb-b8a7-5ef9bf8be068 | date | Date Completed:
| checkpoint | 2.5 - Pre-backfill inspection
63e1ddfb-324e-5352-9960-19ac059be51f | note | Frequency - Prior to backfilling each lot
6ca47f8f-1783-5edc-9745-8a5e7115652f | note | Acceptance Criteria - WITNESS POINT
30198f96-49f8-5a96-8f9d-8b6683ec08e9 | note | ○ The Contractor must provide the Contract Administrator with five (5) working days' notice of intention to backfill trenches within a Lot. This must include details of the date and location of the proposed work.
e44ee0b4-2433-5de2-ac27-d8b2b4fde155 | note | Reference Documents - ZULU-BECA- 001-SPC-00004 cl. 3.8.1
8562ecdb-2c4f-5f07-b889-1f23e5f9f6ed | note | Inspection/Test Method - Inspection
652e0800-e063-5a07-ba7f-3bc1de37badc | note | Record of conformity - This ITP signed
43d6d4a8-04db-576a-b546-2c9247a84fc5 | note | WP
cdb2e9f2-10a0-504c-af39-93028bb6a316 | note | Responsibility - Project Engineer / Principal’s Representative
573ab9dc-8565-5dac-ad8b-861c41d100c2 | date | Date Completed:
| checkpoint | 2.6 - Backfilling conduits
9b79ab7a-473c-565a-a81c-bb41bd53e5af | note | Frequency - Each lot
84a78bd4-7be1-5deb-bfa2-179e60c267dd | note | Acceptance Criteria -
abc9cbbe-1707-5518-b988-c316816c6500 | note | – Concrete encasement of conduits: –
566010c6-75cd-57c1-8111-ec78c8b7c60f | note | ○ Conduits to be encased in 5MPa lean mix concrete as per drawings.
fa092b72-e40e-55ac-98ab-6d7b0007dfee | note | – Trenches in existing pavement: –
de46ec6a-dabe-58d8-8332-7a8328fca9ab | note | ○ Surface shall be reinstated to match surrounding pavement.
1e85192b-473e-51fa-b43d-fedae8eb6680 | note | ○ Unless noted otherwise, reinstate asphalt pavement surfaces to a minimum of 70mm (or to match existing depth (whichever is greater)).
59f28043-12cd-563f-a677-368f1909068b | note | – Trenches in new pavement: –
9fe060f9-0b13-5bae-a2af-be5f946c1a9c | note | ○ Pavement shall be constructed as per the drawings and specification.
26f5dcc8-5e5e-530f-9875-62c54f019961 | note | – In grassed areas –
565604c9-ed7f-5020-8def-0499a9cb91e2 | note | ○ Conduits to be encased in compacted sand bedding. The material shall be non-plastic and comply with properties specified in Table 3-1 & 3-2 of the specification.
12860750-fde5-5604-8134-1a02f743e65e | note | – Backfill layers: –
a744eb01-f590-5431-8686-57e6fd14281b | note | ○ Not exceeding 300mm compacted thickness.
db2c2dad-8f21-55da-88e2-08aee972a7b5 | note | ○ Not less than 90% maximum dry density (test no. 5.1.1).
4cf81bc4-7e92-5a64-a0bf-ff13456f981a | note | ○ Not less than 70% of density index (test E6.1).
dbbd9d0e-81bf-518b-aa0c-e8531768a32f | note | – Compaction testing carried out at a rate of not less than: –
1bb80dc0-28a3-57ad-9a07-c358bd21d958 | note | ○ Bedding: 1 soil test report from the supplier per 300m3 of dust supplied.
dedee7fb-9db4-5c23-90a0-35190daff671 | note | ○ Backfill: 1 test per 400m of conduit laid per 0.5m of backfill depth.
7550c732-f38c-537f-9200-c01e9ff9a7d8 | note | Reference Documents - Drawings ZULU-BECA- 001-SPC-00004 cl. 3.8.3.1, cl. 3.8.3.2, cl. 3.8.3.3 AS 1289 Test no. 5.1.1, Test no. E6.1
3a66f37e-934e-56f1-886a-3e68eae11bff | note | Inspection/Test Method - Verify
c5efc8e5-daf7-5e6f-ab90-b25e211022dc | note | Record of conformity - Test report Aconex reference, This ITP signed
5f74d6c4-d856-5fc1-8b57-bf837c2a8afc | note | TP / IP
1c9176f5-613e-565a-a8f8-7dec5cc6ab00 | note | Responsibility - Project Engineer / Foreman
e5b430f5-d150-5815-94e9-18ca37d37822 | date | Date Completed:
| checkpoint | 2.7 - Conduit markers & warning tape
45368ed3-77e7-5171-ae93-bcbf8cd8ee0b | note | Frequency - Each lot
29da3ecb-bb95-5c21-b2a4-32111784782f | note | Acceptance Criteria - Pavement edge duct markers shall be installed at the edge of pavements immediately over the centreline of duct banks.
59d30ef8-d784-5d37-8c08-6a0a18f2bed1 | note | ○ Warning tape shall be to AS 2648.1, and coloured orange for electrical/white for communications conduits.
28cf0053-f801-58d7-b6cb-b6e4e75f8fc3 | note | Reference Documents - ZULU-BECA- 001-SPC-00004 cl. 3.11, cl. 3.12 AS 2648.1
433db3cd-880b-58a5-96bb-b64607ef2cca | note | Inspection/Test Method - Visual inspection
4c8cc8c4-fe17-5dec-9fdf-60b2222e0f42 | note | Record of conformity - This ITP signed
edc91752-a980-5b96-8dc6-f1574072c350 | note | IP
baaf9703-c6e3-5675-8495-e3496825ad94 | note | Responsibility - Project Engineer / Foreman
d5d45f2f-1e5f-5b35-b476-6a00e3449a19 | date | Date Completed:
| checkpoint | 2.8 - Checking of conduit lines
6ea7d1b1-ffa1-5921-83a5-3151011919a2 | note | Frequency - Each lot
de28fb13-ba74-59ad-8e7a-eeeab8d601aa | note | Acceptance Criteria - HOLD POINT
bcbeb64e-f56a-569b-8128-3ed37af656e4 | note | ○ Following installation, the conduit shall be checked by passing a mandrel (not less than 300mm long and having a diameter of not more than 6mm less than the diameter of the conduit) through each way, followed by a brush with stiff bristles to clean the conduit of any foreign materials.
38f811d4-24d1-5c07-9dac-4c36110837a8 | note | Reference Documents - ZULU-BECA- 001-SPC-00004 cl. 3.9
6634aa92-d07c-546d-a377-973a89791ee2 | note | Inspection/Test Method - Visual inspection
66351acf-25c2-572e-ab3d-e8deb113b632 | note | Record of conformity - This ITP signed, Avionics Primary Trenching Checklist
b4c3b1d6-8dc3-5b46-9a4c-652f4e4c3e1e | note | HP
4bae3308-85c1-5999-a239-9a56912eb3a0 | note | Responsibility - Project Engineer / Principal’s Representative
c6c08a2b-8e73-5271-b9f4-e2d11ff92c70 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.9 - Conduit draw cord
8df5d2ce-8815-57bc-921e-dc99ad009ab5 | note | Frequency - Each lot
16282afc-900c-56dc-8833-be8ad010029a | note | Acceptance Criteria - Each duct way in each duct bank shall be fitted with a single unjointed length of draw cord of a length equal to the length of the duct plus 4m. The draw cord shall be nylon rope and be 6mm in diameter, blue in colour. The ends of the rope shall be coiled at the bottom of each pit or wound around a stake.
68f2e7f4-e2ad-5085-8702-3990e8c8fc8a | note | Reference Documents - ZULU-BECA- 001-SPC-00004 cl. 3.10
5b24093c-85b7-51d8-84d5-238e6ef03f3e | note | Inspection/Test Method - Visual
89ce2275-1a9c-5b93-a389-9b14dc59ca27 | note | Record of conformity - This ITP signed, Avionics Primary/Secondary Trenching Checklist
883bc1e9-e8ae-54f0-a3c5-3319d36a752e | note | IP
33cd7518-82c4-584a-a692-fd104f0153a6 | note | Responsibility - Project Engineer / Foreman
d83875da-a9e6-515e-856e-19e14be8752f | date | Date Completed:
| checkpoint | Final Inspection
39a43258-897d-53f9-8eb9-2a6c7ad42338 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
53ed455d-bef3-5f8d-9f79-194429c69199 | textbox | Print Name:
665cc1aa-388f-535b-8ea2-10b9cf3d21f6 | textbox | Position:
4f86ab93-9bc3-5ff3-b5ad-bb0b015601ba | date | Work Completed On:
24a47102-b649-5f4b-8d21-4dc7e7aff131 | date | Date:
| checklist | FH-ZU2-QU-ITP009 - Unbound Pavements (FCR & RCC) - Rev 0 | itp | ITP009 - Unbound Pavements (FCR & RCC) | e5d7f013-0a9d-4bb9-90ec-d791bb9e9b56
| section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
| checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
22b60133-d07e-5778-afbb-3104cb451e98 | note | Frequency - Prior to commencing works
90628709-661f-5c1d-808d-3f9633505536 | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
bc77cecb-25db-54e2-a46f-f50316ce64bd | note | Reference Documents - Aconex
248e7c02-a029-5336-9878-3422c829cf56 | note | Inspection/Test Method - Visual inspecti on
505c13d3-3958-55d4-b28a-dbe56fcb6509 | note | Record of conformity - This signed ITP
d9b9a31e-4fc1-55c9-8cf1-e24191b8f35b | note | HP*
577c368a-5703-5a58-b59c-18e92dbc9be8 | note | Responsibility - Project/Site Engineer
0ca55223-b839-58b1-9ea2-63b876b41d8e | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls, weather, and material properties.
d49a7852-f9a9-5121-afd2-663081afa613 | note | Frequency - Prior to commencing works
1e3e4950-6df5-54d8-b002-d4b18ac8c1d9 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
46aa07a5-24fd-5c8d-8bf3-189213104141 | note | ○ Check weather prior to starting any works.
4274f253-54a3-50bd-9ec8-7b1601fe3d02 | note | ○ FCR material used for the works in accordance to VicRoads Class 2 Crushed Rock.
9351f45c-6020-5acc-acdf-0786a7e52f32 | note | ○ RCC material to be used for the Works in accordance with VicRoads Class 3 Crushed Rock.
67de20a2-0256-57b6-850f-aadb800e0d07 | note | ○ Checking underlying layer ITP’s (subgrade ITP008 and select fill ITP004 has been completed)
337e8923-b57f-5282-856b-d3a6b8d18b41 | note | Reference Documents - PSP, EMP, TMP, WP SWMS, Spec Cl 4.19, Spec cl. 4.1, VicRoads Technical Note 107 Spec cl. 4.6
b918f1ef-0da1-5bc1-8bb8-6c02335de461 | note | Inspection/Test Method - Visual inspection
6f531f46-a05a-5c16-b04e-195d1c3f4a93 | note | Record of conformity - This signed ITP
3b7b3517-c997-5002-97c8-f1aa5f1e7cae | note | HP*
2de72f79-4994-57b6-a35f-9b3e18858774 | note | Responsibility - Project/Site Engineer, Foreman
baa8b9fa-f889-5d30-8dea-a71cc722d564 | date | Date Completed:
| checkpoint | 1.3 - Material Report - Fine Crushed Rock (FCR) Material & Recycle Crushed Concrete (RCC)
08f8e815-db8e-5c04-a20e-779ea9c698a3 | note | Frequency - 7 Days - Prior to works
f23fc5f1-f6fb-5435-ad79-c5ecdcd035c6 | note | Acceptance Criteria - Material Report to be submitted 7 days prior to works to include;
1344dbf9-3674-54ba-b047-2f9a512d67de | note | ○ Source and Quarry location
dc8222db-ef8f-5c16-b274-2905dc7a31d3 | note | ○ Quarry material is sourced from.
a8449f49-f55e-5365-8100-695b2068f934 | note | ○ Material rock type and petrographic description
8b784087-184c-59ef-b6b6-040c79a2a485 | note | ○ Historical test results
836aacce-c6f4-5341-b85b-04b293e861dc | note | ○ Method of processing and transportation
52202e1b-799b-57e1-bfb2-b5a8c390d48f | note | ○ Material summary of the results of recent test on samples of the material from the source
e2e34f1e-e0b2-5faa-bb77-6746fc484680 | note | Reference Documents - Spec cl 4.20.1
c4580524-9128-5583-a7bf-4fa86d4a90ec | note | Inspection/Test Method - Verify
6f6417f1-69f8-5ad5-984c-fd198378675f | note | Record of conformity - This ITP signed
c8da58f1-5852-54c6-b606-35386ce293d9 | note | HP
27f7bd55-d87c-5dde-b69a-8a690d4a1c5c | note | Responsibility - Project/Site Engineer, Principles Rep
98351715-983d-55b6-b5e4-29818398c2fb | date | Date Completed:
f90cc78c-5577-584a-bf6f-2baea0a79d8a | note | Principal’s Representative - Aconex Ref: Holcim RCC Class 3 - DCWC Mgt-GCOR-009582
6ed4e75b-7d7c-59d4-860f-84f44b2920d0 | note | ○ Holcim FRC Class 2 - DCWC Mgt-GCOR-009581
f1140fed-3d65-5000-a675-33f0cf450936 | note | ○ Stirling Class 3 - DCWC Mgt-GCOR-009565
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Reference Samples
525ba691-af22-5b05-b06f-d97f2febed12 | note | Frequency - 5 Days prior to works
d6fbd216-8984-5446-82cf-f06bf7078519 | note | Acceptance Criteria - Reference samples to be submitted 5 days prior to works commencing. Two bags to be taken each weighing 25kg. One bag submitted to Client, one retained by Contractor
393a62fb-dc1a-51af-820d-43d92dcf2ed5 | note | Reference Documents - Spec cl. 4.20.2
81cb4669-886b-5347-b152-1895c2aef53c | note | Inspection/Test Method - Verify
3df23d20-62cf-5417-b4eb-60cb6864ab05 | note | Record of conformity - This ITP signed
afaad2f4-dbb5-5fd8-87e6-401b5bf4febd | note | HP
54753b28-df32-5121-a510-4e413fb619cc | note | Responsibility - Project/Site Engineer, Principles Rep
ee76c1dc-3531-5a2f-8c1f-475d8f250b39 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Trial Section
65684dbf-f369-509e-a5e8-b314c3fd8819 | note | Frequency - Prior to works
bafdae1c-25bf-5ae2-9cd0-6608d8ef0a98 | note | Acceptance Criteria - Trial section to be completed with Principles Representative approving the use of the spreading machine.
6c6faa28-2c6a-59b8-bc47-3393a4e05f95 | note | Reference Documents - Spec cl. 4.7
af7d6c18-3dcc-50bf-b3f8-53ce25ab318e | note | Inspection/Test Method - Verify
17a066a2-c53c-51e9-a713-f8604f6dba5c | note | Record of conformity - This ITP signed
eeb60278-237d-56da-890e-daecf0bb1cf4 | note | HP
b8253941-a061-5b59-a6f1-8d269d6fe801 | note | Responsibility - Project/Site Engineer, Principles Rep
a035e09f-3c92-5f13-973b-02f96ca5b1ac | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Compaction Equipment
b945be75-e6e9-57a1-8123-6e8633aab849 | note | Frequency - Prior to works
e74b505a-9f5c-54a0-aeea-6de10bb335eb | note | Acceptance Criteria - Pneumatic tyred rollers having a weight of 27t (min roller weight can be 7t spread across 7 wheels). Tyre inflation pressure to be checked. A 15t to 20t smooth drum roller to be used.
2801421f-e441-58d5-bb6a-16a4d3e6997a | note | Reference Documents - Spec Cl 2.4.3 Item 84 Tender Clarifications
7714caf1-b8f8-5140-a270-f11a742d03c8 | note | Inspection/Test Method - Verify
c68e6fd7-3cf1-58cb-b9e5-ef98680eb80c | note | Record of conformity - This ITP signed
1ca6e76d-4a10-59f8-9af4-a8cfd70ad21c | note | WP
de947921-e38e-5dbb-98de-20d29f6f2cf3 | note | Responsibility - Project/Site Engineer, Principles Rep
780ed8c5-c16d-5d7d-a120-b2874bf1d159 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 - Placement of Sub-basecourse and Basecourse
| checkpoint | 2.1 - Layer Placement Parameters
aaa3edf8-61eb-55f2-97a1-d0fb08386030 | note | Frequency - Every Lot
16c77b6b-81f0-5b20-ad8d-8506d7ec2d02 | note | Acceptance Criteria - Summary of Parameters for each Lot;
3f87eaec-bfd5-5113-a5dd-c989fed0fec5 | note | ○ A lot is defined as one layer placed in a single days production of uniform material
ba7c17ca-eae9-5ba4-a3ff-214dac3491bc | note | ○ Max Layer is 200mm
322cb297-e6e8-5565-b3fe-48d519767cce | note | ○ Min Layer is 75mm
ce182ba1-c8fb-5c79-9cb4-9e7811cce7b1 | note | ○ Final Surface Level +0mm, -10mm (excluding intermediate layers)
3fcf686c-043f-5d65-9648-ea4b780b560f | note | ○ Shape: every 10m intervals, <7mm deviation over 3.5m straight edge (excluding intermediate layers)
2a7aa885-9c4f-5381-8ece-bb1b9ccba295 | note | ○ Material to be batched within 1% of OMC
2585bc1f-f9ba-51cb-839f-4f8d9b4863dc | note | Reference Documents - Spec Cl4.8, cl 4.21.2, cl 4.13
cced5364-2910-5d18-aa42-577b9981563e | note | Inspection/Test Method - Verify
8100ba46-80fe-5560-aca3-286dd0f42292 | note | Record of conformity - This ITP signed
be2c8188-b893-5606-951c-1d3052e63cd4 | note | IP
6d1c799a-1c5e-5479-95f5-52693cfb267f | note | Responsibility - Project/Site Engineer
c035320a-65e6-5da3-8edd-85233f228189 | date | Date Completed:
| checkpoint | 2.2 - Placement Checks
35f1d8ab-6103-59c1-8b59-7dbfdfd5a318 | note | Frequency - Every Lot
d330c613-67e4-5ca5-a41d-034019e87353 | note | Acceptance Criteria - During placement of the material check;
a0897ee6-0317-5245-b2d4-b7319354e90a | note | ○ Deliveries do not disturb underlying layer
c52be776-0b87-5bb4-9639-97923473720f | note | ○ Spreading starts from crown / high side where practical.
6558ad17-534d-5102-861d-33bdf6acdef4 | note | ○ Material does not get contaminated during placement / delivery
da1053c0-3a2a-5ac3-86fd-b3ecc6fd4402 | note | ○ Watercart is present to condition material as required
23130571-9585-5f82-a1bd-667592304329 | note | ○ Edges are cut / removed if dry of not compacted with abutting lots
25bb25f1-45b3-507e-b660-1bdfb628c3bb | note | Reference Documents - Spec Cl 4.8
35f5add3-e162-53d8-9bcf-6f098b9c662c | note | Inspection/Test Method - Verify
b7644ee8-0ce7-5f78-90af-aafeca592397 | note | Record of conformity - This ITP signed
5a905e00-c1e4-512f-9a17-ade2ccd58b44 | note | IP
19652dec-189a-5f21-8896-0766c8cb7a88 | note | Responsibility - Project/Site Engineer
2a0baffe-e984-564d-9c01-dab08964c6d6 | date | Date Completed:
| checkpoint | 2.3 - Compaction Check
58e6a7da-0a23-579e-adb3-07ffa5af4807 | note | Frequency - Every Lot
09efdcc0-9ad5-589b-9f7a-29a04ff56202 | note | Acceptance Criteria - During Compaction check;
112f68b3-7620-566d-bcbd-453cf4539fcb | note | ○ Heavy smooth drum roller of 15t to 20t is used for initial compaction
156bec7b-d118-5098-80a4-9f9811800889 | note | ○ Pneumatic roller of 27t will compact material for final consolidation.
63744c10-259a-59ff-aa84-ed5a2ec11330 | note | ○ A heavy smooth drum roller (in static mode) may also be used for final consolidation
1dcab749-3f6d-5dc0-8b70-8e6ccc60521a | note | ○ Watercart Present onsite for conditioning
55bdb2c8-4342-5857-baae-a10bdc7ecac0 | note | ○ Materials are trimmed to required shape and level
d22c4f0e-7900-552c-8a73-ef0db6e4ae0e | note | Reference Documents - Cl 4.10
1993e4bb-389f-5674-aac7-b01ba95c1fb1 | note | Inspection/Test Method - Verify
669b9d6b-f3ad-50de-bde3-67155680d007 | note | Record of conformity - This ITP signed
14eaa2db-1f06-5432-8e0c-27042f49ab02 | note | IP
6cd03551-ea7e-545c-bfad-d40f0419bc20 | note | Responsibility - Project/Site Engineer
045eb3cb-4193-5ec9-b4b2-f7ded14ec478 | date | Date Completed:
| checkpoint | 2.4 - Services & Culverts
cad1544e-6b90-53e9-b346-5cdaec13789b | note | Frequency - Every Lot
6ade1825-13f6-521f-80f3-e6df0e156981 | note | Acceptance Criteria - Check if any culverts or services are with the influence zone for compaction.
f01b9dd3-612c-5a17-a57d-010ef1513183 | note | ○ A general rule, FH will seek advice from the Principles Representative if any culverts, duct banks or RCP pipe are identified closer than 1m from pavement layer surface. If identified, Fulton Hogan will maintain a 1m exclusion zone either side from centre of service for vibrating compaction activities. Hand held DPU’s/whacker plate to be used in lieu of rollers in restricted areas.
67c452e0-d6b9-5f8e-a3da-b3d574687983 | note | Reference Documents - CL4.10
fa8211c9-abd1-57da-b54f-de0c6e5dbe35 | note | Inspection/Test Method - Verify
ffa561c5-3a1c-5b2a-8fdc-90801c716515 | note | Record of conformity - This ITP signed
33423efd-62ae-5c89-b304-dd78ede7b634 | note | IP
54f78c92-1f94-54e5-9290-23165c7f8f9b | note | Responsibility - Project/Site Engineer
d6d1b5b8-e9d7-5583-8a85-3068b4699540 | date | Date Completed:
| checkpoint | 2.5 - Protection of Layer
b5def97a-8a82-52be-9c54-498ac337f247 | note | Frequency - Every Lot
f5abe81d-8f4d-510d-8885-fa3cc5fca33b | note | Acceptance Criteria - Protect area from undue deterioration by;
f417fc95-2acf-5b5c-8b72-7fc970c8db29 | note | ○ Section off area for at least 12 to 48 hours to allow material to dry back.
59af82c2-ee2b-55ae-9f1a-84ba3d796d2f | note | ○ If unable to do so, keep traffic to a minimum
7b0a10bc-80ce-5720-b786-07441ed72b4e | note | ○ Or ensure any traffic that has to cross pavement layers, do not follow the same driving line.
98124425-bbe9-54b3-9173-c49ea88147ad | note | Reference Documents - Cl4.17
941d9051-473f-561a-bb5b-246c9d4cf08f | note | Inspection/Test Method - Verify
4ca87943-c62f-5a1b-b82a-fc898998e077 | note | Record of conformity - This ITP signed
fbcb7b46-d64b-5e69-8d4c-558089c333e1 | note | IP
86dbe21d-b474-525d-b7cc-73d45852ecfe | note | Responsibility - Project/Site Engineer
c1acb8c3-0d37-5859-88bb-9dc12a60a61b | date | Date Completed:
| checkpoint | 2.6 - Proof Rolling
44460523-6468-5e7d-8f76-60c382cfa5cc | note | Frequency - Every Lot
b7f9cddf-e0d6-57dc-b450-1557ea5a71de | note | Acceptance Criteria - Proof rolling will be undertaken at the top layer surface of the imported select fill material for under pavements using a 16T smooth drum roller (minimum), or a 15kL watercart (minimum).
1d13e8cc-aca0-5c16-ade1-a98bb49c050a | note | ○ Principles Representative to be invited to proof roll 24 hours prior to inspection.
2bc6ddb4-edfd-5f91-8fd6-de65508b146e | note | ○ Principles Representative must witness the proof roll.
ebf5a59e-8e44-5291-8371-0f476cc2fda0 | note | ○ Following completion of the successful Proof Roll, Principles Representative will approve Fulton Hogan to place the next layer.
6134a0b9-74fd-5991-9fe4-7f7c835cb261 | note | ○ Placement of next layer can occur once lot is accepted following proof roll. Proof roll inspection will satisfy pre-placement CTB inspection
ed8f929c-5f3c-5d99-9d6c-e9ec5ff8a2c2 | note | Reference Documents - CL 4.11, CL 4.8, CL 4.16, CL 5.9
8853b58d-aa9e-5f04-8604-ca7be2a1e182 | note | Inspection/Test Method - Verify
9166191e-1d47-50c9-a1c2-aa87106416fb | note | Record of conformity - This ITP signed
8d54efd3-12ea-58c5-9db4-1ee9e840e530 | note | IP, HP, WP, HP, HP
b82ae293-b330-51f3-a3dd-5b0af50e15d0 | note | Responsibility - Project/Site Engineer
baa750f2-e49b-504c-a61d-2e359d14fe2f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Completion of Remedial Works (if required)
a6eea7f7-f90d-5f24-ba42-3cee0d13807c | note | Frequency - As required
10860f22-bd45-5045-b42a-51938225a3eb | note | Acceptance Criteria - Completion of remedial works or nonconforming Sub-Basecourse and/or Basecourse to be approved by Principal’s Representative before proceeding with the next layer of pavement Works.
b60361f7-65c4-5619-aaf9-fb1de60ca685 | note | Reference Documents - Spec cl. 4.21.3
a5be587b-5a31-5d92-87c4-2cf51d5227dc | note | Inspection/Test Method - Verify
ba4d1c10-00f9-5670-bb2c-33ef0baf1f43 | note | Record of conformity - This ITP signed
99acb4ef-c1fe-5a03-89cc-dff4993bedc2 | note | HP
a0e4e81b-9909-57d4-ba10-bc175a31943f | note | Responsibility - Project Engineer, Principal’s Representative
8a219366-a68a-5b60-8cff-5a38571304ec | date | Date Completed:
90a2a886-571d-56de-9a6a-670b0a14580e | note | Principal’s Representative - (if required)
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 - Testing, Lot Size and Compliance
| checkpoint | 3.1 - Survey Conformance
ce5c29e5-5140-5189-9eb7-e50ab50e5199 | note | Frequency - Every Lot
f272f98a-afa0-55a2-99ab-2926a15cf644 | note | Acceptance Criteria - Final survey level to be checked in a 5mx5m grid to conform with -10mm to +0mm.
df4c2108-63ab-5b10-b7f3-2e9c90d8b439 | note | ○ Survey report not provided for intermediate layers of the same material type (i.e. for PT2 where multiple layers of same material type placed).
12872338-4862-5c8b-9333-33b95e486659 | note | Reference Documents - Cl 4.13
53f1e0a9-3cd8-5987-afac-9955739ce2e2 | note | Inspection/Test Method - Survey Report
cfaa3583-94cb-5b87-a96f-4b0626c0b7ea | note | Record of conformity - This ITP signed
115ef3cc-0237-5ccb-b90f-4e1d03a9a55a | note | SCP
929cefd4-f1a7-5699-a3e6-84e1cfe5d6df | note | Responsibility - Project/Site Engineer
9d93fb88-69f1-59e3-929a-d5c9541b8328 | date | Date Completed:
| checkpoint | 3.2 - Surface Smoothness
c0ec5a15-a8a0-51ca-90fd-d266a977ae28 | note | Frequency - Every Lot
d3bb6e9d-cacf-567a-bb05-bb6f85f87f76 | note | Acceptance Criteria - Surface smoothness to be checked every 10m by placing a 3.5m long straight edged on the ground a checking any deviations over 7mm. Complete within 7 days of completion of each section. Document results.
c0794366-a9f1-513e-a322-e27e793bf4c7 | note | ○ Intermediate layers and shoulder pavements are not required to be checked.
428ff593-cbc8-5486-9adf-190d324ee211 | note | Reference Documents - Cl 4.14
916d282e-b4f1-5915-a1c9-84918bf87ad0 | note | Inspection/Test Method - Verify
f13e2c07-1d50-5bc0-b7a8-ec257e7c1c05 | note | Record of conformity - Report
0a56ea0b-1e1d-575f-aaaa-8362bd7334a7 | note | TP, HP
7c42df32-edf4-5349-9cac-0db15597dd49 | note | Responsibility - Project/Site Engineer, Principles Rep
7afe6ac4-7764-512e-b7a2-c8fe830be0cc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Layer Thickness
c7d134cc-94cd-5822-9a24-cf05412661f1 | note | Frequency - Every Lot
dfdd1cec-5b69-565b-969b-13bfc3125815 | note | Acceptance Criteria - Check thickness of layer using survey at the frequency of field dry density determinations. Thickness shall not be less than what is shown on the design documentation other than allowable construction tolerances.
39ceb27a-a277-5db6-8968-85e5c122043f | note | ○ Total pavement thickness is to be checked. Intermediate layers, no check is required.
02cf8440-e7ce-5019-8d6d-f32d5fb3afbd | note | Reference Documents - CL 4.12, CL4.21.1
018a61a9-d71a-5691-a975-97cdb35c1e0b | note | Inspection/Test Method - Survey
7625b794-097f-518f-90e0-c3cf230ed64d | note | Record of conformity - Survey Report
381236eb-aca7-59e3-a405-b6edd1e665c5 | note | SCP
53f8aeac-1b5e-5448-811f-f523a49ae4ee | note | Responsibility - Project/Site Engineer
8bc84e71-cdd6-5f5b-afd0-1b535d392c96 | date | Date Completed:
| checkpoint | 3.4 - Degree of Saturation - Sub-Basecourse or Basecourse
88ac18ee-32b3-5465-8cd7-55615a26e84c | note | Frequency - Every Lot
9c74aee7-54c4-5afa-91e6-17f8b6c54a58 | note | Acceptance Criteria -  Degree of Saturation to be tested for information.
7d6d8edb-471d-59a3-84c9-22efe19673c4 | note | ○ Target less than 70% Mean Moisture Ratio.
5267ce29-e9dc-5467-8683-1ff409d3ea82 | note | ○ Test to be taken the shift prior
9ceab416-7620-5e4c-90dd-667de55b8550 | note | ○ If lot gets impacted by significant wet weather, tests to be re-taken
8589b525-694e-5da5-b255-316e9b32bc6b | note | Reference Documents - Cl 4.9
5fc35d50-782c-58c0-a03c-3e2d8632bc41 | note | Inspection/Test Method - Test
36e1d3a5-9404-5501-a43d-8d4439103d9f | note | Record of conformity - Test Report
5b334ed9-a6bc-5b9f-a9a5-188554ebf8fe | note | TP
57654c0f-8304-5154-aabe-6a53ae12880c | note | Responsibility - Project/Site Engineer
2fb7e3e4-a500-5dab-971f-da16c64f635a | date | Date Completed:
| checkpoint | 3.5 - Field Dry Density
ab290cab-8857-5299-aa93-394c9f7fa1cd | note | Frequency - Every Lot
44b41968-019b-5980-9048-f4b4803f2fa7 | note | Acceptance Criteria - Dry density for basecourse layer has the following acceptance criteria:
14d36e20-9b4e-51c7-b303-4820d35263fe | note | ○ Average of 5 consecutive tests exceeding 100% MMDD.
58de0ee5-78b1-54c6-8224-caf072eeab7c | note | ○ No individual test result less than 98% MMDD.
5d48328e-ac3a-5ad6-b3d1-2406a288f5b8 | note | ○ Principal’s Representative approval based on the results of proof rolling.
f93e1ad9-5cf4-5128-a858-cd7b9bd4cdbb | note | Dry density for sub-basecourse layer has the following acceptance criteria:
e55b6308-f7dc-5856-a542-efcc3c4daea4 | note | ○ Average of 5 consecutive tests exceeding 98% MMDD.
9bf576a0-bf13-5841-ab9a-3afc1935f1b8 | note | ○ No individual test result less than 95% of MMDD.
87da770e-45a7-5e52-8aa1-dda76aa5f24a | note | Principal’s Representative approval based on the results of proof rolling.
44ea133f-24b6-54a9-a30f-f261e13a62f9 | note | Reference Documents - CL4.10 Cl4.21.1
f280a436-de2a-53ef-93ab-b1e3225eeeeb | note | Inspection/Test Method - Test
52cdd929-b842-55ad-8145-5e9812049d33 | note | Record of conformity - Report
407dbe1a-efa0-5213-9bb6-8e6f36cbc3c5 | note | TP, HP
ab5827b3-767d-5dbc-a203-d030deba9967 | note | Responsibility - Project/Site Engineer
e7b37db0-a68e-5a1c-bb23-556cc134f8ee | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Quality Assurance Records
6006ffa3-1aa2-59bd-83dc-d6b805ff55b4 | note | Frequency - Each Lot
b2f55ca2-6a14-5a7e-82ba-84de49be30a1 | note | Acceptance Criteria - Submit test results on Aconex for every lot of Sub Base and Basecourse. Results to summarise each test (Moisture content, field dry density and layer thickness).
7bd5a9d8-f1f0-515c-9bd2-db15c58c3a89 | note | ○ Aconex ref to be submitted as Hold Point sign off.
37e3ac2e-1f70-5db3-af28-32a669466602 | note | Reference Documents - Cl4.21.2
c4470a88-b0fb-56dc-9525-ae5913364874 | note | Inspection/Test Method - Verify
e77eb85f-0ce5-5a4d-8372-d2a926cf0d3b | note | Record of conformity - Summary of results
425f643f-a056-5010-9038-22100d4cf06c | note | HP
199e0e4e-ff37-594a-a3d2-8836730d58da | note | Responsibility - Project/Site Engineer
76c8b366-beb3-55a7-bfb4-5516b9aae5c1 | date | Date Completed:
9cafd654-8c3b-5d53-b27f-4fd2723098a3 | textbox | Aconex Ref:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
ed6b8455-38dd-51af-bd54-3125b5c47d2a | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
df9f428d-9eb7-515a-8ac0-5b3ec3fd6875 | textbox | Print Name:
f06a7fa1-f701-5396-b827-73e4dfa88863 | textbox | Position:
e17ead71-e36c-5c5b-8116-ea40ac9b8e17 | date | Work Completed On:
4f3c133c-1503-54e8-8324-f5dd13700c4c | date | Date:
| checklist | FH-ZU2-QU-ITP027 - AGL Cabling - Rev 0 | itp | ITP027 - AGL Cabling | e6f0f3c5-e7c8-47aa-85f4-6016ee88c564
| section | 1.0 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
084ecec0-08c1-5480-8d74-efa85d9a76ee | note | Frequency - Prior to commencing any activity
9cf17b9a-0296-5121-bb59-c09361c4f722 | note | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
c79d28c3-2ad0-5255-8028-702fc73647b9 | note | Reference Documents - IFC Drawings
fc5214f9-eb77-50a2-b18d-2cb2846dce3b | note | Inspection/Test Method - Verify
f53bce20-91ed-5f05-8562-ea715bec3633 | note | Record of conformity - Drawings
3956a579-86ec-5eff-9e4a-7cb57c2eb271 | note | IP
15d1bba0-187d-5a60-9f6a-74c25f25b456 | note | Responsibility - Project Engineer
1d8ecb9a-5b52-5485-b3b7-52afe398bc4d | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
c6e968b0-29d1-5fc3-a00b-f3487f707c88 | note | Frequency - Prior to commencing any activities
e14bf65a-9dc4-5e81-ac7a-17abebc913e8 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
b0147824-8e3a-580c-9a41-7035645ed709 | note | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
e9e53ba2-3666-573d-8745-b4f4b768c75b | note | Inspection/Test Method - Verify
5ee7f0d3-73d9-5ebd-995e-3226eb9d0f9a | note | Record of conformity - Site and office inspection
4ccf422a-beef-54e9-9e0f-58c36f451a5d | note | HP*
a0b07714-756d-5a16-80f7-dd77e5338b67 | note | Responsibility - Project Engineer / Site Supervisor
5b08f91e-7c1b-542d-9d0d-13ac51c58d6f | date | Date Completed:
| checkpoint | 1.3 - Existing service location
f7e0a76f-bb66-599b-8dc6-5c96fecf6108 | note | Frequency - Prior to Start
8b5366c1-2c24-522f-b19b-28fd5bc1b429 | note | Acceptance Criteria - Prior to installing any fittings, location of all existing services to be identified and marked onsite.
73376e7b-6ec6-580d-b9d0-34afd28e1bc4 | note | ○ Services located in the works area to be proven.
9c79d5f1-9689-52f1-9398-fb9f9771e9c0 | note | Reference Documents - SWMS
eea18c1d-6def-5b6b-b17e-24506aa8f41c | note | Inspection/Test Method - Verify
dff13372-6be7-5222-b692-73cfc179bbb3 | note | Record of conformity - APAM Excavation Permit
b56d90d2-979b-5488-a1bf-01570a99015c | note | HP*
d5c96297-fe67-5e2c-85c2-7f12b293f64c | note | Responsibility - Project Engineer/ Site Supervisor
23a9c78d-9f3e-5f6b-8fdb-ebd1dc1753f4 | date | Date Completed:
| checkpoint | 1.4 - Cable route
03bcb88c-dbb4-5a7c-8025-39e72b794caf | note | Frequency - Each Lot
a0bcbaf1-c3f4-5bab-a543-7fa6c5d4066e | note | Acceptance Criteria - HOLD POINT
9a5ce38e-3353-5874-b422-019c9ab8302b | note | ○ Primary cabling route installed as per path shown in construction drawings (and/or approved markup).
90d91336-1d81-5d57-801c-c3a066eaf8ee | note | ○ See relevant lot from ITP 025 – AGL Conduit Installation for cable route.
44c77117-fef3-567e-87e8-19d52c85c1ef | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 5.5.1, ITP025 – AGL Conduit Installation
2e613ce2-b0af-5d92-a459-99d17ae91845 | note | Inspection/Test Method - Verify
3d98ff75-4225-596b-9e58-e1a3c8c2539d | note | Record of conformity - This ITP signed, Aconex reference
b625d644-30b5-51e1-9af1-cccc76587060 | note | HP
01e00bb4-877a-5213-b35e-a1ebdf6557b0 | note | Responsibility - Project Engineer / Beca
29c73fdf-273b-5d49-b87c-712ec8e4165c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 - Material / Equipment Approvals
| checkpoint | 2.1 - Primary cable
a4cfcd29-f001-5898-99d5-aea2ed7dae11 | note | Frequency - Prior to Start
20690dcf-c0f0-5f39-8aa8-2fde40a065b5 | note | Acceptance Criteria - Primary cables shall be:
9670b5af-42c5-5b09-bf68-75b15edff80f | note | ○ 6mm2 cable with black polyethylene jacket and copper tape screen
e637605e-20ef-58b9-90e2-6be82f3e36a7 | note | ○ Rated for 5000V
d326591b-4763-538d-83da-89729d6a441f | note | ○ 7 Strands
ee079a69-7ee0-5d57-849b-4011e89e0ce7 | note | – or approved alternative.
c0c1ca0c-b955-5091-923f-7ed9c45285c9 | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 4.2.1
c563a629-6af2-5db4-910c-9e5cb7e36225 | note | Inspection/Test Method - Aconex
d377bcc3-b1b0-52ec-b726-e8eaf8ee04f9 | note | Record of conformity - Datasheet
4f6e1f99-b816-5649-902a-f1371e263942 | note | HP*
50157a5e-7a28-57ed-b565-fc6723f7cfd2 | note | Responsibility - Project Engineer
2ff1bf0e-8e3b-51f3-b9f1-8f1a2390a308 | date | Date Completed:
| checkpoint | 2.2 - Secondary cable
02c825d0-9463-5d10-908a-5776a6ee38c1 | note | Frequency - Prior to Start
52f4d154-8af1-5719-8224-0f418e45606c | note | Acceptance Criteria - Secondary cables shall be:
44d71d7e-47f4-53ca-8fe0-dcdbf79ac714 | note | ○ Min 4mm2 cable with black nylon jacket.
7a40335d-5509-539c-924c-6fcda49c0716 | note | ○ Rated for 600V
3872fc69-1b47-510d-907f-98720bfaf136 | note | ○ 56 strands
e8ab4674-6ef6-53e9-a70b-7f0d461d0da5 | note | – or approved alternative.
8aff2a2b-fe11-52f6-b2e3-23abc4326c74 | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 4.2.2
4ae35278-4742-5729-8cfd-68865b2188b6 | note | Inspection/Test Method - Aconex
3e6ca5c6-27ef-542a-97b7-94c52dd40f63 | note | Record of conformity - Datasheet
0301d6eb-5530-5d94-9a47-18403d44c79c | note | HP*
3f600ea7-c96b-5ede-aeb1-e1890b3f777e | note | Responsibility - Project Engineer
29144972-5c24-503e-ba07-de15f3241fda | date | Date Completed:
| checkpoint | 2.3 - Cable connectors
91357c0b-6615-5f70-a6d6-3e23d4560efe | note | Frequency - Prior to Start
c92cf1f7-00a2-526f-8576-138d0d9873c3 | note | Acceptance Criteria - Plug and sockets shall be further sealed by the application of double lapped layer of self-amalgamating tape protected with a double layer of PVC insulation tape.
b99c8fd4-8940-5c39-8668-8f6a4f175a5b | note | ○ Field attached plug and socket connections shall be constructed in accordance with the manufacturer’s instructions.
4417737e-8692-58bf-8c97-f3b6cdff95d2 | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 4.3.3
f3e252d4-b3cb-52d1-8e5a-23b63082c72f | note | Inspection/Test Method - Aconex
bb294352-9e84-5ee6-8863-ac6ad920bfa5 | note | Record of conformity - Datasheet
d4a2e8f6-4eff-535e-9cd8-cf7e67cd3e05 | note | HP*
1331058a-48b5-5da6-a7f9-208bfa631de0 | note | Responsibility - Project Engineer
3f816d24-9eef-5296-a933-b1e06087f758 | date | Date Completed:
| checkpoint | 2.4 - Series isolation transformers
6d768cdd-92c9-5df0-b66f-03310679378c | note | Frequency - Prior to Start
58cc99f6-1105-50d9-9640-c9b017da833e | note | Acceptance Criteria - New SITS shall be:
36cdee4a-1209-55b0-9a64-12ebbb5cffd0 | note | ○ Fully encapsulated synthetic rubber watertight (IP68)
0f66dc6f-e6c1-5947-ab6b-b7f626d5f9a7 | note | ○ 6.6 Amps rating
9e43bca9-5498-5d13-b69e-72fbf134f526 | note | ○ Minimum 600 mm long primary tail/1200mm long secondary tail
aa3245e2-c20b-5312-94f0-c807b7047f1e | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 4.3
d8e756e7-9177-5d62-bf54-1db70c39f9bc | note | Inspection/Test Method - Aconex
ad67297c-22b9-5468-9afe-e2de309eebb7 | note | Record of conformity - Datasheet
58c85867-a8e0-5bae-8e91-893355021d6e | note | HP*
c19a30da-ceda-51d4-9c29-64d1c6f68cf4 | note | Responsibility - Project Engineer
aa5c7237-766a-5f7f-ba7c-231f10cec1ab | date | Date Completed:
| section | 3.0 - Cable Installation
| checkpoint | 3.1 - Primary cabling connections
ea9d079c-2a66-55c9-bb18-242e37729a70 | note | Frequency - Each Lot
2243b91b-3809-53de-b099-828910c65b19 | note | Acceptance Criteria - Underground primary cable joints are only to be made where the cable length exceeds the maximum cable drum length or jointed to existing cabling. These joints shall only be made in pits. The joint shall be waterproof and shall allow the jointed cable to be installed within the pits without causing damage or undue strain on the joint.
043c37d0-da9d-5747-bd65-773ae0272a95 | note | ○ Use only approved plug and sockets for joints in primary cables. Primary cable must be jointed to the primary cable tails of SITs using approved cable jointing kits.
6c40c918-3883-5df6-aad4-88a5c5ed27aa | note | ○ Plug and socket connections shall be constructed in accordance with the manufacturer’s instructions paying particular attention to the screen continuity joint and ensuring the rubber housing and insulating silicone remains free from moisture, dirt and debris.
6c65db7a-3b38-512a-be73-ae5e9b1146ca | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 5.5.1
e13925a7-705a-5c56-b184-22641a23caf9 | note | Inspection/Test Method - Verify
846b7873-773c-51e1-9e00-f184596e2726 | note | Record of conformity - This ITP signed
5f3c0794-3a9e-52c7-8071-6008d5ab6eaa | note | IP
508909fd-f8cc-5530-ba2b-0e5bc3884e17 | note | Responsibility - Project Engineer / Site Supervisor
b019303d-e7e5-5e18-a362-fbdeb9436f53 | date | Date Completed:
| checkpoint | 3.2 - Secondary cabling connections
15614fa1-b345-5403-9db2-3c9f0d2ffb08 | note | Frequency - Each Lot
bffd1973-f393-5401-8d63-a0570a17a67d | note | Acceptance Criteria - Individual secondary cables shall be provided for each lamp contained within individual lights. The secondary cable shall be installed in a single, unjointed length from the SIT to the AGL light.
4b01cb52-b615-5ade-bc21-bcf411c5277e | note | ○ A secondary cable that shares a common slot shall not be installed under any light base. Any joints within the slot shall be made utilising crimped links “staggered” and be installed external to the light base.
afdd9390-f698-535e-b1c6-527752df2859 | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 5.5.3
8ca84581-aadb-5430-8c67-78e90d21cd14 | note | Inspection/Test Method - Verify
9304141f-7b41-57c3-98d7-5392d95ffc0d | note | Record of conformity - This ITP signed
13e87572-3f6c-53aa-a953-1be7bb496315 | note | IP
c4862c2c-2c95-5f55-9d2b-c389b45c68db | note | Responsibility - Project Engineer/ Site Supervisor
47ae2efa-08a3-51a3-a7b6-964e99817080 | date | Date Completed:
| checkpoint | 3.3 - Secondary slotting
9e096c81-d57e-52de-aca2-c387d8e3d981 | note | Frequency - Each Lot
48ee0b44-923a-5497-ad9f-8d80f41f7cb5 | note | Acceptance Criteria - Pavement shall be saw-cut to specified depth and thickness and slots cleaned/free from debris.
d9f87c01-cdd0-503a-b474-f622021a407b | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 4.5
0165c77b-68c1-57d5-99ba-46d16a829b60 | note | Inspection/Test Method - Verify
48f4a900-5a6f-59b6-8d1d-400ca5d8111b | note | Record of conformity - This ITP signed, Avionics Secondary Slotting and Sealing checklist
549d7b64-d47a-550f-ab5e-1402dff8847f | note | IP
2b2115c3-a236-5ea3-a202-5f0e0fa7d70a | note | Responsibility - Project Engineer / Site Supervisor
6c2a9dff-ac7d-53b5-be06-592d0d48ddd8 | date | Date Completed:
| checkpoint | 3.4 - Max conduit capacity
b6b31181-2c85-5d37-8d46-a75bbb4e7e8d | note | Frequency - Each Lot
1b87870c-f6d7-5e0e-b697-a38d3829ca60 | note | Acceptance Criteria - If APAM approve three or more cables enclosed in conduits and/or ducts, the total cross sectional area of the conductors must not exceed 40% of the internal area of the respective conduit and/or wiring duct as recommended in AS/NZS 3000 for short distances without bends.
333a725b-5074-5b9a-ae2e-c774ef15a1cd | note | ○ No more than 10 primary cables shall be installed in a conduit
0bd5e56b-56cc-5808-8b49-a3cdf5ed0f66 | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 4.2.3
f1737631-1a73-5351-9176-dc1ede50b9ce | note | Inspection/Test Method - Verify
4d8d6ccb-8ba4-52f7-a489-6cd2068f8376 | note | Record of conformity - This ITP signed
c7ded4d5-231f-5382-bde9-aa38ed255345 | note | IP
6d7361e5-1b4c-52bf-9fa4-0c30d11ac193 | note | Responsibility - Project Engineer / Site Supervisor
e226c20e-d9ce-5287-86b9-610eee1e2e48 | date | Date Completed:
| checkpoint | 3.5 - Secondary sealing
f062f36f-3fa7-5e14-b5de-d61d9ea3b475 | note | Frequency - Each Lot
1adcea5f-6e85-5300-9bcd-c69c1f01545a | note | Acceptance Criteria - Backing rod shall be installed on top of the secondary cable, followed by flexible sealant:
aa8d978a-c98e-549a-9289-0b3b5c4655d8 | note | ○ Dowsil 888 to be used in concrete expansion joints.
5ef02737-3cc2-55cf-abfb-49a9350af82c | note | ○ Dowsil 890SL to be used in asphalt slots.
14f281c1-a5d0-5029-8cd4-1f58a35b8d27 | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 4.5
2ae4e0a1-e1a0-5ce2-8843-962ababbc36f | note | Inspection/Test Method - Verify
b37e2ee4-593d-58af-8372-8386987aef16 | note | Record of conformity - This ITP signed, Avionics Secondary Slotting and Sealing checklist
fff47d18-3cb4-5870-b270-f3edbd0d0f6f | note | IP
64903664-af96-53a8-81e5-5638822bd6b4 | note | Responsibility - Project Engineer / Site Supervisor
ec73ec40-fd32-5e9a-a5fb-1503f94d5f0f | date | Date Completed:
| section | 4.0 - General Works
| checkpoint | 4.1 - Protection of existing cabling
3bf93f01-555b-54d4-a582-037f3bbb5d03 | note | Frequency - Each Lot
248d71c1-0b97-55f6-8e5f-7236a7339eb2 | note | Acceptance Criteria - Where the crossing of existing secondary cables cannot be avoided, the existing secondary cables shall be reinstated and made good.
614967ac-49be-5eb3-b4a4-5e2a416fe8dc | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 5.5.3
197c8456-1b37-576d-b956-4c9dfb1ecfc6 | note | Inspection/Test Method - Verify
f140fba5-11b8-5a1a-8466-c67126c7eb90 | note | Record of conformity - This ITP signed
251241da-1c79-5865-ad28-350adca01eab | note | IP
7fb33dc8-893f-5f67-bda9-36b54ed65019 | note | Responsibility - Project Engineer / Site Supervisor
80dbe2aa-e49d-5f8f-91da-5a384a46d295 | date | Date Completed:
| checkpoint | 4.2 - Slack
5bca6755-97ff-5b88-b7ca-e3148358c514 | note | Frequency - Each Lot
cdedd2a9-f061-5069-9b6a-059946986c83 | note | Acceptance Criteria - Primary Cabling – a single minimum 500mm diameter loop shall be made in each primary cable where they pass through a pit other than a SIT pit.
d5ba2815-1717-57c3-aae8-1159abdf46e2 | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 5.5
e94e0a39-5c2a-5943-9aa6-a1c3d52fafcd | note | Inspection/Test Method - Verify
6621fec5-b16e-52a2-b4a9-9e931b50831e | note | Record of conformity - This ITP signed, ADBSG Installation of Primary Cable checklist
52ae351d-e471-5fe6-918e-14decf9c1691 | note | IP
b267a4d4-a105-5628-83f3-576bf3477c0a | note | Responsibility - Project Engineer / Site Supervisor
dbcf3142-60f1-5794-960a-1cc3d3e52aa5 | date | Date Completed:
| checkpoint | 4.3 - SIT pit earthing rod
a14c2c6f-127a-5a25-a0f4-5c1bdeb75cf0 | note | Frequency - Each Lot
7b891f9c-47f9-57ca-a3b9-2c4ddb46a812 | note | Acceptance Criteria - Earthing inspection pits shall be provided with earth electrodes of sufficient length to achieve the required resistivity of less than 6 ohms. Earthing electrodes shall be copped clad stainless-steel rods of minimum size 13mm diameter.
762d0357-b40a-554d-8701-108c165fcc01 | note | ○ The earth wire size shall be 16 mm2 PVC insulated copper, other than where equipment is wired in PVC/PVC cable in which case the earth continuity conductor may be enclosed within the PVC/PVC sheath.
521a7e30-fe6b-5679-8531-dafd848094db | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 6
2c89753b-8848-5daf-9cb0-974bfbce040c | note | Inspection/Test Method - Verify
e89b7054-9b6d-546e-a45e-54c3166779d3 | note | Record of conformity - This ITP signed
e24392e3-32ab-5e0f-b556-44280a507148 | note | IP
c3b3db98-4d1e-533c-82e4-315160b85025 | note | Responsibility - Project Engineer / Site Supervisor
7f0d89f1-0c1d-5e4c-b946-b26987e2976b | date | Date Completed:
| checkpoint | 4.5 - Identification of configuration
8d761c6c-2d7d-5fb8-a94a-0edb816aa6ff | note | Frequency - Each Lot
76f55867-4af1-5970-addb-837d87187468 | note | Acceptance Criteria - Label all cables for new and existing circuits remaining in service at every access location such as pits, duct crossings, and ALER. Position the labels such that they can be read without displacement of the cables.
82e52b35-f14d-51bd-a162-8bfe8c2d6a02 | note | ○ In transformer pits serving multiple taxiway lights, the Contractor shall label each secondary cable at the transformer connection to indicate the designation of the associated light connected.
d8f2b1aa-e672-58e9-9d9d-a554cb0f8c11 | note | Reference Documents - ZULU- BECA-001- SPC-00003 cl. 7.2
2326d521-a431-5428-aab0-e20472db1be7 | note | Inspection/Test Method - Visual
410ba2ff-f505-5e22-b7e3-dcacb0bad6d6 | note | Record of conformity - This ITP signed
6218bb73-084a-5d77-b9f0-be4ffb63a444 | note | IP
99074f27-35e3-5c20-8bef-1e9b8369b278 | note | Responsibility - Project Engineer
e7cd0188-1683-5cac-854b-edca2a3e23a4 | date | Date Completed:
| section | 5.0 - Post Construction
| checkpoint | 5.1 - As-built Documentation
11dd7507-b970-571b-ac32-4491371ee8ff | note | Frequency - Prior to practical Completion
5d2dc373-07b2-5763-ae3f-1a29a8fb553a | note | Acceptance Criteria - Submission of as built report showing cabling route submitted to the Principal’s Representative prior to practical completion.
36472891-ad44-5c25-b118-0d207308de4c | note | Reference Documents - FH QMP
0e8769aa-d815-501c-96e3-f869244cd8fa | note | Inspection/Test Method - Verify
9c3385b9-97e5-5e23-9ea1-df36f907e5c1 | note | Record of conformity - As-built survey report
ac3a000e-49d2-54d6-89d3-bf30c8214e2d | note | SCP
d1d4caef-8eb9-5a1f-a947-1be67b7498a4 | note | Responsibility - Project Engineer
0901d4b2-d248-5567-9637-773d8239ebee | date | Date Completed:
| checkpoint | Final Inspection
c3c0d97b-0908-5237-a1f1-72513f227cb3 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
05edde7a-f08f-5c70-b88f-1accb1d8d8e4 | textbox | Print Name:
5bdcbcc6-9a38-590f-8004-c7bbf198ca9e | textbox | Position:
31a47a32-f239-5abd-b74e-9127e755a3b1 | date | Work Completed On:
cdce0b6e-8f82-5da0-9dbc-cd8e91518eac | date | Date:
| checklist | FH-ZU2-QU-ITP010 - Cement Treated Base - Rev 0 | itp | ITP010 - Cement Treated Base | f7de3e3b-785e-45cc-bac7-f9774ab68af1
| section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
| checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
8aa88d4b-ee91-5ba0-8457-6ddccc0d3aa5 | note | Frequency - Prior to works
f596a299-9f58-53ca-9c69-525ee7c3cc5c | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex.
e63a70e3-79b5-5073-95c3-410eeed9d6ef | note | Reference Documents - Aconex
66c5096d-0ffa-51b0-b947-f747cf16c41e | note | Inspection/Test Method - Visual inspection
5576b08f-da41-5fb2-928c-3099cdaa6f44 | note | Record of conformity - This signed ITP
bd555431-cb25-5b36-b645-bdbb62cd6733 | note | HP*
3b038d3a-33f6-557b-82bd-e7cd92c4d207 | note | Responsibility - Project/Site Engineer, Superintendent, Foreman
2f246865-c5bc-5edc-9639-3718d72b4815 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
b0b243f7-51c3-55b3-a663-0dc1b1e0b83a | note | Frequency - Prior to works
f696c199-a47f-5990-bd66-7861ff848da2 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
94fa6461-840a-5ed1-8c42-e091c2be9c8f | note | Reference Documents - PSP, EMP, TMP, SWMS & WP
77b7ee44-7821-5616-bd18-d2ce2cac25ba | note | Inspection/Test Method - Visual inspection
63a96ffb-32b4-5e4b-8a97-562a0fa2a122 | note | Record of conformity - This signed ITP
af9cf847-45a8-50a3-a06c-f3aa247d5f84 | note | HP*
1bb9c244-d14a-5e0b-ad9d-5e50f2486391 | note | Responsibility - Project/Site Engineer
20fe73d9-f13f-5d4b-9540-7726d2227e41 | date | Date Completed:
| section | 2.0 - Cement Treated Base Documentation & Trial
| checkpoint | 2.1 - Submission of Mix Design
f84701ba-8df7-56a7-bbf7-fd0108956189 | note | Frequency - 21 days prior to works
4c9630b9-e2f4-5db5-896f-1a0e63df22cf | note | Acceptance Criteria - CTB material and test results to be submitted to the Principal’s Representative for review to ensure that specifications are met and are compliant, prior to the initial placement of the material.
e094d516-039e-569f-9119-c1c7926abfa5 | note | Mix design results will include:
6e374311-1c48-581e-bddc-512318494010 | note | ○ Cement sample should include a CTB material within +/-0.5% of the specified cement content.
7554aa82-ddbf-5f1b-bdd1-acb07d6ad61f | note | ○ Aggregates comply with either Section 4.4 or VicRoads Class 2 or 3 material.
74caf24d-bc49-56b5-a014-a303fa78a0dc | note | ○ Cement shall be Portland Cement Type GP or Type GB complying with AS 3972.
4bd42f13-d34e-5934-acc8-df754cb1cd35 | note | ○ 3% minimum Portland cement content by weight of the dry un-stabilised material.
0998a3e8-f98a-5b9a-be32-e00b897df493 | note | ○ Mean seven-day unconfined compressive strength of CTB to be a minimum of 5MPa and a maximum of 15MPa. No single samples are to be below 5MPa.
42cad487-7e07-5ecf-9580-c34b1c0004d7 | note | ○ Water to be pot
1b7669d0-aaac-57b0-96ea-a1fcdf6df9ca | note | Reference Documents - Spec cl. 5.4, Spec cl. 5.5 AS 3972 VicRoads Class 2, VicRoads Class 3
873572a1-d8cc-565f-94c0-b94eb417573b | note | Inspection/Test Method - Verify
a66909ef-0334-52a2-bb86-0d40152f53e9 | note | Record of conformity - Approved Mix Design Report
2a6c4f49-8b5a-554f-8666-bcb24bd3eb89 | note | HP
5f8594b4-a8be-5f85-bfc9-24cd96c89d3a | note | Responsibility - Project/Site Engineer, Principal’s Representative
6f53238e-be9b-5995-8685-fd629656dbea | note | Principles Rep - Aconex: BecaCPL-GCOR-000790
66263921-7ec1-5447-8330-44ed2cae7d71 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Supply of Information on Materials Source
72c22c59-df34-5e6a-8aae-a691c8b99d03 | note | Frequency - Prior to works
f06bcd80-cb39-5f6c-b7ee-acc980e2837c | note | Acceptance Criteria - Principle Contractor to supply the Principal’s Representative with supply information regarding the source of the CTB material via Aconex.
8162544f-1551-5f20-8f89-31e412124556 | note | ○ Material information will include the material brand, material type, material supply source, and a supporting test certificate from a laboratory registered by NATA to prove material suitability for the Works.
0fa3973c-f303-515a-83ef-710cdaa6e7b0 | note | Reference Documents - Spec cl. 5.21.1, Spec cl. 5.21.1.1 AS3972
f426f090-b259-5e95-9fe5-efd9491e0e42 | note | Inspection/Test Method - Verify
f4fd7777-24a4-5e24-8f03-2efc20b3adda | note | Record of conformity - Approved Supply of Information Material Source
2c108637-99ea-5b69-8af2-367b81ad171b | note | HP
77f8cbba-a50c-5b3b-980b-bc14c923226d | note | Responsibility - Project/Site Engineer, Principal’s Representative
737f78ca-d449-5e8e-9300-55c08726cd26 | note | Principles Rep - Aconex: BecaCPL-GCOR-000790
2deff7dd-cb7b-5ccf-9592-103910360dfc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Production and Construction Trial
2237b766-5dba-5d29-821a-e23e772d006b | note | Frequency - Prior to works
3851ad88-0336-50bc-9701-1a660bba0fbb | note | Acceptance Criteria - Construction Trial for CTB mix to be undertaken by Contractor and reviewed by the Principal’s Representative.
a16ae413-4a25-567f-a41e-e6d4836ce8bd | note | ○ Trial of CTB will be based on the first day of placement. Construction procedure to be reviewed and updated if there are any non-conformances associated with the initial trial.
b2ee570e-0077-5e08-a6d7-b9ab0e54b482 | note | ○ The size of the trial area shall be a minimum of 3.5m wide and 50m in length.
92a07a74-804e-50e3-927c-8e7863345b9a | note | ○ The CTB trial area may form part of the completed works.
9c4ed211-657f-57d9-81c5-2446d3c19ac0 | note | Reference Documents - Spec cl. 132, Spec cl. 5.6
717ed14e-d0fa-59c1-bb81-5da36d688f29 | note | Inspection/Test Method - Verify
2dee421f-a4d7-599a-92f8-3f4f57c30792 | note | Record of conformity - Approved Construction trial report
aae278da-12eb-5ac9-aa6e-efefd64eccb1 | note | HP
22a01488-e3ea-50b4-87f1-af2f3639ea98 | note | Responsibility - Project/Site Engineer, Principal’s Representative
05718d70-ae85-54e4-8dac-399b72b5185c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Placement of CTB Methodology
8f31af96-a04d-519f-825d-c89d24070a0f | note | Frequency - Prior to works
22af0bf6-e6a7-533b-8b84-023de9149711 | note | Acceptance Criteria - Prior to placement of CTB the Principles Representative shall review this Work Method Statement for proposed methods of placement, compaction and curing
668d3fd8-fac2-52af-8caf-cb2488203135 | note | Reference Documents - Spec cl 5.9
9de3b2f3-7747-5f3c-baa3-785a2747e99a | note | Inspection/Test Method - Verify
c9bf8592-c08d-5316-bb18-160a3df6be87 | note | Record of conformity - Aconex Sign off
86c48c51-5b11-53ec-8c30-3f290786b3b5 | note | HP
da4ae08c-fac7-5e47-93e1-6f347419f540 | note | Responsibility - Project/Site Engineer, Principal’s Representative
7786b41c-8d21-537b-9856-adcc3eb88695 | note | Principles Rep - Aconex: BecaCPL-GCOR-000810
58f6c910-c461-5b65-a59d-decf015fc5c0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Provision of Material Samples
f34ea86e-e126-502d-b7d8-799a4d4501b1 | note | Frequency - At Least 5 Days Prior to works
dd7bb70d-a2b5-55c9-94b4-8dfc76fad08d | note | Acceptance Criteria - Principal Contractor to physically handover reference samples to Principal’s Representative of the approved CTB material. To be truly representative, the reference samples will be taken straight from the supplier of the material.
0c874d56-cf4b-5428-a181-0fb5c3e72280 | note | ○ The reference samples shall be divided into two representative portions, with one being held by the Contractor and the second portion by the principal until completion of the Works.
a7eaa790-89eb-560b-bb6a-42b034b9f4b6 | note | Reference Documents - Spec cl. 5.21.1.2
4123a350-addc-57f1-bedd-545a3336c7ad | note | Inspection/Test Method - Verify
e3479ff3-9d0e-5684-8e1e-0bf3b53ff2f0 | note | Record of conformity - Handover of Reference Samples and Aconex sign off
da9049f6-a774-5ab7-b2b1-03431ba9fadc | note | HP
92c0e4db-5ee2-5bbb-a183-8fea440ae72a | note | Responsibility - Project/Site Engineer, Principal’s Representative
ba3782a7-3abb-5d95-b86c-c78ef690149a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 - Placement of Cement Treated Base
| checkpoint | 3.1 - Subgrade, Basecourse Preparation
1d26deef-fe2e-5fdb-a424-a3909955245a | note | Frequency - Each lot
90173b31-4a14-50e9-93e3-3fed40bb5797 | note | Acceptance Criteria - Existing surface of subbase is maintained in compliance with tolerances on surface smoothness and level. The subbase is clean and clear of any foreign matter before the placing of the CTB.
c310d359-b226-5439-8830-9bf651637b3d | note | ○ Principal’s Representative will be notified 24 hours prior to the placement of CTB to allow the subbase to be inspected prior to the placement of the CTB. This will be recorded in ITP009 – Unbound Pavements.
65fd1623-8231-5854-aa9f-5cda3e8b9715 | note | ○ Principles Representative to be notified of the intention to place CTB.
b1ae7aca-a8e4-5915-b171-70d23878625f | note | Reference Documents - Spec cl. 5.7, Spec cl 5.9
35910732-4634-5050-a1f3-a7e82e567390 | note | Inspection/Test Method - Visual Inspection
a9a3fb03-d34e-5643-aeab-c7f7c06b097d | note | Record of conformity - This signed ITP
0061e970-f3a6-5f64-861d-4a3562876699 | note | HP*
b5dc517c-d7f8-5f6b-b8b0-6a317bdab769 | note | Responsibility - Foreman, Site Engineer, Principal’s Representative
de55df49-5ade-5de7-908d-27572a37eefb | date | Date Completed:
| checkpoint | 3.2 - Layer Placement Parameters
15d20a59-abb9-5a63-bbbb-ae10c247e7e7 | note | Frequency - Every Lot
a7549654-01da-5468-98c6-45fd6149d6b2 | note | Acceptance Criteria - Summary of Parameters for each Lot;
9b307856-48e1-5148-b00c-36535f9c5285 | note | ○ A lot is defined as one layer placed in a single days production of uniform material
443263a8-e71e-5b88-afb4-8b92e59bb419 | note | ○ Max Layer is 200mm
bed1a5bc-d098-5239-b2e4-030a8525d7c3 | note | ○ Min Layer is 100mm
187f4fc7-665d-5338-8487-8e92b1d07d02 | note | ○ Final Surface Level +0mm, -10mm (excluding intermediate layers)
7171547a-ee6b-53d6-b20f-7d3ad0a0d8c9 | note | ○ Shape: every 10m intervals, <7mm deviation over 3.5m straight edge (excluding intermediate layers)
01ea9862-06c3-54c0-8365-67d7ef6c4f5d | note | ○ Material is batched within 1% of OMC
154ea760-0093-5671-9a15-c4fb065e211a | note | Reference Documents - Spec Clause 5.9
23e30d10-91f9-5caf-bf9a-50c0b7a25197 | note | Inspection/Test Method - Visual Inspection
e3db2985-1629-55b1-86de-615aa90f8bca | note | Record of conformity - This signed ITP
92da49e6-752c-58e5-a3a5-368767d9eadc | note | IP
131f5628-0346-5a4c-830c-ee5d14e15223 | note | Responsibility - Foreman, Site Engineer, Principal’s
cc2418e7-c804-5128-ace2-e40bde4c6554 | date | Date Completed:
| checkpoint | 3.3 - CTB Placement – Weather
a8945776-a6f4-5b36-b3fe-925c329ce3df | note | Frequency - Each lot
527d722b-c5b1-574b-81b0-1a2b37349e23 | note | Acceptance Criteria - Weather to be check prior to placement, CTB shall not proceed when;
8b6f23cb-bdd6-52db-9b80-19f7c3a85136 | note | ○ Ambient temperature is below 5°C
b5a25fd6-d1a7-555c-a444-784f86bdf94d | note | ○ Temperature is over 35°C
abb0ce29-4364-5f04-86af-c2c1030115d2 | note | ○ Heavy Rain fall is forecasted
e8bd97b5-51ed-58e4-b56f-93694ea86fc5 | note | Reference Documents - Spec cl 5.18
17631fb5-c95b-50f9-96d9-c8cb7cd5a4ae | note | Inspection/Test Method - Visual Inspection
d44b3070-6831-5703-af8f-496e3889538e | note | Record of conformity - This signed ITP
77032644-9c84-5d86-8fa0-8438ebe70d20 | note | HP*
19904e0d-6cd6-551f-af45-e992a7ccbd14 | note | Responsibility - Foreman, Project/Site Engineer
ccba4635-1cdd-5b1f-84fb-6f07cec24b9c | date | Date Completed:
| checkpoint | 3.4 - CTB Placement – Checks
1bb2aa2a-c4ff-561d-a13d-7afbe13bc904 | note | Frequency - Each lot
32f8ef17-8490-50c9-9251-810682a3751a | note | Acceptance Criteria - During CTB placement Activities check;
40f02693-c8d1-535f-a199-ece05f6f73b8 | note | ○ Placement starts on the high side or crown of the layer where practical
048bd7c5-c004-55da-9bc4-93e115f79601 | note | ○ Material is spread in the direction of Taxiway across full width
4f433ccd-ee6c-524f-b818-eae38e7377da | note | ○ Underlying layer is not disturbed during deliveries
d08de34c-ea7f-583a-b415-47e596003fb9 | note | ○ Inspect Material for any contamination through placement activities
a61ff818-105d-5a4e-8680-ff9d042ce44a | note | ○ Adjoining layers are a clean face / vertical
8df5403a-2649-51c2-a3ad-c7303e4bb19d | note | ○ Segregation does not occur
b355b70a-b0ac-5a92-b3ac-1b8a400fe4a1 | note | ○ Placement to be completed within 120 minutes from time of batching and before concrete has obtained its initial set
f4942690-8cd5-558c-9f3a-44274fe159c5 | note | Reference Documents - Spec cl. 5.9 AS1289.5.2.1
b574633f-2bb1-5d4e-950e-ff2484b56389 | note | Inspection/Test Method - Visual Inspection
60226c75-b0de-5c5b-96e9-8673327b422c | note | Record of conformity - This signed ITP
b828ff37-ec7f-50be-94b1-ee32fc7cc07b | note | IP
d1b766ef-1c08-5b21-b039-7f9ab4683bf1 | note | Responsibility - Site Engineer, Foreman
2654885b-329c-5964-89f4-e465307a4a9b | date | Date Completed:
| checkpoint | 3.5 - CTB Compaction – Checks
d318849b-5618-597c-91b3-814e52d4f0e1 | note | Frequency - Each Lot
ae30e580-e65b-59b1-93b6-ceb7450cd2f2 | note | Acceptance Criteria - During Compaction check;
b10036b6-d4c3-53e6-a7dd-623f106280d5 | note | ○ Heavy smooth drum roller of 15t to 20t is used for initial compaction
d1f1c126-533a-5e6a-8dc4-2e235688e671 | note | ○ Pneumatic roller of 27t will compact material for final consolidation.
05876ce7-e80b-5055-948b-92633bd9b857 | note | ○ A heavy smooth drum roller (in static mode) may also be used for final consolidation
8a9f03d1-75fb-512e-bbdb-7318c1488415 | note | ○ Watercart present onsite for conditioning
65490f31-31f1-55fa-ba27-62cb0064acd3 | note | ○ Materials are trimmed to required shape and level
18e147eb-3edb-5867-bda3-b7734942fa05 | note | Reference Documents - Cl 4.10
a5cc52f2-9ea2-51e1-9d76-86f779782816 | note | Inspection/Test Method - Verify
4ed1fdbe-a813-5556-8b34-fa80b91e4a55 | note | Record of conformity - This ITP signed
d2cb62fd-45c5-53ba-a041-c81c964b747c | note | IP
8ca58966-39f3-51c1-9bf7-7cfb7924a9f8 | note | Responsibility - Project/Site Engineer
7d2e2bd3-99ca-5153-891e-45c4cf8e6ee3 | date | Date Completed:
| checkpoint | 3.6 - Curing & Protection
d9202bed-4ccb-5e6c-8eae-441e32bd0d2a | note | Frequency - Each Lot
3d18e78a-fbc1-525b-822e-0dad77056df3 | note | Acceptance Criteria - Curing to commence as soon as CTB has been placed, compacted and trimmed. No plant (other than curing) to track across CTB for minimum 24 hours.
3ff88ce5-7c4d-55c3-8a20-b2077108bb2f | note | Curing to follow one of the below methods;
426e9ca7-487a-5f20-a6ae-ffdc3fd8f5d4 | note | 1. Wet Method: This will involve a watercart lightly spraying the CTB surface for minimum 7 days.
ac0408e5-01eb-511d-bec8-72574746a26a | note | 2. Debonding Coat: The CTB will be covered with a bitumen curing compound. In locations of PCC, will be the C170 seal with 7mm aggregate.
dcc282aa-d774-5d32-a21a-2340833e3a7f | note | Reference Documents - Spec cl. 5.15
c185cb39-41db-5b74-bf4b-58039a1d2486 | note | Inspection/Test Method - Verify
5ed27476-046b-5d4c-91f4-9d6dc280e91b | note | Record of conformity - This ITP signed
4127c5e4-b820-5275-befd-3ba282773570 | note | HP*
90a1f255-e2f6-5258-82f4-a6608d585ead | note | Responsibility - Foreman, Project Engineer, Site Engineer
b29214e6-d20d-57e7-b892-48164a53e9e0 | date | Date Completed:
| checkpoint | 3.7 - Post Placement CTB Inspection
c133101a-b607-579c-b4f9-2cf71ca93f9b | note | Frequency - Every Lot
a7f09b74-8c7e-5e9c-8c19-390ba5710f6c | note | Acceptance Criteria - Prior to the application of the succeeding layer or installation of the de-bonding coat, CTB final surface is to be inspected with the Principle Representative
3dd631f2-a2a1-571d-a620-d5d946c8b5bb | note | Reference Documents - Spec cl. 5.9
84554310-d991-5d29-82f6-a3c07c5d5599 | note | Inspection/Test Method - Verify
09e8586b-eca6-5d3a-a226-2bcb388209a4 | note | Record of conformity - ITP signed
5ccaaf5a-f383-5dcb-9802-a10733a58443 | note | HP
905e8200-14cf-53ec-a676-f2ddc9f34212 | note | Responsibility - Project/Site Engineer, Principal’s Representative
d7a8daed-5a8c-5363-9fc5-cd375d53fabb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
| checkpoint | 4.1 - Field Dry Density
f03186bd-59c9-5281-b6ef-20321711d5ed | note | Frequency - Each Lot One test every 500m2 (or 250T) or part thereof
102f1ebf-e51b-5ed9-ad43-a0896478ebdd | note | ○ Minimum 4 tests for Lots under 800m2 (or 400t)
f5ceefec-34de-5727-916e-0b288c1aabd4 | note | ○ Minimum 6 tests for Lots over 800m2 (or 400t)
803c9230-1f43-5b08-9bac-c416ef40d10d | note | Acceptance Criteria - Average of Specified Minimum Dry Density Ratio (SMDDR) of 97% of the Maximum Modified Dry Density
0f72bb26-c4ac-5f47-9353-d47361c2c94d | note | – Average Equals or Exceeds 96% with no individual result be less than 93%. The lot will be accepted.
54e288c2-afc9-5831-bdd3-c814dbafdac1 | note | – Average Equals or exceeds 96% with a result being less than 93% - an additional 4 tests will be taken
7422857c-dbf4-5cde-8fcd-7a9eebb01ddf | note | – Average is less than 94%, the lot will be rejected
58937cc4-12d9-5cda-a665-45ab2a8da7e5 | note | – Average is in between 94% and 96% - an additional 4 tests will be taken
a9f58864-2561-54a2-bfa0-dab77c1e7259 | note | Reference Documents - Spec cl. 5.10, Spec cl 5.21.2.5
28029483-eb30-5e34-b3a9-ed80ee976a2f | note | Inspection/Test Method - Verify
71a6959e-311c-5755-aa07-77880c544a37 | note | Record of conformity - This ITP signed, Test Report Attached
16a6d560-db93-5e93-aac4-1ef0e3b58824 | note | TP
4d63e4ce-61af-549e-93cd-88e90439f6fe | note | Responsibility - Foreman, Project Engineer, Site Engineer
d729f33b-569d-5d94-bf25-bde0399b776e | date | Date Completed:
| checkpoint | 4.2 - Moisture Tests
48e1392d-43e6-58f5-af5e-7dedfde8269c | note | Frequency - Each Lot One test every 500m2 (or 250T) or part thereof
06c7fffd-057a-5683-a5f7-8a8c381a276e | note | ○ Minimum 4 tests for Lots under 800m2 (or 400t)
2b0ffe7c-a0d8-59f6-bebc-62ca95b1f694 | note | ○ Minimum 6 tests for Lots over 800m2 (or 400t)
ebec3e40-e3e6-5a4b-9711-f0369aaf6a53 | note | Acceptance Criteria - Target Moisture content of +/-1% for information only. Production of CTB to be within 1% of OMC.
b5ab453a-a9ac-5e01-bf8f-b88b1b412688 | note | Reference Documents - Spec cl 5.21.2.5
31eba2f8-121a-5f0a-9bbd-1df0d0fcd5d6 | note | Inspection/Test Method - Verify
1d86b1f4-11bd-5c0c-9580-e4d32aaf98f6 | note | Record of conformity - This ITP signed, Test Report Attached
6a896df5-fbe0-5c11-9572-3ea136c6b665 | note | TP
dd17bd53-ffd2-53b4-ac3a-23be9eb1f240 | note | Responsibility - Foreman, Project Engineer, Site Engineer
da840038-f33d-5214-8629-cc69fb864320 | date | Date Completed:
| checkpoint | 4.3 - Strength Testing
27bc8c7e-95d1-5dcf-88ae-82823e1085d9 | note | Frequency - Each Lot, divided into four approx. equal sub-lots
2fddab20-aeb3-51af-80f7-3033426b797b | note | Acceptance Criteria - A total of 4 sub-lots will be taken as samples, with 2 being used for the 7-day strength testing, and the remaining being used for the 28-day strength testing. 28 day results are for information only.
53e841bf-eed4-57b9-9fbd-fd88b73d2b2a | note | ○ The mean 7-day unconfined compressive strength of the CTB shall be a minimum of 5.0MPa and a maximum of 15.0MPa. No single sample shall be below 5.0 MPa.
2750053b-5e5b-527a-927e-8e87f4aab69a | note | Reference Documents - Spec cl 5.11, Spec cl. 5.21.2.6, AS1012.9, AS5101.4
520a4d5f-8343-5414-af26-941844343fab | note | Inspection/Test Method - Testing
51ba2912-8e23-5929-9c94-7c2fc5b9173a | note | Record of conformity - This ITP signed, Test results
102a9d58-c7cf-58d9-a254-e2b57c059a11 | note | TP
62c9a368-385e-5f8a-a5fd-3173b78cbeb5 | note | Responsibility - Project/Site Engineer
cd63fc81-2748-5204-8c71-1ecdc8d7094d | date | Date Completed:
| checkpoint | 4.4 - Process Control
c610b4ae-a285-5c6e-8fcd-207cb4c478c1 | note | Frequency - Each Lot
139d6cc6-0860-5d37-84ea-5eec2d18cc61 | note | Acceptance Criteria - CTB production and process control test results to be supplied to the Principles Representative
4cf57679-b162-55ad-abc5-71060624730a | note | Reference Documents - Spec cl. 5.21.2.1
a2362452-e6b9-50cc-8ab0-15193aa438e1 | note | Inspection/Test Method - Verify
6b11e16c-b89c-532c-8d84-0dde9b1f6e07 | note | Record of conformity - This ITP signed
f14b3625-4f6b-54d3-86cd-83ac17befadb | note | IP
cbabd8ff-86fb-5ea7-adaf-3d9bcd3a5cc2 | note | Responsibility - Project/Site Engineer
81b3934b-4a7c-5973-9a83-ac3ddb5484e9 | date | Date Completed:
| checkpoint | 4.5 - CTB Layer Thickness
1799115e-1fc2-519a-85de-f01907f95ab3 | note | Frequency - Once Every 30m2
fb01f919-1253-50b5-bafd-444151f02c79 | note | Acceptance Criteria - CTB layer thickness to be measured, recorded, and included in the Quality Assurance records. No CTB layer thickness to be less than that shown on the drawings other than allowable construction tolerances
86aed6fe-a7e1-5bbe-b54d-a6febb6dcee1 | note | Reference Documents - Spec cl. 5.21.5, Spec cl. 5.21.7
1751b0ea-39bf-557f-a987-76db1c978ff5 | note | Inspection/Test Method - Testing & verify
8f655c65-eeac-573b-a41b-ff7a4763d512 | note | Record of conformity - Test results & this ITP signed
1edaa5b4-7fe2-53f7-904d-ef6ccb84713b | note | IP, SCP
440d35fd-e0b5-5913-b784-e8a1609522a6 | note | Responsibility - Project/Site Engineer, Site Engineer
8486d6a6-edbe-5b6f-ad1b-e3320c99b948 | date | Date Completed:
| checkpoint | 4.6 - Quality Assurance Records
e28ad406-42b3-54df-bd45-1d533d8a6992 | note | Frequency - Each Lot
6bff1fb8-fc6a-5245-be5d-b0d34882f2da | note | Acceptance Criteria - Provision of ITP test reports must be submitted within 60 days after the completion of the Works. Principal contractor to supply electronic copy of reports detailing the results of the quality control and testing undertaken.
ff73a1e8-da4b-56d3-b9ad-dd3e0a5b5867 | note | ○ Reports to be transmitted on Aconex and Aconex Reference to be quoted as Hold Point Sign off.
901e3f69-22d4-5dff-a8fb-4777b97224e0 | note | Reference Documents - Spec cl. 5.21.3
dbe748d1-13fc-59a6-b11a-3fde2f3eafe5 | note | Inspection/Test Method - Submission of ITP reports
d186873f-c9c4-57e7-a8a6-10ef7c2b1f91 | note | Record of conformity - This signed ITP
ddbf53ba-4ba6-5162-a876-1db4a0b8cda0 | note | HP
6a8940a0-674a-51b8-a949-c153ebc3521f | note | Responsibility - Project/Site Engineer, Principal’s Representative
d26e1c20-cd8c-5956-8617-743c63ff978f | textbox | Principles Rep - Aconex Ref:
a6b55153-f7f0-5005-ad8c-0083e0fd459c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.7 - Survey As-Built Report
2275ba0b-0e87-5dba-a66e-9441454b85ae | note | Frequency - Each Lot
dbb59df4-c843-56b6-8c73-5f8a99b22177 | note | Acceptance Criteria - The surface level at the top of the final CTB layer shall not deviate from design level at the specified points by -10mm or +0mm. Contractor to provide Survey Conformance report of completed CTB surface layers per Lot.
61d1d193-4712-5f16-853e-4cf7e99a2d55 | note | Reference Documents - Spec cl. 5.17, Spec cl. 3.14.2
c5212fbd-57c5-5049-9e22-15468fa5c769 | note | Inspection/Test Method - Verify
b30b9298-b275-527f-83c5-0965084bdb9c | note | Record of conformity - Completed drawings, survey report, & this ITP signed
a9cbc0bd-f47a-5f26-81e9-5f5cb769aaf6 | note | IP, SCP
3d2bd58c-980e-593c-8704-511a08c99272 | note | Responsibility - Surveyor, Project Engineer
c5056a76-945c-5f08-b874-d76e1d320dbe | date | Date Completed:
| checkpoint | 4.8 - Surface Smoothness
5d4acac4-2875-5596-93f5-1a785ba3e054 | note | Frequency - Every Lot
93786c44-4ebd-54d3-aca1-951acc07afb5 | note | Acceptance Criteria - Surface smoothness to be checked every 10m by placing a 3.5m long straight edged on the ground a checking any deviations over 7mm. Complete within 7 days of completion of each section. Document results.
91fb8cd2-d46e-5227-b807-708f1a461489 | note | ○ Intermediate layers and shoulder pavements are not required to be checked.
c01c18c5-37ba-58b4-a6a2-642d82ab94c0 | note | Reference Documents - Cl 5.17
58c12aac-2d98-5ac4-b686-7c9e9cfaa8e0 | note | Inspection/Test Method - Verify
ed18d16e-eb2c-55be-9c34-5b2c4fd34347 | note | Record of conformity - Report
3b7bb992-09a4-5bdd-9c10-fcc45ede27d4 | note | TP
f9ae33fc-2416-5f39-a778-8195e2fb3791 | note | Responsibility - Project/Site Engineer
effa941f-c08e-5def-b3a5-5ecdab676233 | date | Date Completed:
| checkpoint | 4.9 - Correction of Nonconforming Work
9ec784eb-353e-506d-9619-b27d85a09297 | note | Frequency - Each Lot (if required)
369bd2a4-9673-5e6f-b9a7-c89bb20602c2 | note | Acceptance Criteria - All CTB that do not meet all the specified requirements will be rejected by Contract Administrator. Materials to be removed full depth of the layer and reinstated, unless otherwise approved through the NCR process.
ac35cc23-2d07-57ea-aa08-9d3098856e40 | note | Reference Documents - Spec cl. 5.21.4
99ba277c-f48e-501e-89c3-e4675b0c7544 | note | Inspection/Test Method - Verify
55f90695-7572-5a0e-8395-fe465a26db9f | note | Record of conformity - This Signed ITP
db96ea5a-921e-5ed5-8c15-2a19c2d9a5bd | note | HP
6a3f2218-7f09-5a57-b7a7-c49b0d52d177 | note | Responsibility - Project/Site Engineer, Principal’s Representative
dba5f565-ca20-52ba-aca1-c9ea7c152251 | note | Principles Rep - (if required)
e18f55d4-6a0b-5027-bffa-6021233c4d87 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
f9a7189c-b860-50c9-ac40-38214720411f | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2ed5916a-4453-538c-a5f9-3dc1b4870a03 | textbox | Print Name:
3b7bd65a-2e57-5fdf-babf-8993d668d7c2 | textbox | Position:
90d84dfb-f506-5b4b-b2a3-b1f9ce2894e4 | date | Work Completed On:
bbf80422-452e-53b5-8e68-f944166304fe | date | Date: