## Resources
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Suspended Copper Works Checklist |  | Suspended Copper Works Checklist | 05ae9972-f4ce-4dea-bdcd-c688a10e23bb
| checkpoint | Pipework installed - domestic hot/cold/rain water
| checkpoint | Smoke seal penetrations
| checkpoint | Tested
| checkpoint | Fire rated if necessary
| checklist | Suspended Sewer Drainage Checklist |  | Suspended Sewer Drainage Checklist | 10bc58ef-947e-4db3-a15b-2a2928d388a8
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
| checkpoint | Pipework installation
| checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
| checkpoint | Smoke seal penetrations
| checkpoint | Fire collars installed if necessary
| checkpoint | Test sewer
| checklist | In-Ground Pits/Pumps/Tanks Checklist |  | In-Ground Pits/Pumps/Tanks Checklist | 16b494eb-d7c2-4cd2-a39c-ea11b9f244f2
| checkpoint | Sewer pump well
| checkpoint | Storwater pump well
| checkpoint | Stormwater pits
| checkpoint | Grease interceptor trap
| checkpoint | Conduits rain to IFC location
| checkpoint | Torpedo tanks
| checkpoint | Stormwater detention system
| checklist | Add Daily Site Diary Checklist |  | Daily Site Diary | 16c766d0-3115-4b88-8941-185f0a8a43af
| checkpoint | Attach relevant photos and documents
a0aa1e95-7be9-5273-93ad-0a4cdb5a0105 | textbox | Time on Site
6e01c180-492e-5bc1-846e-44c9ec3ba0fd | textbox | Time off site
cc06bdd5-5b85-5a28-9e44-ff5e9b91bfc9 | textbox | Vehicles
fb855924-f052-5943-a728-9d0aa7209e7e | textbox | Plant
3d411984-77f6-511c-bd18-d4e2cb7af5bc | textbox | Ryder Plumbing Staff Onsite (list names)
| checkpoint | Traffic Control
4282f31f-2616-5e84-98b3-dea740c5204f | textbox | Number of Controllers
6af20406-29c6-5820-bfd8-6f6b179ae183 | textbox | Time on Site
e8432972-8cd3-58b5-b2a0-6a8e47ff03a3 | textbox | Time off site
c6b2d807-6078-5bf0-a611-6fa603d8b934 | textbox | Deliveries / Sub Contractors:
| checkpoint | Works Completed
| checkpoint | Incomplete Works (add details in comments)
| signoff | Signed off by Ryder Plumbing
| checklist | Levels Suspended Drainage Checklist |  | Levels Suspended Drainage Checklist | 1c2da905-63ee-4136-ad14-06f946b31db8
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes female/male/DDA bathroom, kitchen
| checkpoint | Pipework installation
| checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
| checkpoint | Smoke seal penetrations
| checkpoint | Fire collars installed if necessary
| checklist | Basement Pumps/Tanks/Booster Pump Checklist |  | Basement Pumps/Tanks/Booster Pump Checklist | 1e491314-6739-4b38-bf4f-eaf522eb4c69
| checkpoint | Domestic cold water booster pump
| checkpoint | Domestic cold water break tank
| checkpoint | Rainwater pump set
| checkpoint | Rainwater tanks
| checkpoint | Sewer pump board installed
| checkpoint | Stormwater pump board installed
| checkpoint | Suspended Pollutant trap
| checkpoint | Diversion valve
| checkpoint | OSD tank (if applicable)
| checkpoint | Smoke sealed
| checkpoint | Tested
| checkpoint | Fire rated if necessary
| checkpoint | Water meter assembly
| checklist | Rough In Checklist |  | Rough In Checklist | 22a0d6cf-d683-4a7a-a9d1-bf290542f086
| checkpoint | For apartments includes bathroom, bathroom ensuite, kitchen, laundry
| checkpoint | For other areas includes female/male/DDA bathroom, kitchen
| checkpoint | High Level Rough In
| checkpoint | Wall Set Out
| checkpoint | Wall Rough In
| checkpoint | Waste Rollovers
| checkpoint | Gas
| checkpoint | Test Water
| checkpoint | Fire collar installed if necessary
| checklist | Corridor Checklist |  | Corridor Checklist | 2ad0e45b-0fbc-4446-8394-1769ac744510
| checkpoint | Rainwater
| checkpoint | Hot Water
| checkpoint | Hot Water Lagged
| checkpoint | Cold Water
| checkpoint | Test Hot Water
| checkpoint | Test Cold Water
| checkpoint | Test Rain Water
| checkpoint | Fire Caulking (Corridor to Apt)
| checkpoint | Cold Water Meter Manifold
| checklist | In-Ground Stormwater Drainage Checklist |  | In-Ground Stormwater Drainage Checklist | 40454d91-cbee-4312-ad5b-6fb0adcebe0f
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
| checkpoint | Pipework installation
| checkpoint | Pipework checked for correct invert levels & gradients
| checkpoint | Pits checked for correct invert levels & finished floor levels
| checkpoint | Ensure correct locations of pits.
| checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
| checklist | Add Day Docket Checklist |  | Day Docket | 4725fafb-5f3d-4272-af27-fa28fb48bd9d
| checkpoint | Details added below
a25b7203-bd63-5649-adea-f94d06f4da33 | textbox | Work completed
5a6f1be8-42f4-5815-b37b-bb26c27a99ac | textbox | Materials required
a8842232-086e-5b1a-aac6-351f715bf1d4 | textbox | Staff
ff550cec-854e-5e87-81b0-037a1768d062 | dropdown | Hours | 1, 2, 3, 4, 5, 6, 7, 8
| checkpoint | Signed off by Ryder Plumbing
| signoff | Signed off by Builder
| checklist | Vents Checklist |  | Vents Checklist | 5813ca7f-4f70-4c16-b1b4-d04c134629dc
| checkpoint | Vents installed
| checkpoint | Smoke sealed
| checkpoint | Fire rated
| checkpoint | Tested
| checklist | Hot Water Unit Checklist |  | Hot Water Unit Checklist | 66630b25-5c18-4b35-be33-01ab6f267a42
| checkpoint | Hot water unit installation
| checkpoint | Copper works installation
| checkpoint | Smoke sealed
| checkpoint | Fire rated
| checkpoint | Tested
| checklist | Apartment Fit Off Checklist |  | Apartment Fit Off Checklist | 6772ce3b-7105-49c2-9c21-779d5841ee66
| section | Laundry Fit Off
| checkpoint | Laundry Trough
| checkpoint | Laundry Trough Mixer
| checkpoint | Laundry Trough Mini Stops
| checkpoint | Laundry Trough Waste
| checkpoint | Floor wastes - cleared of blockages
| section | Kitchen Fit Off
| checkpoint | Kitchen Mini Stops
| checkpoint | Kitchen Sink Waste
| checkpoint | Kitchen Sink Mixer
| checkpoint | Kitchen Dishwasher
| checkpoint | Kitchen Cooktop
| section | Bathroom Fit Off
| checkpoint | Bathroom Shower Mixer
| checkpoint | Bathroom Shower Rail/Rose
| checkpoint | Bathroom Basin
| checkpoint | Bathroom Basin Mixer
| checkpoint | Bathroom Bottle Trap
| checkpoint | Bathroom Toilet
| checkpoint | Bathroom Urinal
| checkpoint | Floor wastes - cleared of blockages
| section | Balcony Fit Off
| checkpoint | Balcony Tap
| checkpoint | Gas Point
| checklist | Other Areas Fit Off Checklist |  | Other Areas Fit Off Checklist | 847601df-ea86-40ab-aee2-73d6afc42ac6
| section | Kitchen/Butler's Pantry Fit Off
| checkpoint | Kitchen Mini Stops
| checkpoint | Kitchen Sink Waste
| checkpoint | Kitchen Sink Mixer
| checkpoint | Kitchen Dishwasher
| checkpoint | Kitchen Cooktop
| section | Female Bathroom Fit Off
| checkpoint | Bathroom Shower Mixer
| checkpoint | Bathroom Shower Rail/Rose
| checkpoint | Bathroom Basin
| checkpoint | Bathroom Basin Mixer
| checkpoint | Bathroom Bottle Trap
| checkpoint | Bathroom Toilet
| checkpoint | Bathroom Urinal
| checkpoint | Floor wastes - cleared of blockages
| section | Male Bathroom Fit Off
| checkpoint | Bathroom Shower Mixer
| checkpoint | Bathroom Shower Rail/Rose
| checkpoint | Bathroom Basin
| checkpoint | Bathroom Basin Mixer
| checkpoint | Bathroom Bottle Trap
| checkpoint | Bathroom Toilet
| checkpoint | Bathroom Urinal
| checkpoint | Floor wastes - cleared of blockages
| section | DDA Bathroom Fit Off
| checkpoint | Bathroom Shower Mixer
| checkpoint | Bathroom Shower Rail/Rose
| checkpoint | Bathroom Basin
| checkpoint | Bathroom Basin Mixer
| checkpoint | Bathroom Bottle Trap
| checkpoint | Bathroom Toilet
| checkpoint | Bathroom Urinal
| checkpoint | Floor wastes - cleared of blockages
| checklist | In-Ground Sewer Drainage Checklist |  | In-Ground Sewer Drainage Checklist | 848f7650-a788-4f0f-8ac8-749f87107a8c
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
| checkpoint | Pipework installation
| checkpoint | Pipework checked for correct invert levels & gradients
| checkpoint | Book inspection with VBA for in-ground drainage.
| checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
| checkpoint | Test sewer
| checklist | Suspended Stormwater Drainage Checklist |  | Suspended Stormwater Drainage Checklist | 8f5804fe-57ca-4084-8542-065dbb66f1d5
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
| checkpoint | Pipework installation
| checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
| checkpoint | Smoke seal penetrations
| checkpoint | Fire collars installed if necessary
| checklist | Penetrations Checklist |  | Penetrations Checklist | 9d1e8948-66a6-45dc-b348-a1fb358606a6
| checkpoint | All works to be set our as per approved IFC drawings.
| checkpoint | Fire collar installation
| checkpoint | Cast in drains
| checkpoint | Photos of collar end labelling referencing fire matrix if required
| checklist | Other Areas Suspended Drainage Checklist |  | Other Areas Suspended Drainage Checklist | ae05846c-936b-4e71-9df7-6a7d7cfd41a3
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing.
| checkpoint | Pipework installation
| checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
| checkpoint | Smoke seal penetrations
| checkpoint | Fire collars installed if necessary
| checklist | In-Ground Pits/Pumps/Tanks Checklist |  | In-Ground Pits/Pumps/Tanks Checklist | c06f5bdc-4f51-414a-a113-1b2f58b3d81e
| checkpoint | Sewer pump well
| checkpoint | Storwater pump well
| checkpoint | Stormwater pits
| checkpoint | Grease interceptor trap
| checkpoint | Conduits rain to IFC location
| checkpoint | Torpedo tanks
| checkpoint | Stormwater detention system
| checklist | Storm Water Grates Checklist |  | Storm Water Grates Checklist | d7d5efc1-2620-4394-83de-eba01609b1a6
| checkpoint | Grates installed
| checkpoint | Smoke sealed
| checkpoint | Fire rated
| checkpoint | Tested
| checklist | Apartment Suspended Drainage Checklist |  | Apartment Suspended Drainage Checklist | ebe553c3-7d49-4989-b1fe-297fd94aa4ec
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes bathroom, bathroom ensuite, kitchen, laundry
| checkpoint | Pipework installation
| checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
| checkpoint | Smoke seal penetrations
| checkpoint | Fire collars installed if necessary
| checklist | Gas Works Checklist |  | Gas Works Checklist | ec1524a3-de3a-4b73-957d-21bfcf39d445
| checkpoint | Gas Meter set up (Ground floor only)
| checkpoint | Gas Riser room pipe installation
| checkpoint | Pipe anchor/slide guides
| checkpoint | Smoke sealed
| checkpoint | Gas tested
| checkpoint | Fire rated
| checklist | Big Ticket Items (In Ground) |  | Big Ticket Items (In Ground) | f0d17c58-45b7-4e91-93d6-13939839f4f7
| checkpoint | Sewer pump well
| checkpoint | Storwater pump well
| checkpoint | Stormwater pits
| checkpoint | Grease interceptor trap
| checkpoint | Conduits rain to IFC location
| checkpoint | Torpedo tanks
| checkpoint | Stormwater detention system
| checkpoint | LPOD
| checkpoint | Water tap in
| checklist | Commissioning Checklist |  | Commissioning Checklist | ff1b7cc5-0b54-4945-b10e-99fe1389354e
| checkpoint | Includes female/male/DDA bathroom, kitchen
| checkpoint | Test Hot Water Temperature
| checkpoint | Test Waste for leaks
| checkpoint | Run Cycle on Dishwasher