## Resources
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Fit Off Checklist |  | Fit Off | 0995f908-51ea-4d5d-a670-2bf7a9714e67
| section | Laundry Fit Off
| checkpoint | Laundry Trough
| checkpoint | Laundry Trough Mixer
| checkpoint | Laundry Trough Mini Stops
| checkpoint | Laundry Trough Waste
| checkpoint | Hot Water Unit
| checkpoint | Floor wastes - cleared of blockages
| section | Kitchen Fit Off
| checkpoint | Kitchen Mini Stops
| checkpoint | Kitchen Sink Waste
| checkpoint | Kitchen Sink Mixer
| checkpoint | Kitchen Dishwasher
| checkpoint | Balcony Tap
| section | Bathroom Fit Off
| checkpoint | Bathroom Shower Mixer
| checkpoint | Bathroom Shower Rail/Rose
| checkpoint | Bathroom Basin
| checkpoint | Bathroom Basin Mixer
| checkpoint | Bathroom Bottle Trap
| checkpoint | Bathroom Toilet
| checkpoint | Floor wastes - cleared of blockages
| checklist | Add Daily Site Diary Checklist |  | Daily Site Diary | 0f753d99-d7b7-44ae-b80a-ee2acf9e415f
| checkpoint | Attach relevant photos and documents
a0aa1e95-7be9-5273-93ad-0a4cdb5a0105 | textbox | Time on Site
6e01c180-492e-5bc1-846e-44c9ec3ba0fd | textbox | Time off site
cc06bdd5-5b85-5a28-9e44-ff5e9b91bfc9 | textbox | Vehicles
fb855924-f052-5943-a728-9d0aa7209e7e | textbox | Plant
3d411984-77f6-511c-bd18-d4e2cb7af5bc | textbox | Ryder Plumbing Staff Onsite (list names)
| checkpoint | Traffic Control
4282f31f-2616-5e84-98b3-dea740c5204f | textbox | Number of Controllers
6af20406-29c6-5820-bfd8-6f6b179ae183 | textbox | Time on Site
e8432972-8cd3-58b5-b2a0-6a8e47ff03a3 | textbox | Time off site
c6b2d807-6078-5bf0-a611-6fa603d8b934 | textbox | Deliveries / Sub Contractors:
| checkpoint | Works Completed
| checkpoint | Incomplete Works (add details in comments)
| signoff | Signed off by Ryder Plumbing
| checklist | Add Toolbox Meeting Checklist |  | Toolbox Meeting Checklist | 0fcdf965-1236-4f14-b8f9-33d6e0f7a0a3
| section | Attendance
| checkpoint | Attendance - list of attendees added below
| checkpoint | Apologies - list of non-attendees added below
| section | Minutes
| checkpoint | Actions from last meeting
| checkpoint | Administration
| checkpoint | HR
da3a299b-581e-5f36-a3cf-d8f9223a0c65 | note | e.g - Site recognition, any HR issues?
| checkpoint | Safety: (including hazards / near misses / controls / site specific)
| checkpoint | Environment: (including hazards / controls / incidents / impacts)
| checkpoint | Training
b868c5bb-50e1-5063-a5e0-2fa0a5f65034 | note | Competency Assessment Guides (Apprentices) if applicable – are they up to date?
| checkpoint | Plant & Equipment
| checkpoint | Issues & Customer Feedback
| checkpoint | Client/Job specific information:
| checkpoint | Memo’s and other office correspondence
| section | Document Review
| checkpoint | Document uploaded below if applicable
| section | New Business / Other
| checkpoint | Any new business / other comments added below
| section | Meeting Closure
| checkpoint | Meeting Closed
2ef67206-1fe4-5d23-a00f-bdc153a549ed | textbox | Meeting Closed time
c7c8d5fe-4fbb-5046-a920-d85ac8085671 | textbox | Date for next meeting
6b89a8bf-6544-5122-b3a5-9e6cb2cccd05 | textbox | Minutes taken by (Name)
| checklist | Suspended Sewer Drainage Checklist |  | Suspended Sewer Drainage | 1d756ec5-bc83-4db2-959a-dc27127148da
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
| checkpoint | Pipework installation
| checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
| checkpoint | Smoke seal penetrations
| checkpoint | Fire collars installed if necessary
| checkpoint | Test sewer
| checklist | In-Ground Pits/Pumps/Tanks Checklist |  | Pits/Pumps/Tanks | 1d936c12-bbab-4acc-97f0-98b1e16a3830
| checkpoint | Sewer pump well
| checkpoint | Storwater pump well
| checkpoint | Stormwater pits
| checkpoint | Grease interceptor trap
| checkpoint | Conduits rain to IFC location
| checkpoint | Torpedo tanks
| checkpoint | Stormwater detention system
| checklist | Corridor Checklist |  | Corridor | 233e6f4a-fbb4-41e2-a3e6-50a423da7001
| checkpoint | Rainwater
| checkpoint | Hot Water
| checkpoint | Hot Water Lagged
| checkpoint | Cold Water
| checkpoint | Test Hot Water
| checkpoint | Test Cold Water
| checkpoint | Test Rain Water
| checkpoint | Fire Caulking (Corridor to Apt)
| checkpoint | Cold Water Meter Manifold
| checklist | Commissioning Checklist |  | Commissioning | 2aaaa2ee-138d-4546-ad68-2daa5c20e37e
| checkpoint | Includes bathroom, bathroom ensuite, kitchen, laundry
| checkpoint | Test Hot Water Temperature
| checkpoint | Test Waste for leaks
| checkpoint | Run Cycle on Dishwasher
| checklist | DDA Bathroom Fit Off Checklist |  | DDA Bathroom Fit Off | 6364b91c-9105-4ef4-b4ee-7a5e36372635
| checkpoint | Bathroom Shower Mixer
| checkpoint | Bathroom Shower Rail/Rose
| checkpoint | Bathroom Basin
| checkpoint | Bathroom Basin Mixer
| checkpoint | Bathroom Bottle Trap
| checkpoint | Bathroom Toilet
| checkpoint | Bathroom Urinal
| checkpoint | Floor wastes - cleared of blockages
| checklist | Add Day Docket Checklist |  | Day Docket | 80c70592-5318-423b-9d8d-967223262727
| checkpoint | Details added below
b5663d29-d1b1-5b24-83c1-50b1c63a4dfa | textbox | Work completed
e617efdf-c53d-5511-8408-6ce36b7b91a2 | textbox | Materials required
1beed7bc-799c-5440-859e-750c25cb406d | textbox | Staff
dd59606a-8ffb-5f36-b44d-8668a6a78495 | dropdown | Hours | 1, 2, 3, 4, 5, 6, 7, 8
| checkpoint | Signed off by Ryder Plumbing
| signoff | Signed off by Builder
| checklist | Penetrations Checklist |  | Penetrations | 83725e53-b124-4575-80fd-e03edc5b58e5
| checkpoint | All works to be set our as per approved IFC drawings.
| checkpoint | Fire collar installation
| checkpoint | Cast in drains
| checkpoint | Photos of collar end labelling referencing fire matrix if required
| checklist | Apartment Suspended Drainage Checklist |  | Apartment Suspended Drainage | ba184bea-400d-46cb-851a-d5a440075a3f
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing. Includes bathroom, bathroom ensuite, kitchen, laundry
| checkpoint | Pipework installation
| checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
| checkpoint | Smoke seal penetrations
| checkpoint | Fire collars installed if necessary
| checklist | Big Ticket Items (In Ground) |  | Big Ticket Items (In Ground) | ba54f4b9-10ea-489c-b08c-86c4c1d4d855
| checkpoint | Sewer pump well
| checkpoint | Storwater pump well
| checkpoint | Stormwater pits
| checkpoint | Grease interceptor trap
| checkpoint | Conduits rain to IFC location
| checkpoint | Torpedo tanks
| checkpoint | Stormwater detention system
| checkpoint | LPOD
| checkpoint | Water tap in
| checklist | Rough In Checklist |  | Rough In | c51c286d-2dcb-4099-9102-2992c4f0a52c
| checkpoint | For apartments includes bathroom, bathroom ensuite, kitchen, laundry
| checkpoint | High Level Rough In
| checkpoint | Wall Set Out
| checkpoint | Wall Rough In
| checkpoint | Waste Rollovers
| checkpoint | Test Water
| checkpoint | Fire collar installed if necessary
| checklist | Pipework Checklist |  | Pipework Checklist | c88260b3-bc8f-4ccd-88c0-c3950c02937a
| checkpoint | Pipework, material and fitting installed as per approved IFC drawing
| checkpoint | Pipework installation
| checkpoint | Pipework checked for correct crimping/welded joins
| checkpoint | Tested
| checklist | Suspended Copper Works Checklist |  | Suspended Copper Works | cda0a613-c9a6-46d0-94ea-bf6f941179ef
| checkpoint | Pipework installed - domestic hot/cold/rain water
| checkpoint | Smoke seal penetrations
| checkpoint | Fire rated if necessary
| checkpoint | Tested
| checklist | Suspended Stormwater Drainage Checklist |  | Suspended Stormwater Drainage | db846d74-294b-4bd2-8d46-af5658ff4cb4
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
| checkpoint | Pipework installation
| checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
| checkpoint | Smoke seal penetrations
| checkpoint | Fire collars installed if necessary
| checklist | Other Areas Suspended Drainage Checklist |  | Other Areas Suspended Drainage | e33e393a-2e27-433e-8c8e-a29709ba4379
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing.
| checkpoint | Pipework installation
| checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
| checkpoint | Smoke seal penetrations
| checkpoint | Fire collars installed if necessary
| checklist | In-Ground Sewer Drainage Checklist |  | In-Ground Sewer Drainage | eda00818-4bd4-49e8-adbf-d03b7d25c79e
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
| checkpoint | Pipework installation
| checkpoint | Pipework checked for correct invert levels & gradients
| checkpoint | Book inspection with VBA for in-ground drainage.
| checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
| checkpoint | Test sewer
| checklist | In-Ground Stormwater Drainage Checklist |  | In-Ground Stormwater Drainage | f970fbfd-dca4-46c8-843c-cd1be20ddae6
| checkpoint | Pipework, material and fittings installed as per approved IFC Drawing
| checkpoint | Pipework installation
| checkpoint | Pipework checked for correct invert levels & gradients
| checkpoint | Pits checked for correct invert levels & finished floor levels
| checkpoint | Ensure correct locations of pits.
| checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
| checklist | Above Ground Pits/Pumps/Tanks Checklist |  | Above Ground Pits/Pumps/Tanks Checklist | fcd1151f-86c9-48a0-a4f4-225eea5421c6
| checkpoint | Diversion valve
| checkpoint | Rainwater pump set
| checkpoint | Rainwater tanks
| checkpoint | Sewer pump installed
| checkpoint | Sewer control panel
| checkpoint | Stormwater pump installed
| checkpoint | Stormwater control panel
| checkpoint | Grease interceptor trap
| checkpoint | Hot water unit installation
| checkpoint | Main Meter assembly
| checkpoint | Main Gas Meter cupboard