## Resources
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | COM Commission Hot Water Unit |  | COM Commission Hot Water Unit | 06f7685e-41b1-4cf1-8bce-98b68864d2c0
| section | Details:
| checkpoint | Commission Hot Water Unit checked off as below:
14b2d6be-5080-51a1-874d-ee4483f09cc1 | dropdown | Type: | Domestic Electric Storage,Domestic Gas Storage,Domestic Heat Pump,Domestic Gas Instantaneous
5fb40405-d6a3-5f6b-b08d-bdefb0a41ebe | dropdown | Solar Preheat: | Yes,No
22c8f840-565e-55bd-b378-ede429164591 | dropdown | Location: | Indoors,Outdoors,Roof Mounted
7891720a-a648-5e85-9cdd-e004752f7c14 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 &/or AS/NZS-5601 | YES,NO,N/A
7e3855af-0d25-5c91-8930-8e4e8955e0bf | button | Installation complies with current drawings & specifications | YES,NO,N/A
1d60e3e6-e58d-5073-8dab-12294e8968e2 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
7a530a63-6fd3-5e72-9419-3b8da72c7bef | button | Check regulatory clearances & distances from building openings & air intakes (Gas HW Plants) | YES,NO,N/A
30bd4c64-de97-5119-ab6c-6e8d07c9ba4e | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
36bff062-1bba-5957-8861-3f784f561a36 | button | Check all fixing/hold down points | YES,NO,N/A
db992fe6-1c6d-5007-80cf-0fe68746f4c8 | button | Check isolation valves are fully open & non-return valves flow direction | YES,NO,N/A
5ec71b5c-bf2b-5b97-bad4-89ce79599d9b | button | Check water filters are clean | YES,NO,N/A
5099274f-a2de-547b-88eb-f97585ec2187 | button | Check gas valves & connections (if applicable) | YES,NO,N/A
00f9d503-0ef9-5d10-b27d-ac43430a1648 | button | Check flue system & operation (if applicable) | YES,NO,N/A
99a8ad43-47e2-5a1f-a3dc-a594f7a03377 | button | Check hot water delivery temperature | YES,NO,N/A
a51d7a9f-6924-50a1-8dbf-1e763a67c86d | button | Check solar panels & mounting brackets | YES,NO,N/A
2c31fb59-b341-56c9-8434-b848978d4511 | button | Check solar connecting pipework & fittings | YES,NO,N/A
c7da5e89-3295-5ac8-be56-94a3328d07b8 | button | Check solar circulation pump | YES,NO,N/A
| checklist | FO Fit-off Washing Machine Stops |  | FO Fit-off Washing Machine Stops | 084ede22-609c-47d1-8314-3c1f419b77fc
| section | Details:
| checkpoint | Fit-off Washing Machine Stops checked off as below:
0dfc6b34-8d67-5370-a99c-7efcb4ec09d9 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
d7464d01-30d5-5949-aca2-d4c291625469 | button | Installation complies with current drawings & specifications | YES,NO,N/A
2f2f5bc1-240b-5c8b-beff-91219174c6f5 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
08c69f11-ca9f-5383-bc7a-45a70fc4d6ea | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
7d871fa4-1bbb-537c-b84e-d5577009d8d0 | button | Check level & alignment | YES,NO,N/A
09a5dbf2-2579-5c37-bb9c-1b9d3262fa09 | button | Check stops hose connections are capped off | YES,NO,N/A
| checklist | FO Fit-off Wash Basin & Tapware |  | FO Fit-off Wash Basin & Tapware | 105dca39-a556-4a3e-bfa2-98612ffba90c
| section | Details:
| checkpoint | Fit-off Wash Basin & Tapware checked off as below:
e886af90-b793-54d1-9ad3-8f0f05eb8088 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
20e1b460-e447-50a0-9dbe-2d5c87480a3c | button | Installation complies with current drawings & specifications | YES,NO,N/A
3a65d7b9-bc80-5f11-870b-3903307fff18 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
187cc904-2914-5f01-8e8b-d60f97dfa50d | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
1eb568a9-82ae-5567-83e1-0e927dab6728 | button | Check fixing points are secure | YES,NO,N/A
45515bd0-2548-5b43-9fd0-d5d9ce0b3f94 | button | Check level & alignment | YES,NO,N/A
0e79f51c-46a8-5a7a-9216-55a24b08cc51 | button | Check mini stops & cover plates | YES,NO,N/A
787031c9-4d6e-5f53-b7f3-4cbcb1b5aad8 | button | Check flexible connections are not twisted or kinked | YES,NO,N/A
691e0425-0de1-539e-808e-6ba24fa14d86 | button | Check waste & trap connections | YES,NO,N/A
dd9cabea-9357-5948-99e5-2b947f5b96fe | button | Check all functions, controls & remote sensors for correct operation | YES,NO,N/A
2da715d2-cbda-5da9-894e-fa5f8a7fff90 | button | Check trap is clear of debris | YES,NO,N/A
2d76af51-dfc5-5aff-85e4-d6cac952f2d1 | button | Check caulking | YES,NO,N/A
| checklist | COM Commission Gas Appliance |  | COM Commission Gas Appliance | 17d0ab40-08fd-4188-b8b7-1ffd7a5d329b
| section | Details:
| checkpoint | Commission Gas Appliance checked off as below:
02814ae3-1e8f-5bea-be54-c1af03fd7f48 | textbox | Location:
06f06ad3-5cbc-5422-820b-36a2fced76ad | button | Installation complies with latest revision of AS/NZS-5601 | YES,NO,N/A
f0b9eab8-6378-50d5-9663-d794a7a68f46 | button | Installation complies with current drawings & specifications | YES,NO,N/A
27b2507a-186a-5f15-80a8-cba358e35bf8 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
c2c2de6c-32f3-5908-8aae-9a5e1571d1f5 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
d0325010-5b36-54e6-a7b1-6c2ee0498b20 | button | Check fixing points are secure | YES,NO,N/A
2ac3b28f-1508-554d-8141-57c1aa28b6c1 | button | Check level & alignment is correct | YES,NO,N/A
03d2590b-6402-50b7-88ae-88041505ca4d | button | Check surrounding wall material is fire rated | YES,NO,N/A
6d416cf7-25bc-5f1e-9984-b679e7e401ac | button | Check distance from cook-top to range hood complies with manufacturer specification | YES,NO,N/A
b0f2c03b-6f4a-5a61-bab7-b3731d14c608 | button | Check surrounding walls to closest burner distance complies with manufacturer specification | YES,NO,N/A
99954bdd-603f-51e5-965e-ea2fb24c52bc | button | Check gas service has been purged | YES,NO,N/A
f20fb233-b0b2-5cd0-8650-bc0181883ca3 | button | Check flame ignition device | YES,NO,N/A
73c40e0f-a8df-5a33-a371-7bdd5d02b5e7 | button | Check all burners for blockages, etc | YES,NO,N/A
225b7d02-083a-5367-9824-5ca2a31f1088 | button | Check all burners for correct flame operation, height, colour, etc | YES,NO,N/A
6f962439-05cd-5cb8-bc74-3258df380e06 | button | Check flame failure device | YES,NO,N/A
a7a7d58a-6cb3-5ed8-a8b1-f7b6e12b474f | button | Check all functions & controls for correct operation | YES,NO,N/A
| checklist | FO Fit-off Toilet & Cistern |  | FO Fit-off Toilet & Cistern | 193c1712-38e2-44e7-882f-dbf632f26529
| section | Details:
| checkpoint | Fit-off Toilet & Cistern checked off as below:
5ceb6c72-f492-53e0-bed7-ae995c396c59 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
4fbf39c6-53d6-5eaf-85f8-986aebf464ba | button | Installation complies with current drawings & specifications | YES,NO,N/A
dfce44ad-d40a-5ebe-84d8-cac4a2176c0e | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
3fcd8020-ddec-5208-b781-a1ced79b55a3 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
4889530e-2547-5e3e-8969-bd2efb5af57d | button | Check fixing points are secure | YES,NO,N/A
a274f0af-057d-54f6-9be4-f20e37cd15db | button | Check level & alignment | YES,NO,N/A
6ce742e0-eda4-54a8-b558-280dde4e88a5 | button | Check mini stops & cover plates | YES,NO,N/A
a31482ac-cb7c-57a4-b3f1-af779f7c1b7c | button | Check flexible connections are not twisted or kinked | YES,NO,N/A
871ff5b3-c9b8-5b55-a62a-79180a8def78 | button | Check all functions, controls & remote sensors for correct operation | YES,NO,N/A
8c0ddc8d-a09f-58f4-97ad-c566f31399f4 | button | Check trap is clear of debris | YES,NO,N/A
cc48fc6e-5193-5485-ae6e-ca03f6143841 | button | Check caulking | YES,NO,N/A
| checklist | FO Fit-off Laundry Trough & Tapware |  | FO Fit-off Laundry Trough & Tapware | 19470203-a376-4069-ac08-d721379d53ed
| section | Details:
| checkpoint | Fit-off Laundry Trough & Tapware checked off as below:
002eb55e-acc7-5e79-bcc1-28dc1fbc7400 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
a8290a8d-5dab-51d0-8ed4-496d4aabe305 | button | Installation complies with current drawings & specifications | YES,NO,N/A
bb4b980d-7bab-5c81-923c-8c4ea8c80492 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
e5724105-5c0e-54dd-b5db-b2b68db2cc57 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
11235fc4-f29a-51d9-9b51-16a92a2ec434 | button | Check fixing points are secure | YES,NO,N/A
98b63559-a29e-557c-a299-d2cb5627441e | button | Check level & alignment | YES,NO,N/A
ddd107c9-613d-5e4d-9e17-e8882467934a | button | Check mini stops & cover plates | YES,NO,N/A
5fed1b51-05e7-5f20-943e-f88a6e6d8117 | button | Check flexible connections are not twisted or kinked | YES,NO,N/A
90e0a06d-377d-540e-8e46-217718061306 | button | Check waste & water connections | YES,NO,N/A
d9f1c6ad-30aa-559f-b9e6-9604aadf1878 | button | Check stop valves for future connections are capped | YES,NO,N/A
ee231d06-2215-55b3-80c1-6eb5cae5de6b | button | Check all functions & controls for correct operation | YES,NO,N/A
07f8bf63-8924-5a90-8e93-0a4bd0279b6d | button | Check trap is clear of debris | YES,NO,N/A
a118bf6f-c52b-5a7a-a366-67d3e6d928e7 | button | Check caulking | YES,NO,N/A
| checklist | FO Fit-off Hose Tap |  | FO Fit-off Hose Tap | 2010d200-d465-4a67-9bbd-a3dda38cef86
| section | Details:
| checkpoint | Fit-off Hose Tap checked off as below:
daec3a03-fbf3-5ffc-9a60-d56bef47b950 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
e1fe4701-737c-57e2-bbce-cd445cd9a584 | button | Installation complies with current drawings & specifications | YES,NO,N/A
57fc5103-79b6-5fb2-bf8c-5e8bf8a4c7e0 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
cbcd1ae4-ff28-5322-a633-676107699b2c | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
c8f6cefe-7de1-5186-979a-a823374d60f4 | button | Check tap is securely fixed | YES,NO,N/A
eeedb8ed-16ac-59a1-97e7-a77292bc8d99 | button | Vacuum breaker fitted | YES,NO,N/A
8bd12b04-756a-5c45-8e26-49dfffd9413c | button | Check pipe colour coding | YES,NO,N/A
| checklist | DP Install Roof/Balcony Downpipes & Overflows |  | DP Install Roof/Balcony Downpipes & Overflows | 3dd88afd-4371-41ed-b6a1-f59a64224c2d
| section | Details:
| checkpoint | Install Roof/Balcony Downpipes & Overflows checked off as below:
8b8f3542-b293-59d8-8a8e-020eca98a5f9 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
4ab61d5e-316b-5b9a-9b4f-19096fcc1cc1 | button | Installation complies with current drawings & specifications | YES,NO,N/A
c1e291d4-1a8d-57f2-a99e-7373ffe2d179 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
39ba6b6e-6e3e-5014-b46e-35a2dd1880da | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
f2edf32c-11f5-596e-9168-d3f5be586ab5 | button | Check materials & joining methods | YES,NO,N/A
ac59aa32-d3a9-572c-96d5-b8c5d021f2c0 | button | Check alignments, levels, grades, etc | YES,NO,N/A
4d0e6f7b-6bea-5c20-bad7-cf442f7165b2 | button | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation | YES,NO,N/A
955fefe7-c2e9-5d07-bd32-53854637a872 | button | Check connections to roof outlets, overflows, etc | YES,NO,N/A
b577b113-bd75-531a-8944-c6eb8dc88e6b | button | Check connections to balcony outlets, overflows, etc | YES,NO,N/A
7d2ca1e8-2b8b-5615-abd0-48d194d0016d | button | Check connections to gutter sumps, rain heads, overflows, etc | YES,NO,N/A
8cb61e1d-4149-55d0-b368-7605561c15c9 | button | Check inspection openings | YES,NO,N/A
df1ae745-2251-5bd8-9313-b48088a2ea5e | button | Check pipework is clear of debris | YES,NO,N/A
f8a669a4-962e-53c5-bfdb-b8fac3099256 | button | Check open ends are sealed | YES,NO,N/A
| checklist | SD Install Sewer/Stormwater Lead-ins |  | SD Install Sewer/Stormwater Lead-ins | 3fc6dd93-1d22-44ea-8dec-e027f4791405
| section | Details:
| checkpoint | Install Sewer/Stormwater Lead-ins checked off as below:
acce12e8-78db-5acc-a59a-5286dac75ffb | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
a0d6c65f-21dd-52b1-82c4-c22c12911377 | button | Installation complies with current drawings & specifications | YES,NO,N/A
4aff51ee-3dcc-573e-a398-2fdb29c4a9a1 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
7f9a4773-9b8a-53a7-9a15-9b646b9aeab4 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
962063dd-973b-5a96-b268-fbeb09e09905 | button | Check materials & joining methods | YES,NO,N/A
c0b94f93-4220-5a01-b7e8-081720f77ec3 | button | Check alignments, levels, grades, etc | YES,NO,N/A
94dea1fe-aa41-5a05-b678-b1b977ba9d21 | button | Check trench depth, bedding, service clearances, minimum cover, etc | YES,NO,N/A
ae309268-6a9a-5748-9f38-b5da0590c00c | button | Check BT shafts, inspection shafts, etc | YES,NO,N/A
397efee1-f0ed-5701-9eeb-46619480d3bb | button | Check DG & Grate | YES,NO,N/A
0f2ce590-73df-57e9-8b6d-2d238cde00b0 | button | Check inspection openings, etc | YES,NO,N/A
40cc519c-ef95-5ae6-bae6-012494af484d | button | Check pipework & traps are clear of debris | YES,NO,N/A
bd71d76f-966b-5584-84fc-01f4825aff3f | button | Check open ends are sealed | YES,NO,N/A
3f663bb8-cccd-509b-bf16-8234670b1c50 | button | Check pipe trench marking tape | YES,NO,N/A
cbfeb8b6-6a6e-54f8-85ef-7fca1c96b394 | button | Check trench backfill & compaction | YES,NO,N/A
| checklist | COM Commission Rain Water Storage Tank & Pump |  | COM Commission Rain Water Storage Tank & Pump | 68b4fa27-64b2-4214-87c7-33a5e64df2b3
| section | Details:
| checkpoint | Commission Rain Water Storage Tank & Pump checked off as below:
cf225165-b59c-5099-9024-315a14b690b7 | textbox | Tank Capacity:
fbcee803-e113-5d08-b4ed-86fdc31b4b9a | textbox | Location/Lot Number:
549bd50c-4798-539b-be40-7feb0f05b762 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
54b2b5f2-a0c9-51c9-963a-eed832307933 | button | Installation complies with current drawings & specifications | YES,NO,N/A
f2139db7-1833-5969-8a0b-1db2180558b2 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
4913bdbc-02b6-5e4c-a449-ed3f04b2a752 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
e14baabf-321b-5c75-96e2-3cc53266360e | button | Check all fixing/hold down points | YES,NO,N/A
e43097ba-daac-50d0-abfb-85f7e42a00b0 | button | Check isolation valves are fully open & non-return valves flow direction | YES,NO,N/A
b9f7f90e-c3b5-59df-92e4-466c0864e76a | button | Check pressure pump & filters for correct operation | YES,NO,N/A
5077f3e5-f9ca-52b0-b038-6e97f38bd2d5 | button | Check downpipe connections & tank venting | YES,NO,N/A
c25ff3d7-6428-5a85-91cb-8dd6bfd1320b | button | Check mains water back-up supply | YES,NO,N/A
a445b1e7-324d-5562-a1d8-9749a2e5b076 | button | Check tank over-flows to drain | YES,NO,N/A
| checklist | COM Commission Gas Meter |  | COM Commission Gas Meter | 7ee57c73-fe9a-4343-8c45-7532913fe0bd
| section | Details:
| checkpoint | Commission Gas Meter checked off as below:
469a63c4-841b-5996-bb63-a9f4e986c568 | textbox | Serial Number:
013f9c68-7728-5e25-af95-2bf70d36d6ee | textbox | Location/Lot Number:
cf23cc8d-6072-59be-8460-c1f8ffdcf28d | dropdown | Size: | 15mm,20mm,25mm,32mm,40mm,50mm,65mm,80mm,100mm,150mm,225mm
785629db-e1f6-5a61-b710-fdee4c8c82fc | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
08f86d05-1f1c-56ca-b4ec-8d6e72be7f25 | button | Installation complies with current drawings & specifications | YES,NO,N/A
42136f83-c228-5770-8d56-fb9c4338ea41 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
29fb41cc-244f-5a87-a871-e5cbd35ca2ef | button | Check regulatory clearances & distances from building openings, air intakes, etc | YES,NO,N/A
04fa710b-d86d-5617-aea2-47cc1a7f541c | button | Check regulatory ventilation if installed indoors | YES,NO,N/A
9b4c40a5-3849-5e59-81c2-6f2d7a32483e | button | Check correct meter spacing if installed in a manifold assembly | YES,NO,N/A
9e7af284-f85c-57ca-8c61-9e01a1fabf5c | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
0bae9ccc-93c3-50eb-ab94-26ea1f54f490 | button | Check materials & joining methods | YES,NO,N/A
406cfba0-d9e3-5eee-bed0-3eed54b83889 | button | Check alignments & levels | YES,NO,N/A
556b9644-f5f5-5a03-b582-c9f9f814177b | button | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation | YES,NO,N/A
32a2f417-6391-546d-a97a-4591df1202f1 | button | Check isolation valves, pressure regulators, connections, etc | YES,NO,N/A
f0898690-5cee-5fb7-b41b-d696b53907af | button | Check analogue display can be read manually | YES,NO,N/A
| checklist | SD Install Sewer/Stormwater Drainage |  | SD Install Sewer/Stormwater Drainage | 80bc2df6-a7ea-4e3a-863b-1e8b755d5b46
| section | Details:
| checkpoint | Install Sewer/Stormwater Drainage checked off as below:
b59543c2-8f65-5b72-9497-09aafd695c85 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
e5ab5216-afdf-5f5b-ad20-ea0518646a08 | button | Installation complies with current drawings & specifications | YES,NO,N/A
b56976ec-dd99-57cd-a325-94557479571f | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
3d46bb94-fea1-55a5-a8e6-b22efde4b325 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
ecca9e56-e705-5438-b193-13a735af11af | button | Check materials & joining methods | YES,NO,N/A
35cccb4b-1576-5698-bbd1-52a9e8baad65 | button | Check alignments, levels, grades, etc | YES,NO,N/A
327ce3db-3de2-51b5-b97f-fddcb1b6f77b | button | Check trench depth, bedding, service clearances, minimum cover, etc | YES,NO,N/A
8720fea9-b4bf-57b3-a5bc-1a2d41cf5464 | button | Check BT shafts, inspection shafts, etc | YES,NO,N/A
4e0a6afb-13ff-5044-8cac-57f817c7f295 | button | Check inspection openings, etc | YES,NO,N/A
5fab7147-f702-5406-bd2f-e48c6861ba11 | button | Check pipework & traps are clear of debris | YES,NO,N/A
27ddb651-5d9a-5863-bfd6-12ca8512fb15 | button | Check open ends are sealed | YES,NO,N/A
717e7464-adfb-5cc9-88a4-7eecc1253932 | button | Check pipe trench marking tape | YES,NO,N/A
7e5756e7-21af-5092-844b-fa7b12929a35 | button | Check trench backfill & compaction | YES,NO,N/A
ec19a270-45ce-593b-9db8-17f90afc457f | button | Check pre-slab CCTV recording | YES,NO,N/A
| checklist | FO Fit-off Dishwasher |  | FO Fit-off Dishwasher | 84375133-46af-4de5-9f52-ba3f005d2fe2
| section | Details:
| checkpoint | Fit-off Dishwasher checked off as below:
ff74c6e2-f310-5ed6-8c0c-fd6fb4008c1d | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
f6426275-5bb5-5c05-9e2e-b42ff675e44e | button | Installation complies with current drawings & specifications | YES,NO,N/A
ad6c323e-2139-5636-a2b8-3ee50a38e8ff | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
1ae209ef-8571-5f69-876b-3e97b29196d5 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
54160ebe-40a9-5803-9e2e-51ac270cc395 | button | Check fixing points are secure | YES,NO,N/A
bdd9f2fb-9f96-52f2-b600-e9988e5a89f5 | button | Check level & alignment | YES,NO,N/A
c5b4c8a7-c58e-5548-92dd-96939eeafb5a | button | Check isolation valves & non-return valves | YES,NO,N/A
474c9d4f-615c-5051-a20a-9d6baeb89d17 | button | Check pressure reduction valve | YES,NO,N/A
9c2a0e7b-fd31-51a7-90f7-fb17279a9aa7 | button | Check flexible waste & water hoses are not twisted or kinked | YES,NO,N/A
08aa7bd1-4947-586d-b21d-c97aa1fe932d | button | Check flexible waste hose height under cabinet | YES,NO,N/A
6754d08e-be85-5c26-83fb-c15370b04588 | button | Check waste connection to trap | YES,NO,N/A
84248c88-e982-580f-8926-dc21aff4536f | button | Check all functions & controls for correct operation | YES,NO,N/A
| checklist | COM Commission Water Meter |  | COM Commission Water Meter | 8c8f5268-5982-4275-b8f1-437becd7a85e
| section | Details:
| checkpoint | Commission Water Meter checked off as below:
98fef1c7-14ec-53fc-bcad-7d5fa3299e4f | dropdown | Service Type: | Potable Cold Water,Potable Hot Water,Recycled Rain Water,Non-Potable Water
8b8b0b9b-96b7-5c69-9867-bf5c69f024ce | textbox | Serial Number:
4805ca5d-fa2a-52fb-a935-2d038b119c47 | textbox | Location/Lot Number:
a5927b04-43be-5360-8ee3-48b117b6e8a4 | dropdown | Size: | 20mm,25mm,32mm,40mm,50mm
bdc0bbb1-f6b3-59cf-896f-8bb79b304be0 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
1e3321c7-0ee1-5c48-aeae-6926a782c583 | button | Installation complies with current drawings & specifications | YES,NO,N/A
02c90643-de15-5186-bf49-b1582a4c5349 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
5797f206-9162-5bcc-b838-3145a4ca4adb | button | Check regulatory clearances & distances from building openings, etc | YES,NO,N/A
52d0dddc-c015-5dc0-a121-c53bcbd46439 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
d2e9b262-f270-5946-90e4-4471ef0d9084 | button | Check materials & joining methods | YES,NO,N/A
727b6b9c-ebb5-503f-9932-b788cc23f390 | button | Check alignments & levels | YES,NO,N/A
fc98d3fe-245b-5c15-ab26-21ee92a86f27 | button | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation | YES,NO,N/A
d8252b5f-b3ff-5f85-b5ce-f16a1cc202c1 | button | Check isolation valves, pressure reduction valves, water filters, connections, etc | YES,NO,N/A
| checklist | FO Fit-off Kitchen Sink & Tapware |  | FO Fit-off Kitchen Sink & Tapware | 8f3060ac-985a-4f9f-8908-e561355528ea
| section | Details:
| checkpoint | Fit-off Kitchen Sink & Tapware checked off as below:
1a94a8bb-25ba-59ad-9e84-b91383052dfc | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
09c8a3cf-3fde-53ee-a518-8c2329482e41 | button | Installation complies with current drawings & specifications | YES,NO,N/A
c085aee9-1d36-5833-b2d3-22cacce5de11 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
20b0ab71-b5e7-5d33-a477-2feaa34c7f4c | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
7b3f7e8d-bc70-5762-82a9-0c8c90f4fad9 | button | Check fixing points are secure | YES,NO,N/A
4d2bb105-a284-5e5a-ac10-869d5f7ac6d0 | button | Check level & alignment | YES,NO,N/A
ecf1dde3-3d21-5992-b609-b8fab480b844 | button | Check mini stops & cover plates | YES,NO,N/A
dd87507b-aee3-5cbf-a020-c927adb08972 | button | Check flexible connections are not twisted or kinked | YES,NO,N/A
942478c2-8b8d-59a4-bceb-e59cd0b8dc8f | button | Check waste & trap connections | YES,NO,N/A
4e07c9ed-a1d8-5a47-9164-cbfddb77ee6f | button | Check dishwasher waste & water connections | YES,NO,N/A
7063105e-6035-55a0-99fd-8f6ea1e831b9 | button | Check stop valves for future connections are capped | YES,NO,N/A
dd806d6c-b288-5014-b6ef-7deda7801dcd | button | Check all functions & controls for correct operation | YES,NO,N/A
e9e15210-b7cf-5def-9ee8-56f3bd666e15 | button | Check trap is clear of debris | YES,NO,N/A
80edd262-84c1-5dce-b27f-df1d5e178bbd | button | Check caulking | YES,NO,N/A
| checklist | TST Test Sewer/Stormwater Drainage |  | TST Test Sewer/Stormwater Drainage | 8f41446e-2690-4487-ac68-c05f7a09da70
| section | Details:
| checkpoint | Test Sewer/Stormwater Drainage checked off as below:
e3d6409e-8195-5af9-8af7-1ce048480f92 | dropdown | Service Type: | Sewer Drainage,Stormwater Drainage
1e42034a-41aa-59b2-ba0f-87002dce6514 | dropdown | Test Type: | Pressurized Air Test,Static Head Water Test
b6c084d9-4c28-54f1-96b7-182cd79fbacf | dropdown | Air Test Pressure: | 10kPa,15kPa,20kPa,25kPa,30kPa,35kPa,40kPa
31ebe496-0ca3-58b1-8cb6-2e4953322e27 | textbox | Location/Lot Number:
d229683e-ec81-51d8-af36-533c47eef174 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
6b8157e7-d61f-5109-881e-f496870fd56f | button | Installation complies with current drawings & specifications | YES,NO,N/A
e3ae4db9-efaf-5c12-a13a-f969df60936d | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
2a22182f-f5aa-56ba-a18e-41588b6aacbe | button | Testing kit & equipment have current certification | YES,NO,N/A
1a0a3463-ce2a-50ac-b1b4-fa59bf7f4b6a | button | Apply test as per latest revision of AS/NZS-3500 Part 2 (Note: Start & Finish testing photos to be taken only within this Checkpoint) | YES,NO,N/A
| checklist | WG Install Water/Gas Lead-ins |  | WG Install Water/Gas Lead-ins | a2759c9f-a7f0-46e4-8fca-f0a690b205c5
| section | Details:
| checkpoint | Install Water/Gas Lead-ins checked off as below:
d7c50c78-c319-5e76-a5bb-eaad6bf30a18 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
74c9635f-46a1-5545-a2fd-f0b8ffc99111 | button | Installation complies with current drawings & specifications | YES,NO,N/A
8b6b1904-709d-5955-b654-8f4ec72fcddf | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
ba1169e2-47f6-54e1-b3de-cab1b7429a84 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
7c75c01c-ef09-566b-8655-024dc65773b0 | button | Check materials & joining methods | YES,NO,N/A
3c51dbdc-dbaa-538b-b7a0-1df110625268 | button | Check alignments & levels | YES,NO,N/A
b70469c6-ade0-5233-ac1d-acdcb0ca6321 | button | Check trench depth, bedding, service clearances, minimum cover, etc | YES,NO,N/A
cfb14987-9436-5937-97b8-ef8453e08c05 | button | Check connection points to meters, etc | YES,NO,N/A
d86db7c8-5b07-5f74-9684-e8b9ba8ea2d4 | button | Check isolating valves, etc | YES,NO,N/A
e993d65a-5387-5593-b048-94cd99ed3ead | button | Check pipework is clear of debris | YES,NO,N/A
e5d111d8-5cb7-5d6b-8a31-0361d826c8b4 | button | Check open ends are sealed | YES,NO,N/A
c9532b39-72cf-5f55-a235-5c1881bb819a | button | Check pipe colour coding | YES,NO,N/A
56ebc432-14b4-5d07-942f-7d95fd9a67c3 | button | Check pipe trench marking tape | YES,NO,N/A
757c1daf-8202-53c2-9d00-994d61385763 | button | Check trench backfill & compaction | YES,NO,N/A
| checklist | FO Fit-off Hot Water Unit |  | FO Fit-off Hot Water Unit | a626fa3c-c0f5-40c1-8d7f-c670d2296e3b
| section | Details:
| checkpoint | Fit-off Hot Water Unit checked off as below:
e11d3334-1278-5097-b7be-2d949cdee714 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4, &/or AS/NZS-5601 | YES,NO,N/A
ca9caf46-763a-5e00-9e42-1163e21aea48 | button | Installation complies with current drawings & specifications | YES,NO,N/A
02987142-373a-571a-a1d4-2cc2042b6a55 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
48124776-5b89-5a16-a8fb-318c8d404853 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
55a7961c-76fa-55fb-905a-3714dbdf641c | button | Check materials & joining methods | YES,NO,N/A
d3a85d13-6fc7-5b4b-a80b-059f38b8d65b | button | Check level & alignment | YES,NO,N/A
9f82b576-a8ee-5571-b8cf-75957aaca083 | button | Check all pipework, isolation valves, non-return valves, pressure reduction valves, water filters & connections, etc | YES,NO,N/A
666eaa0e-a797-5ac5-bdf6-f3a1c7e59e3d | button | Check bold-down & fixing points are secure | YES,NO,N/A
ba14cd8a-e133-50ad-b987-ce9efa1b06e5 | button | Check thermal pipe lagging | YES,NO,N/A
56f7cfb4-574b-5eb0-8b21-fc02c30542c5 | button | Check PTR valve, safe tray & drainage | YES,NO,N/A
3e6f136a-9187-5171-a88d-30c2b13eb0d8 | button | Check flexible connections are not twisted or kinked | YES,NO,N/A
9f01df94-be67-5d90-b5ab-39654d467c2d | button | Check solar panels & mounting brackets | YES,NO,N/A
0290a059-d423-5cfd-9f7d-fe7ae8cba839 | button | Check solar connecting pipework & fittings | YES,NO,N/A
fb176256-fd72-533b-9e4b-cf47358e9591 | button | Check solar circulation pump | YES,NO,N/A
307c734c-69be-5d03-8ab7-9e58763fcdce | button | Check gas valves, connections, fittings, etc (if applicable) | YES,NO,N/A
96e34ab5-bf6f-53ac-85c0-79377d7b0b54 | button | Check flue system (if applicable) | YES,NO,N/A
| checklist | COM Commission Backflow Prevention Device |  | COM Commission Backflow Prevention Device | ac5d4d4f-0675-4516-a1f2-f3afd1ef2558
| section | Details:
| checkpoint | Commission Backflow Prevention Device checked off as below:
69c808dc-5f67-5220-af8d-ad0d94d88da4 | dropdown | Valve Type: | Reduced Pressure Zone Device,Double Check Valve,Single Check Valve
2db52912-fad3-556b-999a-659488e06850 | dropdown | Hazard Type: | High Hazard,Medium Hazard,Low Hazard
11f0a671-f59e-5307-b295-e7ca65616756 | textbox | Serial Number:
c58074ea-533d-5222-871d-c5fcf6424b64 | textbox | Location/Lot Number:
fca6615b-5ee2-5d56-84cd-c4a833d0f291 | dropdown | Size: | 20mm,25mm,32mm,40mm,50mm
b85f6048-ebea-5ffb-9495-e113c435d783 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
2fd8a33c-aa86-5421-91bc-680a2ecae59d | button | Installation complies with current drawings & specifications | YES,NO,N/A
9b27c7af-36cd-5dbd-b8b2-6ffc2445ed6c | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
2416d6d2-05b6-5354-970d-dcde475478b7 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
140c83d9-4a03-5ced-96d9-ac1bd4e2309c | button | Check only licenced persons to commission testable backflow devices | YES,NO,N/A
| checklist | Add New Task |  | Add New Task | b36a7c04-6349-499f-b232-3449c3dcf56c
| section | Details:
| checkpoint | New task checked off (Add brief description of this task. Add photos & attach any documentation)
| checklist | SD Install Sewer Stacks, Wastes & Vents |  | SD Install Sewer Stacks, Wastes & Vents | b4b14dd1-3bb0-4091-a3c6-7d09eea862a0
| section | Details:
| checkpoint | Install Sewer Stacks, Wastes & Vents checked off as below:
91706ec9-1841-51c6-a8a7-485ecbab5338 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
8909c60f-f59d-5afe-ad3b-624f79c47f3b | button | Installation complies with current drawings & specifications | YES,NO,N/A
e880a2a0-371a-571e-a2b3-e990e2ed31ed | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
462b08b0-2e72-5697-86ca-c1ce322f0d0a | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
d93a16e1-5c63-56fb-b449-30fc90bd6177 | button | Check materials & joining methods | YES,NO,N/A
13968959-2ca7-579c-933c-ef26fb25055b | button | Check alignments, levels, grades, etc | YES,NO,N/A
712053a1-01a1-5ac9-bb01-8130d60a5d55 | button | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation | YES,NO,N/A
951b9a05-af77-516c-a41f-6c15dc3f6bb3 | button | Check expansion joints and anchor points | YES,NO,N/A
c0cff8e2-e1f9-5fa6-8270-8d92082bd0ae | button | Check in-wall fixture mounting brackets & concealed cisterns | YES,NO,N/A
b0fe5a39-aeba-568f-a11c-d4fd78fab2bc | button | Check in-wall waste pipes & vents | YES,NO,N/A
2527e039-67dd-5e18-ae74-a5464e91d8db | button | Check inspection openings | YES,NO,N/A
85c9b18a-4677-5d99-87fe-023d8f9241a1 | button | Check pipework & traps are clear of debris | YES,NO,N/A
72768b2e-7ddd-5e5d-92da-88007ffe134c | button | Check open ends are sealed | YES,NO,N/A
a3ed1402-1c01-5190-8d13-5ce1fed79b34 | button | Check vents are run to atmosphere and weather proofing is complete | YES,NO,N/A
| checklist | WG Install Water/Gas Rough-ins |  | WG Install Water/Gas Rough-ins | b9b4f1f7-1df5-45c4-951a-fdc117662e78
| section | Details:
| checkpoint | Install Water/Gas Rough-ins checked off as below:
261f649c-c84d-56db-b8ba-3032602f9b0c | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
d87702f9-ee66-5dcd-8a08-601905e3633f | button | Installation complies with current drawings & specifications | YES,NO,N/A
0f3bf067-91e2-5352-8ec2-a7b8c7fb9145 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
5605bc99-b6e1-508c-b5d1-f54045af3d8e | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
bdb1a6de-9c56-5094-a371-a4531c683b0c | button | Check pipework can not be holed by plaster screws | YES,NO,N/A
d3c451fc-a172-57d4-bec5-71fd3c8a0214 | button | Check crimp fittings & joints | YES,NO,N/A
64fc9ab2-b60a-55a6-bae4-c114c34707f2 | button | Check for cross connections | YES,NO,N/A
623acc0e-8f67-50e6-b9f6-795ff4044b79 | button | Check alignment & levels | YES,NO,N/A
bedd76a2-5ddd-5e22-b37f-74c7fabf61b2 | button | Check materials & joining methods | YES,NO,N/A
0d288547-8a74-5e08-afc2-85690491739a | button | Check pipe clips, hangers, brackets & fixings for correct size, spacing & pipe separation | YES,NO,N/A
7f392608-ca15-571b-9802-c1c296669d7e | button | Check in-wall mixer bodies & lugged elbows | YES,NO,N/A
1674703a-1231-58e9-8127-7667b135f1a3 | button | Check in-wall fixture mounting brackets & concealed cisterns | YES,NO,N/A
2afc1e6e-ab3e-58d5-ba3b-38f0de0ecbec | button | Check fixture fit-off noggins | YES,NO,N/A
68a8141e-1a34-5aca-84ea-1163470025fe | button | Check sharp edge pipe protection | YES,NO,N/A
6292c9de-c284-5d05-900d-00bb32b0ce51 | button | Check pipe colour coding | YES,NO,N/A
| checklist | FO Fit-off Tundish |  | FO Fit-off Tundish | c6a1ed4a-d92d-4423-8b2a-fd1dcf4ce811
| section | Details:
| checkpoint | Fit-off Tundish checked off as below:
85000e61-7716-5a8d-b72e-1717a40448fc | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
fc23d6ef-e187-53c0-b0c1-9a8169a9ea86 | button | Installation complies with current drawings & specifications | YES,NO,N/A
0ea11770-6eac-5e79-bd88-31f143a51a55 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
c00ff9ed-787d-56e3-9d4e-41017710f18d | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
4607effd-7244-5985-9c80-7d0e129a0ad8 | button | Check fixing points are secure | YES,NO,N/A
be8f2779-b33a-54e3-a229-bb1683206737 | button | Check level & alignment | YES,NO,N/A
bbe3cbae-26f6-573b-b379-9d75c2d93580 | button | Check waste & trap connections | YES,NO,N/A
43f9e78b-7857-57cc-9702-dc8daf19b842 | button | Check trap is clear of debris | YES,NO,N/A
| checklist | COM Commissioning Final Handover |  | COM Commissioning Final Handover | cdbadb4e-e21c-4699-a766-cfa7d91b190c
| section | Details:
| checkpoint | Commissioning Final Handover checked off as below:
6b2a7bbb-7d84-57d6-b84d-1d3306762399 | textbox | Location/Lot Number:
fa2ea374-c292-566d-96a0-07a7d4b2a555 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 &/or AS/NZS-5601 | YES,NO,N/A
4ce5ef5e-31b3-5c6a-959f-78446fa44544 | button | Installation complies with current drawings & specifications | YES,NO,N/A
4f3af7d3-b1d8-5464-bcf6-8da0e9e4eba6 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
565eb3e2-2821-5942-8ec4-8593dd3d9c42 | button | Check for any damage or missing components | YES,NO,N/A
2421ba6c-2fe0-5532-9964-fa143d350c94 | button | Check level & alignment of all fixtures & tapware | YES,NO,N/A
7bb1f1fb-031a-574d-b9ba-c30eb53847c3 | button | Check all fixtures, tapware & components are securely fixed | YES,NO,N/A
6bc67652-3a23-53f9-95ef-34259cf972e7 | button | Check all mini-stops and valves are fully open | YES,NO,N/A
33782244-469e-52d9-b64e-ee1570440a64 | button | Check all pressure reduction & non-return valves | YES,NO,N/A
50d79e60-6743-5041-9ced-eb0980d4c844 | button | Check all flexible connections are not twisted or kinked | YES,NO,N/A
36ccb04c-2953-5cbc-b5e8-6790e7615a46 | button | Check for water for cross connections | YES,NO,N/A
c8ee5908-72b7-5bb1-b6f7-90c2ec12c128 | button | Check fixture wastes & connections | YES,NO,N/A
ddb23791-441c-5a46-8296-660d1bca3ed8 | button | Check dishwasher drain hose is looped hard-up under bench-top | YES,NO,N/A
d5b8c925-d188-5e77-b2fc-fd0a9788ad4a | button | Check pipework & all traps are clear of debris | YES,NO,N/A
db66b81d-ba04-553a-a54a-7a4ce78b9bf9 | button | Check AAV is installed hard-up under bench-top | YES,NO,N/A
e402f184-8f2a-5240-94cd-39ddea07aeec | button | Check future connection water valves are securely capped (fridge/washing machine stops) | YES,NO,N/A
c831bd73-317b-5ddd-b5d4-13ab3e5fb90d | button | Check hot water unit is functioning correctly | YES,NO,N/A
cb865f44-e5ee-563e-93b8-88dc917c8aa7 | button | Check solar collectors are fitted & securely fixed | YES,NO,N/A
d775fcd6-e0fc-5c12-bc4c-93caa82d82fa | button | Check solar circulation pump is functioning correctly | YES,NO,N/A
6b3628ea-1f6a-504e-9f63-0676efe76d58 | button | Check hot water delivery temperature | YES,NO,N/A
878425d7-498f-5646-8c9d-97568a1cadf9 | button | Check dishwasher function through short cycle | YES,NO,N/A
25a96a4e-c6e7-567d-bbd5-6d17ade37a24 | button | Check gas valves & regulators | YES,NO,N/A
8a6cbfc7-d432-5788-a2d3-61e175edcdec | button | Check gas flame stop device | YES,NO,N/A
70d046b3-9d27-5373-9f71-563f5bc77097 | button | Check all gas burner functions | YES,NO,N/A
e2fa7dca-471a-56f0-9979-e42eb36559e8 | button | Check balcony hose tap is securely fixed | YES,NO,N/A
da4f81b1-9185-576d-be98-4af4cff0fc1a | button | Check balcony floor grate is clear | YES,NO,N/A
616a460d-ea21-5151-934e-c0ddcc23e38f | button | Check all downpipes & overflows are fitted correctly | YES,NO,N/A
947bae2a-29c8-5243-9aba-68c76eb8178c | button | Check all vents are finished & weather proofed | YES,NO,N/A
8a7a81d6-abd5-5b7d-b6b5-1f4a6ea3ccf6 | button | Check all fixtures & tapware function correctly | YES,NO,N/A
cf5a741b-1893-525f-8408-b644b984182c | button | Check receipt of all Authority sign-off & acceptance documentation | YES,NO,N/A
f963b8a2-9758-5831-bab0-f8b4678f95ac | button | Check receipt of all manufacturers warranty documentation & owners manuals | YES,NO,N/A
3ed03449-f069-591d-a707-be6bd8aed27b | button | Confirm area has been left clean | YES,NO,N/A
| checklist | TST Test Water Service Pipework |  | TST Test Water Service Pipework | d4e973c8-ec95-45a3-8673-b6653944bd64
| section | Details:
| checkpoint | Test Water Service Pipework checked off as below:
34feebac-61c9-5cd3-8062-5e217a506b27 | dropdown | Service Type: | Potable Cold Water,Potable Hot Water,Recycled Rain Water,Non-Potable Water,Combined
57675006-b08c-5900-897f-7daeb8752ef6 | dropdown | Test Type: | Including Mixers, Excluding Mixers
2bb99da3-a53a-512d-b0e5-08c9afe3053a | dropdown | Test Pressure: | 500kPa,750kPa,1000kPa,1200kPa,1500kPa,1.5xMWP
129c8ca7-b4fc-5827-8c85-03bd7f4f2e58 | textbox | Location/Lot Number:
83591239-864c-50fc-8b8f-596d6f97b1c5 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
fc60d69e-e812-5629-b9f1-d79d0e5abbee | button | Installation complies with current drawings & specifications | YES,NO,N/A
80eddcd1-19c8-594a-99e4-786d345ec693 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
b90df2d5-4ea8-50da-af72-9411eb504a8e | button | Check all valves, mixers, meters, fittings, etc in the test zone are rated for the test pressure required | YES,NO,N/A
e872a53f-026f-51e5-8861-5565029afa16 | button | Testing kit & equipment have current certification | YES,NO,N/A
de48726d-ce36-5694-b44d-1630b7889b6d | button | Apply test as per latest revision of AS/NZS-3500 Part 1 (Note: Start & Finish testing photos to be taken only within this Checkpoint) | YES,NO,N/A
| checklist | TST Test Gas Services Pipework |  | TST Test Gas Services Pipework | d84d30f2-c2ee-49dc-a4b7-4fb904996d2b
| section | Details:
| checkpoint | Test Gas Services Pipework checked off as below:
9014dfc1-70bb-585c-87ab-b5aa6fb88d3a | dropdown | Test Pressure: | 7kPa,1.5 x MWP
e14f4c3e-5e88-520e-a2e6-bb1da3dc3893 | textbox | Location/Lot Number:
d42dedc7-b370-5760-b7f3-9395f53dad8b | button | Installation complies with latest revision of AS/NZS-5601 & ESV Regulations | YES,NO,N/A
0dac14dc-6502-534b-a6e1-77cfd5eb1e18 | button | Installation complies with current drawings & specifications | YES,NO,N/A
0165bdfc-2f60-59c9-9645-f4f1035498ad | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
5c160ad2-c2b5-5b2a-90d3-e6fb1b01b90f | button | Testing kit & equipment have current certification | YES,NO,N/A
56cf3593-dc5a-53c1-b636-42b0f5861455 | button | Apply test as per latest revision of AS/NZS-5601 & ESV Regulations (Note: Start & Finish testing photos to be taken only within this Checkpoint) | YES,NO,N/A
| checklist | FO Fit-off Gas Appliance |  | FO Fit-off Gas Appliance | d88c359a-8bb3-4b5d-a45f-af67f485ea8c
| section | Details:
| checkpoint | Fit-off Gas Appliance checked off as below:
28bce096-3a4b-5326-b56e-f0e3663c4de3 | button | Installation complies with latest revision of AS/NZS-5601 | YES,NO,N/A
d6dabf0b-1c8c-59c7-8dd5-b80653e9d65f | button | Installation complies with current drawings & specifications | YES,NO,N/A
6ebb3fde-b73e-5548-9383-532538d502ed | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
12f577e2-d303-5a61-b006-870e0f575c6f | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
29c3e125-6bb1-54cb-b34b-79fe9d04edcb | button | Check fixing points are secure | YES,NO,N/A
e02d21a9-2cd4-50a7-afb8-f6ecc5d81e94 | button | Check level & alignment is correct | YES,NO,N/A
8ac51942-dfb5-529a-93d0-4f712548b45f | button | Check surrounding wall material is fire rated | YES,NO,N/A
1d02d20e-c1c4-5e72-99cd-1a7e229c6eef | button | Check distance from cook-top to range hood complies with manufacturer specification | YES,NO,N/A
0fd0e186-bb8e-51b1-a53b-685954e649b8 | button | Check surrounding walls to closest burner distance complies with manufacturer specification | YES,NO,N/A
b68d19ce-9847-53bf-be06-a48bfed38641 | button | Check flexible connections are not twisted or kinked | YES,NO,N/A
5160393f-0484-5535-aa00-2ea41a2d990a | button | Check gas isolation valve & cover plate | YES,NO,N/A
5bbbd8f8-4a83-57c8-a29f-15ed2f655595 | button | Check gas pressure regulator | YES,NO,N/A
60334c11-e206-5218-9ede-c6a42efbcb00 | button | Check flame failure device | YES,NO,N/A
fb70851a-6d25-54ec-8ee2-0fa26693167d | button | Check all functions & controls for correct operation | YES,NO,N/A
| checklist | FO Fit-off Bath & Tapware |  | FO Fit-off Bath & Tapware | e9e2fab7-fb19-4ed0-8f5d-7b3ea752b90d
| section | Details:
| checkpoint | Fit-off Bath & Tapware checked off as below:
92359e74-c6ea-5d33-90f2-61b98121e39e | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
2083b6f1-f43d-5f68-8247-28944329daf2 | button | Installation complies with current drawings & specifications | YES,NO,N/A
9676a719-16b0-5d84-b5ea-0b23de661931 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
d02adf5d-2347-5754-985e-e5f4779d42b3 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
24c53831-329e-53f2-85f7-5c6a4c6b435d | button | Check bath floor bedding &/or mechanical support system | YES,NO,N/A
de5ad709-4f22-5f9f-9aeb-210932a6e933 | button | Check level & alignment | YES,NO,N/A
d2146307-16a9-5445-9489-b062713c0ef2 | button | Check wall plates, mixers & diversion valves | YES,NO,N/A
f6bf998d-6e6e-52e4-acf1-5ee2cc84e775 | button | Check outlets, wall rails & hand showers | YES,NO,N/A
5babe0a4-9560-5ac4-a25e-855ff6f9318d | button | Check spa bath pump, heater and pipework | YES,NO,N/A
8254401f-b18e-5dca-8d43-256755f5edf0 | button | Check waste & trap connections | YES,NO,N/A
d69171de-c58c-5a58-9f81-8d6c82b8ac34 | button | Check all functions & controls for correct operation | YES,NO,N/A
fd9751b1-3536-5c5b-8014-e162bf79020d | button | Check floor grate level & alignment | YES,NO,N/A
f97a4b96-a59c-5787-8959-dc20e1054563 | button | Check trap is clear of debris | YES,NO,N/A
c4d9cdbd-5b9a-5151-930f-b733e3ccf527 | button | Check caulking | YES,NO,N/A
| checklist | FO Fit-off Shower & Tapware |  | FO Fit-off Shower & Tapware | eb05e696-2ee6-48e9-99a5-812171422012
| section | Details:
| checkpoint | Fit-off Shower & Tapware checked off as below:
f3beb4e9-f8b0-5996-9291-dd2ba5a4bc98 | button | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 | YES,NO,N/A
dca9c196-053d-527e-9216-1d16fd21cf11 | button | Installation complies with current drawings & specifications | YES,NO,N/A
e38af97c-c76b-529f-843d-871f8ae7b682 | button | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions | YES,NO,N/A
500e3f46-dcfc-51c2-9ab6-1a797951a832 | button | Check all, pipework, fittings, connections, etc for damage or leaks | YES,NO,N/A
d315f48e-b9d4-5234-a804-d01256d4205f | button | Check fixing points are secure | YES,NO,N/A
f1ca0ebd-7b84-5063-b9b4-aa89299936e3 | button | Check level & alignment | YES,NO,N/A
5db00a6d-6715-5e67-9770-581895f88058 | button | Check wall plates, mixers & diversion valves | YES,NO,N/A
4dfd1448-6af0-564f-8d4e-05b4c2d1ec12 | button | Check outlets, wall rails & hand showers | YES,NO,N/A
9251c28b-8591-5312-b6f9-d042b1912978 | button | Check waste & trap connections | YES,NO,N/A
da01715c-1dfd-5486-9aee-422207813ee8 | button | Check all functions & controls for correct operation | YES,NO,N/A
203507fb-231b-514c-885a-5a0c999c036b | button | Check floor grate level & alignment | YES,NO,N/A
e3cbc322-8e6a-594f-b5ce-228555c7c371 | button | Check trap is clear of debris | YES,NO,N/A
ed9117b7-c9c8-586f-a83d-7d2f13a695ed | button | Check caulking | YES,NO,N/A