## Guardrail & Wire Rope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1101A - Te Ngarue Bridge |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Guardrail |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: B1101A |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location :Te Ngarue Bridge
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Setout & Checks
1.1 | Design Check | M | Design check locations of Poles and check for any clashes with underground services or similar | Prior to commencement | Document review | National Standard for Traffic Signal | COR, Photos | Site Engineer
1.2 | Survey Setout | W | Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred. | Prior to commencement | Survey | Consistency with latest revision of Approved Construction Drawing. | Approved Construction Drawing. | Site Engineer
1.3 | Survey Setout - Bridge | H | At transitions and on bridge deck, surveyor to mark each post position. | Prior to commencement | Survey | Section 1.8 of specification (Te Ngarue Bridge) | Approved Construction Drawing. | Site Engineer | CPS Engineer
2 | Material Compliance
2.1 | Barrier Compliance | H | All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4 | Prior to commencement | Visual inspection/ Document review | TNZ M/23:2009 | Manufacturing certificates and delivery dockets | Site Engineer | CPS Engineer
2.2 | Material Suppliers | M | All materials to be sourced from registered suppliers | Prior to commencement | Document Review | Registered suppliers | Materials register | Site Engineer
2.3 | Galvanising Repair Methodology Approval | H | Proposed galvanising repair methodology to be approved by Engineer | Prior to commencement | Document Review | Best practice | Approved / Signature | Site Engineer | CPS Engineer
2.4 | Installer Certification | W | Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers | On Procurement of installer | Written confirmation | ASHTAS operative and installer course | Attendance Certificate | Site Engineer
3 | Guardrail Installation
3.1 | Guardrail Installation Locations | W | Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | Installation Checksheet | Site Engineer
3.2 | W-Beam Guardrail Installation | M | W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | Installation Checklist | Site Engineer
3.3 | Chemset Anchors on bridge structures | H | Location for post to be scanned for rebar position. Contact Engineer if clashes | Each post | Measurement | Absence of rebar at bar location | Installation Checksheet, COR | Site Engineer | CPS Engineer
3.4 | Chemset Anchors on bridge structures | W | Treaded bar to be installed in accordance with the adhesives installation manual | Each post | Visual inspection, measurement | Comply with specification | Installation Checksheet | Site Engineer |  |  | .
3.5 | Concrete spall repairs | H | Engineer to be given opportunity to inspect cleaned off spall repair areas | Each repair | Visual inspection | Best practice | COR / Signature | Site Engineer | CPS Engineer
3.6 | Leading & Trailing End Terminal Installation | W | Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | Installation Checklist | Site Engineer
3.7 | Fit for purpose Inspection | H | Barrier to undergo fit for purpose inspection by competent person System checklists to be completed and co signed by contractor and CPS. All faults to be rectified before acceptance into network maintenance and RAMM | Prior to trafficking, | Visual inspection | Pass inspection RSHDS 4 | Confirmation from inspector | Site Engineer | CPS Engineer
4 | Post-Construction Closeout
4.1 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report with Snag List | Snag List signed by attendees | Quality Manager
4.2 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the Lot of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | Site Engineer | CPS Engineer
4.3 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the Lot of work | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Quality Manager
4.4 | Final Approvals | H | Signoffs by Project Manager, Quality Manager, CPS Manager | At the completion of the Lot of work | Document Review | Ensure all parties have signed and approved ITP | Signatures | Project Manager, Quality Manager, CPS Manager