## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - B1101A - Te Ngarue Bridge Scours - Guardrail | itp |  |  |  |  | ITP - B1101A - Te Ngarue Bridge Scours - Guardrail
section | 1 - Setout & Checks
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Design Check
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - National Standard for Traffic Signal
label | Records - COR, Photos
checkpoint | 1.2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | Records - Approved Construction Drawing.
checkpoint | 1.3 - Survey Setout - Bridge
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - At transitions and on bridge deck, surveyor to mark each post position.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Section 1.8 of specification (Te Ngarue Bridge)
label | Records - Approved Construction Drawing.
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Material Compliance
checkpoint | 2.1 - Barrier Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | Conformance Criteria - TNZ M/23:2009
label | Records - Manufacturing certificates and delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Material Suppliers
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All materials to be sourced from registered suppliers
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Registered suppliers
label | Records - Materials register
checkpoint | 2.3 - Galvanising Repair Methodology Approval
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Proposed galvanising repair methodology to be approved by Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Best practice
label | Records - Approved / Signature
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Installer Certification
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
label | Frequency - On Procurement of installer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
label | Conformance Criteria - ASHTAS operative and installer course
label | Records - Attendance Certificate
section | 3 - Guardrail Installation
checkpoint | 3.1 - Guardrail Installation Locations
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - Installation Checksheet
checkpoint | 3.2 - W-Beam Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - Installation Checklist
checkpoint | 3.3 - Chemset Anchors on bridge structures
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location for post to be scanned for rebar position. Contact Engineer if clashes
label | Frequency - Each post
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Absence of rebar at bar location
label | Records - Installation Checksheet, COR
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Chemset Anchors on bridge structures
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Treaded bar to be installed in accordance with the adhesives installation manual
label | Frequency - Each post
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Comply with specification
label | Records - Installation Checksheet
checkpoint | 3.5 - Concrete spall repairs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Engineer to be given opportunity to inspect cleaned off spall repair areas
label | Frequency - Each repair
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Best practice
label | Records - COR / Signature
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Leading & Trailing End Terminal Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - Installation Checklist
checkpoint | 3.7 - Fit for purpose Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Barrier to undergo fit for purpose inspection by competent person
label | ○ System checklists to be completed and co signed by contractor and CPS.
label | ○ All faults to be rectified before acceptance into network maintenance and RAMM
label | Frequency - Prior to trafficking,
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pass inspection RSHDS 4
label | Records - Confirmation from inspector
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Post-Construction Closeout
checkpoint | 4.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report with Snag List
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 4.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Signoffs by Project Manager, Quality Manager, CPS Manager
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all parties have signed and approved ITP
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT