## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Usage Count | Resource Id
ae2ef32b-5361-4102-b24a-4e275b1d4901 | checklist | CHECKLIST 1 |  | CHECKLIST 1 |  | 1 | 29f6163f-1a10-470c-9206-2aad468534cf
68e3499e-4ec3-4ceb-a224-7c1e41b0083a | section | Pre-Pour Checklist
6eefdc89-3e7d-4048-80d9-f15ef1ebd19e | checkpoint-no-value | Details
1233fbbe-8a90-5695-bf6b-28144e51953d | textbox | Cast Number
d6de33d6-1d6a-59cc-aab5-58e1f9ee90b2 | textbox | Beam Number and Orientation
acb384d1-e98c-5a02-9f7c-1128a2c5f72b | textbox | End Diaphragm
ac5291bc-9b21-45c7-8d84-994c2fdbf8f2 | checkpoint | Shop Drawings approved for Works
| checkpoint | Shop Drawings approved for Works (2)
2016a2e5-4c55-4309-b921-d8d41e29515c | checkpoint | Mould and Sacrificial formwork Dimensions are within Shop Drawings Tolerance
4c1b674a-8bd8-50e8-959b-bec5d6dadc3e | note | Length
822d1104-8a27-5ed9-980e-888b7bf6caaf | note | Width
830ee2ae-8950-5298-a691-e9600cf10537 | note | Height
bab4373d-5276-50ed-954e-45ea96aec8c3 | note | Straightness
b82d264a-3d32-5473-8664-32a90bab9013 | note | Cross-section
d17caf36-2f56-45aa-8839-eaab07f481c9 | checkpoint | Condeck Surface Checked
a0273126-e254-5157-8d98-f128fa5c6b52 | note | Cleaned
9bb4e700-f5d2-5e02-883e-e5072418e64b | note | Sealed
3ec0752e-0691-5a4f-86ac-8445eadef662 | note | Oiled
8cd57883-99a0-42f8-ad58-66984ad264eb | checkpoint | Reinforcement in Accordance with Drawings
800fadac-1be9-5858-94f4-5d4746740084 | note | Reinforcement size
0f320d4a-3d88-5e76-9d42-76621d58e218 | note | Lap Length
f61d890c-4ba6-5c8f-bcd8-10b22c2f1c07 | note | Splicing
62881279-32c4-593b-b849-3eefda69eb96 | note | Bar Chairs
b31c7adc-8ff0-5948-b00d-593cf326b1e2 | textbox | Stitch pour Reinforcement lapping bars spacing maintained and template plate installed
12cb8723-6db8-5a57-b575-655471779936 | textbox | Blockout recess around lifting Hoops
e6843dea-b3b0-4e97-9a47-a3efa46611d0 | checkpoint | Detailed inspection of Mould and cage
eaa4facd-1d2f-4b08-80e6-3990a928d2c8 | checkpoint | Condeck (Top Slab) - Verify all brackets fixed at slab thickening
b6a05ddc-b33c-4577-9ddc-3cc72a035764 | checkpoint | Cover maintained and within tolerance
8529a34d-76d8-4f31-85db-6967eb88a0b0 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
9f215da9-19e9-5047-a80a-c229bb1325f1 | textbox | Ferrules M16x96 (Handrails)
8d90112a-ec60-5a67-a2f3-d316d5261991 | textbox | Ferrules M10x45 (Expansion Joint Cover)
d1b00e18-ceba-57fe-9b5e-6d4e7db97304 | textbox | Ferrules M16x45 (Ladder)
49d2450b-c55f-5f52-8737-b23eef564e73 | textbox | Ferrules (Other type, specify)
7b93bdc5-d314-438a-a850-e6d332b3e4f6 | checkpoint | All Stainless Items are installed in accordance with Drawings
1e328254-d184-5f54-943a-e1976e1eb331 | textbox | Other type, specify
848bea4a-5fd2-4663-ae39-9d8132912600 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
87db205a-a14e-5be0-b795-5d53984ab585 | textbox | Earthing Terminals (FDB-16)
09abc58f-8a0f-5f60-96e2-32bee1276a84 | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
a020b351-e865-5d5e-a4b5-b441cabfd625 | textbox | <20 mOhm across cage Length
4ef34acd-9e10-5711-9e70-4735a0a2bbd0 | textbox | Checklist Completed (North & South) (attach results)
64866f6c-d90f-4fa3-a3b6-3e21dbf3f2aa | checkpoint | All Temperature Loggers are installed as per Approved WMS
7f2ff394-48d1-5d12-a9a5-88aa58174bf6 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
98201a77-f60d-42e1-aeac-0e247f07a663 | checkpoint | All Cooling tubes installed as per drawings
abc7bb6b-54c6-46e9-9079-dd2011873c1d | checkpoint | QA Engineer Check Completed by
13c337bd-ac29-48ff-981d-c8f0c3da8696 | checkpoint | Client Inspector (if present)
641990f8-5fbf-49c7-9db8-78772196809d | section | Supervisor Release
270e0471-ddaa-4fea-bf93-bc6830d4ef5d | checkpoint | Supervisor Release to Engineering Team
63475a55-b247-4c9f-a6af-8f9688b42a90 | section | Casting Checklist
88d83b51-14fd-4dd9-888e-f52da4ab48e4 | checkpoint | Casting Information
1a647942-8258-57e6-b6ff-621161085e77 | textbox | Cast Date
fecc0c3a-5096-4881-90b6-cccae4487b09 | checkpoint | Concrete Delivery Dockets
d392af45-5195-5119-892d-80cfe0b6a20e | textbox | Concrete Delivery Dockets (list all)
c64283ea-038c-4d06-8fc5-48ddcb739795 | checkpoint | Total Concrete Volume
60fa028a-b7ea-54d1-954a-1213bd11e8e1 | textbox | Volume (m3)
39897cd6-ff27-4861-8aee-a711a8c2cbdc | checkpoint | Mix Design Verified
f8a395fa-8391-5639-a09e-c5241875a63d | textbox | Specify mix used
eba528a8-7ff1-4e49-aeee-27a8ef33b623 | checkpoint | Ambient Temperature within Limits
a4f51cbb-ff6a-5071-bca5-5481459038f1 | note | max 38°C
2002f385-03af-43f4-858e-f106bb05accb | checkpoint | Concrete Temperature
897bf355-b709-54f5-9399-3a7efa254455 | note | max 32°C
d2f2f96e-3a73-4cbf-a3b8-a4fa69c044d7 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
51a0000b-6d9c-512b-afdd-7d5a45ae465e | textbox | Slump (list all)
8c53b798-3f67-45b1-a665-758c3169c99f | checkpoint | Trucks Tested for strength
1db14c07-5972-5f2c-9497-617ae1c2a547 | textbox | Test Report Reference Number (list all)
4b7e892d-b8ce-4bb5-8a6e-9496502a8a60 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
b59b4ded-7fa0-4694-a5a9-b00f8590f345 | checkpoint | Concrete Placed within allowable time from Batching Plant
319cc792-6968-4cc3-b6c5-a99f41eb2d97 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
718d8a30-99dd-4f73-83ac-380c831d2579 | checkpoint | Required Finish Applied as per Drawings
292f6f49-a744-4a83-8f6e-8a8a44f1fbc0 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
413d70ce-bd3e-463b-afc4-419b411a10de | checkpoint | Concrete Covered Overnight
516f68de-00f2-4e61-8f20-57944d7a8169 | checkpoint | Cylinders Stored next to Bed
031a6c14-2f56-4f87-a028-eff4d714973f | section | Stripping Checklist
076e0db6-0059-4127-b3ab-4f013bf30fb2 | checkpoint | Date Stripped
901c78d2-ef96-5ae6-a1f7-9a653c24de1a | textbox | Enter Date
850503af-24ff-4d57-ba84-aaf78a56acc4 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
f0b85fdc-6c4d-511a-a42b-626445232756 | note | Conversion KN to MPa = Reading / 7.851
786038d6-bea8-5d36-850d-c5b0f8eeb594 | note | Stripping strength 20MPa
ab2f98ba-453f-546d-8399-ab6d61235c1c | textbox | Stripping Strength (Stage-2 Casting)
be8099a8-54d6-474a-8ca9-5ab2fc0d7bef | checkpoint | Lifting Strength Achieved
ddd53939-10f1-5062-be90-0c69a5b2b2d6 | note | Lifting strength required for stage 2 casting - 20MPa
990eb32e-733a-5942-8ad7-1dc6175f29d7 | textbox | Specify strength at time of lifting
16864bfc-1338-4dfd-882c-4b69230bc084 | checkpoint | Curing Strength (Stage-2 Casting)
775b182d-e021-55ec-9a45-7abb946c1815 | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
c4a6b006-d64b-56cc-af22-7a32fa98085e | note | Tarped until the curing strength achieved
02c30163-e235-48e7-87f1-1703e463bf18 | checkpoint | Lifted and Handled as per Drawings
bb4a283c-bd7e-475d-a1b7-f3d1aa8f65c6 | checkpoint | Product Clearly Labelled
3aa16a9a-e718-4a6c-a90a-c2b5aee249db | checkpoint | Storage as per Approved Temporary Works Drawings
810abbdd-62e8-4356-bd02-e764a528a4f3 | checkpoint | Secondary Curing as per Approved Methodology
9a1677df-6ab7-45e9-b757-ae5877ee264d | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
df44e42b-2e80-5f94-ac7f-80765b72e6f9 | note | Length
e4265a90-0641-5ae7-9983-17040cae58b3 | note | Width
7bb4ba7f-c14e-56fd-9171-dbeee66caa97 | note | Height
ff36979f-97bd-5709-a920-421e847495e8 | note | Straightness
f932effb-f869-5bc3-b54d-3dc7703f8e53 | note | Cross-section
30ccb5b5-812e-4b9b-8f3b-6c2bfd14644a | checkpoint | Specified Finish Achieved
c35933d3-afe2-483f-8653-4170bdb5ed17 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
a4c9f700-bb5d-5e3a-a5ae-51c28d8141b9 | textbox | Ferrules
3cde73a1-6070-5769-9afb-cb3e15618119 | textbox | Stainless Items
f6ffd1c4-9b9b-50c3-aac9-88cfb320a9fb | textbox | Lifters
8d91365d-45e2-5a6d-abc6-191ce31f5767 | textbox | Blockouts
13bd3877-1b7a-42bf-b918-89927084649f | checkpoint | Post-Pour Works Completed (As Required)
7a542891-b623-52f8-ae88-77c1c09fb89f | textbox | Ferrules are Cleaned and Capped
80630288-7f59-5868-b4d3-3428afa34d9b | textbox | Roughened Surfaces are Greencut
915898d3-a5d9-5e68-9706-7a0fa68a24a2 | textbox | All Miscellaneous Items are Completed
d6e3d8bf-4ab1-4dc9-abd1-2585855323bb | checkpoint | Temperature Logging Completed and Conforming. Attach Results
b27b11ea-6c6b-4acb-8c20-3dbdaad30d3d | section | Any Defect Identified
3b98eaf7-717e-4b08-92e6-2c0f193e079f | checkpoint | Punchlist Completed
802199c4-5558-40fa-a321-79a686c16752 | checkpoint | Repairs Required (if applicable)
8093547a-ee5b-4731-923d-f89189fd48a3 | checkpoint | Repairs Completed as per approved WMS (if applicable)
99cec26b-bb2c-4c06-919d-15ca8569b6d8 | checkpoint | Crack Map Completed
dca1dbb7-0aee-4152-ad0d-39cedf858014 | checkpoint | Any NCR Required (if applicable)
0c873deb-8fee-488b-89cb-f98a99faca72 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
2ab4d46d-a47b-47af-8a0a-812e74c51c85 | section | As-Built Drawings
eb5d1254-5417-4d2b-8863-ea78b86c8750 | checkpoint | As-Built Drawings Completed, Stamped and Attached
f4df64ac-f83e-4122-8da8-59131910cf70 | section | Concrete Strength Test Report
d5a1cee2-30d1-497d-9924-b455d50c06e2 | checkpoint | Concrete Strength Test Report Received
72ed3bf3-f25d-562e-9513-1b400cbb5e33 | textbox | Concrete Test Report
009f2cbd-af76-54bf-99ce-3bcdafdfefd1 | textbox | 7 Day Strength (List all)
bde663bb-3906-572f-9122-80785c06ca94 | textbox | 28 Day Strength (List all)