## toadd
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
079503f0-da90-4107-8e0e-d2371d03c7c0 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AA-AE, 07-09) | Toilet (02.504) + Cleaner's Sink, Drinking Fountain & Paint Collection Tank | Fix 1 Checklist
8ffb1bfa-26c9-4cc6-9e15-3422a4a159d4 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 1 | Grid (AD-AE, 08-09) | Scenery Dock (02.040) | Fix 1 Checklist
7976fce8-717b-4a29-be47-72bcd723fb08 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | Drinking Fountain (AC-AD, 13-14) | Fix 1 Checklist
ac2fa1e5-ece1-47a5-a8c9-6a1c5cf80ccf |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AA-AD, 14-16) | UD WC (02.537) | Fix 1 Checklist
8379d729-e8a1-4e4c-95a8-28c85584e86a |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AD-AL, 11-12) | Grid (AD-AE, 11-12) | Fix 1 Checklist
ee8aa5d8-7d8d-4006-b619-d7922968827f |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AD-AL, 11-12) | Grid (AJ-AL, 11-12) | Fix 1 Checklist
537e3182-e726-465d-855d-116f16fa9075 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AL-AN, 14-16) | Drinking Fountain (AL-AM, 13-14) | Fix 1 Checklist
55a37d30-68c2-4507-8b3f-5dad48f5f4f5 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AL-AN, 14-16) | Ensuite (02.572) | Fix 1 Checklist
a4e53c98-53f5-4e40-809a-bc47033408ce |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 2 | Grid (AL-AN, 14-16) | UD WC (02.570) | Fix 1 Checklist
758e8f3b-f980-491a-9e76-6c41508617b6 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 3 | Wardrobe Kitchenette (02.582A) | Fix 1 Checklist
09afb8a0-ea48-4ac0-803f-dfab016563de |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Dressing Room (02.522)
fcc9271c-eb3d-4659-b4da-eff4c37010d1 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | WC1 (ZA-ZB, 13-14)
13e4d9fe-b7fe-476c-96ed-a8552883f243 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Ensuite (02.524)
c4b4d24e-2a49-4ad3-810b-44857d73e00e |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Ensuite (02.523)
fa37eefd-59e0-4732-9ac6-c17b6f327dad |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Crew Stand By Room (02.532)
76ec1206-c71e-43c1-bcae-53afd4a682e7 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Room (AA-ZA, 13-14)
bba35c35-0aee-490f-bbdd-c169a452d05c |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | WC2 (AA-ZA, 14-15)
f96ff568-421a-4850-92c1-b6a6ec2fe4dd |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Kitchen (AA-ZA, 14-15)
59969d2f-ab03-4cbd-9310-ab6ba7a41f5e |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 02 | Zone 6 | Corridor & Performer BOH Spaces (Cold Shell) | Sound Lock (02.526)
e7453a57-49f8-4cfa-8d7b-4d6aaa2a1855 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 03 | Zone 2 | UD WC (03.518) | Fix 1 Checklist
d3f4a1aa-ec08-4e86-891d-736f1be0b031 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 03 | Zone 2 | Female Amenities (03.517) | Fix 1 Checklist
fe75ece9-f009-45bb-b7b5-fdd7d87eb336 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 03 | Zone 2 | UD Ambulant (03.541) | Fix 1 Checklist
60fa189b-0a87-48db-97e5-a4e1873866f3 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 03 | Zone 6 | Male Amenities (03.516) | Fix 1 Checklist
b7f938a5-681f-42b1-9951-2063e17e8f49 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05 | Zone 6 | Female Amenities (05.532) | Fix 1 Checklist
081c56f3-b049-4cfc-bc7c-f807d0a1e862 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05 | Zone 6 | UD WC (05.533) | Fix 1 Checklist
78674d3e-d777-4c52-a460-24def9a2b516 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05 | Zone 6 | UD Ambulant (05.534) | Fix 1 Checklist
09c2b339-a04f-43dd-bb5b-b9a846543e20 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05 | Zone 6 | All Gender Inclusive (05.537) | Fix 1 Checklist
b2194e0b-bfec-4c69-b506-91fd6bded0c6 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05 | Zone 6 | Male Amenities (05.535) | Fix 1 Checklist
3b062248-fc9a-49e5-8cf4-7323fba794f1 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05A | Zone 1 | WC (05.523) | Fix 1 Checklist
b65c9bd1-98da-4d05-ba2e-216fda6603b3 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05A | Zone 1 | WC (05.544) | Fix 1 Checklist
0a0f1749-d8f2-4172-a440-78455c0a9f86 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05A | Zone 1 | WC (05.545) | Fix 1 Checklist
e9ed9f0e-90ae-48b0-a18c-e99747169930 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05A | Zone 2 | Dock Manager's Office (05.515) | Fix 1 Checklist
6c81ada8-46b7-4a88-90db-f0abd941531c |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 05A | Zone 6 | Grid (AA-ZA, 15-16) | Fix 1 Checklist
8dbb51d0-eadc-46e7-baa9-283fe1847472 |  | not-started | Fix 1 Checklist | checklist | FALSE | FALSE | QA | Hydraulics | New | Level 06 | Zone 1 | Stage Door Entry (06.501) | Fix 1 Checklist