## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
900c402c-ad46-5426-9644-519edd5ab87e | checklist-flat | Inspection Chamber |  | Inspection Chamber
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| checkpoint | Notify and gain permit from principal contractor / client for inspection (hold point)
| signoff | Notify and gain permit from principal contractor / client for inspection
ca296f48-5010-50b6-a3a2-23677a2db500 | checkpoint | Latest specifications and standards nominated in ITP
7aeeba92-0cf6-54f9-a401-eb28f9fdb45a | checkpoint | Setout & alignment as per latest available drawing (include revision below)
74b286b3-b05a-5aad-934f-f09b92983298 | textbox | Drawing & revision number(s)
ed781823-b922-5b22-bf4a-304071d811fa | textbox | Correct approved materials as per sample register
7352cecd-2bc9-5dd7-9bbd-936329b10848 | checkpoint | Manufacturer's Quality
8a00d5e7-3ce7-51f4-af32-e5fc9c5c4b90 | checkpoint | Inspection Chamber Excavation
2a633554-714a-54c4-accc-3f0dc1ad1ed9 | checkpoint | Inspection Chamber Installation & correct invert levels (as per AS 3500.2 Section 4.8)
0ccc95fa-921b-541d-b612-6d25903a866c | checkpoint | Builder sign off prior concealment
76292889-214a-5db8-951b-594cd3c00c00 | checkpoint | Backfilling (as per AS 3500.2 Section 5.5)
906120c4-7320-577c-b59b-a33920fe4392 | checkpoint | Compaction of Material (As per Specification / Geotechnical report)
092c3e50-687d-53e8-b755-d32154258313 | checkpoint | Clean and Flush
518c7cc2-b6ff-516d-908c-a56b6acfffbc | checkpoint | Inspection Prior to Closure
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
ff1454ea-5fff-5d36-ac54-8ac8bcf522fa | note | Passing above includes Builder sign-off
20c637af-9351-59b0-befc-4f06e5d9fc97 | tickbox | Area clean