## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
57a806ff-ad2a-5d03-9079-a2c67c54da29 | checklist-flat | Pit |  | Pit
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| checkpoint | Notify and gain permit from principal contractor / client for inspection (hold point)
| signoff | Notify and gain permit from principal contractor / client for inspection
ca296f48-5010-50b6-a3a2-23677a2db500 | checkpoint | Latest specifications and standards nominated in ITP
7aeeba92-0cf6-54f9-a401-eb28f9fdb45a | checkpoint | Setout & alignment as per latest available drawing (include revision below)
f4070de4-8412-52a5-919f-02529508b1a0 | textbox | Drawing & revision number(s)
c84052a2-32fc-5b62-b215-6f941ab26799 | textbox | Correct approved materials as per sample register
7352cecd-2bc9-5dd7-9bbd-936329b10848 | checkpoint | Manufacturer's Quality
b931097a-3775-5017-a67c-db1a22de8b67 | checkpoint | Pit Excavation
1ab8ff05-21cc-53d3-a6aa-cacd258e1077 | checkpoint | Pit Installation & correct invert levels (as per AS 3500.3 Section 7.5)
0ccc95fa-921b-541d-b612-6d25903a866c | checkpoint | Builder sign off prior concealment
66b0e408-970e-5756-8977-04d70a63d862 | checkpoint | Backfilling (as per AS 3500.3 Section 6.2.11)
906120c4-7320-577c-b59b-a33920fe4392 | checkpoint | Compaction of Material (As per Specification / Geotechnical report)
092c3e50-687d-53e8-b755-d32154258313 | checkpoint | Clean and Flush
518c7cc2-b6ff-516d-908c-a56b6acfffbc | checkpoint | Inspection Prior to Closure
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
b6de496b-efa9-5201-aa86-b50086f8a583 | note | Passing above includes Builder sign-off
fef867d3-bbd1-5a89-a505-925acfe089d0 | tickbox | Area clean