## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
fb7c2c01-ed09-56c4-b73a-da4e5b80cdf5 | checklist-flat | Rough In Checklist |  | Rough In Checklist
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| checkpoint | Notify and gain permit from principal contractor / client for inspection (hold point)
| signoff | Notify and gain permit from principal contractor / client for inspection
c14305f2-9ed6-5c66-ba84-f6e1dbe68b58 | checkpoint | Setout & alignment as per drawing (include revision below)
727a45f5-271f-5b07-9faa-77440e511108 | textbox | Drawing & revision number(s)
d9ac4413-d238-59a4-b98d-983141533a2c | checkpoint | Material type (as per sample submission)
801a3b0d-b193-55e7-a017-ac6d43d66cc7 | checkpoint | Welding / pressfit / push fit / witness marks (as per AS 3500.1)
3aac1dd7-d23f-58b7-819a-461e7a9081b7 | checkpoint | Support & fixings checked (acoustic / seismic / water hammer/ silicone) - Add Photos below
080af063-649e-586e-8d35-309a1a84fbda | checkpoint | Pipework installation checked against standards (as per AS 3500.1)
5f445bf0-7c65-5ebf-86df-b16d210f8575 | checkpoint | Check no cross connection
72f3c870-8985-5ea8-acf6-7ed803653557 | checkpoint | Heights double checked before room sign off as per sample submission
217d4079-0f29-5ee0-bb14-7857526eec4a | checkpoint | Pipe risers water sealed per floor & capped off to prevent damage
d1d7c92f-2450-562a-83bf-0092c5dba049 | checkpoint | Correct sewer ventilation installed
6e02cdeb-70f0-5c38-8fc1-13b3b41b9393 | checkpoint | Pressure test water lines to (1500kpa)
6fff9bea-2a31-551d-96df-36b4e7276458 | checkpoint | Identification of services
57c060f6-fbee-549c-a65d-8c07b4dcd4cd | textbox | Services
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
a2a56273-3d2e-5b45-a8ae-3d078cd41d88 | note | Passing above includes Builder sign-off
0d339bcb-3e1e-5402-a9ab-e7c9dba9ee31 | tickbox | Area clean