## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
a1b4cf07-ae97-57db-83e3-6607381693d6 | checklist-flat | Sewer AG |  | Sewer AG
083eb9c4-fa14-554f-aec0-197652d9497a | checkpoint | Employee trained for task and reviewed installation instructions (product QR code / manufacturer's website / instruction manual)
| checkpoint | Notify and gain permit from principal contractor / client for inspection (hold point)
| signoff | Notify and gain permit from principal contractor / client for inspection
c14305f2-9ed6-5c66-ba84-f6e1dbe68b58 | checkpoint | Setout & alignment as per drawing (include revision below)
9f5bfc79-865f-5120-b541-ceffbb8b9085 | textbox | Drawing & revision number(s)
ce322e6d-7f63-5bf6-a477-b5f1a151ddbc | checkpoint | Grades, fittings & joints installed to standards
410bf4a7-cdb4-5244-8684-ed3de2b0fb1a | checkpoint | Fixings & seismic support to standards
65c25f8f-22a4-5daa-a14b-2023299a2c1d | checkpoint | Expansion joints per floor installed correctly & clipped
af8e630c-839c-5cad-bff7-e6f0b9c48092 | checkpoint | Pipe risers sealed per floor & capped off to prevent damage
e0f8ec9c-302d-5bb0-8eb3-f4e80b61eade | checkpoint | Correct invert level (As per Standards)
6a147b79-3c3a-5107-9ae1-c708993977f5 | checkpoint | Vents and AAV installed (As per Standards)
58c39949-84e1-5bec-9481-afb3069adeb5 | checkpoint | Acoustic lagging installed to acoustic specification
0eb38021-b577-5e0e-8e61-1868053ab9b4 | checkpoint | Pipework water tested to 15Kpa
7a255cfd-1417-58ed-a027-9a1a06843d91 | checkpoint | Identifications of services
a51941bf-58da-55a5-9a43-3db39640fbb2 | checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
e75379fb-b4d5-5695-844e-519058b24034 | note | Passing above includes Builder sign-off
7a05bd1e-1c34-5c78-9c01-f1b575d5101c | tickbox | Area clean