## General
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 | [5 empty] | C | Check point | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | M2F |  |  | Lot ID Number: |  |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[7 empty] | E | Examine | QE | Quality Engineer | Lyssa Gatehouse | LG
ITP Number: | DS2681-SH58-ITP-M-001 - Drainage Materials DS2681-SH58-ITP-C-005 - Drainage (Pipes) |  |  | Version: | Rev 1 |  | H | Hold Point | QM | QA Manager | Diliban Sengottian | DS
ITP Description: | Drainage | [5 empty] | I | Inspection | SV | Surveyor | Jim Robbins | JR
Discipline: | Civil | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | John Masters | JM
Specification: | MCIP SH58 East of Moonshine Road to Transmission Gully- Project Specification | [5 empty] | O | Operation | ST | Superintendent | Nick Talbot | NT
[7 empty] | R | Review | PE | Project Engineer | Dehan Erasmus | DE
Drawings: | 80510096-02B-100-C111-Rev 1 80510096-02B-100-C112- Rev 1 , 80510096-02B-100-C113-Rev 1 | [5 empty] | S | Subcontractor | SE | Site Engineer | Tyrese Dickson | TD
[7 empty] | V | Visual Verification | EM | Environmental Manager | Ross Glubb | RG
Prepared By: (Name) | Tyrese Dickson |  |  | Date: | 2025-07-16 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
Construction Manager |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2025-07-31
Project Manager |  | Name: | Gordon Lemon |  |  | Signature: |  |  |  |  | Date:
QA Advisor |  | Name: | Lissa Gatehouse |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: please use the correct ITP No. check the ITP register in the WBS, ie DS2681-SH58-ITP-C-005 Drainage (Pipes) DS2681-SH58-ITP-C-006 Drainage (HW/MH/Sumps) DS2681-SH58-ITP-C-007 Drainage (Rock Flumes)

## Materials
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
3.1 | Backfill Aggregate (AP65, AP20) | Prior to construction | Project Specification CL 16.3.21 | Trench Fill. Site Won Material can be used with agreement of Engineer. *free of unsuitable material as defined in the Earthworks Specification. *Fill to contain no more than 20% passing a 75μm sieve. *Fill to have maximum particle size of 100mm *Fill particles shall be able to be incorporated within a single layer. Further, less than 30% of particles shall be retained on the 37.5 mm sieve. *Unless otherwise approved, the MSE Wall Fill shall have a Liquid Limit less than 70% and a PI less than 6%. *MSE Fill shall be able to be tested in accordance with conventional compaction test methods for soil. Where Nuclear Densometer is used, these methods require less than 20% retained on the 37.5 mm sieve. Where between 20% and 30% of particles are retained on the 37.5 mm sieve the above test methods shall still be adopted and test reports annotated appropriately including reference to any test calibration or correction adopted | IANZ Lab Report | Prior to works | Visual, Document Review | H | ER
3.2 | Bedding Aggregate (AP5, AP10, AP20) | Prior to construction | Project Specification CL 16.2.12 | The bedding material shall contain no organic material that will affect embedment material performance The bedding material shall be free of materials that would be physically or chemically harmful to any pipeline component, including any protective coating | IANZ Lab Report | Prior to works | Visual, Document Review | H | ER
3.3 | Filter Cloth | Prior to construction | 80510096-02B-900-C205 Rev1 | Filter fabric Terram 1000 or similar to be used as per drawing | Manufacturer technical data sheet Photos | Prior to works | Visual, Document Review | W | SE
3.4 | Pipes, Manholes, Sumps and Headwalls | Prior to construction | Project Specification Cls. 16.2.3, 16.2.5, 16.2.7, 16.2.8, | RCRRJ pipes & fittings AS/NZS 4058:2007 UPVC pipes & fittings AS 1254 2010 Rubber rings used in flexible joints shall comply with AS 1646 Precast concrete structures shall comply with NZS 3106 | Manufacturer technical data sheet DN-QUA-QC-10-Incoming Material Inspection Photos | Prior to works | Visual, Document Review | W | SE
3.5 | Rock Flume - Rip Rap | Prior to construction | Project Specification CL 23.2.3 | Rock sizing as per the contract drawings. Greywacke rock with specific gravity no less than 2.65 See Cl23.2.3 for grading envelopes | IANZ Lab Report | Prior to works | Visual, Document Review | H | ER
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check cl, can't find 16.1.5

## Construction (Pipes)
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
4.1 | Trench subgrade | Upon trench excavation | Project Specification Cl 16.3.12 | Contractor to confirm suitability of foundation material and where the Engineer considers that the foundation material below the pipes or structures is unsuitable as defined in the earthworks specification, this material shall be removed and replaced as outlined in the earthworks specification 3 blows per 100mm | Scala Testing Record Sheet DN-QUA-QC-04 | 10m intervals | Witness Point | W | SE
4.2 | Foundation Undercut and backfill (WHERE REQUIRED) | Prior to backfill | Project Specification Cl 16.3.12 TNZ F/1 | Visual inspection of subgrade. Engineer to confirm any undercut treatment, if required. | ConQA Hold Point | Before placing bedding | Holdpoint | H | ER
4.3 | Filter Cloth | During construction | 80510096-02B-900-C205 Rev1 | Pipe bedding shall be placed within a layer of geotextile fabric as indicated in the drawings. | Photos | Continous | Witness Point | W | SE
4.4 | Bedding for rigid pipe | Prior to laying pipe | Project Specification Cl 16.4.1 80510096-02B-900-C205 Rev1 | Bedding material shall be as shown on the drawings | Photos, As bults | Continous | Witness Point | W | SE
4.5 | Bedding for flexible pipe | Prior to laying pipe | Project Specification Cl 16.3.17 | Flexible pipe material shall be bedded as per below table | Photos, As bults | Continous | Witness Point | W | SE
4.6 | Laying pipes | During construction | Project Specification Cl 16.3.18 | All pipes shall be laid in accordance with the relevant standards, the manufacturer’s instructions and good trade practice. Pipe jointing shall be carried out such that the finished joints are watertight and present a smooth invert. For concrete pipes, the spigot and the inside of the socket of pipes shall be clean before jointing. Rubber rings for flexible joints shall be free of dust, grease or dirt. The rubber rings shall be mounted evenly on the extreme end of the spigot | Photos DN-QUA-QC-28 Stormwater Installation Checksheet | Continous | Witness Point | W | SE
4.7 | Tolerances | During construction | Project Specification Cl 16.3.42 | The permissible deviation from the designated level of the invert at each manhole shall be ± 25mm. The permissible deviation of the alignment and grade of each culvert and pipeline shall be ±20mm from the designated line and level, or from the line between pipe or culvert inverts at successive manholes or catchpits as applicable, when measured over any 6m length, with all such deviations being gradual. | As-built | Continous | Witness Point | W | SV
4.8 | Backfilling & compaction | During backfilling | Project Specification Cl 16.3.20 | Hardfill shall be compacted in layers not exceeding 150mm loose depth using approved mechanical compaction equipment. Selected fill and Ordinary fill unless specified otherwise, shall be compacted to at least 90% MDD at optimum moisture content. Pavement layers shall be compacted as per the pavement specification and corresponding ITP | Photos NDM Test Results DN-QUA-QC-09 | Continous | Witness Point | W | SE
4.9 | Inspection Testing | After laying pipe | Project Specification Cl 16.3.43 | Pipes smaller than 600mm diameter shall be hydrostatically tested and inspected by CCTV to identify any leaks or deficiencies in joints. Pipes larger than 600mm diameter shall be CCTV tested | Photos | Prior backfilling | Witness Point | W | SE
4.10 | As-built Survey | Upon completion of works | N/A | As built survey record completed | As-Built | After Works | Witness Point | W | SE
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hold point for ER Reply: Wouldn’t it be more of a check point cz it says “Contractor to confirm” which is us.
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: as built?
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: installation check sheets ie. DN-QUA-QC-28 Stormwater / Drainage Installation Checksheet. DN-QUA-QC-32 PE Pipe Installation Checksheet Reply: installation checksheets?