## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DS2681-SH58-ITP-M-001 - Drainage Materials | itp |  |  |  |  | DS2681-SH58-ITP-M-001 - Drainage Materials
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Backfill Aggregate (AP65, AP20)
label | Inspection Point: Quality Control Activity - Prior to construction
label | Specification Reference - Project Specification CL 16.3.21
label | Acceptance Criteria - Trench Fill. Site Won Material can be used with agreement of Engineer.
label | ○ free of unsuitable material as defined in the Earthworks Specification.
label | ○ Fill to contain no more than 20% passing a 75μm sieve.
label | ○ Fill to have maximum particle size of 100mm
label | ○ Fill particles shall be able to be incorporated within a single layer. Further, less than 30% of particles shall be retained on the 37.5 mm sieve.
label | ○ Unless otherwise approved, the MSE Wall Fill shall have a Liquid Limit less than 70% and a PI less than 6%.
label | ○ MSE Fill shall be able to be tested in accordance with conventional compaction test methods for soil. Where Nuclear Densometer is used, these methods require less than 20% retained on the 37.5 mm sieve. Where between 20% and 30% of particles are retained on the 37.5 mm sieve the above test methods shall still be adopted and test reports annotated appropriately including reference to any test calibration or correction adopted
label | Verifying Document - IANZ Lab Report
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Visual, Document Review
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Bedding Aggregate (AP5, AP10, AP20)
label | Inspection Point: Quality Control Activity - Prior to construction
label | Specification Reference - Project Specification CL 16.2.12
label | Acceptance Criteria - The bedding material shall contain no organic material that will affect embedment material performance
label | ○ The bedding material shall be free of materials that would be physically or chemically harmful to any pipeline component, including any protective coating
label | Verifying Document - IANZ Lab Report
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Visual, Document Review
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Filter Cloth
label | Inspection Point: Quality Control Activity - Prior to construction
label | Specification Reference - 80510096-02B-900-C205 Rev1
label | Acceptance Criteria - Filter fabric Terram 1000 or similar to be used as per drawing
label | Verifying Document - Manufacturer technical data sheet, Photos
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Visual, Document Review
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 3.4 - Pipes, Manholes, Sumps and Headwalls
label | Inspection Point: Quality Control Activity - Prior to construction
label | Specification Reference - Project Specification Cls. 16.2.3, 16.2.5, 16.2.7, 16.2.8,
label | Acceptance Criteria - RCRRJ pipes & fittings AS/NZS 4058:2007
label | ○ UPVC pipes & fittings AS 1254 2010
label | ○ Rubber rings used in flexible joints shall comply with AS 1646
label | ○ Precast concrete structures shall comply with NZS 3106
label | Verifying Document - Manufacturer technical data sheet, DN-QUA-QC-10-Incoming Material Inspection, Photos
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Visual, Document Review
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 3.5 - Rock Flume - Rip Rap
label | Inspection Point: Quality Control Activity - Prior to construction
label | Specification Reference - Project Specification CL 23.2.3
label | Acceptance Criteria - Rock sizing as per the contract drawings.
label | ○ Greywacke rock with specific gravity no less than 2.65
label | ○ See Cl23.2.3 for grading envelopes
label | Verifying Document - IANZ Lab Report
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Visual, Document Review
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2681-SH58-ITP-C-005 - Drainage (Pipes) | itp |  |  |  |  | DS2681-SH58-ITP-C-005 - Drainage (Pipes)
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench subgrade
label | Inspection Point: Quality Control Activity - Upon trench excavation
label | Specification Reference - Project SpecificationCl 16.3.12
label | Acceptance Criteria - Contractor to confirm suitability of foundation material and where the Engineer considers that the foundation material below the pipes or structures is unsuitable as defined in the earthworks specification, this material shall be removed and replaced as outlined in the earthworks specification 3 blows per 100mm
label | Verifying Document - Scala Testing Record SheetDN-QUA-QC-04
label | Frequency - 10m intervals
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.2 - Foundation Undercut and backfill (WHERE REQUIRED)
label | Inspection Point: Quality Control Activity - Prior to backfill
label | Specification Reference - Project SpecificationCl 16.3.12 TNZ F/1
label | Acceptance Criteria - Visual inspection of subgrade. Engineer to confirm any undercut treatment, if required.
label | Verifying Document - ConQA Hold Point
label | Frequency - Before placing bedding
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Filter Cloth
label | Inspection Point: Quality Control Activity - During construction
label | Specification Reference - 80510096-02B-900-C205 Rev1
label | Acceptance Criteria - Pipe bedding shall be placed within a layer of geotextile fabric as indicated in the drawings.
label | Verifying Document - Photos
label | Frequency - Continous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.4 - Bedding for rigid pipe
label | Inspection Point: Quality Control Activity - Prior to laying pipe
label | Specification Reference - Project SpecificationCl 16.4.1 80510096-02B-900-C205 Rev1
label | Acceptance Criteria - Bedding material shall be as shown on the drawings
label | Verifying Document - Photos, As bults
label | Frequency - Continous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.5 - Bedding for flexible pipe
label | Inspection Point: Quality Control Activity - Prior to laying pipe
label | Specification Reference - Project SpecificationCl 16.3.17
label | Acceptance Criteria - Flexible pipe material shall be bedded as per below table
label | — — — — — — — — — — —
label | Pipe OD mm ¦¦ Bedding below base of pipe mm ¦¦ Bedding above crown of pipe mm ¦¦ Bedding either side of the pipe mm
label | — — — — — — — — — — —
label | ≤ 150 ¦¦ 100 ¦¦ 100 ¦¦ 100
label | >150 and ≤ 300 ¦¦ 100 ¦¦ 150 ¦¦ 150
label | >300 and ≤ 450 ¦¦ 100 ¦¦ 150 ¦¦ 200
label | > 450 and ≤ 900 ¦¦ 150 ¦¦ 150 ¦¦ 300
label | > 900 and ≤ 1500 ¦¦ 150 ¦¦ 200 ¦¦ 350
label | > 1500 ¦¦ 150 ¦¦ 300 ¦¦ 0.25 x Pipe OD
label | — — — — — — — — — — —
label | Verifying Document - Photos, As bults
label | Frequency - Continous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.6 - Laying pipes
label | Inspection Point: Quality Control Activity - During construction
label | Specification Reference - Project SpecificationCl 16.3.18
label | Acceptance Criteria - All pipes shall be laid in accordance with the relevant standards, the manufacturer’s instructions and good trade practice. Pipe jointing shall be carried out such that the finished joints are watertight and present a smooth invert.
label | ○ For concrete pipes, the spigot and the inside of the socket of pipes shall be clean before jointing. Rubber rings for flexible joints shall be free of dust, grease or dirt. The rubber rings shall be mounted evenly on the extreme end of the spigot
label | Verifying Document - Photos, DN-QUA-QC-28 Stormwater Installation Checksheet
label | Frequency - Continous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.7 - Tolerances
label | Inspection Point: Quality Control Activity - During construction
label | Specification Reference - Project SpecificationCl 16.3.42
label | Acceptance Criteria - The permissible deviation from the designated level of the invert at each manhole shall be ± 25mm.
label | ○ The permissible deviation of the alignment and grade of each culvert and pipeline shall be ±20mm from the designated line and level, or from the line between pipe or culvert inverts at successive manholes or catchpits as applicable, when measured over any 6m length, with all such deviations being gradual.
label | Verifying Document - As-built
label | Frequency - Continous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SV
checkpoint | 4.8 - Backfilling & compaction
label | Inspection Point: Quality Control Activity - During backfilling
label | Specification Reference - Project SpecificationCl 16.3.20
label | Acceptance Criteria - Hardfill shall be compacted in layers not exceeding 150mm loose depth using approved mechanical compaction equipment.
label | ○ Selected fill and Ordinary fill unless specified otherwise, shall be compacted to at least 90% MDD at optimum moisture content.
label | ○ Pavement layers shall be compacted as per the pavement specification and corresponding ITP
label | Verifying Document - Photos, NDM Test Results, DN-QUA-QC-09
label | Frequency - Continous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.9 - Inspection Testing
label | Inspection Point: Quality Control Activity - After laying pipe
label | Specification Reference - Project SpecificationCl 16.3.43
label | Acceptance Criteria - Pipes smaller than 600mm diameter shall be hydrostatically tested and inspected by CCTV to identify any leaks or deficiencies in joints.
label | ○ Pipes larger than 600mm diameter shall be CCTV tested
label | Verifying Document - Photos
label | Frequency - Prior backfilling
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.10 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Specification Reference - N/A
label | Acceptance Criteria - As built survey record completed
label | Verifying Document - As-Built
label | Frequency - After Works
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE