## Checklist Template Builder
Component | Name | Values
checklist | Fit-out - Postline
checkpoint | Council preline inspection passed / subcon QA received / GN preline ITPs complete
checkpoint | Wall linings to progress following GIB guidelines / arch wall tupe details
checkpoint | Check GIB fixing orientation and fixing spacings in accordance with GIB guidelines
checkpoint | Ensure perimeter fire sealant has been applied to GIB
checkpoint | Ensure all GIB joins and fixings have been stopped over and terminate to underside of floor above (or where applicable in accordance with consented plans)
checkpoint | Ensure any service penetrations have fire collars installed / stickered / QA received
checkpoint | Ensure in wall powerpoints have flush boxes installed as per passive fire detail requirements
checkpoint | Postline inspection checklist established / signed off from subcontractors
checkpoint | Council postline inspection No. 1
checkpoint | Additional notes / comments - Handover QA te second fix

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty

## Sheet1
Council preline inspection passed / subcon QA received / GN preline ITPs complete
Wall linings to progress following GIB guidelines / arch wall tupe details
Check GIB fixing orientation and fixing spacings in accordance with GIB guidelines
Ensure perimeter fire sealant has been applied to GIB
Ensure all GIB joins and fixings have been stopped over and terminate to underside of floor above (or where applicable in accordance with consented plans)
Ensure any service penetrations have fire collars installed / stickered / QA received
Ensure in wall powerpoints have flush boxes installed as per passive fire detail requirements
Postline inspection checklist established / signed off from subcontractors
Council postline inspection No. 1
Additional notes / comments - Handover QA te second fix