## Checklist Template Builder
Component | Name | Values
checklist | Fit-out - Pre-line (Ceiling)
checkpoint | Ceiling Grid RL checks
checkpoint | Ceiling Grid installed - services accounted (check penetrations relative to deflection head detail, where applicable)
checkpoint | Services installed (establish preline services sign off sheet - check RCP setout for lighting / sprinkler / mech locations). Check services to external spaces
checkpoint | Service passive fire collars installed / intubatt / other passive requirements underside of slab complete / QA received
checkpoint | Ensure seismic details have been followed as per consented design - Engineer / consultant preline inspection
checkpoint | Ensure sprinkler installation has been pressurised and signed off prior to lining (QA received)
checkpoint | Ensure overhead hydraulic pressure test complete / QA received (prior to ceiling lining)
checkpoint | Mech grilles checks on appeture openings relative to the diffusers and grill sizes in relation to RCP setout
checkpoint | Coordinate access hatch framing / location relative to service maintenance
checkpoint | AC inspection No.2 Pre line
checkpoint | Celling GIB infalled
checkpoint | Additional notes / comments - Handover QA to second fix

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty