## Checklist Template Builder
Component | Name | Values
checklist | Fit-out - Preline (Walls)
checkpoint | Structural QA Received
checkpoint | Gridlines / RL datum marked on floor
checkpoint | Bottom plate setout per arch setout plan
checkpoint | Underslung service peno marked / core drilled
checkpoint | Wall framing complete as per consented details / wall types
checkpoint | Packers installed to underside of bottom plate
checkpoint | DPM between framing and Substrate
checkpoint | Stud centres and fixing centres as per consented details
checkpoint | Check all door openings have been constructed to the RO dims outlined in the door schedule / arch set
checkpoint | Check connection details are in accordance with structural PS1 / NZS 3604 (if applicable)
checkpoint | Nogging plan established / agreed with service trades (FFE / Appliances)
checkpoint | Nogging plan checked and approved by specialist subcontractors (e.g., kitchen / fireplace etc.)
checkpoint | Checking manufacturer guidelines for specific fixing requirements
checkpoint | Check moisture content of timber prior to lining (if applicable to timber frame)
checkpoint | All nails flush within framing to receive GIB
checkpoint | Create sublist if applicable to fire IT wall (check passive fire requirements - fire collars installed / stickered / QA received)
checkpoint | Complete prelim service sign off sheets (ensure sub-con preline QA received / check intumescent complete QA received / purchaser changes incorporated)
checkpoint | Checklist for purchaser change incorporation
checkpoint | Consultant preline inspection (BVT / Holmes / WAM / BG&E / Marshall Day)
checkpoint | Line single side of internal wall (follow GIB manufacturer guidelines)
checkpoint | Pelmets / bulkheads / services to exterior space complete and sealed
checkpoint | Insulation has been installed as per consented plans (no gaps between insulated panels and frame)
checkpoint | Ensure wall cavity is free of debris / clean prior to GIB cover (vacuum tracks)
checkpoint | Council hydraulic inspection / sign off (two inspections depending on quantum)
checkpoint | Ensure caps on inspection points are reinstalled after council hydraulic inspection
checkpoint | Additional comments / photos (applicable to a unique room type - such as service room etc.)

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty

## Sheet1
Structural QA Received
Gridlines / RL datum marked on floor
Bottom plate setout per arch setout plan
Underslung service peno marked / core drilled
Wall framing complete as per consented details / wall types
Packers installed to underside of bottom plate
DPM between framing and Substrate
Stud centres and fixing centres as per consented details
Check all door openings have been constructed to the RO dims outlined in the door schedule / arch set
Check connection details are in accordance with structural PS1 / NZS 3604 (if applicable)
Nogging plan established / agreed with service trades (FFE / Appliances)
Nogging plan checked and approved by specialist subcontractors (e.g., kitchen / fireplace etc.)
Checking manufacturer guidelines for specific fixing requirements
Check moisture content of timber prior to lining (if applicable to timber frame)
All nails flush within framing to receive GIB
Create sublist if applicable to fire IT wall (check passive fire requirements - fire collars installed / stickered / QA received)
Complete prelim service sign off sheets (ensure sub-con preline QA received / check intumescent complete QA received / purchaser changes incorporated)
Checklist for purchaser change incorporation
Consultant preline inspection (BVT / Holmes / WAM / BG&E / Marshall Day)
Line single side of internal wall (follow GIB manufacturer guidelines)
Pelmets / bulkheads / services to exterior space complete and sealed
Insulation has been installed as per consented plans (no gaps between insulated panels and frame)
Ensure wall cavity is free of debris / clean prior to GIB cover (vacuum tracks)
Council hydraulic inspection / sign off (two inspections depending on quantum)
Ensure caps on inspection points are reinstalled after council hydraulic inspection
Additional comments / photos (applicable to a unique room type - such as service room etc.)