## Master List Templates
Id | Type | Name | Values | Prompting Name | Postfix
476febf2-1493-5be7-a25f-f4be0daece1e | checklist | Civil - Buildings Subgrade |  | Civil - Buildings Subgrade
606f4989-cde0-5ab9-9048-2df0f74fa4b6 | section | Subgrade base
fdb5d37f-13aa-5917-af01-f0bd350f4657 | checkpoint | Geotech Eng inspection report received- and close-out
9f374058-523a-51d7-af5e-29dea4014e04 | checkpoint | Geotech Eng Inspection of subgrade and proof rolling prior to filling
f9fc5ad9-c3cc-5625-be1d-9d951f4c6a2e | section | Building Subgrade build-up
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
b3babae7-c304-5715-87b7-a50d6011888c | checkpoint | Placement of hardfill layer compacted as per design
544336ba-4c54-5b65-a180-ab3ce6162ee6 | checkpoint | Drainage piping installed under foundation level
fda57dd3-011e-59ea-aa90-8fb243302d78 | checkpoint | Platforms spot checks heights and location
01c3fba2-d641-5507-84da-ade9056c73db | section | Subgrade Sign-off
4549aefd-2866-57ea-8e2d-284fe71e2202 | checkpoint | Subgrade QA and test results received
4ac43318-94bc-5b10-bc98-5090ab4183ff | checkpoint | Geotech Eng Inspection of subgrade and proof rolling report received and close-out
84e3b7f6-1336-5832-ba14-44a37efddb47 | checklist | Civil - Drainage Checklist |  | Civil - Drainage Checklist
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
6fc31946-8ec6-548f-9a42-e7a3c4dc9b6c | checkpoint | Locates done on site – confirm no clash with pre-existing underground services
70925b34-3c7a-5e8a-89fe-c5029e6296dc | checkpoint | Appropriate permits in place
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
e6ed9704-ca11-5a56-8d2b-cc84b2b09107 | checkpoint | Upload drawings / check services depths, confirm location, filling/digging
3cf4fad5-07c6-5cc8-b8bd-69cb6f9d5340 | checkpoint | Clear work area
931fbffa-ba09-5e61-b63d-bad3b1f9895a | section | Trenching
3d9ea26c-deeb-541a-b01f-873c951a827a | checkpoint | Delineation of area
e0c824c0-d00e-5043-8996-d208e919092b | checkpoint | Benching appropriate for ground conditions
0555bfc1-0860-513b-b84b-b967a5a418a6 | checkpoint | Safety of trenching conditions and edge protection
615fa8e3-d8e7-5573-808c-a9b565e0114e | checkpoint | Civil Eng inspection report received and close-out if unsuitable subgrade conditions exist
e8adbc84-b448-5119-bc35-7edd8200d05f | section | Installation
0ecf9847-ede4-50d3-ad92-a9b1891892a7 | checkpoint | Confirm correct bedding material being used and spot check RL’s
fb02bf04-b9a1-5e4b-b29f-6b91b7ddf965 | checkpoint | Manhole installation
6cd6e903-e416-4d0c-ad82-38ffba52e1ff | tickbox | Confirm MH diameter
b20e33ff-fc40-4a16-8b7c-42ee5e2617e2 | tickbox | Reo
e2f4d1fa-78bc-40c5-9bec-31016f9be862 | tickbox | Joint sealing (if precast)
7add8d48-662a-43f2-befd-1db905d9cf23 | tickbox | Invert level
523ada56-529e-428b-8752-17e6d2d0b8e3 | tickbox | Confirm concrete grade
94063e5b-c468-5f89-8050-d222186ababa | checkpoint | Pipes installed and correct junctions/connections
7b89279e-9cd4-51f9-abf8-758524e98bb4 | checkpoint | Civil Eng inspection report received and close-out for first pipe run
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
cdae24e3-f52c-5821-bab7-00dabfe4f429 | section | Backfilling
27b457e7-7059-5eb9-a15f-27a280c882d5 | checkpoint | Appropriate backfill material
a79deac1-27f7-5ee2-bd88-3cff4f906ffb | checkpoint | Backfill at 150mm lifts and compact as per Civil spec
e790533e-8db3-53c9-a5f2-cf1629abce42 | section | Post Backfilling
dfc4d584-25bb-53f9-b04b-3906021f843d | checkpoint | Internal manhole works
c86e0894-36d8-5186-a72f-a7a7428cfd3e | tickbox | Civil Eng Splitter weir manholes – weir pre-pour inspection (first manhole)
c3a67ff4-f316-5eb8-94c4-e8e2570875ab | tickbox | Splitters and benching completed
b149ea5b-8877-5451-a521-86623cc71b56 | checkpoint | Soakholes
48fd210a-d850-52e2-942a-7ba870883371 | tickbox | Civil Eng Inspection of selection of rock bore installation report received and close-out
4a6d677c-9c3b-5c2a-8e83-9eba1b8a40c8 | tickbox | Civil Eng inspection of selected of soakage testing
51f0e36e-6c5e-5e7c-8c74-38d8b2b34328 | tickbox | Council inspection report received and close-out – as-built plan required
932958ed-7cf7-5701-aa36-da14eb06e1f3 | checkpoint | Drainage QA received and as built
641d0e88-5490-52a2-846c-b412aba39545 | checklist | Civil - Footpath In Ground Services |  | Civil - Footpath In Ground Services
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
a57236d1-7414-58d5-8bc9-91a9b6b7d461 | checkpoint | Stormwater laterals exposed and extended to sump locations
9baec433-6c5b-5811-a312-0e73d1ecd6d7 | checkpoint | Trench formed and sand bed completed
370e2b8c-8b2b-5dd9-a37f-158568b99aa4 | checkpoint | Conduits underslab completed
db5b3ed6-e2a8-5d6a-a1e9-25a1b894d1f0 | section | Services trench
e62d478a-e598-5adc-9fdd-149eb48bfd8d | checkpoint | Electrical cables running from DB location to each unit
a700415a-0dad-518c-9666-4b707bb229ec | checkpoint | Electrical cables top covered and cable slab installed and covered
7c2be880-7d8d-5f74-8ae3-ed25b3592de4 | checkpoint | Hydraulic service joined and water tested
fbbcd6db-8c72-55bf-b28b-df60a467c50b | checkpoint | Chorus pits & tuds located and levels agreed
816996c3-4da1-5832-aeb1-41f2b25edd29 | checkpoint | Fire alarms conduits and cables completed
588cb6be-2adf-5261-8558-0f7a4e251642 | checkpoint | Conduits crossing roads where required
314145c8-0e23-58a1-9491-f8ab0abcdca1 | section | Post-services
aa603d40-f9c9-5328-953c-882cb2bc8b5a | checkpoint | Fines cover
5d2cf323-3299-5b11-9cbd-7ea6d4a3eb00 | checkpoint | Chorus pits to final RL
3d39e3c3-b613-564d-a05c-5075ce2a5b55 | checkpoint | Final backfill & compacted
87fc0d00-a383-58b6-ab69-d9b199bda0d0 | checklist | Civil - Roads |  | Civil - Roads
fe56cd71-651d-5f6c-8cfd-5c86bc9121a1 | section | Pre-Hand Over
5148c6f8-a77f-527e-b92b-f9d9d4821e7e | checkpoint | In ground services QA and testing received
42a61e44-440d-5a1e-8068-c1e9e48ae635 | tickbox | Electrical
c68df2b7-adde-5b3a-871a-292154477b66 | tickbox | Hydraulic
41cee28b-f4b3-51ac-9062-3d755d000c7f | tickbox | Coms, Chorus
854c83c4-5873-545f-8281-2e122731b927 | tickbox | Façade works completed
272568c2-0382-5fc3-9ad1-4a3aedeb0011 | checkpoint | Drainage works complete
3f8ea192-45de-53b4-86d1-d3de021e33b9 | tickbox | Cess pits, manhole benching and final RL, all ORG installed
126f67bf-8aaf-57fe-8376-467c740ec8a4 | checkpoint | Road clear and ready for hand over
71db995e-a76e-55d9-be63-517255c34562 | section | Road Build-Up
a83dc549-b61c-54f0-96d8-51f258ef993d | checkpoint | Ensure road is built up in GP65
262514ef-5494-5f92-b6d9-c6f39d2a8dba | checkpoint | Ensure testing is completed.
5a09b68e-2b8f-53da-9a15-a11867047b21 | tickbox | CRB 6 and proof rolled
17b7f12d-ce8b-510d-a816-95b8e26eacd3 | section | Channel Drains Install
bb87e57e-721d-5d89-b6ea-88808813f6d9 | checkpoint | Correct RL to slab
30166c39-0e89-5362-8c15-df039b60e1df | checkpoint | Sumps installed
b05fa4a6-f921-59d4-95f2-c5b9e4fe0496 | checkpoint | Channel drains QA
d0cb6112-d450-5f09-af9a-328054e421d1 | checkpoint | Channel drains encased on concrete
b1a7a369-c9ee-5f56-9bc6-4e17652f0373 | section | Kerb Install
90d34e50-d977-5f2b-b374-376d046c08d9 | checkpoint | Layout/pre-pour
a3fd0010-c33f-53e3-8302-9d006e7704fc | tickbox | Spot Check RL’s
935bd2ec-153b-5ab7-8887-048730a75c82 | tickbox | Confirm mix
ad61d071-1033-5b5b-a8c6-fe63e323d767 | tickbox | Check kerb location
80f1a504-1b67-5992-9f12-cd9d1cf99401 | tickbox | Check kerb type
d67186d6-4524-59c5-bbce-f7e9deb1015c | checkpoint | Saw cuts 4m spacing
abdbdbd0-78ce-5b3c-830b-6d0a1f3763f4 | checkpoint | Chip/cracks
eab13ac6-14db-5035-883f-c33cce0583d4 | section | Concrete Loading Bays
ff629839-f9fd-50b2-bb35-9a8fbeeca485 | checkpoint | Build Up
32257c5f-a1f3-501d-b026-6a7135041c38 | tickbox | 100mm GP40
033f8ade-ee8f-551f-9de5-385cab926729 | tickbox | Sand/fines
1b6bdbdc-3117-5dc9-b647-3de5869632ad | checkpoint | 1 layer 661 mesh 60mm top cover
b72bfe4f-99ba-5edd-9eca-a8bea4714ace | checkpoint | Trimmer bars at corners 2*D16 1200mm long
ab0bf92e-decc-51a5-90b7-49c07d569f45 | tickbox | Unless corner coincides with sawcut
6ffe637e-2592-59f4-a38b-95df6b7d750c | checkpoint | Trimmers around manholes
e1ebc7a4-7cad-5c1d-b5dd-2a6fee0f377d | checkpoint | Refer Civil drawing 115
b023a3a8-b9c9-5473-b065-c6d256cd7231 | checkpoint | 175mm 30MPa
fbe38a2f-d0a8-5a35-9500-f3eca9a78e43 | checkpoint | Chamfer at asphalt transition asphalt to sit 5mm proud.
a2703076-dec8-5cd2-8367-632993fce580 | checkpoint | Broom finish
ee491c5e-366c-5dd5-a08f-cb86f86dec45 | checkpoint | Saw cuts
7e94dd05-516b-51c3-b688-78c98fb2146a | section | Walkway Install
268ad485-62de-54ee-b00a-8eab58fd2b59 | checkpoint | Water cure 7 days
f6ff1306-f409-5149-b875-3cf4c6a3d0b2 | checkpoint | Chorus Tuds
69b3d83d-440c-5d71-84a3-d0f9fd1c77e4 | tickbox | Set out to correct height and slope
0b29ead1-307e-59e4-acbf-e3a3028dc029 | checkpoint | Build Up/Falls
8c3f67fa-10b2-548d-9d8a-99d03e7592b3 | tickbox | 150mm GP40 or 200mm GP65 and 100mm GP40
1618d43a-cad7-525f-93f2-4013179c6ac0 | tickbox | Check RL’s at critical points
c242b2c7-f965-50de-a6ab-67a15fba6772 | tickbox | 25mm asphalt thickness
7aa537cd-4cdf-5040-99fe-6386f9ffe9f1 | checkpoint | Lay Walkway
7bef1887-1151-5472-8988-40fb83664587 | tickbox | Visual check finish/transitions
c3c7d6dc-dcdf-5488-b0dc-70a4daf02d2b | section | Manhole Lids Install
cec5eca4-7897-5d7e-b465-b8fb86df1f9f | checkpoint | Set to proper RL and grade
ab88d75f-bdfd-5ae2-a660-999c7f212bf6 | section | Road Install
a4f1d781-dec7-557f-979d-599a977b14c6 | checkpoint | 100mm GP 40
02eb2810-ff33-5624-9420-eaa67a0206f4 | tickbox | 3% slope from crown
4972956e-2b55-537e-a605-fe849f6e775c | tickbox | 35mm Asphalt thickness
93387ac6-9511-5e9e-ad29-f2a890476064 | section | Line Marking
3f8cf446-37cd-5aa9-9d15-d0d6334a5d93 | checkpoint | Layout as per Drawings
8ed1a955-09a7-52eb-8577-61e3d5288d67 | checklist | Facade - Below Ground Waterproofing |  | Facade - Below Ground Waterproofing
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
71eaca1a-dc8e-548e-8e84-c7b14ddea80f | checkpoint | Panel QA received
336476cf-2c52-5a59-9048-079a327c9e11 | checkpoint | Block wall QA received
6b1dae77-bebd-5280-9af9-6e95fc260f59 | checkpoint | Panel joints grouted/sealed
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
7323e262-86ed-5ede-9576-f20450e3a5ef | checkpoint | Safe access
e8adbc84-b448-5119-bc35-7edd8200d05f | section | Installation
da85d330-03d8-5e66-ab76-7d91942ff7dc | checkpoint | Waterproofing as per architectural drawings
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
7987d1f8-08d1-5899-976d-79a0afd1f479 | section | Post install
989871be-aba4-5e45-85d3-f4d0e28fec9f | checkpoint | Protective layers
eb390947-6e7f-5f05-a77d-c2f5f9b6b425 | checkpoint | Tanking QA received
3f90fead-f925-5db0-982f-6577cb67d414 | checklist | Facade - Shop Front |  | Facade - Shop Front
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
d87a44c6-82e4-5a6e-8ea5-738b83a64b8c | checkpoint | Site measure complete
eda16b89-f9ce-5777-98ab-9930a317b6df | checkpoint | Steel QA received
e452d693-f926-521a-be17-61fc6b56028e | checkpoint | Carpentry sign-off received
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
8db7e7ef-4c0c-59e7-95d8-4a6672ab8735 | checkpoint | Waterproofing sign off as per details
4917beb7-f0f8-5f58-a9a2-1512a2a3386b | section | Install
c79558c5-3678-595b-a6b0-6b50c19364e1 | checkpoint | Prime surfaces
53fc179c-513c-54f0-803f-a101965008e0 | checkpoint | Seismic frames
0091b4c9-1a71-5438-8ddc-498f5b835d5c | checkpoint | Inserts
2f70ac11-f967-5c96-af53-3da4d2f2a928 | checkpoint | Glazing
8efbed92-edfe-5dff-8517-5ef9206e3cf9 | checkpoint | Air seals completed
d06aeed3-5bd4-5829-921a-cbd3766e1a71 | checkpoint | Bespoke flashings measured
7987d1f8-08d1-5899-976d-79a0afd1f479 | section | Post install
573a1f71-7a32-5e86-9309-348834f85f8b | checkpoint | Protection 1.5m high
ecb7b9ce-f0de-5d0e-8e19-a2d425443aa7 | checkpoint | AAMA 501 water test completed and passed – results received
2d1408c4-b066-56c9-90d7-5eeddd6c469d | checkpoint | QA subby and consultant (inspection requirements?)
8c32fe5d-7ac9-59d7-b844-f665d374bc44 | checklist | Fitout - Carpentry Framing |  | Fitout - Carpentry Framing
706b60ea-050c-59e6-a703-00b88e0f65ca | section | Mezzanine
d1a6e424-3fe0-547b-b92d-c31e929199a7 | checkpoint | Framing complete as per Arch details
c2b87717-a0f5-5a07-aef3-730b8f13872a | checkpoint | DPM between timber and beam
c4f9829e-f6d6-50d2-b951-bc61b4bbd3cc | checkpoint | Balustrade 150x150mm 19mm packer.
41a37996-965a-5128-879c-5a52b5cb720e | checkpoint | Framing/beam packing continuous to receive the Balustrade posts
9a038cf5-57e9-512c-8055-1666bd4aa5e6 | checkpoint | Stair measure complete
3e8e9343-d8ea-57da-97ff-1185caad4bbe | checkpoint | Stairs received on site and installed
b66c592c-c0cd-53c7-a450-2119745e3e28 | checkpoint | 70mm min width of stringer against precast
1a12cd23-9e42-51c5-923d-c80b5f1f5bc6 | checkpoint | Inside stringer notching clear
86940b36-29bd-5d81-98bd-35df43d809af | checkpoint | Base of stair detail correct
e5e7fa6e-5913-5e8c-b0eb-33c1925319db | checkpoint | Battens to receive Fireline installed correctly
c653728c-649a-55de-994c-eb277b379245 | checkpoint | All nails flush within framing to receive GIB
f386de94-edd0-5eb1-b581-7a5452375b4d | checkpoint | Fireline installed as per Spec
17f763c6-fcb1-5acc-9ca6-48f8ccab8b4f | checkpoint | AC inspection No.1 Post line Fireline
6cd41070-f9d1-549f-9af0-3c6a8635f903 | section | Bathroom
aa58232c-76b3-5d38-9b6e-163775638158 | checkpoint | DPC between timber and concrete
ea3cae1d-3aa0-515e-aa18-f0826ab02036 | checkpoint | Framing as per Arch drawings
d33f19c1-33a0-5ed7-818b-95da4af8191c | checkpoint | Fixings to concrete panel and slab correct
89825f2b-dfa4-52fe-b07f-22ee5e5a9632 | checkpoint | Door opening Correct
a34953e6-df1a-5718-8418-517a1c8bbdcf | checkpoint | Service nogs / stud exclusion zones
bdc70eb3-a533-5469-8d5c-fd7e90201467 | checkpoint | Set out confirmed by EXP and accepted by ZYJ
7ba27a1e-a8ff-50a1-bea0-7e07515acdc9 | checkpoint | All nails flush within framing
10115974-443a-57cb-a1ff-dae01fa120fb | checkpoint | AC inspection No.1 Pre-line inspection
f739e0ba-863e-5d5e-b499-995c9323fde5 | checkpoint | GIB install to walls
2f9d034f-c449-5e84-ba88-4baf0be618cd | checkpoint | Ceiling Grid installed – services accounted.
506e631b-ad1b-5060-b7fd-fa467d532a5f | checkpoint | Services installed – TRF, AM, TC
314e1b9b-36b3-5c7e-b654-a665bd4f332a | checkpoint | Ceiling GIB installed
693a28b8-037e-5e10-bf1a-5b3811e58ef8 | checkpoint | AC inspection No.2 Post line
25c54d66-a71c-5581-8c41-82c21de450b2 | checklist | Fitout - Installation |  | Fitout - Installation
706b60ea-050c-59e6-a703-00b88e0f65ca | section | Mezzanine
036dc21b-da82-52b2-bc88-343274e11d89 | checkpoint | Balustrade measure
867c52f3-8be3-5f83-b09c-9c655b5cf6ef | checkpoint | Stairwell opening and location as per arch dwg 1701
2e7f0abf-25f1-5476-8407-3818ad482623 | checkpoint | Order stairwell
a140a112-4b34-579c-9b36-b8b5ee4b0897 | checkpoint | Check detail for balustrade (3302 – interior details)
ec939da5-a256-5e3c-aa1f-edc1e610a1a0 | checkpoint | Stair details as per arch and SD
7edc27e5-3776-5a22-b5e2-250918fac0df | checkpoint | Handrail site measure
69dd9f3b-532b-59d6-97a8-b3d403998d4b | checkpoint | Install eco-ply ceiling
616ebc9b-b0ce-52cb-b057-f3c3cd5fc58b | signoff | Line/stop internal service penetration prior to eco ply
b5e4a1a0-0b83-5b1f-9f41-ae7c4a496bab | section | Bathroom Walls/Ceilings
b42e53da-8be2-5bd8-8e81-4244606c54b9 | checkpoint | Bathroom Lining
a26b98e4-b5e1-5fe7-8a31-0a415a65c910 | signoff | Bathroom are lined and fire stopped before bathroom framing
3d3ce6a2-4654-5120-8b31-ac5390c8e9ea | section | High Level Services
5059a1f0-2393-56ae-b4b0-560b6ba2ee5e | checkpoint | Services sign-off
4fa287dc-eaed-51f1-a9aa-0a23efc9cc8a | checkpoint | Pre-line photos
2f9a136d-40df-5426-8389-9cbfb643afb7 | signoff | Council Pre-Line Inspection
13ae98cc-ede0-58ba-85a5-7c5c616ef727 | section | Set / Sand / Paint
2d55462c-eb29-599a-b5dd-6aa69bca6643 | checkpoint | Plasterboard fixings as per requirements (aqualine x standard)
9e36b48b-1dfa-5072-941d-9fb2f905515d | section | Tiling and Waterproofing
0b09512a-fbd2-52a0-a8b9-56998ac978ea | checkpoint | Stopping complete
0db008cc-1374-51ef-a302-f8250b12cd43 | checkpoint | Sealants installed
5d289f3c-c031-52f1-be1d-70b144189242 | checkpoint | Waterproofing QA
02542a7c-0bb7-59ba-a407-e3974076fbec | checkpoint | Tiling QA
89a616fa-860f-52f4-9b0b-cb323817e28e | checklist | Fitout - Prestart |  | Fitout - Prestart
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
697bf317-67ff-519d-b526-ebf452de5294 | checkpoint | Slab poured and curing complete
6522b52b-eb96-58da-8507-9de0ab961f8c | checkpoint | Mezzanine steel QA/Sign-off
a596d44c-482b-509f-8c5e-2db4b568ff64 | checkpoint | Intumescent paint to mezzanine steel (beams and posts)
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
18ef9da2-81ba-59db-97eb-e0412ee6167d | checkpoint | Sealant complete between precast panels
d58cae26-248d-58a5-b25f-2df42eaff649 | checklist | Inspection - Consultant Inspection |  | Inspection - Consultant Inspection
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
bf517bd7-8525-5cb8-a942-700cf16ca3ba | checkpoint | Inspection completed, attached and any relevant observations closed out
85d5c57f-5087-594a-9409-ad4a5f8cf854 | textbox | Date of inspection
d22c574d-b540-5c25-bcde-870e97bc0a2b | textbox | Type of inspection
056b2541-4a8b-5b2c-9acb-bfec89374578 | textbox | Area of inspection
540522ff-0a02-5422-9757-c4e19e4bf71c | tickbox | Inspection report attached
181deb7a-6dd2-5d74-a387-ac01506142bf | signoff | Sign off
8cb9c790-21c9-53e5-8695-f5ca4f7805ae | checkpoint | All relevant observation closeout evidence attached here if applicable
88bdd135-f1c4-58ad-8725-aad5bdc3811f | textbox | Corrective action required
181a4e8d-b609-5791-9af4-02acdb97e4c0 | checklist | Inspection - Council Inspection |  | Inspection - Council Inspection
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
bf517bd7-8525-5cb8-a942-700cf16ca3ba | checkpoint | Inspection completed, attached and any relevant observations closed out
a811dc5b-ac83-5470-8e22-e6605df80fcd | textbox | Date of inspection
eaa36b12-dd05-5534-9855-79c4bd6c0898 | textbox | Type of inspection
bc8f8242-678a-5cb5-861d-6fb07e05967b | textbox | Area of inspection
46b42bf2-dfd2-563b-b4d1-592bae41d634 | tickbox | Inspection report attached
bd8c65cf-b0da-509c-8292-66c15022fdc4 | dropdown | Inspection outcome | Fail, Partial Pass, Pass
181deb7a-6dd2-5d74-a387-ac01506142bf | signoff | Sign off
8cb9c790-21c9-53e5-8695-f5ca4f7805ae | checkpoint | All relevant observation closeout evidence attached here if applicable
747abae4-11b7-5603-bb0c-287329ec618b | textbox | Corrective action required
2c6f704e-07d1-5a29-8dd2-6f7c6e3d177f | checklist | Inspection - Council Inspection - Observations |  | Inspection - Council Inspection - Observations
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8cb9c790-21c9-53e5-8695-f5ca4f7805ae | checkpoint | All relevant observation closeout evidence attached here if applicable
747abae4-11b7-5603-bb0c-287329ec618b | textbox | Corrective action required
18c5bd05-2d67-5017-9393-467ee75973d8 | checklist | Structure - Footing |  | Structure - Footing
49216957-2608-563a-9792-0b986252bfb2 | section | 1. Pre-start
83757901-fdca-546f-bcad-2815b45f49a0 | checkpoint | QA for sub-grade and relevant services received
54063088-7028-5862-b40f-9b24c13359b7 | checkpoint | i. Site concrete allowed for in cut.
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
d0614c10-c0e2-595c-bfbd-30ddf23daf86 | checkpoint | Clear work Area
d5a60d48-2852-5e2c-b71d-61f4e94f4ef9 | checkpoint | Review construction drawings and set-out
bd20e1b6-099c-5153-9b02-4e654ce297f2 | checkpoint | Geotechnical Eng inspection report received and closed-out
e0e3e034-48f5-542c-b869-0979cf4177db | section | 2. Pre-pour
ea5dac00-8871-5c40-b286-895524a87f89 | checkpoint | Service trade sign off/QA
7397c715-a355-5a46-8f1b-2be638397502 | checkpoint | Waterproof sign off/QA
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
42644806-8464-59f7-8675-1027e59995f6 | checkpoint | Check RL levels
59e03791-9bf6-59e9-91f3-6ab4db6e23df | checkpoint | Check foundation width for propping
af5ce7c0-6bc8-5861-ad39-7f8c4f42d0ae | checkpoint | Sump position check and block-off foundation if clash
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
5cecb2ac-2dfe-5448-a033-863899c43e48 | checkpoint | i. Details checked
cb5b19ae-e20d-5147-b141-6afabdaf77e7 | checkpoint | ii. Starters, scabbling, cover checked
e2c36572-6712-5dfa-b2c4-13cb3edb10ba | checkpoint | iii. Clean formwork and ready to pour
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
9d0d3c67-d49e-5fe2-bebf-8c84348b2d43 | section | 3. Access/Safety
4fa20912-e3fc-500b-a6f3-72d3ed64eb40 | checkpoint | Clear access for trucks/pump
14bb3162-fda7-5348-b6c2-98e6ecb36712 | checkpoint | Exposed reo capped
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
b540541e-5122-5d39-808b-b1a6277a2164 | section | 4. Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
6fea4f0b-4513-5602-9160-8cd14439e710 | section | 5. Post pour
029328f0-831c-5bbc-9e78-fa17f1144320 | checkpoint | Finish
9d7176dc-6a92-5294-a339-a0abc31db422 | checkpoint | Levels
05d49877-405e-5ca7-ac4d-0474e72df349 | checkpoint | Starters
687f1a33-1091-559a-9ac4-966e91336963 | checkpoint | Pour QA received including dockets
0c008f59-a31d-5984-a392-5c1814864c75 | checklist | Structure - Footings |  | Structure - Footings
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
019fa518-72a3-504a-9265-f6c001d13afa | checkpoint | Geotechnical Eng subgrade inspection report received and closed-out
8a66bc2a-cd9c-560e-98b4-9912ff60901f | checkpoint | Check for clash
68b7f33a-f761-59dd-bb89-42c82a23dd59 | checkpoint | Upload drawings, detail /Mark up plan
98eac42e-af65-5dc4-b6f1-7666bee9eacc | section | Pre-Pour
ea5dac00-8871-5c40-b286-895524a87f89 | checkpoint | Service trade sign off/QA
7397c715-a355-5a46-8f1b-2be638397502 | checkpoint | Waterproof sign off/QA
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
35733a88-c483-5b5f-8112-d2ea94cc5f00 | checkpoint | Check levels
83c0a60c-3b33-5d9b-929b-f50bd9bdc1a4 | checkpoint | GN inspection- Prepour
584da06d-898d-523c-b9f4-22a18cbc177b | tickbox | Reo details checked
f7bd4f24-eb8c-5624-b00a-362ef018334b | tickbox | Drawings UpToDate, check for CAN’s
74cbf223-aa2a-5067-a82a-359ef2f7a809 | tickbox | Starters, scabbling, cover checked
53503008-e82f-5299-ab6d-bed590ee638f | tickbox | Clean formwork and ready to pour
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
7005594c-6828-5a1b-a3ed-02d1475a8a8a | checkpoint | Stop-End checked
1512ce3f-a5f9-5f73-99b9-c541f4bf7ce9 | checkpoint | Pour sequence mark-up
7c9274bd-3e73-5ee4-9ce5-02557985e458 | section | Access/Safety
4fa20912-e3fc-500b-a6f3-72d3ed64eb40 | checkpoint | Clear access for trucks/pump
14bb3162-fda7-5348-b6c2-98e6ecb36712 | checkpoint | Exposed reo capped
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
ea01ed4c-5af4-5250-b3ca-42fe03639dc7 | section | Pour
00734634-14a8-5ab1-b1e0-6036529a6e03 | checkpoint | Concrete Dockets and test report received
22afa579-4459-5e7b-97d7-64b112407ce2 | checkpoint | Curing agent
7b86cbdf-38d7-5d51-a5a0-dfd4a02ba50e | checkpoint | Pour QA received
53fca44a-0c9e-56e1-a718-d2c4c558feaf | checklist | Structure - Foundation (Crane base) |  | Structure - Foundation (Crane base)
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
d0614c10-c0e2-595c-bfbd-30ddf23daf86 | checkpoint | Clear work Area
83757901-fdca-546f-bcad-2815b45f49a0 | checkpoint | QA for sub-grade and relevant services received
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
b696ccbd-929c-567c-915a-7ade694694ac | section | Pre-pour
0ed53981-b780-52ed-b9ab-1aea7e8eef1a | checkpoint | i. attached mark-up
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
caa5a581-0247-5ae3-a6ae-ba78c45bbfd4 | tickbox | i. Check RL levels and benchmarks
0d929532-cb83-5ce2-9c4a-99f84d97ad7e | tickbox | ii. Check Dimensions and alignment
2db0a076-be0b-5fe3-b3ff-f9bd5b82720e | tickbox | iii. Check form ties and propping
105cfc37-7d29-5a64-9bf9-6df0b7ab4b1b | tickbox | iv. Overall Cleanliness and Seals and ready to Pour
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
f7d80b5f-94df-5167-a34e-ca29973e1737 | tickbox | i. Details checked
b8e8bf08-9677-5afa-abb0-4bfa03dba012 | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked
806dbf34-39b2-5a2b-a318-55c666bc54f2 | tickbox | iii. Check reinforcements size, spacing and cleanliness
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
7c9274bd-3e73-5ee4-9ce5-02557985e458 | section | Access/Safety
4fa20912-e3fc-500b-a6f3-72d3ed64eb40 | checkpoint | Clear access for trucks/pump
14bb3162-fda7-5348-b6c2-98e6ecb36712 | checkpoint | Exposed reo capped
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
ea01ed4c-5af4-5250-b3ca-42fe03639dc7 | section | Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
7568b665-16ed-5d54-a161-d84f77bf5e0b | section | Post pour
356dedcb-e6d5-5d90-9916-c74d8fdcc5e7 | checkpoint | Checks
9ab2fa7e-dbc3-5e17-ad7e-2852a62afc11 | textbox | i. Finish
0274814d-3ec3-5b97-8e1f-9f44841a5539 | textbox | ii. Levels
687f1a33-1091-559a-9ac4-966e91336963 | checkpoint | Pour QA received including dockets
4f97df4e-cbb7-5b32-a33f-022e34e20125 | checklist | Structure - In Situ Concrete |  | Structure - In Situ Concrete
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
0ffdcc56-bfde-5ea0-97be-42691ecfa405 | checkpoint | Toe footing sign-off/QA received
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
f4afdd8a-c977-5bbd-b2ce-5603d1cb8cd5 | tickbox | Details checked
cf7a75f9-6ea0-5598-ae03-be89634b63a1 | tickbox | Starters, scabbling, cover checked
efc2b0ba-3b9a-5e7e-b881-f150eed948f2 | tickbox | Clean formwork and ready to pou
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
1512ce3f-a5f9-5f73-99b9-c541f4bf7ce9 | checkpoint | Pour sequence mark-up
bf746d09-eb5d-52df-874a-daeedc1c4408 | section | Access/safety
3a763264-d599-5d85-ba06-d37b061e98ca | checkpoint | Access for sprayer/pump
e2145c56-21b8-5177-a720-be0c613ad7dd | checkpoint | Check TA
637c4992-cb53-5841-a981-f633a4419ad2 | checkpoint | Safe access to all areas of spray
14bb3162-fda7-5348-b6c2-98e6ecb36712 | checkpoint | Exposed reo capped
5a1035df-1113-56b4-9896-04ef53f25908 | section | Spray / Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
071e3a2e-1e26-5c0a-9c50-c7e2518a6125 | section | Post spray / pour
356dedcb-e6d5-5d90-9916-c74d8fdcc5e7 | checkpoint | Checks
ce5936fb-8e0e-5442-9801-fffd5c95e226 | tickbox | Finish
992922c9-907d-5778-9509-70522abec791 | tickbox | Levels
13a83971-9503-59b1-ac81-fa8a27a242b2 | checkpoint | Pour QA received including concrete dockets
a0b56229-b37b-58a6-b0fd-603e0af0cb20 | checklist | Structure - In Situ Concrete (RC beam) |  | Structure - In Situ Concrete (RC beam)
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
e0e3e034-48f5-542c-b869-0979cf4177db | section | 2. Pre-pour
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
ef670c48-dd41-58db-8dbc-dd945f5516a5 | tickbox | i. Check RL levels
59eddef0-00da-5f22-a2ab-30a529c82e76 | tickbox | ii. Check Dimensions and alignment
bdefe7ea-878a-596b-aeb3-149950ee53bf | tickbox | iii. Check form ties and propping as per design
80b1ee4d-6fd6-57a1-9ced-097408f47914 | tickbox | iv. Overall Cleanliness and Seals and ready to Pour
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
4e5d82a3-f934-5139-8283-73ce2bc1f737 | tickbox | i. Details checked
73f10c1c-277e-5c04-a6a9-7e931fee4a14 | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked
f5731e97-5ca3-56f6-8c3c-6af68c52ff6f | tickbox | iii. Check reinforcements size, spacing and cleanliness
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
bf746d09-eb5d-52df-874a-daeedc1c4408 | section | Access/safety
3a763264-d599-5d85-ba06-d37b061e98ca | checkpoint | Access for sprayer/pump
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
14bb3162-fda7-5348-b6c2-98e6ecb36712 | checkpoint | Exposed reo capped
ea01ed4c-5af4-5250-b3ca-42fe03639dc7 | section | Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
7568b665-16ed-5d54-a161-d84f77bf5e0b | section | Post pour
356dedcb-e6d5-5d90-9916-c74d8fdcc5e7 | checkpoint | Checks
96130089-885a-5f11-b19d-965309b31ae8 | tickbox | i. Finish
70429381-23b3-5218-8f98-dc19683a3743 | tickbox | ii.Levels
13a83971-9503-59b1-ac81-fa8a27a242b2 | checkpoint | Pour QA received including concrete dockets
701276f2-a11f-52a9-a1f3-8bab2f2f88c4 | checklist | Structure - In Situ Concrete (RC Column) |  | Structure - In Situ Concrete (RC Column)
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
1c27b406-c765-5886-bf0c-65c48bfa0973 | checkpoint | Footing sign-off/QA received
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
b696ccbd-929c-567c-915a-7ade694694ac | section | Pre-pour
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
8685dbce-2133-5d07-8902-bf433aa93781 | tickbox | i. Details checked
4aa88abf-c69b-52a2-bdfa-35c68e892550 | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked and cast in items
1902df8e-3afa-5e19-98df-9adcf3cb7f9b | tickbox | iii. Check reinforcements size, spacing and cleanliness
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
8300dac9-f555-52cb-a65e-86f5edebee79 | tickbox | i. Check RL levels and benchmarks
09c13d34-cb05-5209-aef2-cdcf91e72529 | tickbox | ii. Check Dimensions and alignment
ea780471-ca3d-5fad-b208-36d8c3777237 | tickbox | iii. Check form ties and propping
125efa4b-7a4d-5650-8cc1-1622edd5f5a0 | tickbox | iiii. Overall Cleanliness and Seals and ready to Pour
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
bf746d09-eb5d-52df-874a-daeedc1c4408 | section | Access/safety
3a763264-d599-5d85-ba06-d37b061e98ca | checkpoint | Access for sprayer/pump
637c4992-cb53-5841-a981-f633a4419ad2 | checkpoint | Safe access to all areas of spray
14bb3162-fda7-5348-b6c2-98e6ecb36712 | checkpoint | Exposed reo capped
ea01ed4c-5af4-5250-b3ca-42fe03639dc7 | section | Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
7568b665-16ed-5d54-a161-d84f77bf5e0b | section | Post pour
356dedcb-e6d5-5d90-9916-c74d8fdcc5e7 | checkpoint | Checks
8b38a299-6686-54d9-b015-fa67395355b5 | tickbox | i. Finish
b522fb61-afcb-571e-bf33-915efc435e9e | tickbox | ii.Levels
13a83971-9503-59b1-ac81-fa8a27a242b2 | checkpoint | Pour QA received including concrete dockets
6f571cfa-104d-56ee-a597-5f3c3501b936 | checklist | Structure - Insitu Piles |  | Structure - Insitu Piles
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
fa854218-a048-5817-83c1-54b624ca5e07 | checkpoint | Pile location marked and confirmed
54ab31e2-3a9f-562d-85f1-082c82283406 | checkpoint | Pile Cage dimension and specification checked
1ebc5b73-a0a5-50a2-b26f-fa90f8f31aac | note | Attach Docket
8d15bdc7-6a9d-5788-a315-1d9445e6898b | checkpoint | Pile drilling Card - refer details with the approved pile schedule
0f4d5277-af29-5182-963f-31c029e626fa | checkpoint | Engineer Inspection
68f07f27-6806-59b5-a0c8-81b428ff4da3 | checkpoint | Concrete pour & docket received
6319d10e-388f-56a5-957f-93be0b6f97c7 | checkpoint | Mill Certificate received
84dfdbd6-74cb-589b-a2ba-7e7cc09c960a | checkpoint | Surveyworks Asbuilt check
e5f74f48-5d22-5a5f-8bc4-8987f4773e3f | checklist | Structure - Insitu Piles Checklist |  | Structure - Insitu Piles Checklist
f098d60e-4676-578c-9a8d-80deb16efe0d | section | Preliminary Tasks
b3d569ed-9475-5d4a-8a00-520b3be74bed | checkpoint | Confirm Pile installation plan including methodology, material and equipment submitted
aad92bda-2664-5684-85d8-ac46105d5e3f | note | Sub-Contract signing
db54c794-a679-547e-8f2a-06c97dc155cc | section | Site Start Up Tasks
993f7154-158c-55db-b3e7-da0f3797b552 | checkpoint | Confirm full services and utilities check by subcontractor. Permit to work in place
1ff69a78-304f-5ff1-bef9-2327ab135518 | note | Prior to mobilization
c1557eda-c6c6-5a53-972b-5f240e7d9647 | checkpoint | Confirm an adequate site surface has been established for a safe working platform and check periodically once installation is underway.
274e4199-4609-5c0e-bcf0-af268e3c000a | note | 1 week prior and intermittently after
c9a8aff5-a8d1-56dc-abd4-ed27f241cdce | checkpoint | Confirm all piles to be set out in accordance with design requirements and appropriate procedures taken to protect adjacent services, structures etc.
39b65b1d-06eb-5451-9329-ee7c0c1ba814 | note | Prior to installation of 1st pile
aebcabcd-83f7-56b1-8b68-8398620da714 | section | Construction Tasks
fa35bf5b-07c8-53e8-b04e-366581b402ac | checkpoint | Confirm correct equipment is in place to check the verticality and position of rig, and that the mast is vertical in both axes prior to construction of each pile
8f90764a-26a5-54fd-ad0e-41520fa86710 | note | Prior to installation of 1st pile and periodically after
404d298a-0bfc-59dd-8585-f41f5058c7bf | checkpoint | Confirm pile construction has not been carried out within the specified distance of newly cast piles until concrete has attained the strength specified. Refer to installation methodology provided.
70b4018e-e24d-5d43-afcf-77c7e21de1c2 | note | Each pile
551ed97c-662e-5857-9c2d-aad66f1c3c2b | checkpoint | Confirm that pile depth has been checked at completion of boring. Toe level to at or below target depth
1d929ece-f6f1-5a54-b680-7583325fbe41 | textbox |  |  |  | m depth
31fa7856-713f-5a2e-8d38-fd9bc67d051c | note | Each pile
4d4d5018-a233-5740-a9ab-a74b2d6f001f | checkpoint | Sight delivery dockets to confirm all in accordance with engineers specification.
5b01ba3e-dffa-5ac4-a11f-64a1cae3968d | note | Each concrete delivery
9f7456ad-ed61-5135-bd28-5023a09fc11f | checkpoint | Confirm that subcontractor has checked that steel is not excessively rusted, cage has been sturdily constructed and that the correct cage has been installed for each pile.
7af01921-38cc-575c-8eb4-2f2e9815a008 | note | Each reinf. Cage batch
b65428ed-4893-591c-8951-b8b3b9957866 | checkpoint | Dimensional check, length, bar diameter, nr of bars. Make sure compliant with technical package.
61f8d457-3081-5c32-935f-e095776a9b7f | note | Random control check
b972867f-9d12-5d7d-8f84-cab4ff357594 | checkpoint | Check cage has been installed at the correct level and is centralised, ensure cover requirements are met. All as per specification and documents.
c9a27d0a-9e00-544c-af03-c5f0e10465a1 | note | Random control check
dfb8f96d-edde-5f8b-84a6-3f67108dce39 | checkpoint | Obtain Engineers site reports and signoff as required.
a8d66440-d4f6-56dc-ac2c-85f4087b08a3 | note | As per Contract
79798116-2c6b-530a-b879-212d2e0ee0ee | checkpoint | Confirm top of piles have been trimmed to elevations indicated on design drawings prior to construction of pile caps.
a1f5f14b-1587-5c9c-84f9-c2d8b78ae80c | note | After completion of installation
7ec868c7-8800-5dec-b031-e531b754a910 | section | Post Construction Tasks
107fb26b-e914-581c-8e05-9ce3b903d01e | checkpoint | Obtain as-built drawings to confirm grid layout is completely in accordance with all drawings and specifications (all within tolerance)
937c4592-d188-5c57-9c64-385a32ef5100 | note | After completion
38105a5a-6616-513b-ad47-5ac7e0e64fa3 | checkpoint | All data and records required provided to Structural Engineer after completion of pile installation (as per required contract specification). Include any Engineer’s site reports and sign off.
157dad8c-3e70-5546-b991-bcbd5b78a21e | note | After completion of works
98a16908-2d14-544c-a743-d173849dfecf | checkpoint | Dynamic pile testing (if required by the contract) carried out as per specification requirements. Written pile test results submitted for acceptance. Obtain sign off from Structural Engineer. (Attach certificate)
269a9bb3-f1c9-5664-a58f-17b5ac3698af | note | As per contract requirements
dfbbf48b-84ce-5c42-84f1-61520bcf07b8 | checkpoint | Confirm all inspections as identified on the cover page have been undertaken
06600b44-5607-5b42-b8d8-ad2c9d51181e | note | After Completion
3c34c2de-1e09-549d-81de-87ef21f35729 | checkpoint | Subcon QA received including pilecards and dockets
a33b8733-d04d-585d-b0b0-062e6660d79b | checklist | Structure - Lift Pit |  | Structure - Lift Pit
49216957-2608-563a-9792-0b986252bfb2 | section | 1. Pre-start
d0614c10-c0e2-595c-bfbd-30ddf23daf86 | checkpoint | Clear work Area
729d31bd-7f9d-5171-9fe3-cbee78014c1e | checkpoint | QA for sub-grade and relevant services received (if applicable)
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
bd20e1b6-099c-5153-9b02-4e654ce297f2 | checkpoint | Geotechnical Eng inspection report received and closed-out
e0e3e034-48f5-542c-b869-0979cf4177db | section | 2. Pre-pour
7397c715-a355-5a46-8f1b-2be638397502 | checkpoint | Waterproof sign off/QA
92757ad1-c7d4-5289-93e1-b6ca644f4f95 | tickbox | i. DPM including tapes and laps
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
5c0b3054-469b-5a0e-852a-4dfcd210ec41 | tickbox | i. Check RL levels
484ccc91-c87a-5d5a-852a-6ff7ab5f7053 | tickbox | ii. Check Dimensions and alignment
e1fa039b-647d-5d68-bba0-cc1bf9ffdaa7 | tickbox | iii. Check form ties and propping
07fe1de6-af71-50d4-aa88-4dbb505d32ce | tickbox | iv. Overall Cleanliness and Seals and ready to Pour
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
8e58b85f-60d0-5646-885f-7cfd1888f2d9 | tickbox | i. Details checked and shop drawings
9fdc42d8-3094-5449-b9ac-8a92ce69478a | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked
e38adc7c-ab46-5e17-a5b8-78140768f6c8 | tickbox | iii. Check reinforcements size, spacing and cleanliness
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
9d0d3c67-d49e-5fe2-bebf-8c84348b2d43 | section | 3. Access/Safety
4fa20912-e3fc-500b-a6f3-72d3ed64eb40 | checkpoint | Clear access for trucks/pump
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
b540541e-5122-5d39-808b-b1a6277a2164 | section | 4. Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
6fea4f0b-4513-5602-9160-8cd14439e710 | section | 5. Post pour
356dedcb-e6d5-5d90-9916-c74d8fdcc5e7 | checkpoint | Checks
99706468-0534-5ca0-941b-8e2c2bc50909 | tickbox | i. Finish
1f07d691-ac0a-5ce2-a552-485cc3bdba43 | tickbox | ii. Levels
687f1a33-1091-559a-9ac4-966e91336963 | checkpoint | Pour QA received including dockets
05d49877-405e-5ca7-ac4d-0474e72df349 | checkpoint | Starters
b6e55b78-990b-4b40-a700-c6c84e4e1c23 | checkpoint | Pour QA received including dockets
83a952cb-6ddd-50ac-9833-6b3a8d5fd5bf | checklist | Structure - Pole Retaining Wall |  | Structure - Pole Retaining Wall
49216957-2608-563a-9792-0b986252bfb2 | section | 1. Pre-start
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
d0614c10-c0e2-595c-bfbd-30ddf23daf86 | checkpoint | Clear work Area
d5a60d48-2852-5e2c-b71d-61f4e94f4ef9 | checkpoint | Review construction drawings and set-out
bd20e1b6-099c-5153-9b02-4e654ce297f2 | checkpoint | Geotechnical Eng inspection report received and closed-out
34b9f0a5-544c-5de3-bedc-dd447584c7df | section | 2. Set up/ Pre-pour
ea5dac00-8871-5c40-b286-895524a87f89 | checkpoint | Service trade sign off/QA
7397c715-a355-5a46-8f1b-2be638397502 | checkpoint | Waterproof sign off/QA
42644806-8464-59f7-8675-1027e59995f6 | checkpoint | Check RL levels
f40405f9-50ff-5295-a0fc-6dfaf5067aef | checkpoint | Subcon sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
8e7bec4b-3b08-5d71-a637-6c83dc3ef847 | tickbox | i. Details checked
8ff39581-c639-5c71-b7f4-0a428ffb4e4c | tickbox | ii. Verify materials and check poles for visible defects or damage
badded84-0aae-59a2-91e0-3b1d197072b7 | tickbox | iii. Poles are placed according to alignment and levels.
16407ff3-4abe-59c0-a6a6-9fa0fcfa095f | tickbox | iv. Ensure poles are secured and ready for pour
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
9d0d3c67-d49e-5fe2-bebf-8c84348b2d43 | section | 3. Access/Safety
a90d0cbd-ad6e-5c52-a84e-b20d6ef463fe | checkpoint | Clear access for trucks/pump/rigs
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
b540541e-5122-5d39-808b-b1a6277a2164 | section | 4. Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
6fea4f0b-4513-5602-9160-8cd14439e710 | section | 5. Post pour
7fbefc0b-46e5-53ce-b23e-e8b71da246d8 | checkpoint | Backfilling (200mm in layers)
9d7176dc-6a92-5294-a339-a0abc31db422 | checkpoint | Levels
687f1a33-1091-559a-9ac4-966e91336963 | checkpoint | Pour QA received including dockets
00bd4b87-8776-5a96-b947-7a0b71cff9d0 | checklist | Structure - Pre-cast Beams |  | Structure - Pre-cast Beams
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
743c28f1-59b4-596c-8be2-9ee7b9de5947 | checkpoint | Propping onsite and in place
5b123df3-406c-5492-89ea-844e111646cb | section | Delivery Inspection
08fddbb0-d3ca-5cef-be30-bbeb46c2b143 | checkpoint | Check for damage/defects on arrival
47830021-a611-5bcf-8c28-812b9cfcf786 | checkpoint | Measurement checks in line w/ IFC dwg
e8adbc84-b448-5119-bc35-7edd8200d05f | section | Installation
037c647d-7728-595c-9393-6fe62aede80b | checkpoint | Check alignment and leveling meet specs. before placement
2b42579f-66b2-5566-92a9-0bdb9a142077 | checkpoint | Ensure proper connection and anchoring
4ea49093-789d-5357-a79d-9c8b3dd7364c | checkpoint | Check positioning and orientation
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
5bf63d92-a32e-5105-abe3-7dabfaa8676e | section | Post installation
8467f920-054c-5b71-b7a6-ee73a0a8bdf8 | checkpoint | Verify final positioning and alignment
ceb235d6-094c-5f84-9bc0-5fb8078c8bc7 | checkpoint | Check for damage to the beams
0321a694-eb2c-53d7-ba72-6ff4491dcfa7 | checkpoint | Monitor and control grouting/backfilling processes
786efc0a-889b-5ba7-ae23-ca93140909e8 | checkpoint | Beam installation QA
9441fa5a-b70e-4b0e-bb44-e05425916c52 | checklist | Structure - Pre-cast Column |  | Structure - Pre-cast Column
b302cb36-c98f-4db5-82d6-3b63807ce9ec | section | Pre-start
57807cd8-218f-4e46-a651-bff3949a48a9 | checkpoint | GL and datum provided
fb225520-f337-4c73-ae54-3920d258bf00 | checkpoint | Confirm adequacy of curing for foundation
fe37dbb1-f521-4767-be14-45267b2f5f26 | section | Delivery Inspection
a063db32-3e6c-4167-8b35-c7126ee51be5 | checkpoint | Check for damage/defects on arrival
bdede2ec-d509-4e39-8e29-865d408d0c1c | checkpoint | Measurement checks in line w/ IFC dwg
9ea1a24b-0506-4576-be59-480c8f6bbdbd | section | Installation
ca0db676-9bb3-4ff8-abd4-98f72492e4f1 | checkpoint | Check alignment and level of the foundation before placement
f8840f49-9bc1-4e4d-83e3-48e3a1dff2e7 | checkpoint | Ensure proper connection and anchoring
da84db34-70c9-4915-847b-1978149a658c | checkpoint | Sample vertical check, positioning and orientation
d441748c-97a9-4d6b-aa37-8c6ef69bfeae | checkpoint | Inspect welds quality (NDT testing if specified)
e9c5f089-779e-4037-93b5-b5a93cdb088e | checkpoint | Monitor and control grouting or backfilling processes
3cb95410-6907-4e0d-bf02-bd67a1b8a2f2 | checkpoint | Structural Eng inspection report received and close-out
d21b1e04-0c39-43c7-b4df-2c161ef3af95 | section | Post installation
02b03a5b-742e-47a5-bdbf-298a0ee3ec50 | checkpoint | Verify final positioning and alignment
f3241261-de67-4233-bcff-b547ef96c691 | checkpoint | Check for damage to the columns
63297abb-8dc1-4297-93a1-99d07d666a19 | checkpoint | Column installation QA
37e7500e-7bea-502e-a02d-2e9848d3f4a2 | checklist | Structure - Pre-cast Panels |  | Structure - Pre-cast Panels
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
d829e616-3d5d-5abf-97d2-c2da0877315d | checkpoint | PrePour PCP inspection done
81b6bbde-5b47-5b98-ae4d-fb337534dab8 | checkpoint | Timber guides installed – including spacers
f63e3f87-f913-5ffa-b26d-8d27fb0dc3c3 | checkpoint | Deadmen on site and in position
8a66bc2a-cd9c-560e-98b4-9912ff60901f | checkpoint | Check for clash
6e6525c4-5ea1-52aa-b7df-b64b9dec3492 | checkpoint | Any CAN, Engr requirements
63adf318-d3b7-5a85-aa24-bab58f49593a | section | Delivery & Install
08fddbb0-d3ca-5cef-be30-bbeb46c2b143 | checkpoint | Check for damage/defects on arrival
b371a46d-bafb-58aa-bcdf-d432b5f03940 | checkpoint | Props & propping bolts onsite
03288ed7-6fec-59b2-a3b9-14c9a0b93c08 | checkpoint | Panels unloaded correctly
5d98fe66-28c2-5184-a6c6-1afcb1fe49cc | checkpoint | Measure internal dimensions
f0211ad1-a6ac-5d45-9d35-43a7dc081e8b | checkpoint | Panels Plumb & Flush
8c8cc9c4-a9e1-51d0-bec8-a0c9b541ff38 | checkpoint | Props Installed
5c093506-1560-53bd-ad0c-e8bc2f647001 | section | Grouting & Sealant
f7a5396f-8ca8-571b-a140-2739887c1964 | checkpoint | Drypacking done
c96fb444-857c-5a66-8e69-a2636d0e548a | checkpoint | Grouting pumped
6109c38d-4844-5efe-a97a-d8e23e5f6233 | checkpoint | Sealed between panels
2a7e5e91-b553-5e70-a594-53dd5a04ac86 | section | Post Checks
76ce6db7-5f22-593f-8499-eaf287f25b47 | checkpoint | PCP supplier QA received
a05f4dab-fe2a-5bba-a227-d217a80a8fa0 | checkpoint | Subs installation QA received
da0e7c76-2b1c-59d3-a1d4-8a5896fb296a | checkpoint | Grouting, Drypacking & Sealing QA received
9e59c084-2331-591d-b54b-04ac648c0c01 | checkpoint | Vertical check done
dc313256-b255-5b6d-a113-d3458199b608 | checklist | Structure - Retaining Wall |  | Structure - Retaining Wall
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
b0a3467b-2505-52d7-a9b2-5e1a73ced25d | checkpoint | Foundation QA
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
d4de1726-dfe1-53d8-b787-661284b41c8c | checkpoint | Check starters
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
aff55e30-d5e4-5cbb-be5a-48ebf30b57d7 | checkpoint | Confirm expansion joints
6ef3e858-cdc0-54da-97f7-c58a51788289 | section | During works
890e1c1a-4f1f-56c2-9263-91ce48cff0b7 | checkpoint | Check reo details
c621c5b0-8feb-551c-8e89-694b04dd9472 | checkpoint | Expansion joints
d7cacbe1-ae72-574c-84eb-4d1e3ea22317 | checkpoint | Bottom clean-outs for inspection
19f0d98f-e6d5-5b68-88d9-fd0615654bbd | checkpoint | Check set-out
dcc08292-b774-56b5-abd4-3c0692b97a11 | checkpoint | Pointing of joints
08728588-3612-58ab-964c-0206f0c27779 | section | Pre-pour (blocks infill)
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
1733e04a-f19f-5584-a5a9-7eb75ff06c37 | tickbox | Details checked
d8c18b7e-707b-5a67-afe9-58da36c6cba6 | tickbox | Any CANs
982c83d1-b708-5ac3-b00c-ed885b316b9b | tickbox | Starters, cover checked
f8b24e9c-b2d0-5f99-a8cd-42c63a3a96da | tickbox | Clean-outs free of debris and ready to inspect/pour
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
08ad1820-d715-568b-a2b1-b973d4735daa | checkpoint | Form work and clean-out covers in place
1512ce3f-a5f9-5f73-99b9-c541f4bf7ce9 | checkpoint | Pour sequence mark-up
40b22933-24bf-5029-acf3-280a8adaf82c | checkpoint | Max 2.4m lifts
7c9274bd-3e73-5ee4-9ce5-02557985e458 | section | Access/Safety
4fa20912-e3fc-500b-a6f3-72d3ed64eb40 | checkpoint | Clear access for trucks/pump
14bb3162-fda7-5348-b6c2-98e6ecb36712 | checkpoint | Exposed reo capped
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
7568b665-16ed-5d54-a161-d84f77bf5e0b | section | Post pour
356dedcb-e6d5-5d90-9916-c74d8fdcc5e7 | checkpoint | Checks
27c6c37a-5ec7-5664-87ab-a652d1114885 | tickbox | Finish
034ad420-9149-5e49-b324-c847c9642e0e | tickbox | Levels
32270be0-e164-556a-93f8-2b51de5a11b4 | tickbox | Starters
d90179a5-d0a0-59f8-8c97-e4c3bfe29113 | checkpoint | Block and pour QA received
07aa0b33-8ac3-53dc-b4a4-d36eac8f403e | checklist | Structure - shotcrete |  | Structure - shotcrete
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
494625ae-6bc1-534d-830a-6a654d0a8d6b | checkpoint | Review IFC dwgs
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
b696ccbd-929c-567c-915a-7ade694694ac | section | Pre-pour
5632e47f-48b9-599e-898a-6f2756835321 | checkpoint | Check surface preparations (adjacent wall protection)
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
a053b812-1f9a-5567-891f-0856b5eb84b9 | tickbox | i. Details checked
0297003d-fcce-59ed-8be7-4876944fbc9c | tickbox | ii. Any CAN, Engr requirements
5a82d12c-dcaf-5106-b87e-fda684f23168 | tickbox | iii. Scabbling, support bars, reinforcement quality
3e5ecf69-6791-58ec-a4e5-9c43f2683c19 | tickbox | iv. Check reinforcements size, lapping, covers and starters
5a0ee8e1-8fec-5550-8b20-0e61e012f745 | tickbox | v. confirm waterstop
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
bf746d09-eb5d-52df-874a-daeedc1c4408 | section | Access/safety
3a763264-d599-5d85-ba06-d37b061e98ca | checkpoint | Access for sprayer/pump
637c4992-cb53-5841-a981-f633a4419ad2 | checkpoint | Safe access to all areas of spray
b113baeb-3b41-50b6-a5e7-8651c6f9b403 | section | Spray
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
4112da04-7ea0-5af6-b85b-fbfb2951e821 | checkpoint | shotcrete placement timing (within 90 mins)
b92f2267-9d93-5f51-b68b-a7c50213d58a | section | Post spray
356dedcb-e6d5-5d90-9916-c74d8fdcc5e7 | checkpoint | Checks
e52b6789-823d-5af1-b530-ec7c2ebf4452 | tickbox | i. Finish
dba42595-6eef-5ed9-bfc5-9adb4a7da99c | tickbox | ii. Levels
13a83971-9503-59b1-ac81-fa8a27a242b2 | checkpoint | Pour QA received including concrete dockets
383520aa-2fe1-56b2-a6f5-fc0c93971ad0 | checklist | Structure - Slab on Grade |  | Structure - Slab on Grade
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
3a1ec8a4-d377-5859-8b50-bec5bebbdabf | checkpoint | Columns/GB sign-off/QA received
5059a1f0-2393-56ae-b4b0-560b6ba2ee5e | checkpoint | Services sign-off
2db17213-52f0-5fcf-82fe-bac71a4e8033 | tickbox | i. Electrical
5dafd3d9-ca0f-5e88-95c1-1b002d6ef3a0 | tickbox | ii. Fire
7a5cb49b-941c-5367-9781-1d50b178e975 | tickbox | iii. Hydraulic
bbb45f58-32b2-5d21-ad4d-ac5a73bc5821 | tickbox | iv. Comms and Fibre
64d4345c-8964-572c-8ce3-e87f602ae62d | checkpoint | Subgrade sign-off/QA received
b8181f2e-bd2c-5271-a8e7-38744f074124 | tickbox | i. Backfill and blinding
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
98eac42e-af65-5dc4-b6f1-7666bee9eacc | section | Pre-Pour
353474a4-5da7-5d43-85fb-4f4a8166573a | checkpoint | Waterproofing sign-off/QA
2da6d233-ca40-5197-b8b3-6a70ba58b2f4 | tickbox | i. DPM including tapes and laps
26241039-dfa7-5037-8cf3-fd1b17fff318 | tickbox | ii. Waterstop where applicable
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
d8bc15f1-9368-533a-b4de-67dc94a2345c | tickbox | i. Step down/ falls
0c082847-d6dd-5e98-a5a9-c2f4481df9bf | tickbox | ii. Ties, propping, seal formworks
01bbc981-d2d5-58cc-9b04-bbb0fc919928 | tickbox | iii. Seismic gap/expansion joints
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
af1066b9-f756-508b-b045-1a1110ff77b2 | tickbox | i. Details checked
c328f3ae-58d7-55bf-97b8-881d55c3cffe | tickbox | ii. Any CANs
600c7ed6-7566-55fe-8c80-fe17623ba846 | tickbox | iii. Check starters, scabbling, cover checked, thickenings
732e662e-c306-5272-9f02-7beb1257f24b | tickbox | iv. Reinforcement size, spacing, supports.
1b8ababd-265e-5b51-babf-f0b8eb13583e | tickbox | v. Clean formwork and ready to pour
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
fe8baad7-0db1-546b-89fd-595d776f32da | section | Access/safety/protection
4fa20912-e3fc-500b-a6f3-72d3ed64eb40 | checkpoint | Clear access for trucks/pump
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
caa6afbf-cb59-5cdd-a9ec-08bbbc4febfb | checkpoint | Panel and steel protection
cf419b06-9788-5950-ac6d-f97eaec0b538 | checkpoint | Skip clean and ready
ea01ed4c-5af4-5250-b3ca-42fe03639dc7 | section | Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
7568b665-16ed-5d54-a161-d84f77bf5e0b | section | Post pour
029328f0-831c-5bbc-9e78-fa17f1144320 | checkpoint | Finish
9d7176dc-6a92-5294-a339-a0abc31db422 | checkpoint | Levels
22afa579-4459-5e7b-97d7-64b112407ce2 | checkpoint | Curing agent
11ad770a-5f2c-5777-ad61-c2e46bff998f | checkpoint | Saw cuts within 24h of pour and slurry removed
13a83971-9503-59b1-ac81-fa8a27a242b2 | checkpoint | Pour QA received including concrete dockets
3c62919a-478c-5c11-88db-68a8cb8fac41 | checklist | Structure - Structural Steel |  | Structure - Structural Steel
3459d73a-db93-5fbf-8132-8ffb65193541 | section | Pre-Start
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
00d58ec9-57c5-532c-ade1-44da53a8cdb8 | checkpoint | Panel sign-off/QA received
cc575815-e213-59ce-93ff-c6ae22082a80 | checkpoint | Slab QA received
14558a3a-d0f4-5d53-b536-eefd0e152168 | checkpoint | Area clean/clear for access equipment
6e6525c4-5ea1-52aa-b7df-b64b9dec3492 | checkpoint | Any CAN, Engr requirements
7f29f79d-be84-5c98-91ce-eb2416a257ae | section | Erection
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
9a69e85d-69aa-5d6d-b5d9-aec8a4c3061d | tickbox | Welds
914bfb02-e308-57f9-826f-cd832af9781e | tickbox | Bolts
e6e31638-59f9-5938-b041-99004963d4a2 | tickbox | Tensioning
e42e0477-975d-5519-9f35-3d20a40f0deb | tickbox | Spot check RL’s and plumb
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
f182c449-3451-5c51-8d98-1ba832eb871d | checkpoint | Propping where required
d312932f-9aa1-5617-b011-4bb3aced30ae | section | Post Erection
2b694cd0-28dd-532a-be3b-9c6480238cb6 | checkpoint | Primer touch-ups
eda16b89-f9ce-5777-98ab-9930a317b6df | checkpoint | Steel QA received
7bb111a2-4a3f-5163-b1dc-40abf1a2e483 | checkpoint | Grout under columns
568b6503-b010-551b-9383-ec1fc87bff11 | checklist | Structure - Structural Steel - Column and Beams |  | Structure - Structural Steel - Column and Beams
3459d73a-db93-5fbf-8132-8ffb65193541 | section | Pre-Start
2dc5b541-1e83-5291-927f-4a0e3edbc0ce | checkpoint | RL for support beams/ Plinth
ba1f1018-27b2-5faf-b9d6-7542e3804742 | checkpoint | Plate support/ bolts surveyed and checked as built
cc575815-e213-59ce-93ff-c6ae22082a80 | checkpoint | Slab QA received
6966cb0a-e2b6-5c70-9e8f-12c4ccd3236f | checkpoint | checked tolerances, packing space
14558a3a-d0f4-5d53-b536-eefd0e152168 | checkpoint | Area clean/clear for access equipment
7760539a-2893-54c9-b7da-421865eba296 | section | Safety
47d4fc9b-e807-5a59-94bb-47bb83667732 | checkpoint | review weights and lifting gears inspected
88e7df1a-d370-59c7-a96b-489bf3d842e0 | checkpoint | taglines secured
9ecf7bb2-bffd-5316-bf45-a79fce14aa8e | checkpoint | Work space demarcation
7f29f79d-be84-5c98-91ce-eb2416a257ae | section | Erection
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
d5e46124-5087-5abb-a7e7-b9289c4e2258 | tickbox | i. Welds, bolts, plumb, alignment, etc. as per design
2062daf2-f74a-5bc5-b458-2ffc50f7d9d5 | tickbox | ii. QA test requirements such as Torque test, Welding test (NDT - UT/MPI)
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
32deefd2-9e36-5251-9e3f-ddacc8ba968e | section | Post erection
f182c449-3451-5c51-8d98-1ba832eb871d | checkpoint | Propping where required
2592d4a3-bf5e-5f4c-bb4a-291b867033c5 | checkpoint | Spot check RL’s and plumb
2b694cd0-28dd-532a-be3b-9c6480238cb6 | checkpoint | Primer touch-ups
eda16b89-f9ce-5777-98ab-9930a317b6df | checkpoint | Steel QA received
7bb111a2-4a3f-5163-b1dc-40abf1a2e483 | checkpoint | Grout under columns
02ef4e9a-78c6-5587-b2f2-7f00346e291d | checklist | Structure - Structural Steel - Roof, Mezzanine & Shopfront |  | Structure - Structural Steel - Roof, Mezzanine & Shopfront
3459d73a-db93-5fbf-8132-8ffb65193541 | section | Pre-Start
00d58ec9-57c5-532c-ade1-44da53a8cdb8 | checkpoint | Panel sign-off/QA received
3fe48b13-db76-5fa8-9a04-1f905de94929 | checkpoint | Check shopfront opening with Lancom - Key members location
9d78fbf8-8c87-5b9f-a959-ec3a979dcb55 | checkpoint | Slab QA received (not required for roof steel install)
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
14558a3a-d0f4-5d53-b536-eefd0e152168 | checkpoint | Area clean/clear for access equipment
7f29f79d-be84-5c98-91ce-eb2416a257ae | section | Erection
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
00ed825a-c6f5-5270-bf27-1e7703c2fc11 | tickbox | Welds, bolts, tensioning, etc. as per design
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
d312932f-9aa1-5617-b011-4bb3aced30ae | section | Post Erection
f182c449-3451-5c51-8d98-1ba832eb871d | checkpoint | Propping where required
2592d4a3-bf5e-5f4c-bb4a-291b867033c5 | checkpoint | Spot check RL’s and plumb
2b694cd0-28dd-532a-be3b-9c6480238cb6 | checkpoint | Primer touch-ups
eda16b89-f9ce-5777-98ab-9930a317b6df | checkpoint | Steel QA received
7bb111a2-4a3f-5163-b1dc-40abf1a2e483 | checkpoint | Grout under columns
40708056-19db-5e80-8c55-45b95a26877b | checklist | Structure - Suspended Slab |  | Structure - Suspended Slab
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
1128355e-0aec-55ab-97be-7b323d56b6d0 | checkpoint | Beam/Precast/Steel QA/ signoff
dae58761-c428-5149-a3bb-c8e30bccf6c5 | checkpoint | Edge protection in place
ac17dada-014f-50f0-8210-1bac22952b37 | checkpoint | Access provided
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
b696ccbd-929c-567c-915a-7ade694694ac | section | Pre-pour
014b7d51-b3aa-5424-82e7-f3753dd47a9f | checkpoint | Propping sign-off/QA received
aec5b457-d09f-5039-a492-8a871a35a266 | checkpoint | Services marked out and double mesh
353474a4-5da7-5d43-85fb-4f4a8166573a | checkpoint | Waterproofing sign-off/QA
1caa78bc-8ed9-557b-8f33-1ec4503824f2 | tickbox | i. DPM including tapes and laps
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
4b9b77da-c578-5a93-adee-3a3e1885bd45 | tickbox | i. Step down/ falls
855ba951-2aa7-5f5f-aa2a-8b0a785a5985 | tickbox | ii. Ties, propping, seal formworks
f3290555-49ca-5b51-8fcc-13585372ce5b | tickbox | iii. Seismic gap/expansion joints
d7c37fa0-0f71-5b51-97d3-bcf30fb83166 | checkpoint | Reo sign-off/QA received
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
a21af35b-d2f6-5044-94b3-f053e1cf4cb4 | tickbox | i. Details checked
2ed8943e-837f-5cf8-9056-06772db590c6 | tickbox | ii. Openings checked
17a02416-3245-5104-8fb5-04b101f39fab | tickbox | iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
9b619e67-ccb0-5e99-abc8-014d903de047 | tickbox | iv. Clean and ready to pour
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
7c9274bd-3e73-5ee4-9ce5-02557985e458 | section | Access/Safety
4fa20912-e3fc-500b-a6f3-72d3ed64eb40 | checkpoint | Clear access for trucks/pump
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
ea01ed4c-5af4-5250-b3ca-42fe03639dc7 | section | Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
7568b665-16ed-5d54-a161-d84f77bf5e0b | section | Post pour
029328f0-831c-5bbc-9e78-fa17f1144320 | checkpoint | Finish
9d7176dc-6a92-5294-a339-a0abc31db422 | checkpoint | Levels
54216289-40a6-5ca2-bc12-31adfc701dc6 | checkpoint | Curing agent and canvas protection (standby)
9d39a9f0-1447-589d-ac56-e4ccb0fcea4e | checkpoint | Pour QA and dockets received
7647ec05-22fc-5a59-8d78-dd149a56486e | checklist | Structure - Suspended Slab - comflor |  | Structure - Suspended Slab - comflor
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
82f7c537-238c-5264-aaee-b8e26cbcb061 | checkpoint | Beam QA/ signoff
dae58761-c428-5149-a3bb-c8e30bccf6c5 | checkpoint | Edge protection in place
ac17dada-014f-50f0-8210-1bac22952b37 | checkpoint | Access provided
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
b696ccbd-929c-567c-915a-7ade694694ac | section | Pre-pour
d81a8251-d1db-57e7-bf9f-59ac33231b1c | checkpoint | Comflor sign-off/QA received
d3910e96-7c62-5bd0-b1e2-e015d3c01040 | tickbox | i. Stud testing completed
014b7d51-b3aa-5424-82e7-f3753dd47a9f | checkpoint | Propping sign-off/QA received
aec5b457-d09f-5039-a492-8a871a35a266 | checkpoint | Services marked out and double mesh
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
82d8dbd1-2a07-57ad-8159-dad012c040e7 | tickbox | i. Step down/ falls
19f28f3b-ec5c-5841-84ac-a88deb13f20a | tickbox | ii. Ties, propping, seal formworks
d7c37fa0-0f71-5b51-97d3-bcf30fb83166 | checkpoint | Reo sign-off/QA received
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
d1542daf-d937-5502-a197-deb99b3d7e66 | tickbox | i. Details checked
22227eb9-bf7f-56e8-8da3-62a88b5829d4 | tickbox | ii. Openings checked
2f2e36ca-b90e-55e0-9539-6d4ecfdfb2af | tickbox | iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
4a43084e-b270-544f-9f77-a82293ef9f96 | tickbox | iv. Clean and ready to pour
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
7c9274bd-3e73-5ee4-9ce5-02557985e458 | section | Access/Safety
4fa20912-e3fc-500b-a6f3-72d3ed64eb40 | checkpoint | Clear access for trucks/pump
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
ea01ed4c-5af4-5250-b3ca-42fe03639dc7 | section | Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
7568b665-16ed-5d54-a161-d84f77bf5e0b | section | Post pour
029328f0-831c-5bbc-9e78-fa17f1144320 | checkpoint | Finish
9d7176dc-6a92-5294-a339-a0abc31db422 | checkpoint | Levels
54216289-40a6-5ca2-bc12-31adfc701dc6 | checkpoint | Curing agent and canvas protection (standby)
9d39a9f0-1447-589d-ac56-e4ccb0fcea4e | checkpoint | Pour QA and dockets received
86406f25-03ee-5196-8e3c-7fb38a2db29b | checklist | Structure - Toe Footings Checklist |  | Structure - Toe Footings Checklist
1eaebdae-e82b-5b86-a8f4-934478434df4 | section | Pre-start
71eaca1a-dc8e-548e-8e84-c7b14ddea80f | checkpoint | Panel QA received
584fe501-a006-5092-ac63-d1af5e79e6f3 | checkpoint | GL and datum provided
40e67c6b-943e-5fa7-baca-bab527678f9a | checkpoint | Backfill to foundation level completed
a4bdb730-9a6e-5f96-acaa-1639a52392f5 | checkpoint | Clean work area
98eac42e-af65-5dc4-b6f1-7666bee9eacc | section | Pre-Pour
ea5dac00-8871-5c40-b286-895524a87f89 | checkpoint | Service trade sign off/QA
354d54d7-8be6-5a3f-b98c-5cf9d2df7760 | checkpoint | Formwork signoff/QA
7397c715-a355-5a46-8f1b-2be638397502 | checkpoint | Waterproof sign off/QA
9c0ffa72-d50a-5f3a-b596-d82304623105 | checkpoint | Photo of water bar installed (TBC if required)
29003858-bc73-5b0b-9166-4d1ba811ad44 | checkpoint | DPM where required
a4c8e8e0-d927-5e93-8883-00e01d59bbac | checkpoint | Reo sign off/QA
3e03c72b-e399-5793-ab7c-37b149dcda4b | checkpoint | GN inspection
573a38aa-3f26-5e3e-b1f2-114cdf7850c4 | checkpoint | Details checked
1c16575b-5e26-56fe-b2d4-d6473c70d7de | checkpoint | Any CANs
bfcdafcd-7206-567f-b415-36c280948736 | checkpoint | Starters, scabbling, cover checked
405dc3d2-123a-5226-a7fa-393bbe016923 | checkpoint | Clean formwork and ready to pour
da6d1d24-3c56-5bc2-b09a-50108f7969fa | checkpoint | Structural Eng inspection report received and close-out
73d3bac0-a81a-59da-bcbf-d7b1b924082f | checkpoint | Council inspection report received and close-out
1512ce3f-a5f9-5f73-99b9-c541f4bf7ce9 | checkpoint | Pour sequence mark-up
7c9274bd-3e73-5ee4-9ce5-02557985e458 | section | Access/Safety
4fa20912-e3fc-500b-a6f3-72d3ed64eb40 | checkpoint | Clear access for trucks/pump
14bb3162-fda7-5348-b6c2-98e6ecb36712 | checkpoint | Exposed reo capped
2f19fa60-d578-5d21-89cb-318d82ce6c8e | checkpoint | Safe access to all areas of pour
ea01ed4c-5af4-5250-b3ca-42fe03639dc7 | section | Pour
031feda4-8603-5c7c-bec4-2feb2345ed9b | checkpoint | Confirm mix
4a11825a-463c-5da5-9111-4246f335000b | checkpoint | Confirm concrete is being tested (slump and cylinders)
72e2440b-1e70-5004-80be-0ead8b0abc22 | checkpoint | Weather recorded
e9cda004-e5f8-503a-881e-37bef446cf38 | section | Post Pour
029328f0-831c-5bbc-9e78-fa17f1144320 | checkpoint | Finish
9d7176dc-6a92-5294-a339-a0abc31db422 | checkpoint | Levels
05d49877-405e-5ca7-ac4d-0474e72df349 | checkpoint | Starters
687f1a33-1091-559a-9ac4-966e91336963 | checkpoint | Pour QA received including dockets

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
07f42aca-ba0a-4271-b914-38a859c25bd7 | checklist | Facade - Balustrades |  | Facade - Balustrades
a38c9d69-bb14-42c3-b626-414d37cd489e | section | Pre-start
c33b94e8-e517-46f4-980b-20f696924363 | checkpoint | Clean work area
604c2c64-8561-4aad-b464-815a02470198 | checkpoint | Verify site is prepared according to approved design
c24eeda4-1eee-460f-bb6b-2a5227e42d01 | checkpoint | Glass Panels: Verify thickness, type (laminated/tempered),
1d06c243-fab7-4f31-955f-f108598d9f03 | checkpoint | Aluminium Panels: Confirm grade (6063 T6), powder-coated finish, and corrosion resistance
e0da2944-3a11-4ddb-8624-6a314211c348 | checkpoint | Slat Profile Balustrades: Ensure proper slat spacing and use of stainless steel screws (grade 316)
b1e61032-0352-495d-939f-6de6bd7232a1 | section | Installation
d277101a-25d6-422f-b07f-dbcb48492bc1 | checkpoint | Confirm Handrail height
0bfd1e7c-8262-4aec-94dd-4fd476e4edaf | checkpoint | Confirm Baluster spacing requirements
2eb950fa-050f-4b26-8305-1c1218dbae19 | checkpoint | Ensure proper Anchoring, appropriate screws, botls, connectors.
fbac98bd-8ecc-43ee-a58e-c303c432ba23 | checkpoint | Ensure sealing with Sikaflex® AT-Facade or equivalent sealant for weather and air protection, as detailed in the specifications.
1ab84376-adc1-4d63-9a5b-7085df715ca8 | checkpoint | Architectural Eng inspection report received and close-out
be5a66e7-4c6d-4683-a616-df2d340a3777 | section | Post Installation
706f0251-8bdb-41a5-b25e-40f92c090d57 | checkpoint | Ensure required documentation. (test reports and compliance certifications provided)
3c4683aa-8142-494b-9fa1-40ef66f23882 | checkpoint | Conduct comprehensive walkthrough to verify overall quality and compliance
1efc0df0-9be6-4c9c-86da-5f52913170a4 | checklist | Facade - Eaves and Roof |  | Facade - Eaves and Roof
ec0476b7-babb-45ed-b0bf-31ad5d09d373 | section | Prestart
f4662a67-729d-4085-94bc-ba6a5c624a91 | checkpoint | Steel & panel QA
c773c752-8291-49ba-b64d-46b64892aa19 | checkpoint | Verify roofing system specifications and requirements.
f38f8347-1439-4200-82dc-16085338bbd6 | checkpoint | Confirm delivery and quality of roofing materials
8db9f2a4-6b31-4130-bc04-3f486eebfb8d | checkpoint | Ensure proper site access and safety measures.
11cd5b57-fdaf-4ab4-891a-caaf980f32b4 | checkpoint | Review plans for vents, electrical, mechanical, and other service penetrations.
03389759-05d7-4c29-9491-2bc2b1029297 | section | Eaves
86815223-4118-464c-b624-194e09b17636 | checkpoint | Framing - DPC between Timber and Steel
36a633f0-a6b6-4efc-8531-a0dc3a5aaa94 | checkpoint | Framing - Timber frame fixings to steel frame/purlins
f4becfe1-40fe-42f7-b85f-c22872fdd17b | section | Services
df12b7a3-0f16-478b-8873-e68c2349fa2d | checkpoint | Services signoff/QA including nogs
371cc94b-5f6c-5a1c-95c6-612d7920d36b | tickbox | i. Vents
65aef3aa-0ba0-5b16-ab83-fc5181c11dee | tickbox | ii. Electrical
1f5df509-a7f6-5dcb-8925-f4494c2acaf1 | tickbox | iii. Mechanical
bbd93859-dd4b-5e76-9f32-350329c4c0fe | tickbox | iv. Others
7dbab5cd-3713-4aa1-93ec-b3c5631d91e6 | checkpoint | Roof Installation
09047f1d-6c19-4d26-a438-43603edc0823 | checkpoint | 1. Underlayment and Insulation:
2072fbd3-e897-4e0e-811c-2ee847d9ba64 | checkpoint | Make sure roof underlayment is installed as per the manufacturer’s instructions.
da1c0a5c-36cf-4c35-93d0-aecb4995097a | checkpoint | Insulation is installed evenly with no gaps.
d0ad1182-d951-4e14-8d11-b650fb645c81 | checkpoint | Confirm vapor barriers and moisture controls are in place.
e119ce4f-9936-4992-b4a5-4eaca9b75dff | section | 2. Roofing Membrane and Flashing:
c4d04c2b-c1fc-45fc-8b85-533bb3cbc220 | checkpoint | Check the membrane is fully attached and seams are sealed.
46ecd61f-f47c-4ce1-9d09-be2ec967c487 | checkpoint | Ensure flashing is installed around edges, vents, and chimneys.
73d2373f-d1c7-4926-a461-048dc1cc76dd | checkpoint | Inspect parapet caps and joints for correct sealing.
1062a9cd-e3a9-4c5b-ad94-8cbedabedf38 | section | 3. Roofing Panels:
2f726a8a-c6c4-494a-8876-f321a29d01f5 | checkpoint | Panels are aligned and fastened securely.
b116a65c-a566-479f-8494-f95199f55db6 | checkpoint | Closure strips and fasteners are correctly installed.
fec9142e-febd-4ba6-b3fb-d675a7d50d9e | checkpoint | Roof edges, ridges, and valleys are properly sealed.
bd6e71ae-8b07-4880-be38-0a16535e0dd4 | section | 4. Gutters and Drainage:
2f1dcbaa-0d12-4ad1-8d2a-00ae4ca0ed7c | checkpoint | Internal gutters and downspouts are securely attached and sloped for drainage.
1beaf3a1-6c96-4d9a-8ece-55365bdc1025 | checkpoint | Gutters are free from obstructions.
05c31952-df50-4c90-a7eb-f01b8859d741 | checkpoint | Waterproofing around gutters is properly sealed.
31e71a8b-40cb-4d02-b4c4-0080251c43d9 | section | 5. Skylights and Roof Penetrations:
dec55b91-74a7-424c-8f51-b1653fe1ff12 | checkpoint | Skylights and roof hatches are sealed and flashed properly.
72a1ae2d-2b2d-40d8-89e1-d46745a8f258 | checkpoint | Check for waterproofing around all penetrations.
04c3b4df-1746-4cc3-96be-c9da6ea6b416 | section | 6. Fasteners and Fixings:
a7efa68b-ddb1-4b0c-bcae-8d2e69558cb2 | checkpoint | Correct type and size of fasteners used, installed securely.
646cc253-4fb8-4c89-8cdd-12084dd19630 | checkpoint | Ensure no loose or missing fasteners.
75549ad6-f02c-48d8-8727-5333472a91b2 | section | 7. Safety Systems
d705dcd6-23e2-4b99-9a01-6506714f34f7 | checkpoint | Inspect installation of safety balustrades and maintenance walkways.
638907c1-966e-4304-838f-78a7e6b963c4 | checkpoint | Ensure abseiling points and plant screens are correctly installed.
dc35dcbe-42c3-402c-bc05-aa7ab486d73d | section | Council Inspection
e9fdd607-32de-434d-99c9-29ddc0cf15b1 | checkpoint | Roof framing inspection report received and closeout
c65b5e0c-0049-4848-823b-353f5e93240f | checkpoint | Wraps inspection report received and closeout
e82a821a-10ca-4304-88e8-2465fea8314a | checkpoint | Roof Substrate inspection report received and closeout
c5bcd9ab-7676-4aaa-b7fa-42be8ebde14d | checkpoint | Roof/deck membrane inspection report received and closeout
11491a66-74b4-4c4d-a6de-76030ea9e568 | section | Post-Installation
847582e0-f453-41cf-98ad-568b80353a04 | checkpoint | Inspect all flashings and sealants for integrity and coverage.
8f46baab-1b7e-4b3f-877a-d401e109dd7a | checkpoint | Ensure removal of all debris and waste from the roof and site.
cea07d08-2c7c-46f0-8132-dcb64e058759 | checkpoint | Perform water test to check for leaks and proper drainage.
0c3d5e22-6ee5-4b11-a854-a2fe501aa929 | checkpoint | Roof signoff/QA
4ff83eb9-1969-4b87-af7b-6d0471bd35a0 | checklist | Facade - External Cladding |  | Facade - External Cladding
dcd99bd0-b094-453d-8203-f74798ac8cb1 | section | Prestart
b43ca0bb-43c9-4c48-a36a-97a178dbf902 | checkpoint | Verify materials specified in the plans match the delivery (e.g., timber, cladding systems, insulation).
1b86359d-9d91-4fa8-99f7-663ff1d0b2b4 | checkpoint | Verify that materials are stored correctly to prevent damage.
765ad361-bcb4-4ba5-9cb0-282436cda079 | checkpoint | Check that the site is safe and accessible for installation.
bbdf1fcd-c34c-4703-9af0-35810fb09771 | checkpoint | Confirm the area is clean and free of debris.
2f8d69f8-24f8-4d60-9a6c-a104ecd2a35c | section | Pre-Installation
260113ad-ab70-45cc-afed-0e5997b64d8c | section | Substrate and Framework:
389407aa-c78a-4889-95e3-bf4a00654685 | checkpoint | Inspect timber or steel framing (e.g., 140mm timber framing, 92mm steel stud)
48b33dac-f7d0-48c8-a2ce-8126caf6bc65 | checkpoint | Confirm the installation of GIB® Weatherline® or other specified internal linings as per dwg.
174d803e-a421-49f7-b389-3bcc40226e4c | section | Cladding and Insulation:
f1f1b015-d6b8-48eb-8e8b-8fc298389dc2 | checkpoint | Check that insulation values, (e.g. R3.2 insulation for wall types) are installed as specified
6e3b4a0c-e5d7-4dd5-8c9a-9789bdcc9575 | checkpoint | Ensure all substrate surfaces are clean and ready for cladding installation, with proper
f963deb2-f190-4f34-a1f2-c4aff55fb162 | checkpoint | Preparation of moisture barriers and flashing.
c1c83bc9-e0ef-44e7-b4ea-9d40bd97921b | section | Fire and Acoustic Compliance:
fd3ee460-7d21-4786-8409-a24c61fb7df8 | checkpoint | Review fire rating and acoustic insulation requirements, (GIB® FYRELINE for fire-and GIB
8313b28e-6191-445d-a5a7-481f6cc6883d | checkpoint | Ensure fireproofing systems and expansion joints are correctly positioned as per drawings.
5f442ea0-d193-4c45-857b-1a245bf77074 | section | Council Hold Points
bc95e417-d68c-4561-949e-0d8170597f00 | checkpoint | Council inspection wall frame and underlay report received and close-out
0a027630-5e7a-443d-90bc-2485659f1801 | section | Installation
143b7cba-4a98-4440-a300-9cb10e262f64 | checkpoint | Cladding Panel
4c215860-0a29-4b84-9378-ca0ed9153949 | checkpoint | Verify that cladding materials like 3mm powder-coated aluminum and 55mm STOPOREN
8ae28e93-1dae-4f1c-9d2a-33dd60641ce8 | checkpoint | Check for uniform panel alignment, consistent spacing, and proper attachment to the
f30db2e1-40ab-47d2-9237-478e4358dc48 | checkpoint | Confirm that the cavity behind the cladding (e.g., 20mm cavity for some wall types)
d9bce4de-f47e-4fb9-9514-595b0e8dfef6 | section | Fixings and Anchoring
c64db800-1536-495a-80fd-2b31c4df9328 | checkpoint | Ensure all fasteners, anchors, and fixing systems are secured according to design.
21822bee-10c2-4a79-8dda-2a6a2aa5eef4 | checkpoint | Check that fixing points are properly aligned with the structural framework
b689cea2-5b53-4ac4-b6bd-90cd5d0d3358 | section | Sealing and Flashing
6b71e975-b856-435b-a9af-6c81c8d00b74 | checkpoint | Inspect sealant joints, weatherproofing membranes, and flashing around penetrations
72e2bb67-1281-45e0-a079-f5e8f10c7b83 | checkpoint | Ensure that all exposed joints and edges are sealed to prevent water ingress
5f893388-56ba-4d41-ab39-5d748ef9ce55 | section | Council Hold Points
163d300a-b345-417b-b267-d58dd81b75b4 | checkpoint | Council mid-installation inspection for cladding, insulation, and internal lining received and closeout
196cfef0-f457-4f4c-915d-172a3b0c0cc2 | section | Post-Installation
6becd5b2-6f2e-4c7c-8df3-b58f7441ea1b | checkpoint | Conduct a thorough inspection of the completed facade cladding.
affd8c8f-39b0-43a3-b3f8-62a5cefa32bc | checkpoint | Ensure all cladding is securely fixed and aligned.
2d2c0548-c7a9-439a-b67c-f576ff747741 | checkpoint | Check that all joins and seals are properly completed.
85e270a8-299b-4e0e-8806-9e09b8633e6d | checkpoint | Confirm and inspect correct primers and coat numbers for any paint finishes as per specification
5206db6e-1a16-459a-bc3d-574094aa79fe | checkpoint | Subcontractors QA received
7e57f231-fd80-4370-a8b8-d1db4de0ea3a | section | Council Hold Points
3f3aa6a7-2e92-438f-85b7-42d63b5e8d12 | checkpoint | Arrange a final inspection with the council to sign off the completed work.
e600696e-9d37-4706-9b87-4ab0bc9675b0 | checklist | Facade - Glazing and Doors |  | Facade - Glazing and Doors
167a1001-8c2e-4123-bd89-2d6ae99fbd46 | section | Pre-Start
bffc2e0f-52d8-40e1-90c1-3fdb84ba98d8 | checkpoint | Confirm all relevant drawings, schedules, and specifications are available and reviewed.
4b5780b1-2838-4fa2-99f9-cebb96224bf8 | checkpoint | Verify glazing and door specifications from the schedule.
958c1970-18c0-45bb-9176-e50fdb97eee1 | checkpoint | Ensure the site is prepared and clear for installation.
c19257a2-c3b4-445d-b965-b43ac80018b2 | checkpoint | Check for adequate access for delivery and installation of glazing and doors.
641e8b05-a438-42c0-b6df-b9d90e640dc1 | checkpoint | Verify that all required materials (glazing, doors, frames, seals, etc.) are on-site and match the specifications:
b0d4ab1a-46c5-4f23-ac91-8b17ac8843d6 | section | Installation
709ffc8e-b3cb-4af8-b44c-7e68c233354c | section | 1. Glazing
1c263a19-a5af-4922-acd6-46282c255343 | checkpoint | Check the frame for correct alignment and secure fixing.
0f85fc14-d535-4fdb-add1-da002972466b | checkpoint | Inspect glazing materials for any damage before installation.
f6e62098-6fb4-4d93-bc39-9bceaf8a21d7 | checkpoint | Ensure glazing units are installed with appropriate spacers and seals.
3c4c4953-49a3-4bc7-a0cd-5b423c817b08 | checkpoint | Ensure the steel framed fire-rated window system meets fire rating requirements.
356f76da-746a-4c11-b143-7afc7bb82f6c | checkpoint | Verify the glass type and thickness (e.g., acoustic, fire-rated) is as per the glazing schedule​
97b286b8-61b7-4cc0-93bb-114aa0ccf76c | section | 2. Doors
72eafe76-cfa4-4305-9a2a-f552dd8d1c91 | checkpoint | Ensure frames are correctly positioned and securely fixed.
90f429cc-0e2f-4556-a969-62dbd8df313c | checkpoint | Check doors for damage before installation:
27c7bd1f-e130-4c18-b7b9-054d480eda07 | checkpoint | Check roller doors for damage before installation.
701b0fd1-6c46-43cc-931a-4a667e7f5793 | checkpoint | Confirm that fire-rated doors meet the fire rating requirements
2338aa48-2054-4a51-bdf6-56082c2959c6 | checkpoint | Verify fire-rated and egress doors meet specified requirements.
945dc4f4-255b-49d3-920b-602a6b4ad26d | section | 3. Seals and Flashings
2b0d2b27-56cd-4d89-9165-70b822d98baf | checkpoint | Check that all seals and flashings are installed as per specifications.
8bc12b5a-12f9-41ac-9699-16bf28caf572 | checkpoint | Ensure water and air tightness are maintained around all openings.
29b21e41-45bd-4f43-ac89-973075c5617b | section | 4. Hardware and Operation
ae62b7c7-c778-49ef-ace6-a96f67cbc02d | checkpoint | Ensure that all hardware (e.g., locks, handles) is installed correctly and operates smoothly.
256b93f0-d195-4e53-a22b-b0614f1a6ee0 | checkpoint | Verify that doors open and close smoothly without obstruction.
7514e4e8-c1d4-44d2-a32c-0e40d31242af | checkpoint | Ensure locking mechanisms function correctly.
791a2113-841d-4634-9290-bbd173a7275b | section | Post-Installation Checks
9f9fa1a6-484f-402c-b71d-c825f86bf4dd | checkpoint | Check for any signs of damage or defects.
0e2669d6-6675-42dd-8ea8-51b80459f73b | checkpoint | Test all doors for proper operation, including roller doors.
08229551-9a71-4ec0-9aec-458ed98da306 | checkpoint | Verify that glazing provides the required performance (e.g., thermal, acoustic).
b152465d-fb2f-41c1-96af-811d869507d3 | checkpoint | Remove any protective films from glazing.
2c8e11ab-b92c-42c0-aaa4-01a1ecb6de6f | checkpoint | Installer QA received
246e1b17-9bdd-45dd-964f-e3e55e443431 | checklist | Fit-out - Ceiling |  | Fit-out - Ceiling
4d1e1c7e-f9aa-4394-9cbc-b1b3c5f4fd96 | section | Prestart
99993ee3-3491-4804-9fba-2491f5c551b4 | checkpoint | Verify materials on-site comply with specification
a85771ee-f2d0-4dab-a8b4-a7de0d449357 | checkpoint | Check proper labeling on materials
58b43f83-589c-47a7-9732-f4db4d4d9458 | checkpoint | Check site condition for suitability (e.g. cleanliness, weather)
c90f98b6-04c2-4f7d-9d2f-0caa7c8c660c | section | Safety
fbd3550d-8d66-45b5-82b7-86aee238c459 | checkpoint | Ensure all necessary safety equipment (PPE, scaffolding, fall protection)
d964ead3-35f5-471f-b6b6-642e16a985ed | checkpoint | Ensure the site is clean and ready for installation.
f59e658c-77a6-4ebe-8d82-ef982d15b69c | section | Installation
6a22e29f-0667-4739-97e7-e45e5fcdeb3a | section | 1. Framing & Structure Check:
7c8cf21e-7d16-4710-a630-81bbaedbc015 | checkpoint | Ensure steel framing for plasterboard fixing is straight, aligned, and securely fixed​.
552fd9d2-6743-4286-ab54-d9e948794333 | checkpoint | Verify fasteners, brackets, and support hardware are in compliance with structural requirements.
f9f97be0-3b52-49e0-9276-560fe80081ec | section | 2. Plasterboard Installation:
c033e335-607f-462a-a22f-d5c02abdd16c | checkpoint | Install 13mm GIB® Standard Plasterboard for ceilings and bulkheads.
ddca2bad-86d5-47e7-9f16-aa076e727708 | checkpoint | In bathrooms/laundries, install GIB® Aqualine for water resistance.
c363364e-eaaa-4552-a266-a27426859a7e | checkpoint | Use GIB® 90-degree corner trims and shadowline beads at all external and ceiling-to-wall junctions​.
8e2b6d7f-9d2a-45fa-9ccd-8575cdbd7ced | section | 3. Bulkhead & Recess Features:
d4fa3d75-bcec-4f6d-b97f-63c615f6b450 | checkpoint | Construct plasterboard bulkheads in living, kitchen, dining, and bedroom areas, following bulkhead design details​
78e74684-64c3-4d5d-8be8-2dfb1047f93a | checkpoint | Ensure proper installation of GIB® stopping beads to exposed board edges in recesses​
6ec80c51-9e3b-464b-b485-632b684397a2 | checkpoint | Use selected tile finishes in areas that extend into ceiling coving​
1e5bfc76-c59d-43b1-8180-9b9135a24050 | section | 4. Lighting & Fixtures:
e62ad959-4b4e-4cdb-b455-677a2986baed | checkpoint | Ensure proper integration of linear LED strip lighting along ceiling edges as per electrical plans​
58d261e8-ab90-4730-8e75-334406d7c06a | checkpoint | Verify cutouts for lighting and other fixtures are accurately placed.
ab6765d0-916d-4ee0-9179-bafd2edabeec | section | 5. Finishing Applications:
a631bb17-c409-4826-8473-aea186e80136 | checkpoint | Apply Level 4 plaster finish for most areas (standard), and Level 5 finish for areas requiring a higher level of smoothness​
9753bc37-4856-42c5-a6e4-bdac6ffdf9ea | checkpoint | Apply selected paint finish over plasterboard​.
e929c548-674a-461e-a45c-5c9ba32ec477 | section | Post-Installation
fc0d18d7-e067-4f4b-9725-93d4b58bfe38 | checkpoint | Perform a comprehensive walkthrough to identify any defects or issues.
e3372cd4-afe8-416e-8db6-75e4b1a04f53 | checkpoint | Complete and accurate installation and inspection documentation.
3a6472b9-308a-4dee-9785-08753c7f8e51 | checkpoint | Engineers/Architects and inspectors Sign-off
8c28a52a-1f7f-4ba0-9932-35d53dc2677b | checklist | Fit-out - Floor Finishes - Park & Garden |  | Fit-out - Floor Finishes - Park & Garden
1b018188-ed06-4283-a533-e00a392a0344 | section | Prestart
2029b681-3b7d-4b50-a803-01c9fea8e749 | checkpoint | Check apartment details (unit numbers)
b3275214-ea9e-4ad6-aac1-f88e46248325 | checkpoint | Confirm specifications and floor plans
093837d7-6be1-412f-91c9-264f81f5b269 | checkpoint | Confirm construction materials used in floor finishes
1335fcfd-ca11-44b9-bcdf-11d45c1458c1 | checkpoint | Ensure proper surface Preparation, including cleaning and level
aa0a2b8a-ec3d-431b-8868-51c16e5dea25 | section | Installation
0f20ec42-a032-44ca-bb77-4e1941880952 | section | Substrate
fa3b1762-3311-422f-b4e8-a7aea2aaecdc | checkpoint | Verify installation of 19mm hardie Secura floorboard
256fca1e-b00b-4650-b84d-a6edbe169d15 | checkpoint | Verify the concrete slab is primed (e.g., MXS120 Primer) and ready for installation
96a795ef-5d8b-41d1-93af-9cc6a5795b87 | checkpoint | Confirm installation of batten and cradle systems (e.g., Acoustiflor, ZZ-5438) for raised floors and soundproofing
0ec6ca0f-942a-4ba6-a213-7aea8c9c275c | section | Waterproofing
38eb6086-d991-4c53-ab72-93a89bd726ba | checkpoint | Verify correct application of membrane (full coverage)
b8b6014b-0ead-46e2-9845-78315ad57946 | checkpoint | Check for overlaps and sealing around edges and penetrations
ae9cd205-9f00-4109-8730-d16a5b02459d | checkpoint | Conduct waterproofing tests in all wet areas
b9184fbf-be76-471c-a6b7-dca678b2b126 | section | Tile Installation
58123644-7e5a-4766-8858-d86343394e5a | checkpoint | Confirm tiles (TL02 Porcelain, etc.) are installed with appropriate tile adhesive over waterproof membranes
0e4d22a3-4aec-4734-bb44-e6790073779b | checkpoint | Check installation of chrome floor grates and drainage systems at shower waste points
cf7417d7-8e27-4d1f-bec6-8744569ce3e8 | checkpoint | Verify that aluminum angle finishing trims are installed at the edges of tiled areas
cd3aaac7-d57e-4f3c-b0d2-25fbc7772b0b | checkpoint | Confirm correct grout color and cleanliness
f7c67999-58d4-4008-b508-04c4d95ed81d | section | Timber Veneer
8f128e05-1e35-44aa-af43-c1833024ed32 | checkpoint | Verify correct adhesive, and primer ensuring a smooth and even finish
a9cf69ee-1a03-4be8-8e9a-cca0dc63c146 | checkpoint | Check for timber quality, consistent colour, grains and quantity
0567f7ae-2b92-4f8e-992b-06c4f74c7268 | checkpoint | Check expansion requirements and waterproofing in wet area transitions
ed7bcf9b-c471-4cdb-8db0-dd8c32ff6d22 | section | Carpet Installation
e3d70538-5321-43f1-a734-62dcf3302c9c | checkpoint | Check seams, stretching and alignment
2936c246-20e6-40b1-989c-de6db3cae249 | checkpoint | Ensure underlay and carpet thickness
147bf304-a474-459c-bbdc-a540720fb3dd | section | Shower System Installation
256c394a-85e0-484e-b916-56e93ba3bdb5 | checkpoint | Confirm installation of Newline Profinish shower trays with the specified adhesive
7fa498b8-c4ed-4a47-bb2c-9ed8a59184c4 | checkpoint | Ensure shower cradles are trimmed and spaced according to the design (37mm height)​
41806f90-32cd-4dfe-904f-cd4289855f2e | section | Post Installation
11d7c07f-74fe-409c-a070-d0916a181964 | checkpoint | Inspect entire flooring surface for defects
37ebd5dd-8631-4c17-b207-50a4f4982149 | checkpoint | Confirm all floor elements are correctly installed
d20f1ddd-20b0-4904-b32c-f2db28d8c0f6 | checkpoint | Compile Subcontractors QA
47b13c00-401e-490e-853a-a375222ce4f0 | checkpoint | Archi Engineer SignOff
14e6e7ac-d139-420f-9936-403c624dac41 | checklist | Fit-out - Preline |  | Fit-out - Preline
7663b50c-4035-483a-b446-b0fe4b641ea0 | section | Pre-start
09cc101c-1b58-44b8-aa89-b80766b6f166 | checkpoint | Verify that all relevant construction drawing and specs
3359c99e-655d-4b26-9c42-22b14be7ae03 | checkpoint | Ensure that all required inspections (e.g., previous stages) have been completed and signed off.
cec96513-2fc8-4064-a8fe-59c0738b17da | checkpoint | Check that the work area is clear, safe, and ready for service installation.
6a4dc4cb-9f34-4351-b031-d29c5989bb99 | checkpoint | Check the condition of materials for any damage or defects.
13a524b9-0c82-4f0e-b184-03903baa3da9 | checkpoint | Confirm that all service providers (e.g., electricians, plumbers, HVAC) are scheduled.
92d7fffa-f82d-4ed7-89e7-86ff57d72e7a | checkpoint | Check for any potential conflicts between services (e.g., electrical, plumbing, gas).
2ca1f858-91e4-4083-b8cb-ff4bad635cc3 | section | Installation
0eafc3c5-c988-44cd-8b8f-2daeec831dd4 | checkpoint | Check the placement of services within walls, ceilings, and floors to avoid conflicts with other systems.
6ed89342-cc74-4b87-b2b0-764f33de912c | checkpoint | Inspect the installation of fixings and supports to ensure they are secure
920344ab-5646-4121-aaf1-1082cf24e136 | checkpoint | Confirm that all penetrations through walls, floors, and ceilings are sealed and fire-stopped as required.
7a557890-d54f-4d7a-bc05-ef19d67a10b1 | checkpoint | Ensure that all connections (e.g., water, gas, electrical) are properly made
15a06b61-247b-4635-aef9-fe478b2f2be0 | checkpoint | Verify that isolation valves, control switches, and outlets are installed in accessible locations.
5ce9dea2-1ba6-4cf2-b0e8-31b5ea798a0d | checkpoint | Ensure that all installed services are labeled correctly.
fe7458b0-c75b-4695-9df7-bb4a3ff4c264 | checkpoint | Conduct pressure tests on gas and water lines to check for leaks.
f47903e5-39bd-4ae1-bcb3-f5705b5f9f75 | checkpoint | Perform electrical tests (e.g., continuity, insulation resistance) to ensure safety.
68eb9263-acdc-4294-99f7-6d69c8a3efc2 | checkpoint | Verify that all tests have QA and signed off
9df0acf2-e990-46ad-937f-20373fba58b3 | checkpoint | Council inspection report received and close-out
6b033f50-dab7-4493-9651-00ebcb026938 | section | Post-installation
4b76bf30-525a-4cd8-826a-5e22d6956b7f | checkpoint | Verify that all service terminations are in the correct locations and accessible.
2e082685-21fe-4ff0-84d6-0f24da3a04ec | checkpoint | Inspect the quality and no visible defects or issues.
f3c63f92-f986-4c7d-ab7b-ae07199a3c7d | checklist | Fitout - Interior Wall |  | Fitout - Interior Wall
3dfe37bf-c1a9-4488-a201-c240bb3b7a14 | section | Prestart
76a979d1-5670-43da-9471-12fc81a85e16 | checkpoint | Check materials delivered (e.g. GIB toughline/Standard etc.)
5a8e0592-3da3-4e20-9959-b739e01930bc | checkpoint | Check Latest Architectural Drawings
6f47a075-664c-405f-a33b-1dcc0b1bd8ec | checkpoint | Area clear and dry
ba75d41a-bf9d-4625-8e6d-7b6eafb2af0e | checkpoint | Check slab levels and shear walls quality (grinded and clean)
f8080c49-ed26-4418-bb28-e549f344285f | checkpoint | Check T&B levels and drops
23c457f9-f553-45ad-b1be-d0e5145ca662 | checkpoint | Confirm Grid lines lay-out and RL offset level clearly marked
d2bfc0dd-ac64-4c95-89ce-56f1e5895615 | section | Installation
8c8fe146-314a-4c59-b791-b0c84463d2f9 | section | Framing
6af9e31f-206e-4657-a5d9-f6445c323a19 | checkpoint | DPC installed
e44920c1-f165-4a3a-b464-d9abaabeb4e3 | checkpoint | Check correct gauge of materials/screw used
3cc3076d-5a15-4f26-8025-dda71909055b | checkpoint | Check and confirm studs and track spacing per area of installation
48143d4e-419b-4ba6-b3ea-3399357a551c | checkpoint | Confirm door opening with schedule
53a1903d-ad45-4da9-bcd0-55ce9ba4a777 | checkpoint | Check Head track installation
252bc75c-9ac7-4bc1-a992-c31e0ead5760 | checkpoint | Check framing nogs installed
8c278e53-aeca-4079-bec0-4fa9408f38bc | checkpoint | Attached SubCon QA
d6e65a4c-b889-407a-a555-0b1dc1a61df1 | checkpoint | Inspect final set-out detail and check with ITP
3ca25207-28cb-40c9-b3fd-e574115bb29f | section | Insulation
6e68f583-266d-4a21-96ca-cf570e4d5936 | checkpoint | Check type and R value used (e.g., PINK® BATTS® R2.2).
092f15c4-8ace-4ab0-a6e2-5a9b17c92546 | checkpoint | Confirm proper installation, (No gaps, compression)
2e952a1c-bd8b-49d2-8d95-b1fc3a301210 | section | Lining
232b3ddc-5702-4cb3-b540-cce2e51e165c | checkpoint | Inspect materials for compliance (e.g., GIB® TOUGHLINE, NOISELINE).
58c12a2d-cd32-44e3-b1c6-bf81758fcedb | checkpoint | Confirm linings fixed to framing with appropriate fasteners
b3dae0f3-8895-4ee6-b9c3-52e9a37f9723 | section | Electrical and Plumbing Penetrations:
1371a15f-f2b4-44df-8bcd-d749149eee68 | checkpoint | Check penetrations
5ef573e5-9376-4778-9769-6267afebc96c | checkpoint | Insure proper sealing around penetrations
dc80ebef-919f-43cb-9d17-ecc358733b87 | section | Post Installation
885b8bff-3ae5-4999-9460-42cc3b98cd1c | checkpoint | Conduct overall visual inspection.
ee830464-3869-444d-9170-2ded615b7db8 | checkpoint | Check for damage, defects or poor workmanship
1e23b1d0-4e7c-47f1-9e5d-c919d935819f | checkpoint | Confirm that all fire-rated walls meet the GIB specs
a674c242-bfa3-400a-9699-2d7d6c3ec2c3 | checkpoint | Ensure smoke-rated walls comply with the required standards.
9cd829d6-f796-440a-b9ba-bc4a6753af6a | checkpoint | Verify that fire stopping is complete and compliant for all penetrations and junctions.
bcfc8dd2-aab2-4643-ac69-0dbe34bb6959 | checkpoint | Confirm SubCon QA signoff
4e34c540-64cd-41a0-a80b-a805afa05fd6 | checklist | Fitout - Internal Waterproofing |  | Fitout - Internal Waterproofing
a765c4fc-a505-442f-8cfe-8e62d82270ad | section | Pre-start
4a6b40e0-63c2-47f8-a1ed-95064353e084 | checkpoint | Floor cleared from waste materials and are in correct locaion, flush and grinded down
c4d376ad-4fd5-4116-abe1-b3fe923e0504 | checkpoint | Confirm primer used to floors and walls as per specification; curing time
db9e6ec3-5c4e-4153-9a0d-fdb67ccf0bd8 | checkpoint | Check correct fall and levelling compound are available
f8960a4d-3bae-4440-ba51-2ced034c5c0c | checkpoint | Confirm RL's on levelling compound in relation falls and door clearance
07bd3fa2-a315-4f14-9b66-ab5b1e36cc79 | section | Installation
f9c2450e-4a61-4f5d-97a4-ec5da79c382b | checkpoint | Confirm correct mixing ratios of materials
477582a4-ebfc-43cb-850f-97edeb5100cb | checkpoint | Check for uniform application without gaps or bubble
bc4341b8-9b88-4ee7-b6ac-f969c1de6252 | checkpoint | Ensure proper curing time is followed
983db5b3-22b8-4774-ad42-272bf9945a47 | section | Joint Sealing
7a0869a6-7dfc-4827-9abd-053c0201e766 | checkpoint | Inspect all joints sealing and proper sealing used
72c7d4e8-5ae4-43e4-a2f0-6d4564fa50ab | section | Flood testing
70ebe83b-8e02-4635-abe9-d028ac6b2432 | checkpoint | Perform 24 hrs flood test
20956219-8a88-4e5a-b42c-d8bb61ee994c | checkpoint | Observed signs of leakage or water penerations
7d42a93f-4257-44b0-97ac-807ad73d2b45 | checkpoint | If found with leaks - reflood, and retest
bcd1a187-a7f9-43f5-a311-fb9af904ae60 | checkpoint | Subcon to submit QA checkilst report
db301d3c-ffd6-480a-8421-01cd012aa794 | checklist | Fitout – Internal Windows and Doors |  | Fitout – Internal Windows and Doors
d6ecee3c-e277-43e8-93d6-9baa34a83015 | section | Pre-Start Inspection
929b16f2-28b8-421d-847d-a866efc09148 | checkpoint | Confirm that door and window schedules match the approved project drawings.
9cfc00cf-5f7a-4f48-b994-999ecda11aeb | checkpoint | Ensure the correct types of doors and windows are delivered (refer to provided schedules for specifics)
dd252de4-99df-44ee-af6a-38da89c8613f | checkpoint | Verify that all required hardware and accessories are on-site.
b7771048-6370-4e93-8df3-ba68bf112a30 | checkpoint | Rough opening height and width. (tolerance +- 10mm)
51cdef7c-3d3f-48d7-816e-bdd7e06a2482 | section | Installation Inspection
f87e3f8d-2698-465d-9a0d-55d698aabdeb | section | 1. Alignment and Leveling
d3cec008-bb78-4684-b6fb-3c9a7b1251af | checkpoint | Check that all windows and doors are installed level and plumb.
d4027346-5f3e-4a7c-bb77-0e14ddf63dc6 | checkpoint | Ensure that the gaps around the frames are consistent and within allowable tolerances.
68840c05-ef2b-4679-a7a8-63a831c4a228 | section | 2. Fixing and Fastening
a520098b-08c9-4a52-94f8-93296ad39ef1 | checkpoint | Verify that all doors and windows are securely fixed as per the manufacturer's guide and specs.
164202d8-65af-4d5b-9a6d-b0c262344255 | checkpoint | Inspect the use of appropriate screws, bolts, and other fasteners as required.
952be4bb-5ec9-4194-9fc6-5d24ffd5422a | section | 3. Sealing and Insulation
af3fdcfa-e711-4f86-a776-62e973902e9b | checkpoint | Ensure that all frames are adequately sealed to prevent air and water ingress.
6254fc38-b230-4f4f-9d4b-bd20e37f0404 | checkpoint | Confirm that any insulation required around the frames is correctly installed.
a5437301-9efa-4207-9bef-f60332e0567c | section | 4. Fire and Smoke Stop
7f3dcd03-abc8-4b58-a483-b3a854678d44 | checkpoint | Smoke stop systems and fire-rated windows are installed according to the fire report rqmts.
4a587dc7-b84a-43c7-9b0a-1b04cee14d39 | section | 5. Hardware Installation
c8ab24da-e5f4-45b6-979f-02207d94a624 | checkpoint | Ensure that all hardware (e.g., locks, handles) is installed correctly and operates smoothly.
6e863a69-54f4-4ffe-a1a0-8310d046d905 | checkpoint | Check that all roller doors function as intended without obstructions.
6992a68c-0215-410b-9f45-d95c8154a2db | section | Post-Installation Inspection
0b344f3c-eef6-443d-bd73-2ae647da7f1e | checkpoint | Confirm that all doors and windows open and close smoothly without binding.
eb0a0d80-0e38-4872-bfc5-6e120c5abcd1 | checkpoint | Verify that locking mechanisms engage properly and provide secure closure.
c46540b9-5af5-45df-b64b-71af14906630 | checkpoint | Ensure that all installations are free from scratches, dents, and other damages.
cdc76a9a-32fb-4fa5-a6c3-81e22a2e3851 | checkpoint | Obtain sign-off from the appropriate parties, confirming that all inspections are passed.
37e07b3e-f8c7-42e2-a809-c043fcdb05fe | checklist | Structure - BorePile |  | Structure - BorePile
e55ef99d-c7ad-4278-8917-fb14f3e8c765 | section | Pile base (Pre drilling)
18ce09d8-de7e-4eed-b6a6-31a187de0ac7 | checkpoint | Check ground suitability for Piling Rig
bb6ee1b2-3db9-480c-8a43-b82cda45cf6c | checkpoint | Geotech Eng inspection report received- and close-out (Proof Drilling)
c0be4f09-91d6-4d4b-ad4a-d9629338d86b | section | Set up and drilling
6f711d9b-2b0c-4e89-8dcb-ac65751a871a | checkpoint | GL and datum provided
d20b2f8c-8174-4dd7-a8ed-1ea67b896acc | checkpoint | Subcontractor marks out piles / setting out
45ca670d-8519-42d3-a012-1841c326f2fa | checkpoint | subcon to Test drilling Fluids ( polymer/bentonite)
6bb297a0-8f0e-4b8b-be5e-24b33cf40713 | checkpoint | Boring/ casing installation /Diameter/ Plumbness / Depth check to RL
714faff5-488f-43a0-b911-c77474d564fa | checkpoint | Inspection of reinforcement cages, connection, welding / placement of cages
9590e722-72a9-423b-80e1-a89affbd21d9 | checkpoint | Confirm Platforms heights, location, cut-off
c4782ed6-22f3-4348-a33b-436835ba74f1 | checkpoint | Structural Eng inspection report received and close-out
deee5387-ec7a-40e9-803f-97f3e8d8b1af | checkpoint | Council inspection report received and closed-out.
33cf4f49-3978-497b-b6f4-56b042890196 | section | Access/Safety
ed55ad2c-d9cf-4697-92b4-b818c235a155 | checkpoint | Clear access for trucks/pump/workers
724d9427-f144-4c34-828e-69244f42cf6f | checkpoint | Sediment erosion controls in place
12097424-6fdb-45e9-85ca-6d399936c2c9 | section | Pour
bf86a3b9-7a8f-4da3-9dff-b66549cffc48 | checkpoint | Confirm design mix
85a78a3a-35f4-4f44-a903-9b7f84a9b217 | checkpoint | Confirm concrete is being tested (slump and cylinders samples)
76f2feb6-dc2a-4c93-b0be-37c7f5c57986 | checkpoint | Weather recorded
12c05018-9d06-4be9-bbb5-7562b24289db | section | Post Pour
a1e8fd30-862c-4f82-9168-f3da8829b10c | checkpoint | Check and confirm Pile as-built
224f18e8-1cb9-420c-bd07-f852d01163e8 | checkpoint | Check and confirm Starter bars
d5bd7cd6-1eeb-4db6-b22e-7207fa83a0f4 | checkpoint | Subcon QA received including dockets
8c82140f-77c7-4bda-ab95-806a7302514a | checklist | Structure - FRP Strengthening |  | Structure - FRP Strengthening
02371a9a-d273-4bdd-83b7-16e11b725ebe | section | Pre-Start
a8ff9956-4a7e-4e8c-80e1-3b713114fac6 | checkpoint | Ensure necessary permits and approvals are obtained
c6dd32f8-c2e0-42cb-96bd-e2acecd65068 | checkpoint | Check for documentation for material certifications and test report
711a59a9-6235-4aaa-8a91-29f8e93d5d68 | checkpoint | Check storage conditons for FRP components
1020686b-0712-4683-a82b-9132e19811ad | checkpoint | Confirm site ready to receive FRP (eg. Clean, dry, free of contaminants)
f222e8bb-e566-4a0f-99c7-5febfb1ae6a3 | checkpoint | Confirm approved FRP installation procedures
97989b60-e11e-42a5-af5f-e49735f1a352 | section | Safety
9392f2ee-2bbb-4497-b0a4-b414e22be23f | checkpoint | Clear access
546ee26c-5b42-4b07-8b6a-c8ed0cc8b1a4 | checkpoint | Workers PPE
ef0b0b19-49ba-45d0-ab10-d50a76671fb9 | checkpoint | Safe working platform; safety sign boards etc
1932ac8b-7e9e-46f4-9110-a0b0aabbdec9 | section | Installation
8f7292e1-87d8-4832-b12d-5f8a13f8ce24 | checkpoint | Surface Preparation (bare concrete exposed- to repair >0.3mm width cracks)
33e37fa3-1516-4612-b0b3-5ab00ac6c5c2 | checkpoint | Inspect adhesive mixing process
44f35958-2843-4e28-886f-41c641614254 | checkpoint | Ensure overlaps (min. 200mm) and sealed joints
b0067de4-dddf-41ad-b835-21a7517a6806 | checkpoint | Inspect installation of anchors and fasteners
dbfdba2a-0b14-4b5b-acab-52e3ac0fba68 | checkpoint | Confirm spacing and alignment
90b68052-9b3c-413f-841a-08f446ebfd76 | checkpoint | Structural Eng inspection report received and close-out
c7115c66-3fc1-41b7-a87f-865f9bb9e017 | section | Post Installation/Curing
01563ba5-1bb0-41dd-af05-7f9b076d1c39 | checkpoint | Confirm adequate drying time (48 to 72hrs)
efe4fd48-4c30-417e-97a3-07a4ee1e58eb | checkpoint | Conduct thickness measurements to comply with design specs
a498f0f5-f703-47a0-ad8b-22ea3f63daf2 | checkpoint | Do visual inspection for defects/air pockets and irregularities
294c2200-74fd-4541-b193-fbb8bb32111b | section | Documentation
90fae3bf-9ffc-490f-a82f-9d2c91dfed90 | checkpoint | Specialist Installer QA/ITP submission
7ae66c01-6269-46b5-bfc2-349861c3eae2 | checkpoint | Document any deviations from the installation plan
77db6ddb-7b14-4600-a889-292e88752188 | checklist | Structure - In Situ Concrete - others |  | Structure - In Situ Concrete - others
54892e4a-3cdd-45b4-affc-dd2613a8460c | section | Pre-start
6376213c-cc8b-4e39-a584-4102d6d2a8f7 | checkpoint | Foundation sign-off/QA received
a7a203d0-838d-48a0-b378-a86c59ed80b9 | checkpoint | GL and datum provided
03fb3b02-69a3-492c-869f-a7bc08381ebd | checkpoint | Clean work area
64bd6596-5272-4bf4-b074-9abf5d5c633b | checkpoint | Review construction drawings and setout
444ac695-bf49-4192-b3e6-097d4bcc053e | section | Pre-pour
f0b422d6-f387-4292-8807-249c71074512 | checkpoint | Service trade sign off/QA
bab20424-3abf-5354-a352-d9c5b612b100 | tickbox | i. attached mark-up
11169e63-7f9d-458f-91d5-4069c507c372 | checkpoint | Formwork signoff/QA
d1f9ffd1-f199-4527-bbe5-3b3df7a18872 | checkpoint | Reo sign off/QA
fe31d434-d897-4c3c-ae1c-32c10d0e5b4f | checkpoint | GN inspection
0e059990-c3db-5343-acb2-237c074fad41 | tickbox | i. Drawings UptoDate, check for CAN's
4b337958-70ed-572a-be3c-4133ef26fbc3 | tickbox | ii. Reinforcement details checked
3df20ac6-4d3f-5f93-a3e1-c9ac87209d47 | tickbox | iii. Scabbling, Starters/ embedment depth, cover checked
8c9aea54-5ead-5a98-bffc-f467d5ea0eb8 | tickbox | iv. Clean formwork, seals and ready for pour
a2d3f9a4-ed65-4b1f-9646-ea78a81aed5f | checkpoint | Structural Eng inspection report received and close-out
1887420a-7578-4d3a-8e43-f1c4f8bf6bb6 | checkpoint | Council inspection report received and close-out
dfdfc147-bee4-4609-bfe1-e02d72e84e57 | section | Access/safety
b0887993-2401-4ef3-9316-abff880ae226 | checkpoint | Access for trucks/pump
23007e35-2447-478f-923b-088caebda6fe | checkpoint | Safe access to all areas of pour
6d1be17c-892a-4e0a-bfba-0759564f2b18 | checkpoint | Exposed reo capped
a75ac578-8822-45c7-a210-dd2c28ce9dc7 | section | Pour
1022932d-f1ee-40a2-ab7e-f20266b5226d | checkpoint | Confirm mix
55b77d4c-f26e-4920-b4e6-0499967dea54 | checkpoint | Confirm concrete is being tested (slump and cylinders)
55aaa372-dba4-44f9-971d-683f067ba0bc | checkpoint | Weather recorded
e5b20dae-175b-437d-8950-f9db927513ac | section | Post Pour
78c86796-5b2b-4023-83e3-8bb97f48f735 | checkpoint | Checks
11b00868-d969-58d5-92aa-d72b45c679fd | tickbox | i. Finish
89ff5943-3b3d-5f86-bd2a-f3c0db8dd3f9 | tickbox | ii. Levels
c44ac869-412e-4887-a350-ff7841ab3dda | checkpoint | Pour QA received including concrete dockets
00970781-3304-450f-ae89-4dae60009e1e | checklist | Structure – Foundation (Pilecaps and Ground beams) |  | Structure – Foundation (Pilecaps and Ground beams)
ddddc9aa-7937-422b-862e-8723a8a9e38e | section | Pre-start
7bb95f18-23b2-4a02-b0cc-acb9cd3d3750 | checkpoint | QA for sub-grade and relevant services received
ff01948f-bcfb-51c7-85c2-a23d82081fe6 | tickbox | i. Site concrete allowed for in cut
89be1677-2b79-4e29-a678-73660770059f | checkpoint | GL and datum provided
585b78e0-78bd-4aee-9026-4ae718071997 | checkpoint | Review construction drawings and set-out
0647a4af-e9a3-4c28-8477-647101ab56f2 | checkpoint | Geotechnical Eng inspection report received and closed-out
038a7c95-bac0-47e3-acca-062d72901bd7 | section | Pre-pour
af3b93b4-d5b1-4da8-8f80-3c313fd8b5ae | checkpoint | Service trade sign off/QA
bafe5713-caa8-42c7-bc88-c5d74843b536 | checkpoint | Waterproof sign off/QA
0609c43b-c71c-40f5-923f-945481aac6d8 | checkpoint | Formwork signoff/QA
c4291fe1-cbd8-4492-bc81-a2979b3ab2a1 | checkpoint | Reo sign off/QA
9c933e2d-44ac-4436-b8ad-56f85ad68b83 | section | GN inspection
7a19b640-5652-483b-ac65-a467d1f2284c | checkpoint-no-value | Inspection Details:
b553da4b-bd32-5457-80a3-39d8fa2124b3 | tickbox | i. Drawings Uptodate, check for CAN's
ae15955c-28fc-5cb2-8caf-5b71d7cdc035 | tickbox | ii. Reo Details checked
8217eaac-c9f7-5ac6-8a85-b37e46257ea0 | tickbox | iii. Scabbling, Starters/ embedment depth, cover checked
aaaf8773-83d3-5170-862a-1f90b44096db | tickbox | iv. Clean formwork and ready for pour
400c4fb2-80e6-514c-a6f3-ee0f71e22a79 | tickbox | v. Stop-end check
8d0b8b36-b0ce-4211-b568-f785ec5fc3f3 | checkpoint | Structural Eng inspection report received and close-out
74f187da-321e-473a-b5cd-0fb011e65d09 | checkpoint | Council inspection report received and close-out
7bb6680a-4105-48c4-8991-bbe5e2a23db1 | section | Access/Safety
cce0cd7b-6a49-478b-9166-ab9f6b683830 | checkpoint | Clear access for trucks/pump
208dfa80-1b96-462a-9241-7cfb77a5609d | checkpoint | Exposed reo capped
1c068041-dbbc-4c1c-b522-3e6a29604d93 | checkpoint | Safe access to all areas of pour
787a4253-5692-466c-9cde-11d03cb44f1c | section | Pour
264b9909-b0b0-4d08-babd-5a650e41893e | checkpoint | Confirm mix
bbae7f2b-e58e-49f0-9e16-11f2f0ec09bc | checkpoint | Confirm concrete is being tested (slump and cylinders)
7320a782-b95a-4cd6-80c1-1163e48f2b6f | checkpoint | Weather recorded
0c96bd94-b55d-44ea-b80a-66ccae1f076a | section | Post pour
cb9b558d-0613-4716-b5c6-0387e4098bda | checkpoint | Checks
0e58b667-22c3-579c-95e0-cbd7223efe21 | tickbox | i. Finish
1a44be8d-97b0-538b-8dc3-7977bf410f7a | tickbox | ii. Levels
d1ef5b4b-52df-5e4e-9586-4d6d1b03d129 | tickbox | iii. Starters
2d346144-27e5-4e3b-9b9f-3c14b8f9e237 | checkpoint | Pour QA received including dockets
902a8dd7-7137-4a2f-89e1-6fca91bfab0b | checklist | Structure – In Situ Concrete (Plinth) |  | Structure – In Situ Concrete (Plinth)
3e4de753-8172-428f-9398-187f4d7e1e5e | section | Pre-start
00d6dd8a-9de9-4880-9391-ff0311046836 | checkpoint | Ground Beams sign-off/QA received
5fc50596-5f11-4500-af56-4a2a5927ddb4 | checkpoint | GL and datum provided
04860077-8ec3-4004-aac5-fbd956888933 | checkpoint | Clean work area
e8c412c6-51eb-4164-9d0a-64ef38e069ae | section | Pre-pour
fde8bd82-3ad8-4b09-9380-e5c8db2edf82 | checkpoint | Service trade sign off/QA
dcbdefb1-dc1a-43fb-b981-7d7377b77864 | checkpoint | Formwork signoff/QA
85ed2e10-c23a-47a0-a9c5-0891946d6f43 | checkpoint | Reo sign off/QA
7dffebd8-7381-406a-94e3-abcbe68dfccb | section | GN inspection
06e7cdf4-5586-4704-bb34-609a61a90cdc | checkpoint-no-value | Inspection Details:
285de617-4479-54c2-b7d1-041994a75b5f | tickbox | i. Reo Details checked
9b23e9f9-aef4-5aaf-8684-036c019745c7 | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked
113f79b3-7b11-57e8-bbbd-1e7b09b3b28b | tickbox | iii. Check reinforcements size, spacing and cleanliness
5c8f55ef-488e-5a89-ac2b-991fa919609c | tickbox | iv. Confirm Anchor Embedment and survey checked
d0f18120-f7ee-5bad-b941-b43f9c0a1e6e | tickbox | v. Drawing UptoDate, check for CAN's
673977e8-c8d6-419d-9844-8a0572c543d6 | checkpoint | Structural Eng inspection report received and close-out
411d1f19-9b9f-4cb8-9f97-621728a892c3 | checkpoint | Council inspection report received and close-out
aad82d70-acfe-41a3-a78e-131fb8c3a07f | section | Access/safety
9028158f-0035-4b15-ad04-f7f2f6a3f5b7 | checkpoint | Clear access for trucks/pump
91ebe69c-ffa6-41d3-8f89-b0df7481f46c | checkpoint | Exposed reo capped
173a2e99-2d6a-4916-8258-8809f7ca976e | checkpoint | Safe access to all areas of pour
16a6e0fb-5b93-4e17-95cc-9fddf948fa30 | section | Pour
aede4b15-ec68-4537-a9c6-a857772b0e76 | checkpoint | Confirm mix
abf37df7-0cab-4e08-9c33-f7646c5276b9 | checkpoint | Confirm concrete is being tested (slump and cylinders)
4ec56c0f-5cc5-4986-b3dd-9a8341d64010 | checkpoint | Weather recorded
a70faefd-ba49-4a83-a8c1-0a8815864e46 | section | Post pour
d5e60a70-cec5-41eb-a512-2677b65014cb | checkpoint | Checks
08112011-2562-5b30-acb4-f181580ba69a | tickbox | i. Finish
d4ab6b68-e73c-51aa-990b-41f26c94ab90 | tickbox | ii. Levels
90c57d21-f02e-58bd-8870-d446f1148bc0 | tickbox | iii. Anchors
0037de45-9cf9-4afe-ac47-0e5e1dc73fd9 | checkpoint | Pour QA received including concrete dockets