## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Fit-out - Bathroom
section | Details
checkpoint | Postline checks – Checks walls are square and plumb
checkpoint | Check heights / placement of fittings and fixtures relative to bathroom setout plans
checkpoint | Stopping complete
checkpoint | Sealer coat installed to walls / first coat installed to ceilings
checkpoint | FLC / Screed compound if required (check door threshold / transition)
checkpoint | Shower base site measured / flood tested offsite post manufacture (QA required) / delivered and installed
checkpoint | Sealants installed
checkpoint | Waterproofing installed as per manufacturer system guidelines
checkpoint | Waterproofing QA
checkpoint | Flood test shower bases post waterproofing install
checkpoint | UFH test and QA (if applicable)
checkpoint | Tiling QA (check tile setout plan / grout lines relative to FFE)
checkpoint | Fittings and fixtures (towel rails / shower glass / accessories etc installed)
checkpoint | Additional notes / comments – Handover QA to second fix
checklist | Fit-out - Postline
section | Details
checkpoint | Council preline inspection passed / subcon QA received / GN preline ITPs complete
checkpoint | Wall linings to progress following GIB guidelines / arch wall tupe details
checkpoint | Check GIB fixing orientation and fixing spacings in accordance with GIB guidelines
checkpoint | Ensure perimeter fire sealant has been applied to GIB
checkpoint | Ensure all GIB joins and fixings have been stopped over and terminate to underside of floor above (or where applicable in accordance with consented plans)
checkpoint | Ensure any service penetrations have fire collars installed / stickered / QA received
checkpoint | Ensure in wall powerpoints have flush boxes installed as per passive fire detail requirements
checkpoint | Postline inspection checklist established / signed off from subcontractors
checkpoint | Council postline inspection No. 1
checkpoint | Additional notes / comments - Handover QA te second fix
checklist | Fit-out - Pre-line (Ceiling)
section | Details
checkpoint | Ceiling Grid RL checks
checkpoint | Ceiling Grid installed - services accounted (check penetrations relative to deflection head detail, where applicable)
checkpoint | Services installed (establish preline services sign off sheet - check RCP setout for lighting / sprinkler / mech locations). Check services to external spaces
checkpoint | Service passive fire collars installed / intubatt / other passive requirements underside of slab complete / QA received
checkpoint | Ensure seismic details have been followed as per consented design - Engineer / consultant preline inspection
checkpoint | Ensure sprinkler installation has been pressurised and signed off prior to lining (QA received)
checkpoint | Ensure overhead hydraulic pressure test complete / QA received (prior to ceiling lining)
checkpoint | Mech grilles checks on appeture openings relative to the diffusers and grill sizes in relation to RCP setout
checkpoint | Coordinate access hatch framing / location relative to service maintenance
checkpoint | AC inspection No.2 Pre line
checkpoint | Celling GIB infalled
checkpoint | Additional notes / comments - Handover QA to second fix
checklist | Fit-out - Preline (Walls)
section | Details
checkpoint | Structural QA Received
checkpoint | Gridlines / RL datum marked on floor
checkpoint | Bottom plate setout per arch setout plan
checkpoint | Underslung service peno marked / core drilled
checkpoint | Wall framing complete as per consented details / wall types
checkpoint | Packers installed to underside of bottom plate
checkpoint | DPM between framing and Substrate
checkpoint | Stud centres and fixing centres as per consented details
checkpoint | Check all door openings have been constructed to the RO dims outlined in the door schedule / arch set
checkpoint | Check connection details are in accordance with structural PS1 / NZS 3604 (if applicable)
checkpoint | Nogging plan established / agreed with service trades (FFE / Appliances)
checkpoint | Nogging plan checked and approved by specialist subcontractors (e.g., kitchen / fireplace etc.)
checkpoint | Checking manufacturer guidelines for specific fixing requirements
checkpoint | Check moisture content of timber prior to lining (if applicable to timber frame)
checkpoint | All nails flush within framing to receive GIB
checkpoint | Create sublist if applicable to fire IT wall (check passive fire requirements - fire collars installed / stickered / QA received)
checkpoint | Complete prelim service sign off sheets (ensure sub-con preline QA received / check intumescent complete QA received / purchaser changes incorporated)
checkpoint | Checklist for purchaser change incorporation
checkpoint | Consultant preline inspection (BVT / Holmes / WAM / BG&E / Marshall Day)
checkpoint | Line single side of internal wall (follow GIB manufacturer guidelines)
checkpoint | Pelmets / bulkheads / services to exterior space complete and sealed
checkpoint | Insulation has been installed as per consented plans (no gaps between insulated panels and frame)
checkpoint | Ensure wall cavity is free of debris / clean prior to GIB cover (vacuum tracks)
checkpoint | Council hydraulic inspection / sign off (two inspections depending on quantum)
checkpoint | Ensure caps on inspection points are reinstalled after council hydraulic inspection
checkpoint | Additional comments / photos (applicable to a unique room type - such as service room etc.)
checklist | Fit-out - Second Fix
section | Details
checkpoint | Passive fire QA reports received (flush boxes installed to powerpoints etc)
checkpoint | FRR door tags installed
checkpoint | Ensure entiriety of door leaf is painted (check top and bottom edges and behind hinges)
checkpoint | Door undercuts follow required specification
checkpoint | Waterproof paint used in wet areas (check specification for requirements)
checkpoint | AlL FFE items have been installed in accordance with finalised architectural layout plan
checkpoint | Sprinkler caps are removed before council inspection
checkpoint | Check power and lights are working
checkpoint | AC unit is functional / Fans are accessbile through access hatches
checkpoint | Hot Water is at temperature (48 degrees)