## Master List Templates
Id | Type | Name | Values | Prompting Name
187c7a08-f880-403f-a1e6-d61a382d0f39 | checklist | Carpet Tile Installation Christchurch |  | Carpet Tile Installation Christchurch
0da344bf-eae1-47ff-b13f-fdf2e6777f02 | section | Preparation
510343f8-0c92-4b7e-8c6b-b73e5252e462 | checkpoint | Check area clear of all other trades and their materials
ec7202ba-a399-5c6f-b9ed-842356c83457 | button | Does slab need moisture mitigation? | YES, NO, N/A
f586bb9c-39c4-5963-9bf4-603570343c3c | button | If yes, Has this been completed? | YES, NO, N/A
8a3296fe-33e0-4abe-80c5-b2403df7d0b8 | checkpoint | Check floor if prep is required
c82a905b-85cc-492a-81e1-ca0db6b7d9dd | section | Installation
98f75821-a912-4aa5-b0cc-1c0eb23d9f7e | checkpoint | Confirm carpet tile colour, pattern direction & layout
0b913c7e-2e22-5073-b84d-11e021b24eee | checkpoint | What glue is being used?
d470153b-7cdc-43df-a4e9-8be0e23800ce | checkpoint | Install carpet tiles
0f45ebfe-ce88-4c15-8589-714e8b32b8a4 | checkpoint | Install trims as applicable
c668d22f-d99b-44b1-8d92-496f36190e3b | section | Handover & Signoff
d0dd9dc5-9c1b-40ac-8240-6bc59952968a | checkpoint | Remove all excess material & rubbish ready for handover
b77d1ce7-c2f9-41ea-970b-b28fe4be16b4 | checkpoint | Clean any excess glue
b32e2a5f-09ae-4037-81b3-b709f3a07999 | checkpoint | Installation is free of defects
291ca414-22e6-5faa-ab59-fe90366d1b1b | textbox | Has this room been completed and ready for approval | YES, NO
ce975b9d-eb68-427c-b7f8-044cdf1ba103 | signoff | Send to Client for Approval
c93d0870-d985-4677-a66c-2b480ad2bc0c | checklist | H&S - Pre-start Meeting |  | H&S - Pre-start Meeting
f995310e-df87-4200-9da4-91854270a82e | section | Project Information
6baf4fe7-da06-45e3-b265-e02eae7fdaab | checkpoint | Project information
d03af8a7-65e5-5b57-986d-038cfa1ac63f | button | Select meeting type: | Site-specific, In-house
f6d9e808-d18c-5955-956a-4fa89bb2b98e | textbox | Project name/location of site:
2b30b865-247e-5fff-83e8-ad80d5a20fc8 | textbox | Name of person running this meeting:
e36831f3-a203-5e5b-894b-384bda66dd66 | textbox | Company:
ff21e9c9-49a4-5467-a172-93a26af90abe | date | Date:
85aa083c-0e30-513b-bb06-993e021c5735 | textbox | Scope of work:
80e4fdf7-ea95-42e6-aa6d-0a5375f944dd | section | Checklist
20c0d502-c812-4b82-880f-05769d5aae62 | checkpoint | Location of First Aid kit
971fe8e8-fee1-4389-a937-973d6bed6304 | checkpoint | Weather conditions appropriate for commencement of works?
750d7275-47de-4c61-9c25-4703c610308f | checkpoint | Site access arrangements e.g. security ID badges / inductions / signing in procedures
a6af41bb-7507-41f2-b4e4-3b5afc508d68 | checkpoint | Access to buildings
babc3b89-8170-4496-8b3d-12d67e107844 | checkpoint | Parking / segregation of vehicles & pedestrians / emergency vehicle access
73ec4a4e-ca56-4628-889d-d86f23184470 | checkpoint | Contractors toilet and smoking areas
6cbb44d2-0a5d-4084-b9a7-fb9cc8137781 | checkpoint | Any deliveries this week?
5d234b8e-8d85-4f95-8aed-36be4f8852fb | checkpoint | Fire safety – routes & muster points
b9767aba-6ef9-49f9-9ca7-f72a03fe401d | checkpoint | Hours of working / potential for noise impact
4600b554-e239-45b6-b99d-c67e2ba34c24 | checkpoint | All workers instructed in relation to today’s work requirements?
13e57fe9-c7fd-4a3b-95a4-5d579d98f602 | checkpoint | Workers adequately trained to complete tasks e.g. MEWP, forklift, working at heights
b8cc93ad-d36e-43eb-864b-933506a52d2d | checkpoint | Plant, equipment and materials up-to-date, and safe for use?
1fd3886f-a3c0-4545-910d-26b7230bdeb6 | checkpoint | All portable fire extinguishers readily available?
1435bd6e-c595-49ca-9e67-22feb0aeea73 | checkpoint | All workers have suitable PPE for all tasks to be performed?
d18bae0f-633a-4b30-8546-41844b359d18 | checkpoint | Are emergency exits clearly marked and accessible?
2776bd0e-5e6e-44d4-bd53-ae1985f8861f | checkpoint | Is lighting & ventilation adequate?
b7e0ffa7-283f-4e84-b675-e81b6323029a | checkpoint | Do noise levels allow clear communication?
7c381451-7a8a-4dfd-849b-d6128f99b505 | checkpoint | Are any live electrical wires exposed?
538dca21-6bd8-475a-b872-4e5ad7531d0b | checkpoint | Are there any trip hazards present?
db8e9b18-bbcb-4dc8-b5cc-05b5093f5f60 | checkpoint | Are trolleys available to move heavy loads around the workplace?
8050fa6f-6283-4432-8ec4-756c3b3dc9a8 | checkpoint | Are there any risk of injuries from machine parts or exposure?
b2d733a9-2c98-48ec-98d5-f9bb4fcf1ed7 | checkpoint | Are there procedures to follow when shutting down equipment?
5c1e6b5a-6d72-4855-859c-e076194e9d64 | checkpoint | Are all employees aware of storage, organisation and placement of parts, tools, etc.
f8858fbe-daec-43c7-a522-5e6a1d88e9ff | checkpoint | Are all employees aware of hazards (dust, chemicals, heat, excessive noise, etc.) that may be created by the job?
2ac1f091-832e-44fe-ad8f-30703b98273a | checkpoint | Have obvious problems been immediately remedied? (e.g. missing machine guards)
b4bb5423-d24e-436b-b311-79d1d76bc470 | checkpoint | Has equipment that could help reduce hazards been identified?
552c581e-b1da-462e-a985-12405844ebc0 | checkpoint | Have physical changes necessary to reduce hazards been made? (e.g. improve lighting or ventilation)
2fe29e68-1b35-4f94-8fdb-4dbca88c002e | checkpoint | Are there ways to eliminate, combine, or rearrange job steps to reduce hazards?
3337bc1d-dd40-47db-b7ff-071fbd3bd491 | checkpoint | Have new job procedures been communicated once changes are made?
17c8d3eb-f774-41f3-8095-e1e24a6f012c | checkpoint | Have hazards that can’t be eliminated been identified?
93eba4cb-bc93-4c7b-bc9e-f0989c9847a3 | checkpoint | Are ways to change hazardous job procedures being pursued?
87277468-4248-46a2-b7cf-6e01e00b3605 | section | Review
b41e3253-fd3e-4ce5-b9eb-70898711a37b | checkpoint | Record of attendance and discussions
7f4f8adf-973d-503a-85f6-6a522706c29d | textbox | Date:
48a1a7f3-8122-566e-ac51-d0be68f02074 | textbox | Location:
e56e140d-ec18-5354-8a5c-5efcbc9e2213 | textbox | Attendees:
eae47de7-c80d-5cec-98a9-6bfa683eb809 | note | (separate attendees with a comma)
9fec8e64-a6fd-4c4d-bdcb-a42f9f68a8af | checkpoint | Reviewed by management
cb44d3a7-7066-5279-b701-fb80a65ad066 | date | Date:
bc1626f6-6345-43e0-adfd-265846ab6c02 | signoff | Reviewer to sign
b672b0e5-8349-4730-8ffa-365a9c20462f | checklist | H&S - Task Analysis |  | H&S - Task Analysis
02c24034-8d96-461e-b5e8-b8566842e360 | section | Details
61bcde31-7b93-48b7-b3e4-92075b76f0ee | checkpoint | Details
10b5c3aa-3e3f-5f5e-8287-01dafdf94e3e | textbox | Job description:
e2a99419-098c-5f64-a920-a624354087e2 | textbox | Project/site:
8fcd5748-1a14-5b1b-bde4-5e48a4bf127f | textbox | Date:
a4b2c9a4-f1be-5348-bf9d-4b62955badbf | textbox | PPE required:
c7a5f28c-6831-5ba4-aaab-c44c76c4ac93 | textbox | Plant required:
1b248994-78f4-5293-853e-eecfa8ff8cc0 | textbox | Signage required:
9aa48ea0-647f-412d-a18e-0eced66361d3 | signoff | Person completing this task analysis to sign here
762efb7f-8c51-4880-91ad-639be95b2021 | checkpoint | Task 1
67dfc7da-716a-5961-906b-c1a919379f12 | textbox | Describe steps required:
6e5da1f1-cff2-5d6e-b4c6-74217006ba5d | button | Select initial risk | Very Low, Low, Moderate, High, Very High
860e1332-7c6f-5ee7-8584-0940cd3b53b7 | textbox | Identify hazards:
fd6e75d8-4a14-507e-abab-e544f9668bbb | button | Select action required | Eliminate, Minimise
83d3866f-b4fb-5585-b29a-66c948341d26 | textbox | Control methods:
d9be0c63-5f6a-5b15-a95c-7bf0e9d05359 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
337caae2-e7d2-444e-83ea-7063f401e0cc | checkpoint | Task 2
2dfaa70e-d8d6-5cda-92ac-4e2160ff8850 | textbox | Describe steps required:
8ad53430-3595-5e01-97fc-1645f8779ff7 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
a021041f-6c77-5341-84f0-8620ca73416f | textbox | Identify hazards:
c4452e08-6b56-5d09-8cf4-1d283631e0c7 | button | Select action required | Eliminate, Minimise
b0cf4df5-a122-523d-a3f7-43df44b2acb4 | textbox | Control methods:
f9e1250b-808f-5363-aadc-12c4ee07f7fa | button | Select residual risk | Very Low, Low, Moderate, High, Very High
119d61b9-a74a-48de-b2aa-caeb6491bcb0 | checkpoint | Task 3
781de649-094c-511e-a87c-834ef4c86c88 | textbox | Describe steps required:
38c1fe4a-61c8-5ed4-b01e-8f17c88e2515 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
58b3e480-0f56-5133-8b30-0b241a406175 | textbox | Identify hazards:
82516e36-2212-5386-b56b-22accb316502 | button | Select action required | Eliminate, Minimise
1e2ad1d5-265e-5fde-a1dd-a37da9ebaf8a | textbox | Control methods:
c7d10436-6879-5d7d-bdef-fdf920e13440 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
b0263b81-6784-47e4-9952-77f203a42c67 | checkpoint | Task 4
04399993-8cff-5d37-8e34-29c5b7c92101 | textbox | Describe steps required:
6e361e5f-973f-518b-9952-6d7921a59c87 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
c4238965-baea-5aa7-9d97-5ea31d00b63d | textbox | Identify hazards:
798a296d-5270-5a7e-b099-cfcedd8c0119 | button | Select action required | Eliminate, Minimise
0ad5e508-df54-5101-b112-ec5c1c0e1a37 | textbox | Control methods:
5b300176-32f8-5707-9eb3-822dfb17b68c | button | Select residual risk | Very Low, Low, Moderate, High, Very High
6b62b72b-640b-4313-82e3-d95d97113d2f | checkpoint | Task 5
6e213035-2e08-586d-8fc2-71f7409014ee | textbox | Describe steps required:
1577bb7f-e9e7-5e27-8e1b-f4698dd96698 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
c666a778-4d1d-5249-b3bb-8ad5b092b2aa | textbox | Identify hazards:
1fbe077d-2cb8-5d2d-ad97-e28839b6d916 | button | Select action required | Eliminate, Minimise
fe5d875c-de11-5d25-81be-d73239b4de9d | textbox | Control methods:
51471fff-f76f-53cc-b3cf-a2cdbaa2c1f7 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
a8411340-c3a9-4d42-88d6-359bb57338f1 | checkpoint | Task 6
69ab320a-5170-58c8-8a1e-bb3137950c5c | textbox | Describe steps required:
8bde3027-7c78-59f4-a1dd-ca2c3405864a | button | Select initial risk | Very Low, Low, Moderate, High, Very High
782ba44a-ad70-5e81-9885-7e2fbfcfae5b | textbox | Identify hazards:
1557f37c-5fa4-5799-b242-f3b744e4446a | button | Select action required | Eliminate, Minimise
ec7d44a2-1858-5706-95f5-745bb3ccfda1 | textbox | Control methods:
7df066b0-4371-5093-af74-d543e5541987 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
7072868c-80f7-4046-a2ed-11d34fe9f4c5 | checkpoint | Task 7
638dfb05-c464-5a37-9f7a-162d9d929814 | textbox | Describe steps required:
2b769dad-8ca6-52b4-9eaa-665c0892bf48 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
433cd17a-6b20-5907-8f39-608f3c49421e | textbox | Identify hazards:
f3c33b2c-c2fc-52b5-8db6-7e956cc6b0d9 | button | Select action required | Eliminate, Minimise
19e56326-d8c8-5d94-bf5b-e6fecd4c9ae7 | textbox | Control methods:
8c59d938-bbf9-585b-b602-d496a8244e19 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
ef3d220b-1654-421a-ae0f-77e306e83dde | checkpoint | Task 8
e81115cd-695c-57a1-a59f-26355ac42df3 | textbox | Describe steps required:
9674d59d-8146-5a0f-97bc-02571bbdbc83 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
409b248d-c8f6-56e3-b782-46b3f3b93081 | textbox | Identify hazards:
51561e69-4009-5913-8fd2-8c520881eb93 | button | Select action required | Eliminate, Minimise
7d914aeb-9a46-55cf-8e29-a023992f582c | textbox | Control methods:
5a51cafc-c89d-5efe-8de5-35b58a7db7d3 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
723713c0-2ad6-4412-b5f1-c6290080c6ec | checkpoint | Task 9
ff4564b5-0ef6-5043-bd68-d1de2381a18f | textbox | Describe steps required:
98bc72a9-bd92-5686-a700-2f729800b9d1 | button | Select initial risk | Very Low, Low, Moderate, High, Very High
29d603af-c6fd-563a-986c-aca086ec620a | textbox | Identify hazards:
3517a0fa-8773-5d75-b50f-ffa96ea645a0 | button | Select action required | Eliminate, Minimise
4f689a34-892e-53b2-a754-9cd0f8531e51 | textbox | Control methods:
722be686-2c1b-5d38-bee5-07171e3ec934 | button | Select residual risk | Very Low, Low, Moderate, High, Very High
efdf6700-4569-4da9-afc8-69687339be23 | checkpoint | Task 10
66397646-dd20-5835-a6b7-20b6c9d5c911 | textbox | Describe steps required:
c21edd9f-5a39-5f11-b0d8-bcba67ed34fe | button | Select initial risk | Very Low, Low, Moderate, High, Very High
b9e3e658-417b-566e-9bd4-538ad661e1ac | textbox | Identify hazards:
4296bf87-40b9-5c32-b681-603eb61292d9 | button | Select action required | Eliminate, Minimise
36953fe3-af69-530c-8475-c597c8488e02 | textbox | Control methods:
76f0e470-3932-538e-a0a1-81275005532e | button | Select residual risk | Very Low, Low, Moderate, High, Very High
542e5474-8bdf-4c5d-b0ac-ea546947dbac | checkpoint | Signoff
56d049ad-aff8-4885-a737-53a393f8a936 | signoff | All persons involved in this task analysis to sign here
4871b8cb-94bd-469a-aef2-b59f4c4c34f3 | checklist | H&S - Toolbox Minutes |  | H&S - Toolbox Minutes
a8bb597b-4ab1-4e08-9565-b23f429536fe | section | Details
bee60a29-acda-437a-9d91-8be76cf7ec4c | checkpoint | Record of attendance and discussions
33e44442-8734-5bb8-a306-9744d326db5f | textbox | Date:
a1f844e1-6be1-5f0f-b494-cbd1783d9d36 | textbox | Location:
899fedca-9983-5f4d-9df5-8590fd8c453c | textbox | Attendees:
9bc93c04-dd10-5d66-9511-0c12b70d4f82 | note | (separate attendees with a comma)
cb25b26e-9381-4176-a068-477a121804b3 | checkpoint | Matters arising from previous minutes
15b4f455-5147-54aa-874e-ed122895db65 | textbox
0b463de1-acfd-4217-adea-655eccc52493 | checkpoint | Safe work practices/incidents
91d8d2f7-0f1e-5544-9a0c-4d85bcd42f87 | textbox
394b5664-d364-458e-82fe-543800e2e427 | checkpoint | New hazards discussed/reviewed
848fb4c1-ad29-52d9-9329-5b9493c6150c | textbox
32d0200b-95e5-416f-bea3-3ba54664430b | checkpoint | Training/employee concerns
0a36c047-71dc-5ae8-8dbf-0c885cf84335 | textbox
389fc063-cdd7-4a43-8184-e8cbda9e8638 | checkpoint | Description of today's work
6724233a-c193-50b9-8963-985d8622ff6e | textbox
5ba17559-84cb-4649-8e0a-1f6241c51d53 | checkpoint | Other items
275bc1f2-111a-597b-890d-c787b534cf69 | textbox
04ffb757-9127-4b4c-b891-06989ec5568a | checklist | Job Sheet Pre Site Information |  | Job Sheet Pre Site Information
e4942a9b-a78c-4d8f-b22a-6e7ccc00a8ad | section | Details
5a028b3f-099b-442c-be5e-ac9c7966acbc | checkpoint-no-value | Details
a26ddb7e-8320-5654-b3cd-e1d2c8aee313 | textbox | Physical Address:
a1ed8cb5-57a5-58d4-ba71-fc7e853abd67 | textbox | Hills Job Number:
bd9453c1-252f-5467-b8c1-1bb3bb08534a | textbox | Onsite Foreman:
1bb7979f-3995-5203-8a1c-84019c5d4f4b | textbox | Access Details:
bf347bad-8df1-55e9-aa17-935e39710bd6 | textbox | Site Hours:
be9993b8-3c5d-5550-a0c6-d4db1e21b9d8 | textbox | Is there an induction required for site? When?
446e345f-1ea0-4843-8bf6-981fc5e5aa9b | checkpoint-no-value | Has slab been tested for moisture?
8a530487-454d-55f6-a36b-9749ec388252 | button | Select: | YES, NO, N/A
eed2c096-8c89-4a63-adc6-3c0cfab1cc86 | checkpoint-no-value | Is slab requiring moisture treatment?
f6b40c2d-7ead-59a3-98a6-b987701de538 | button | Select: | YES, NO, N/A
7e5d396b-26bc-4b5b-95fb-a0d0d1ce18e6 | checkpoint-no-value | What floor preparation is required?
c9e57a2b-4acb-4545-9c61-d2ab1c87c4de | checkpoint-no-value | What floor preparation products are approved?
b6d0d7dc-1ee7-4830-8a48-26f06a0851e3 | checkpoint-no-value | Carpet tiles - have direction and pattern been approved?
f07c5cf2-d36a-4938-a63c-2791d6514fe9 | checkpoint-no-value | Vinyl
656fc534-3b4d-5fe1-9b97-5dbb47db06b5 | textbox | Types
ad4d53cb-4941-5a6f-825d-a5ff86c5a33d | textbox | Coving height and type
ef1c63cf-7826-501c-a510-4fe04518ecbd | textbox | Capping
25f3cdaa-7354-5a24-a83d-789a8c66aeb0 | button | Vinyl, have manufacturer's instructions been attached or reviewed? | YES, NO, N/A
3f83fd87-2071-4638-a33b-8b15cae41cf6 | checkpoint-no-value | Glue selection
273551f8-382f-5b08-80fe-35823e6802cf | tickbox | As per specification
98bc096e-ce90-5bb5-8d5a-39ad931ad19c | tickbox | As per Hills approval
fee8670a-481a-5a52-aa83-8ee00b80de27 | textbox | Glue for floor vinyl:
1aeb8e5a-fc12-57b8-b94b-bd769104bb8e | textbox | Glue for wall vinyl:
9fba6ea7-eb82-500f-8903-12130b3e6e1c | textbox | Glue for carpet tiles:
5c1b39f9-c8e5-4260-8db8-b697849459d2 | checkpoint-no-value | Finishing trim selection
6730240c-7bc2-50e3-96bc-81acf198e7c7 | tickbox | As per specification
2117e0bb-9772-5bd6-960a-43b018656b2c | tickbox | As per Hills approval
f49d0c36-15bf-58c2-90dc-0d1714996ed1 | textbox | a - Trims for carpet meets vinyl – type – colour
4df421f8-818c-5fa1-a146-4733da59583e | textbox | b - Trims for carpet meets concrete – type – colour
379d0eb0-7dff-5b95-98aa-224e2e5fee87 | textbox | c - Trim to top of vinyl cove – type – colour
8dab16ea-2835-5bec-9b75-b8fe19082f4c | textbox | d - Trim around wall vinyl – type – colour
4c81b8d6-8958-5fad-a289-6641e3ebd33f | textbox | e - Any nosings required – type – colour
64b6ac16-d750-5593-a4ce-e00e6c7a4982 | textbox | f - Have any of the above items been powder coated
eb517923-3e50-42dd-b245-361a799f8ea4 | checkpoint-no-value | Have areas of high sunlight been identified and noted for epoxy glue?
cd30a82c-3e1c-4547-a921-347170b6b736 | checkpoint-no-value | Is there any other information relevant to this job required?
3f117b87-02fb-4b24-8d9f-67396951e48b | checklist | Vinyl Installation Christchurch |  | Vinyl Installation Christchurch
b731c29b-6c76-4b52-8ee0-913d31714d04 | section | Preparation
0a779698-1c26-40d8-8513-b66134a7cf74 | checkpoint | Check area clear of all other trades and their materials
08ec80f3-e9bc-5b7d-b4de-1ac05c7c35e8 | button | Does slab need moisture mitigation? | YES, NO, N/A
41a7757a-f2f6-52b5-a297-b232c789f2f6 | button | If yes, Has this been completed? | YES, NO, N/A
75178e98-7f25-48c1-8966-f98b9e7856b3 | checkpoint | Check floor for U3 (3mm variance over 3m)
670a2f15-f562-4965-9dfc-5b76144c11e1 | checkpoint | Check wall for smoothness where coving
36ca0840-e4d4-43ef-84d5-9a1836ad04a7 | checkpoint | Acclimatise vinyl
003a931f-4ee9-40b5-8a65-9186a4a108ab | section | Installation
8ee8465d-8966-49de-b53d-fdf4f6c47c87 | checkpoint | Confirm vinyl colour & layout direction
0a2e952d-addd-436b-b57a-100d2e57239a | checkpoint | Confirm coving location/type
93b37c49-928b-542b-a7ee-574023442b3d | checkpoint | What glue is being used?
28d5f997-9188-4906-a039-74b40e809ef1 | checkpoint | Install vinyl
7f6521b2-c7ec-4d01-bd5b-f8854b98130b | checkpoint | Install coving & capping/sealant as applicable
ffae4237-2a10-4d63-be71-9d19ac85023c | checkpoint | Seams welded with correct colour match
efcb8f5d-2901-4f8e-bb02-84a13cbdd3f9 | checkpoint | Install trims as applicable
d2a44dac-e274-4993-8fa1-085f2c51d69d | section | Handover & Signoff
5f5cffac-7062-41cf-94fd-a8fd7cf649f1 | checkpoint | Remove all excess material & rubbish ready for handover
48c23a96-5efe-4794-ae84-32ee8461576c | checkpoint | Clean any excess glue
4f01f759-3a80-4c91-9131-0b62f591a74b | checkpoint | Installation is free of defects/bubbles
b9b3bc65-4891-5f25-afec-dc46bc4db9f9 | textbox | Has this room been completed and ready for approval | YES, NO
e7fda3a2-979b-4277-9f69-928a86aacfbb | signoff | Send to Client for Approval

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
988773bb-a82c-461e-8adb-bc16871051c9 | checklist | Carpet Tile Installation |  | Carpet Tile Installation
853777c4-ab05-43e2-abc1-b759383ee7c1 | section | Preparation
bd2ed55a-369e-469f-ab3b-f736df2afb4c | checkpoint | Check area clear of all other trades and their materials
fcb2f81c-ec2b-425d-976c-44663ff9ab9b | checkpoint | Check floor if prep is required
8339ce92-e1d4-4d86-ab2b-7839967eb329 | checkpoint | Measure area
8ba7a99c-a3c2-4841-bd75-fb99be961509 | section | Installation
ebd9cae2-8e02-4d01-83da-04b543dbdd5a | checkpoint | Confirm carpet tile pattern direction/layout
b06889c2-7623-4f33-a8e8-f0f1f8dd683b | checkpoint | Glue out floors
962f2f31-9be3-48b1-8f64-098bf096dccd | checkpoint | Install carpet tiles
45e07f1a-755d-4a9f-88f2-05f558267b4d | checkpoint | Install trims as applicable
f32e9646-a507-4163-b0dc-4986db5b3190 | section | Handover & Signoff
3306d86a-563b-46b4-a954-d0f170ef586b | checkpoint | Remove all excess material
500d4d93-b155-45e7-9c58-9c8f2e2067a1 | checkpoint | Clean any excess glue
97ea7789-c667-495f-8237-9615787dbb7c | checkpoint | Report for inspection
a63d3a7b-0822-4f09-a538-06f6ce269d79 | checkpoint | Quality Approval
a29c0a64-f07d-4021-b79f-f41668df43c7 | signoff | SEND TO CLIENT FOR QUALITY APPROVAL
07de23ba-01a5-401b-bc31-da08a097b6ce | checklist | Entry Mat Installation |  | Entry Mat Installation
ad18aaac-fef5-4b45-9a19-f5791a0b4417 | section | Details
72fa857c-795f-4933-b102-753ec49f5081 | checkpoint | 1. PRE-INSTALLATION CHECKLIST
12a996f7-a051-5dfa-938f-764404117554 | button | Leighs Handover of Area | YES, NO, N/A
d3dc978b-47b0-5467-98d5-85fbb379e7ed | button | Confirm materials delivered | YES, NO, N/A
f797e9f8-29b3-53fc-a836-35487fc9e6b0 | button | Gather Materials and Tools | YES, NO, N/A
863bd4f1-3d0f-4d9c-a22c-b092ebd4c98e | checkpoint | 2. SURFACE PREPARATION
08c68a29-b1bf-52cf-a159-6961764c5684 | button | Check Area clear of all other trades and their materials | YES, NO, N/A
559f6626-d969-55e9-a15b-c9c46d044572 | button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
c699f547-f864-560c-b2d2-cc9170db4377 | button | Check Recess Level meets requirements | YES, NO, N/A
b7ec8882-1354-5384-859d-c412901c1ad8 | button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
7ca4ad36-74d3-43d1-ac79-7429971b39e5 | signoff | Hold works to confirm preparation required
4dc7e51c-bff8-4ce9-b016-93ad99b47a9f | checkpoint | 3. PREPARE ENTRY MAT FOR INSTALLATION
8ab712da-7279-5038-a632-36b78d5ecc68 | button | Install Matwell frame | YES, NO, N/A
0b20b4dd-f6f4-5dd2-a1d6-70c33f5de521 | button | Level Floor to suit Thickness | YES, NO, N/A
71bc56b3-5d95-5b2e-87af-60471eaaadea | button | Dimention measured on site | YES, NO, N/A
b2ec7e85-7b63-45ff-a4a0-662ccdbfa82f | checkpoint | 4. ENTRY MAT INSTALLATION
f0869a0a-d628-5f07-aef4-197e3680e263 | button | Drop Entry Mat in to matwell | YES, NO, N/A
dbf0c82d-5b2f-46e9-82eb-92b37b93337d | checkpoint | 5. FINAL INSPECTION
4099c884-dc2d-58ab-80a2-3e473d673ede | button | Confirm no visible defects or issues. | PASS, FAIL, N/A
1d449020-e6ca-402a-ba09-2a915274f281 | checkpoint | 6. SUBCONTRACTOR VERIFICATION
1a91615f-5bf8-5fff-9649-6dfe680f5c0b | textbox | Actions/Remedial Items (if any)
5e16b064-b699-4754-bc22-a14aca11c5e3 | signoff | Subcontractor representative (Full name)
641f6258-31c3-445f-9c1f-6bc941e84ead | checkpoint | 7. LEIGHS VERIFICATION
019b613d-fc69-5b68-94e0-b403303e3b8d | textbox | Actions/Remedial Items (if any)
72b6e0a0-e9aa-4894-8a99-c089ea8cdf6d | signoff | Verified by Leighs representative (Full name)
f72589b6-50bb-4cf4-81fa-a8b0653816be | checklist | Floor Preparation |  | Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c79cacf5-613c-4999-9e8c-006cbaa9db03 | checkpoint | Check Area clear of all other trades and their materials
a0fc198e-27ca-42ae-9d1a-9b050bb3d6d2 | checkpoint | Grind Floor
83158405-3556-4c38-9f43-c27f9676cf55 | checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
07b6a332-8ad1-4045-b86a-7907b3df5d04 | checkpoint | Apply Moisture Fix
b1fd22f3-12ce-4e1e-a3e9-3d5c18403ac0 | checkpoint | Disc purged material
802b481b-c577-4e4b-a93f-e515cf28dc5c | checkpoint | Are there any cracks that require remediation?
ac1d0dc1-b8e1-4d86-bdea-481178b37571 | checkpoint | Remediate cracks
bb02fe18-68b7-4eec-b01f-a8bf23cb5d99 | checkpoint | Check floor for U3 (3mm variance over 3m)
5fd34fab-4704-46f4-891d-e99ef71cc029 | checkpoint | Check doors level within 2mm
f9ba4e37-160e-4350-8e1c-d05dc7fb588d | checkpoint | Apply Floor Levelling Compound as required
6a54e696-8b63-49ad-9c2b-dfe0956f079e | checkpoint | Apply feather coat, Sanded, Edges
0840d8b5-01b7-4c59-bc0a-d06805e51096 | signoff | SEND TO CLIENT FOR QUALITY APPROVAL
67a69e8a-371c-4d30-bf23-c0ec6572837e | checklist | Floor Preparation - Moisture Fix |  | Moisture Fix
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c322c14a-87ed-477c-ac20-e89261cf3801 | checkpoint | Check area clear of all other trades and their materials
01ec7475-0ef0-4ab2-a05d-27e8df09db76 | checkpoint | Have moisture readings been taken or required
ee867717-e0fb-49ba-8abc-eacc7af56018 | checkpoint | Is the pH level acceptable?
43946758-5e46-4d23-9af1-27f4f1aa9f70 | checkpoint | Check the concrete substrate dryness (RH)
e7a711b7-3657-4ac9-bcba-498cb337d65a | checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
ad8978ad-1aea-4698-9236-b0045885bc52 | checkpoint | Grind Floor
51d04702-ff8c-43c7-9144-6b651bbd0a21 | checkpoint | Does floor have U3 finish (3mm variance over 3m)
f1f75a4b-7f7f-4831-83c5-e3da4190ec48 | checkpoint | Are there any cracks that require remediation?
d6aec194-d0c9-43b6-86fe-982afbe239b6 | checkpoint | Remediate cracks
0198ea01-c3ee-48a3-9a7d-74817c11ee7f | checkpoint | Apply Moisture Fix
569ef868-f85a-432a-85db-c6dfaf95e66d | checkpoint | Disc purged material
c329ae2c-c06b-4906-af3d-ef4706fa7966 | checkpoint | Apply Floor Levelling Compound
ccdc7f50-7289-4b9b-807d-b8a6e4d1f236 | checkpoint | Apply feather coat, Sanded, Edges
b03b29d0-82c7-44a4-badc-cd48ae07c4d6 | signoff | SEND TO CLIENT FOR QUALITY APPROVAL
465394dd-7ef6-4223-a27d-c7dc4025f423 | checklist | Floor Vinyl Installation |  | Floor Vinyl Installation
4925d304-0a8d-43ea-a5f4-292a3826d7f3 | section | Preparation
976e3840-6b9c-4431-b9f7-5f4001d0bef1 | checkpoint | Check area clear of all other trades and their materials
c9892cd2-e655-4c02-b877-febc257e018c | checkpoint | Check wall for smoothness where coving
016dc3c5-61c7-4b2d-a815-1f0173038347 | checkpoint | Measure area
f7a143aa-9b34-4b4e-a546-80bb0e2504df | checkpoint | Acclimatise vinyl
e31b5253-3eb6-4815-b2c3-66e3de67553c | section | Installation
72808679-ae2f-492d-9d47-8e734d09898e | checkpoint | Confirm vinyl layout direction
2636252f-0909-4080-bf82-2298015f8cd0 | checkpoint | Confirm coving location/type
700cc6e8-0b9b-4d5d-adb5-35ded0be9962 | checkpoint | Glue out floors
1ac870ae-efbd-4bc9-b887-0b9daee516f6 | checkpoint | Install vinyl
7bc79e63-7085-4e6d-84d4-cbe59835100d | checkpoint | Install coving & capping/sealant as applicable
ab64f9ff-a868-4082-9a16-cd0ab3445b63 | section | Handover & Signoff
e1b1131f-a5a3-42b9-8474-28d38435d3e4 | checkpoint | Remove all excess material
f1e1a1a1-302c-4856-8785-408bf7f0697a | checkpoint | Clean any excess glue
5a386cec-6c1c-4f32-ba92-777fbb65ceea | checkpoint | Report for inspection
c4dcacf8-5964-41bf-9246-c6dcf5664b5a | checkpoint | Quality Approval
7ab8a5f6-de63-4cc9-9abb-1e10bf75d95a | signoff | SEND TO CLIENT FOR QUALITY APPROVAL
94e83ac7-950c-4ef8-968d-ef2d2f073cad | checklist | Wall Vinyl Installation |  | Wall Vinyl Installation
c7cfdd35-05e0-408f-8aeb-569598190c8b | section | Preparation
15349248-9c2c-4083-9e64-c838d9dfa956 | checkpoint | Check area clear of all other trades and their materials
5df6fe16-70b0-4b53-b187-3a457c4e35fb | checkpoint | Check walls are prepared to a Level 4 finish with a seal coat
15221f11-49af-41ce-813b-e3ef7b6af62e | checkpoint | Measure area
e1127021-c4f5-4bee-95d1-0192e13b0a35 | checkpoint | Acclimatise vinyl
5263a992-a110-45a2-9a8f-d27cbfc2a9cc | section | Installation
6a3ffe3b-dc11-4156-ba35-e571b294dd43 | checkpoint | Confirm wall vinyl direction as per cutting plan
9edbc71d-b397-4124-8d16-db0fc0b57b7a | checkpoint | Confirm wall vinyl type as per finishes schedule
e65eb776-81d2-4b84-8617-2b47fe72f145 | checkpoint | Glue out wall
6507f1f4-1983-4019-a91b-05fb7780f345 | checkpoint | Install wall vinyl
c4da0523-fb13-4f3a-bd3b-fa0c83101644 | checkpoint | Install coving & capping/sealant as applicable
59f5b691-9f43-4803-aec3-44505158b39f | checkpoint | Weld joins
4a597f7c-6e41-443c-96ff-ebc51a7048d8 | checkpoint | Wipe down the wall to remove adhesive residue or dust
c9ba8aab-4843-472f-9282-c287ce9b46e7 | section | Handover & Signoff
5d5a044e-5456-46c1-a81a-59e45d014dfa | checkpoint | Remove all excess material
e428a1ca-4bdb-40f4-9c3f-f25e270a3e6b | checkpoint | Report for inspection
8852f268-fbdb-4003-aa07-0f939fb3caf6 | checkpoint | Quality Approval
3f31fca6-ab64-4a82-adb7-9384dbab98b2 | signoff | SEND TO CLIENT FOR QUALITY APPROVAL