## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Floor Preparation (North Building) |  | Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c79cacf5-613c-4999-9e8c-006cbaa9db03 | checkpoint | Check Area clear of all other trades and their materials
a0fc198e-27ca-42ae-9d1a-9b050bb3d6d2 | checkpoint | Grind Floor
83158405-3556-4c38-9f43-c27f9676cf55 | checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
07b6a332-8ad1-4045-b86a-7907b3df5d04 | checkpoint | Apply Moisture Fix if required for job
b1fd22f3-12ce-4e1e-a3e9-3d5c18403ac0 | checkpoint | Disc purged material
802b481b-c577-4e4b-a93f-e515cf28dc5c | checkpoint | Are there any cracks that require remediation?
ac1d0dc1-b8e1-4d86-bdea-481178b37571 | checkpoint | Remediate cracks
bb02fe18-68b7-4eec-b01f-a8bf23cb5d99 | checkpoint | Check floor for U3 (3mm variance over 3m)
5fd34fab-4704-46f4-891d-e99ef71cc029 | checkpoint | Check doors level within 2mm
f9ba4e37-160e-4350-8e1c-d05dc7fb588d | checkpoint | Apply Floor Levelling Compound as required
6a54e696-8b63-49ad-9c2b-dfe0956f079e | checkpoint | Apply feather coat, Sanded, Edges
0840d8b5-01b7-4c59-bc0a-d06805e51096 | signoff | SEND TO CLIENT FOR QUALITY APPROVAL
| checklist | Carpet Tile Installation (North Building) |  | Carpet Tile Installation
853777c4-ab05-43e2-abc1-b759383ee7c1 | section | Preparation
bd2ed55a-369e-469f-ab3b-f736df2afb4c | checkpoint | Check area clear of all other trades and their materials
fcb2f81c-ec2b-425d-976c-44663ff9ab9b | checkpoint | Check floor if prep is required
8339ce92-e1d4-4d86-ab2b-7839967eb329 | checkpoint | Measure area
8ba7a99c-a3c2-4841-bd75-fb99be961509 | section | Installation
ebd9cae2-8e02-4d01-83da-04b543dbdd5a | checkpoint | Confirm carpet tile pattern direction/layout
b06889c2-7623-4f33-a8e8-f0f1f8dd683b | checkpoint | Glue out floors
962f2f31-9be3-48b1-8f64-098bf096dccd | checkpoint | Install carpet tiles
45e07f1a-755d-4a9f-88f2-05f558267b4d | checkpoint | Install trims as applicable
f32e9646-a507-4163-b0dc-4986db5b3190 | section | Handover & Signoff
3306d86a-563b-46b4-a954-d0f170ef586b | checkpoint | Remove all excess material
500d4d93-b155-45e7-9c58-9c8f2e2067a1 | checkpoint | Clean any excess glue
a63d3a7b-0822-4f09-a538-06f6ce269d79 | checkpoint | Quality Approval
a29c0a64-f07d-4021-b79f-f41668df43c7 | signoff | SEND TO CLIENT FOR QUALITY APPROVAL
| checklist | Floor Vinyl Installation (North Building) |  | Floor Vinyl Installation
4925d304-0a8d-43ea-a5f4-292a3826d7f3 | section | Preparation
976e3840-6b9c-4431-b9f7-5f4001d0bef1 | checkpoint | Check area clear of all other trades and their materials
c9892cd2-e655-4c02-b877-febc257e018c | checkpoint | Check wall for smoothness where coving
016dc3c5-61c7-4b2d-a815-1f0173038347 | checkpoint | Measure area
f7a143aa-9b34-4b4e-a546-80bb0e2504df | checkpoint | Acclimatise vinyl
e31b5253-3eb6-4815-b2c3-66e3de67553c | section | Installation
72808679-ae2f-492d-9d47-8e734d09898e | checkpoint | Confirm vinyl layout direction
2636252f-0909-4080-bf82-2298015f8cd0 | checkpoint | Confirm coving location/type
700cc6e8-0b9b-4d5d-adb5-35ded0be9962 | checkpoint | Glue out floors
1ac870ae-efbd-4bc9-b887-0b9daee516f6 | checkpoint | Install vinyl
7bc79e63-7085-4e6d-84d4-cbe59835100d | checkpoint | Install coving & capping/sealant as applicable
ab64f9ff-a868-4082-9a16-cd0ab3445b63 | section | Handover & Signoff
e1b1131f-a5a3-42b9-8474-28d38435d3e4 | checkpoint | Remove all excess material
f1e1a1a1-302c-4856-8785-408bf7f0697a | checkpoint | Clean any excess glue
c4dcacf8-5964-41bf-9246-c6dcf5664b5a | checkpoint | Quality Approval
7ab8a5f6-de63-4cc9-9abb-1e10bf75d95a | signoff | SEND TO CLIENT FOR QUALITY APPROVAL
| checklist | Wall Vinyl Installation (North Building) |  | Wall Vinyl Installation
c7cfdd35-05e0-408f-8aeb-569598190c8b | section | Preparation
15349248-9c2c-4083-9e64-c838d9dfa956 | checkpoint | Check area clear of all other trades and their materials
5df6fe16-70b0-4b53-b187-3a457c4e35fb | checkpoint | Check walls are prepared to a Level 4 finish with a seal coat
15221f11-49af-41ce-813b-e3ef7b6af62e | checkpoint | Measure area
e1127021-c4f5-4bee-95d1-0192e13b0a35 | checkpoint | Acclimatise vinyl
5263a992-a110-45a2-9a8f-d27cbfc2a9cc | section | Installation
6a3ffe3b-dc11-4156-ba35-e571b294dd43 | checkpoint | Confirm wall vinyl direction as per cutting plan
9edbc71d-b397-4124-8d16-db0fc0b57b7a | checkpoint | Confirm wall vinyl type as per finishes schedule
e65eb776-81d2-4b84-8617-2b47fe72f145 | checkpoint | Glue out wall
6507f1f4-1983-4019-a91b-05fb7780f345 | checkpoint | Install wall vinyl
c4da0523-fb13-4f3a-bd3b-fa0c83101644 | checkpoint | Install coving & capping/sealant as applicable
59f5b691-9f43-4803-aec3-44505158b39f | checkpoint | Weld joins
4a597f7c-6e41-443c-96ff-ebc51a7048d8 | checkpoint | Wipe down the wall to remove adhesive residue or dust
c9ba8aab-4843-472f-9282-c287ce9b46e7 | section | Handover & Signoff
5d5a044e-5456-46c1-a81a-59e45d014dfa | checkpoint | Remove all excess material
8852f268-fbdb-4003-aa07-0f939fb3caf6 | checkpoint | Quality Approval
3f31fca6-ab64-4a82-adb7-9384dbab98b2 | signoff | SEND TO CLIENT FOR QUALITY APPROVAL