## Table 1
Project Name: Otaki to North of Levin Project (O2NL) Prepared by: Miguel G Antonio Rev. No. A
| ITP No.: Ō2NL-STH-000-CN-ITP-0002 Project | [9 empty] | Miguel G Antonio
| Construction Process: |  | Engineer: Ō2NL-STH-000-CN-CEP-0006_A – General Fencing Works Approved by: Matt Diederich
LEGEND | [9 empty] | REFERENCE DOCUMENTS
Verification Activity | [9 empty] | Development:
CEP-0006 – General Fencing Works
| H | Hold Point |  | Work shall not proceed past the Hold Point until released by the organisation imposing the Hold Point.
DN1210-016 ITP Fencing_Rev 1
| W | Witness Point |  | An inspection point that may be witnessed by the organisation imposing the Witness Point.
Implementation:
| I | Inspection |  | Formal inspection activity to be undertaken and recorded. | [5 empty] | Include the relevant CEP.
| S | Surveillance |  | An activity that is subject to ongoing monitoring.
| R | Review |  | Review of text reports/records or other evidence of compliance.
Responsible Inspectorate (RI) (may be modified to meet site specific requirements)
APPROVAL/REVISION
SA – South Alliance
PM – Project Manager
[10 empty] | Rev |  | Date |  | Details |  |  |  | App’d (Alliance) | App’d (Client)
CM – Construction Manager
ENG – Responsible Engineer
[10 empty] | A |  | 2025-07-21 |  | Issued For Construction
SUP – Supervisor
SQN – Subcontractor Quality Nominee
QMR – Quality Management Representative
SMR– Safety Management Representative
EMR– Environment Management Representative
COMMS – Community Liaison
Construction Process: |  |  |  |  | General Fencing Works | [7 empty] | ITP No.: | ITP-0002 |  |  | Rev A
Item |  | Basic Job Step |  |  |  | RI |  | Acceptance Criteria | Applicable Standard | Inspection Test |  |  |  | Verification Activity by |  |  | Verifying Records |  |  | Sign-off
[10 empty] | Method |  |  | Frequency | SubCon | Alliance | Client
1.0 Preliminaries
1.1 |  | CEP approval & sign-off |  |  |  | SA |  | Completely reviewed by all disciplines w/ document completely signed-off & issued for construction | Ō2NL SA Interdisciplinary Review | Review |  |  | Prior to Start; Any change of scope/ methodology | R | R |  | Signed CEP
1.2 |  | JSEA approval & sign-off |  |  |  | SA |  | Completely reviewed by all disciplines w/ document completely signed-off & issued for construction | Ō2NL SA Interdisciplinary Review | Review |  |  | Prior to Start; Every 6 months; change in working parameters or risks | R | R |  | Signed JSEA
1.3 |  | Ecological & Environmental walkthrough |  |  |  | EMR |  | Ecological & environmental sign-off to proceed with works in the area / lot planned |  | Area / Lot walkover |  |  | Prior to start of works | H | H |  | Documented correspondence / ITP Sign-off (EMR)
1.4 |  | Communication to stakeholders (where required) |  |  |  | SA |  | Proper communications with stakeholder that fencing works relates to (e.g. balance land owner, lots sharing designation boundaries) | NZTA Contractor Obligations | Advance Comms / Letter Drop (as required) |  |  | Prior to start of works | H | H |  | Documented correspondence / ITP Sign-off (Comms)
1.5 |  | Valid Permits related to scope of works |  |  |  | ENG/ SUP |  | Completely filled-out with accurate & up-to-date information of the site and scope of works necessary | Ō2NL SA Permits & Register | Review |  |  | Prior to start of works / Weekly as work continues | H | H |  | Permit Sign-off & Preliminary ITP Sign-off
1.6 |  | Extent of Fencing set-out |  |  |  | ENG |  | Ensure fence line has been properly marked out and agreed with engineer in accordance with any property obligations and drawings | Contractor Obligations / Design Drawings | ENG Approval |  |  | Prior to start of works; any revision to IFC drawings/ data | W | H |  | ITP Sign-off (ENG)
1.7 |  | Existing Fence Network |  |  |  | ENG |  | Confirm limits of any existing fences or fence network that is affected by planned fencing works | Contractor Obligations / Design Drawings | ENG Approval |  |  | Prior to start of works | W | H |  | Survey Data & ITP Sign- off (ENG)
2.0 Material Compliance
2.1 |  | Timber (Posts, Stays, Battens, rails, palings) |  |  |  | ENG |  | Finished treatment | O2NL Project specifications | ENG Approval |  |  | Prior to installation | I | R |  | Copy of delivery docket
2.2 |  | Steel (Wire / Chain Link Fence) |  |  |  | ENG |  | Standard galvanised high tensile steel wire | O2NL Project specifications | ENG Approval |  |  | Prior to installation | I | R |  | Copy of delivery docket
2.3 |  | Steel Gates & Fittings (Fixings, fasteners, gudgeons, hinges, chains, locks, etc) |  |  |  | ENG |  | Correct dimensions & galvanised treatment and all fittings are fit for purpose | O2NL Project specifications | ENG Approval |  |  | Prior to installation | I | R |  | Copy of delivery docket
3.0 Construction
3.1 |  | 7-wire Fence/s |  |  |  | ENG |  | As per typical 7-wire detail | Per design drawings | Visual Inspection/s & ENG Approval |  |  | Throughout construction | R | W |  | Photo documentation & ITP Sign-off
3.2 |  | Deer Fence/s |  |  |  | ENG |  | As per typical deer fence detail | Per design drawings | Visual Inspection/s & ENG Approval |  |  | Throughout construction | R | W |  | Photo documentation & ITP Sign-off
3.3 |  | Paling Fence/s |  |  |  | ENG |  | As per typical paling fence detail | Per design drawings | Visual Inspection/s & ENG Approval |  |  | Throughout construction | R | W |  | Photo documentation & ITP Sign-off
3.4 |  | Electric Fence/s |  |  |  | ENG |  | As per typical electrification detail | Per design drawings | Visual Inspection/s & ENG Approval |  |  | Throughout construction | R | W |  | Photo documentation & ITP Sign-off
3.5 |  | Stream-crossing Fences / Flood Gates |  |  |  | ENG |  | As per typical flood gate detail | Per design drawings | Visual Inspection/s & ENG Approval |  |  | Throughout construction | R | W |  | Photo documentation & ITP Sign-off
4.0 Post-Construction
4.1 |  | Survey As-built |  |  |  |  | ENG | Quality check on completed fence based on location vs project designation | Within project designation | ENG Approval |  |  | Upon completion of works | H | W |  | Survey Data & ITP Sign- off (ENG)
4.2 |  | Stake-holder acceptance (where required) |  |  |  |  | SA | Documented satisfactory acceptance of boundary | Contractor Obligations | Comms |  |  | Upon completion of works | W | W |  | As-built Documentation & ITP Sign-off