## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | O2NL-STH-000-CN-ITP-0002 General Fencing Works | itp
section | 1.0 Preliminaries
checkpoint | 1.1 - CEP approval & sign-off
label | RI - SA
label | Acceptance Criteria - Completely reviewed by all disciplines w/ document completely signed-off & issued for construction
label | Applicable Standard - Ō2NL SA Interdisciplinary Review
label | Inspection Test: Method - Review
label | Inspection Test: Frequency - Prior to Start; Any change of scope/ methodology
label | Verification Activity by: SubCon - R
label | Verification Activity by: Alliance - R
label | Verifying Records - Signed CEP
checkpoint | 1.2 - JSEA approval & sign-off
label | RI - SA
label | Acceptance Criteria - Completely reviewed by all disciplines w/ document completely signed-off & issued for construction
label | Applicable Standard - Ō2NL SA Interdisciplinary Review
label | Inspection Test: Method - Review
label | Inspection Test: Frequency - Prior to Start; Every 6 months; change in working parameters or risks
label | Verification Activity by: SubCon - R
label | Verification Activity by: Alliance - R
label | Verifying Records - Signed JSEA
checkpoint | 1.3 - Ecological & Environmental walkthrough
label | RI - EMR
label | Acceptance Criteria - Ecological & environmental sign-off to proceed with works in the area / lot planned
label | Inspection Test: Method - Area / Lot walkover
label | Inspection Test: Frequency - Prior to start of works
label | Verification Activity by: SubCon - H
label | Verification Activity by: Alliance - H
label | Verifying Records - Documented correspondence / ITP Sign-off (EMR)
holdpoint | HOLD POINT
checkpoint | 1.4 - Communication to stakeholders (where required)
label | RI - SA
label | Acceptance Criteria - Proper communications with stakeholder that fencing works relates to (e.g. balance land owner, lots sharing designation boundaries)
label | Applicable Standard - NZTA Contractor Obligations
label | Inspection Test: Method - Advance Comms / Letter Drop (as required)
label | Inspection Test: Frequency - Prior to start of works
label | Verification Activity by: SubCon - H
label | Verification Activity by: Alliance - H
label | Verifying Records - Documented correspondence / ITP Sign-off (Comms)
holdpoint | HOLD POINT
checkpoint | 1.5 - Valid Permits related to scope of works
label | RI - ENG/ SUP
label | Acceptance Criteria - Completely filled-out with accurate & up-to-date information of the site and scope of works necessary
label | Applicable Standard - Ō2NL SA Permits & Register
label | Inspection Test: Method - Review
label | Inspection Test: Frequency - Prior to start of works / Weekly as work continues
label | Verification Activity by: SubCon - H
label | Verification Activity by: Alliance - H
label | Verifying Records - Permit Sign-off & Preliminary ITP Sign-off
holdpoint | HOLD POINT
checkpoint | 1.6 - Extent of Fencing set-out
label | RI - ENG
label | Acceptance Criteria - Ensure fence line has been properly marked out and agreed with engineer in accordance with any property obligations and drawings
label | Applicable Standard - Contractor Obligations / Design Drawings
label | Inspection Test: Method - ENG Approval
label | Inspection Test: Frequency - Prior to start of works; any revision to IFC drawings/ data
label | Verification Activity by: SubCon - W
label | Verification Activity by: Alliance - H
label | Verifying Records - ITP Sign-off (ENG)
holdpoint | HOLD POINT
checkpoint | 1.7 - Existing Fence Network
label | RI - ENG
label | Acceptance Criteria - Confirm limits of any existing fences or fence network that is affected by planned fencing works
label | Applicable Standard - Contractor Obligations / Design Drawings
label | Inspection Test: Method - ENG Approval
label | Inspection Test: Frequency - Prior to start of works
label | Verification Activity by: SubCon - W
label | Verification Activity by: Alliance - H
label | Verifying Records - Survey Data & ITP Sign- off (ENG)
holdpoint | HOLD POINT
section | 2.0 Material Compliance
checkpoint | 2.1 - Timber (Posts, Stays, Battens, rails, palings)
label | RI - ENG
label | Acceptance Criteria - Finished treatment
label | Applicable Standard - O2NL Project specifications
label | Inspection Test: Method - ENG Approval
label | Inspection Test: Frequency - Prior to installation
label | Verification Activity by: SubCon - I
label | Verification Activity by: Alliance - R
label | Verifying Records - Copy of delivery docket
checkpoint | 2.2 - Steel (Wire / Chain Link Fence)
label | RI - ENG
label | Acceptance Criteria - Standard galvanised high tensile steel wire
label | Applicable Standard - O2NL Project specifications
label | Inspection Test: Method - ENG Approval
label | Inspection Test: Frequency - Prior to installation
label | Verification Activity by: SubCon - I
label | Verification Activity by: Alliance - R
label | Verifying Records - Copy of delivery docket
checkpoint | 2.3 - Steel Gates & Fittings (Fixings, fasteners, gudgeons, hinges, chains, locks, etc)
label | RI - ENG
label | Acceptance Criteria - Correct dimensions & galvanised treatment and all fittings are fit for purpose
label | Applicable Standard - O2NL Project specifications
label | Inspection Test: Method - ENG Approval
label | Inspection Test: Frequency - Prior to installation
label | Verification Activity by: SubCon - I
label | Verification Activity by: Alliance - R
label | Verifying Records - Copy of delivery docket
section | 3.0 Construction
checkpoint | 3.1 - 7-wire Fence/s
label | RI - ENG
label | Acceptance Criteria - As per typical 7-wire detail
label | Applicable Standard - Per design drawings
label | Inspection Test: Method - Visual Inspection/s & ENG Approval
label | Inspection Test: Frequency - Throughout construction
label | Verification Activity by: SubCon - R
label | Verification Activity by: Alliance - W
label | Verifying Records - Photo documentation & ITP Sign-off
checkpoint | 3.2 - Deer Fence/s
label | RI - ENG
label | Acceptance Criteria - As per typical deer fence detail
label | Applicable Standard - Per design drawings
label | Inspection Test: Method - Visual Inspection/s & ENG Approval
label | Inspection Test: Frequency - Throughout construction
label | Verification Activity by: SubCon - R
label | Verification Activity by: Alliance - W
label | Verifying Records - Photo documentation & ITP Sign-off
checkpoint | 3.3 - Paling Fence/s
label | RI - ENG
label | Acceptance Criteria - As per typical paling fence detail
label | Applicable Standard - Per design drawings
label | Inspection Test: Method - Visual Inspection/s & ENG Approval
label | Inspection Test: Frequency - Throughout construction
label | Verification Activity by: SubCon - R
label | Verification Activity by: Alliance - W
label | Verifying Records - Photo documentation & ITP Sign-off
checkpoint | 3.4 - Electric Fence/s
label | RI - ENG
label | Acceptance Criteria - As per typical electrification detail
label | Applicable Standard - Per design drawings
label | Inspection Test: Method - Visual Inspection/s & ENG Approval
label | Inspection Test: Frequency - Throughout construction
label | Verification Activity by: SubCon - R
label | Verification Activity by: Alliance - W
label | Verifying Records - Photo documentation & ITP Sign-off
checkpoint | 3.5 - Stream-crossing Fences / Flood Gates
label | RI - ENG
label | Acceptance Criteria - As per typical flood gate detail
label | Applicable Standard - Per design drawings
label | Inspection Test: Method - Visual Inspection/s & ENG Approval
label | Inspection Test: Frequency - Throughout construction
label | Verification Activity by: SubCon - R
label | Verification Activity by: Alliance - W
label | Verifying Records - Photo documentation & ITP Sign-off
section | 4.0 Post-Construction
checkpoint | 4.1 - Survey As-built
label | Acceptance Criteria - Quality check on completed fence based on location vs project designation
label | Applicable Standard - Within project designation
label | Inspection Test: Method - ENG Approval
label | Inspection Test: Frequency - Upon completion of works
label | Verification Activity by: SubCon - H
label | Verification Activity by: Alliance - W
label | Verifying Records - Survey Data & ITP Sign- off (ENG)
holdpoint | HOLD POINT
checkpoint | 4.2 - Stake-holder acceptance (where required)
label | Acceptance Criteria - Documented satisfactory acceptance of boundary
label | Applicable Standard - Contractor Obligations
label | Inspection Test: Method - Comms
label | Inspection Test: Frequency - Upon completion of works
label | Verification Activity by: SubCon - W
label | Verification Activity by: Alliance - W
label | Verifying Records - As-built Documentation & ITP Sign-off