## Sheet1
1.1 | Material Compliance | HP | Ensure the supplied paint system meets the requirements as per the specification. . | Prior to commencement | Document review | NZTA S10 Approved paint system to be signed off by the Design Engineer | Painting system manufacturers records | 1.1 - Material Compliance | ACTION (Hold, Monitor, Witness) - HP | Detail - Ensure the supplied paint system meets the requirements as per the specification. . | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review | Conformance Criteria - NZTA S10 Approved paint system to be signed off by the Design Engineer | Records - Painting system manufacturers records | 1.1 - Material Compliance
1.1.1 | Material Compliance | HP | Confirmation of Design life not less than 10 years | Prior to commencement | Document review |  |  | 1.1.1 - Material Compliance | ACTION (Hold, Monitor, Witness) - HP | Detail - Confirmation of Design life not less than 10 years | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review | Conformance Criteria - | Records - | ACTION (Hold, Monitor, Witness) - HP
1.1.2 | Material Compliance | HP | Confirmation of cleaning product (to align with TDS) - Pressure washing of substrate no greater than 2700psi. | Prior to commencement | Document review |  |  | 1.1.2 - Material Compliance | ACTION (Hold, Monitor, Witness) - HP | Detail - Confirmation of cleaning product (to align with TDS) - Pressure washing of substrate no greater than 2700psi. | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review | Conformance Criteria - | Records - | Detail - Ensure the supplied paint system meets the requirements as per the specification. .
1.1.3 | Material Compliance | HP | Collection of names, experience and qualifications of coating applicators | Prior to commencement | Document review | NZTA S/10 4.1 c | Applicator's detail submission | 1.1.3 - Material Compliance | ACTION (Hold, Monitor, Witness) - HP | Detail - Collection of names, experience and qualifications of coating applicators | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review | Conformance Criteria - NZTA S/10 4.1 c | Records - Applicator's detail submission | Frequency - Prior to commencement
1.2 | Submit Frequency | HP | Subcontractor to produce specification for the extent and frequency of testing for Design Engineer for approval | Prior to commencement | Document submission |  | Approved subcontractor testing schedule | 1.2 - Submit Frequency | ACTION (Hold, Monitor, Witness) - HP | Detail - Subcontractor to produce specification for the extent and frequency of testing for Design Engineer for approval | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Document submission | Conformance Criteria - | Records - Approved subcontractor testing schedule | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
2.1 | Contruction | HP | Visual inspection to ensure it is dust free, clean and repaired prior to application. Any fairing coat/grout that is used to achieve the F5 finish will need the required curing time as per product specification. | Prior to commencement | Visual inspection and Document review | Ensure PCP and Snag List for the structure are both signed off BBO sign off for Pre paint inspection to ensure F5 finish has been achieved | Completed PCP CHAR(AMP) Snag List | 2.1 - Contruction | ACTION (Hold, Monitor, Witness) - HP | Detail - Visual inspection to ensure it is dust free, clean and repaired prior to application. Any fairing coat/grout that is used to achieve the F5 finish will need the required curing time as per product specification. | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Document review | Conformance Criteria - Ensure PCP and Snag List for the structure are both signed off BBO sign off for Pre paint inspection to ensure F5 finish has been achieved | Records - Completed PCP CHAR(AMP) Snag List | Conformance Criteria - NZTA S10 Approved paint system to be signed off by the Design Engineer
2.2 | Pre-paint cleaning and substrate verifications | W | Demonstration of substrate cleaned all dust, dirt and other surface contaminants must be removed. Using manufacturer’s approved surface cleaner | Before painting | Visual inspection |  |  | 2.2 - Pre-paint cleaning and substrate verifications | ACTION (Hold, Monitor, Witness) - W | Detail - Demonstration of substrate cleaned all dust, dirt and other surface contaminants must be removed. Using manufacturer’s approved surface cleaner | Frequency - Before painting | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection | Conformance Criteria - | Records - | Records - Painting system manufacturers records
2.3 | Construction - pre paint checks | W | Pre-paint checks Relative Humidity (Measured), Air Temperature (Measured), Surface Temperature (Measured), Dew Point (Calculated) Surface minus Dew Point (Calculated), Dry Surface (Visual Inspection) | Before painting | Measuring Devices | QA Checksheets |  | 2.3 - Construction - pre paint checks | ACTION (Hold, Monitor, Witness) - W | Detail - Pre-paint checks Relative Humidity (Measured), Air Temperature (Measured), Surface Temperature (Measured), Dew Point (Calculated) Surface minus Dew Point (Calculated), Dry Surface (Visual Inspection) | Frequency - Before painting | Inspection / Test Method submission, visual inspection, testing, measure, review - Measuring Devices | Conformance Criteria - QA Checksheets | Records - | 1.1.1 - Material Compliance
2.4 | Construction | W | Design Engineer to be advised when painting is occuring so they can visit site and do a visual inspection | During Painting | Visual Inspection |  |  | 2.4 - Construction | ACTION (Hold, Monitor, Witness) - W | Detail - Design Engineer to be advised when painting is occuring so they can visit site and do a visual inspection | Frequency - During Painting | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection | Conformance Criteria - | Records - | ACTION (Hold, Monitor, Witness) - HP
2.5 | Construction | W | Demonstration of surface moisture conditions. - 1 test every 46m² or for every time painting | Before painting (minimum 28 days after concrete, grout and fairing coat has cured) |  | NZTA S/10 8.8 refers to ASTM D4263 |  | 2.5 - Construction | ACTION (Hold, Monitor, Witness) - W | Detail - Demonstration of surface moisture conditions. - 1 test every 46m² or for every time painting | Frequency - Before painting (minimum 28 days after concrete, grout and fairing coat has cured) | Inspection / Test Method submission, visual inspection, testing, measure, review - | Conformance Criteria - NZTA S/10 8.8 refers to ASTM D4263 | Records - | Detail - Confirmation of Design life not less than 10 years
2.6 | Painting | HP | Ensure dust control throughout application and curing. Co-ordinate other site activites that may generate dust to stop until the paint is dry. | Before and During painting | Visual inspection | No dust |  | 2.6 - Painting | ACTION (Hold, Monitor, Witness) - HP | Detail - Ensure dust control throughout application and curing. Co-ordinate other site activites that may generate dust to stop until the paint is dry. | Frequency - Before and During painting | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection | Conformance Criteria - No dust | Records - | Frequency - Prior to commencement
2.7 | Painting | HP | Ensure subcontractor records the date, type, location and extent of all coatings | During Painting | Drawings |  |  | 2.7 - Painting | ACTION (Hold, Monitor, Witness) - HP | Detail - Ensure subcontractor records the date, type, location and extent of all coatings | Frequency - During Painting | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings | Conformance Criteria - | Records - | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
2.8 | Painting | HP | Recoating time as per manufacturers specifications, and weather conditions. | After painting | Document Review |  |  | 2.8 - Painting | ACTION (Hold, Monitor, Witness) - HP | Detail - Recoating time as per manufacturers specifications, and weather conditions. | Frequency - After painting | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review | Conformance Criteria - | Records - | Conformance Criteria -
2.9 | Completed paint system | HP | 1. Dry Film Thickness 2. Bond Strength | 14 days after painting | NZTA S10 Section 13.2 | DFT minimum of 100 microns Bond strength minimum 2MPa | IANZ Test Results or other approved | 2.9 - Completed paint system | ACTION (Hold, Monitor, Witness) - HP | Detail - 1. Dry Film Thickness 2. Bond Strength | Frequency - 14 days after painting | Inspection / Test Method submission, visual inspection, testing, measure, review - NZTA S10 Section 13.2 | Conformance Criteria - DFT minimum of 100 microns Bond strength minimum 2MPa | Records - IANZ Test Results or other approved | Records -
2.1 | Completed paint system | HP | Post works inspection with BBO Sign Off | At completion of painting | Dry Film Thickness | The completed paint system or coating shall be of uniform thickness, free of runs, sags, pinholes and bubbles, mudcracking, dry overspray, grit inclusion etc. All such imperfections shall be removed or made good to the satisfaction of the Design Engineer. |  | 2.1 - Completed paint system | ACTION (Hold, Monitor, Witness) - HP | Detail - Post works inspection with BBO Sign Off | Frequency - At completion of painting | Inspection / Test Method submission, visual inspection, testing, measure, review - Dry Film Thickness | Conformance Criteria - The completed paint system or coating shall be of uniform thickness, free of runs, sags, pinholes and bubbles, mudcracking, dry overspray, grit inclusion etc. All such imperfections shall be removed or made good to the satisfaction of the Design Engineer. | Records - | 1.1.2 - Material Compliance
3.1 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file | At completion of Lot | Document Review |  |  | 3.1 - Lot Number QA File | ACTION (Hold, Monitor, Witness) - W | Detail - Ensure all OFIs are closed and included within QA file | Frequency - At completion of Lot | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review | Conformance Criteria - | Records - | ACTION (Hold, Monitor, Witness) - HP
3.2 | Delivery dockets | W | Delivery Dockets to be included in QA file | At completion of Lot | Document Review |  | Delivery Dockets | 3.2 - Delivery dockets | ACTION (Hold, Monitor, Witness) - W | Detail - Delivery Dockets to be included in QA file | Frequency - At completion of Lot | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review | Conformance Criteria - | Records - Delivery Dockets | Detail - Confirmation of cleaning product (to align with TDS) - Pressure washing of substrate no greater than 2700psi.
3.2 | As-builts | HP | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | 3.2 - As-builts | ACTION (Hold, Monitor, Witness) - HP | Detail - Red pen mark up drawings to be included in QA file | Frequency - At the completion of the Lot of work | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings | Conformance Criteria - | Records - Asbuilt Drawing | Frequency - Prior to commencement
Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
Conformance Criteria -
Records -
1.1.3 - Material Compliance
ACTION (Hold, Monitor, Witness) - HP
Detail - Collection of names, experience and qualifications of coating applicators
Frequency - Prior to commencement
Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
Conformance Criteria - NZTA S/10 4.1 c
Records - Applicator's detail submission
1.2 - Submit Frequency
ACTION (Hold, Monitor, Witness) - HP
Detail - Subcontractor to produce specification for the extent and frequency of testing for Design Engineer for approval
Frequency - Prior to commencement
Inspection / Test Method submission, visual inspection, testing, measure, review - Document submission
Conformance Criteria -
Records - Approved subcontractor testing schedule
2.1 - Contruction
ACTION (Hold, Monitor, Witness) - HP
Detail - Visual inspection to ensure it is dust free, clean and repaired prior to application. Any fairing coat/grout that is used to achieve the F5 finish will need the required curing time as per product specification.
Frequency - Prior to commencement
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Document review
Conformance Criteria - Ensure PCP and Snag List for the structure are both signed off BBO sign off for Pre paint inspection to ensure F5 finish has been achieved
Records - Completed PCP CHAR(AMP) Snag List
2.2 - Pre-paint cleaning and substrate verifications
ACTION (Hold, Monitor, Witness) - W
Detail - Demonstration of substrate cleaned all dust, dirt and other surface contaminants must be removed. Using manufacturer’s approved surface cleaner
Frequency - Before painting
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
Conformance Criteria -
Records -
2.3 - Construction - pre paint checks
ACTION (Hold, Monitor, Witness) - W
Detail - Pre-paint checks Relative Humidity (Measured), Air Temperature (Measured), Surface Temperature (Measured), Dew Point (Calculated) Surface minus Dew Point (Calculated), Dry Surface (Visual Inspection)
Frequency - Before painting
Inspection / Test Method submission, visual inspection, testing, measure, review - Measuring Devices
Conformance Criteria - QA Checksheets
Records -
2.4 - Construction
ACTION (Hold, Monitor, Witness) - W
Detail - Design Engineer to be advised when painting is occuring so they can visit site and do a visual inspection
Frequency - During Painting
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
Conformance Criteria -
Records -
2.5 - Construction
ACTION (Hold, Monitor, Witness) - W
Detail - Demonstration of surface moisture conditions. - 1 test every 46m² or for every time painting
Frequency - Before painting (minimum 28 days after concrete, grout and fairing coat has cured)
Inspection / Test Method submission, visual inspection, testing, measure, review -
Conformance Criteria - NZTA S/10 8.8 refers to ASTM D4263
Records -
2.6 - Painting
ACTION (Hold, Monitor, Witness) - HP
Detail - Ensure dust control throughout application and curing. Co-ordinate other site activites that may generate dust to stop until the paint is dry.
Frequency - Before and During painting
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
Conformance Criteria - No dust
Records -
2.7 - Painting
ACTION (Hold, Monitor, Witness) - HP
Detail - Ensure subcontractor records the date, type, location and extent of all coatings
Frequency - During Painting
Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
Conformance Criteria -
Records -
2.8 - Painting
ACTION (Hold, Monitor, Witness) - HP
Detail - Recoating time as per manufacturers specifications, and weather conditions.
Frequency - After painting
Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
Conformance Criteria -
Records -
2.9 - Completed paint system
ACTION (Hold, Monitor, Witness) - HP
Detail - 1. Dry Film Thickness 2. Bond Strength
Frequency - 14 days after painting
Inspection / Test Method submission, visual inspection, testing, measure, review - NZTA S10 Section 13.2
Conformance Criteria - DFT minimum of 100 microns Bond strength minimum 2MPa
Records - IANZ Test Results or other approved
2.1 - Completed paint system
ACTION (Hold, Monitor, Witness) - HP
Detail - Post works inspection with BBO Sign Off
Frequency - At completion of painting
Inspection / Test Method submission, visual inspection, testing, measure, review - Dry Film Thickness
Conformance Criteria - The completed paint system or coating shall be of uniform thickness, free of runs, sags, pinholes and bubbles, mudcracking, dry overspray, grit inclusion etc. All such imperfections shall be removed or made good to the satisfaction of the Design Engineer.
Records -
3.1 - Lot Number QA File
ACTION (Hold, Monitor, Witness) - W
Detail - Ensure all OFIs are closed and included within QA file
Frequency - At completion of Lot
Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
Conformance Criteria -
Records -
3.2 - Delivery dockets
ACTION (Hold, Monitor, Witness) - W
Detail - Delivery Dockets to be included in QA file
Frequency - At completion of Lot
Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
Conformance Criteria -
Records - Delivery Dockets
3.2 - As-builts
ACTION (Hold, Monitor, Witness) - HP
Detail - Red pen mark up drawings to be included in QA file
Frequency - At the completion of the Lot of work
Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
Conformance Criteria -
Records - Asbuilt Drawing