## Sheet1
1.1 | CEP approval CHAR(AMP) sign-off | SA |  | Completely reviewed by all disciplines w/ document completely signed-off CHAR(AMP) issued for construction | Ō2NL SA Interdisciplinary Review | Review | Prior to Start; Any change of scope/ methodology | R | R | Signed CEP | 1.1 - CEP approval CHAR(AMP) sign-off | RI - SA | Acceptance Criteria - Completely reviewed by all disciplines w/ document completely signed-off CHAR(AMP) issued for construction | Applicable Standard - Ō2NL SA Interdisciplinary Review | Inspection Test: Method - Review | Inspection Test: Frequency - Prior to Start; Any change of scope/ methodology | Verification Activity by: SubCon - R | Verification Activity by: Alliance - R | Verification Activity by: Client - | Verifying Records - Signed CEP | 1.1 - CEP approval CHAR(AMP) sign-off
1.2 | JSEA approval CHAR(AMP) sign-off | SA |  | Completely reviewed by all disciplines w/ document completely signed-off CHAR(AMP) issued for construction | Ō2NL SA Interdisciplinary Review | Review | Prior to Start; Every 6 months; change in working parameters or risks | R | R | Signed JSEA | 1.2 - JSEA approval CHAR(AMP) sign-off | RI - SA | Acceptance Criteria - Completely reviewed by all disciplines w/ document completely signed-off CHAR(AMP) issued for construction | Applicable Standard - Ō2NL SA Interdisciplinary Review | Inspection Test: Method - Review | Inspection Test: Frequency - Prior to Start; Every 6 months; change in working parameters or risks | Verification Activity by: SubCon - R | Verification Activity by: Alliance - R | Verification Activity by: Client - | Verifying Records - Signed JSEA | RI - SA
1.3 | Ecological CHAR(AMP) Environmental walkthrough | EMR |  | Ecological CHAR(AMP) environmental sign-off to proceed with works in the area / lot planned |  | Area / Lot walkover | Prior to start of works | H | H | Documented correspondence / ITP Sign-off (EMR) | 1.3 - Ecological CHAR(AMP) Environmental walkthrough | RI - EMR | Acceptance Criteria - Ecological CHAR(AMP) environmental sign-off to proceed with works in the area / lot planned | Applicable Standard - | Inspection Test: Method - Area / Lot walkover | Inspection Test: Frequency - Prior to start of works | Verification Activity by: SubCon - H | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Documented correspondence / ITP Sign-off (EMR) | Acceptance Criteria - Completely reviewed by all disciplines w/ document completely signed-off CHAR(AMP) issued for construction
1.4 | Communication to stakeholders (where required) | SA |  | Proper communications with stakeholder that fencing works relates to (e.g. balance land owner, lots sharing designation boundaries) | NZTA Contractor Obligations | Advance Comms / Letter Drop (as required) | Prior to start of works | H | H | Documented correspondence / ITP Sign-off (Comms) | 1.4 - Communication to stakeholders (where required) | RI - SA | Acceptance Criteria - Proper communications with stakeholder that fencing works relates to (e.g. balance land owner, lots sharing designation boundaries) | Applicable Standard - NZTA Contractor Obligations | Inspection Test: Method - Advance Comms / Letter Drop (as required) | Inspection Test: Frequency - Prior to start of works | Verification Activity by: SubCon - H | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Documented correspondence / ITP Sign-off (Comms) | Applicable Standard - Ō2NL SA Interdisciplinary Review
1.5 | Valid Permits related to scope of works | ENG/ SUP |  | Completely filled-out with accurate CHAR(AMP) up-to-date information of the site and scope of works necessary | Ō2NL SA Permits CHAR(AMP) Register | Review | Prior to start of works / Weekly as work continues | H | H | Permit Sign-off CHAR(AMP) Preliminary ITP Sign-off | 1.5 - Valid Permits related to scope of works | RI - ENG/ SUP | Acceptance Criteria - Completely filled-out with accurate CHAR(AMP) up-to-date information of the site and scope of works necessary | Applicable Standard - Ō2NL SA Permits CHAR(AMP) Register | Inspection Test: Method - Review | Inspection Test: Frequency - Prior to start of works / Weekly as work continues | Verification Activity by: SubCon - H | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Permit Sign-off CHAR(AMP) Preliminary ITP Sign-off | Inspection Test: Method - Review
1.6 | Extent of Fencing set-out | ENG |  | Ensure fence line has been properly marked out and agreed with engineer in accordance with any property obligations and drawings | Contractor Obligations / Design Drawings | ENG Approval | Prior to start of works; any revision to IFC drawings/ data | W | H | ITP Sign-off (ENG) | 1.6 - Extent of Fencing set-out | RI - ENG | Acceptance Criteria - Ensure fence line has been properly marked out and agreed with engineer in accordance with any property obligations and drawings | Applicable Standard - Contractor Obligations / Design Drawings | Inspection Test: Method - ENG Approval | Inspection Test: Frequency - Prior to start of works; any revision to IFC drawings/ data | Verification Activity by: SubCon - W | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - ITP Sign-off (ENG) | Inspection Test: Frequency - Prior to Start; Any change of scope/ methodology
1.7 | Existing Fence Network | ENG |  | Confirm limits of any existing fences or fence network that is affected by planned fencing works | Contractor Obligations / Design Drawings | ENG Approval | Prior to start of works | W | H | Survey Data CHAR(AMP) ITP Sign- off (ENG) | 1.7 - Existing Fence Network | RI - ENG | Acceptance Criteria - Confirm limits of any existing fences or fence network that is affected by planned fencing works | Applicable Standard - Contractor Obligations / Design Drawings | Inspection Test: Method - ENG Approval | Inspection Test: Frequency - Prior to start of works | Verification Activity by: SubCon - W | Verification Activity by: Alliance - H | Verification Activity by: Client - | Verifying Records - Survey Data CHAR(AMP) ITP Sign- off (ENG) | Verification Activity by: SubCon - R
2.1 | Timber (Posts, Stays, Battens, rails, palings) | ENG |  | Finished treatment | O2NL Project specifications | ENG Approval | Prior to installation | I | R | Copy of delivery docket | 2.1 - Timber (Posts, Stays, Battens, rails, palings) | RI - ENG | Acceptance Criteria - Finished treatment | Applicable Standard - O2NL Project specifications | Inspection Test: Method - ENG Approval | Inspection Test: Frequency - Prior to installation | Verification Activity by: SubCon - I | Verification Activity by: Alliance - R | Verification Activity by: Client - | Verifying Records - Copy of delivery docket | Verification Activity by: Alliance - R
2.2 | Steel (Wire / Chain Link Fence) | ENG |  | Standard galvanised high tensile steel wire | O2NL Project specifications | ENG Approval | Prior to installation | I | R | Copy of delivery docket | 2.2 - Steel (Wire / Chain Link Fence) | RI - ENG | Acceptance Criteria - Standard galvanised high tensile steel wire | Applicable Standard - O2NL Project specifications | Inspection Test: Method - ENG Approval | Inspection Test: Frequency - Prior to installation | Verification Activity by: SubCon - I | Verification Activity by: Alliance - R | Verification Activity by: Client - | Verifying Records - Copy of delivery docket | Verification Activity by: Client -
2.3 | Steel Gates CHAR(AMP) Fittings (Fixings, fasteners, gudgeons, hinges, chains, locks, etc) | ENG |  | Correct dimensions CHAR(AMP) galvanised treatment and all fittings are fit for purpose | O2NL Project specifications | ENG Approval | Prior to installation | I | R | Copy of delivery docket | 2.3 - Steel Gates CHAR(AMP) Fittings (Fixings, fasteners, gudgeons, hinges, chains, locks, etc) | RI - ENG | Acceptance Criteria - Correct dimensions CHAR(AMP) galvanised treatment and all fittings are fit for purpose | Applicable Standard - O2NL Project specifications | Inspection Test: Method - ENG Approval | Inspection Test: Frequency - Prior to installation | Verification Activity by: SubCon - I | Verification Activity by: Alliance - R | Verification Activity by: Client - | Verifying Records - Copy of delivery docket | Verifying Records - Signed CEP
3.1 | 7-wire Fence/s | ENG |  | As per typical 7-wire detail | Per design drawings | Visual Inspection/s CHAR(AMP) ENG Approval | Throughout construction | R | W | Photo documentation CHAR(AMP) ITP Sign-off | 3.1 - 7-wire Fence/s | RI - ENG | Acceptance Criteria - As per typical 7-wire detail | Applicable Standard - Per design drawings | Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval | Inspection Test: Frequency - Throughout construction | Verification Activity by: SubCon - R | Verification Activity by: Alliance - W | Verification Activity by: Client - | Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off | 1.2 - JSEA approval CHAR(AMP) sign-off
3.2 | Deer Fence/s | ENG |  | As per typical deer fence detail | Per design drawings | Visual Inspection/s CHAR(AMP) ENG Approval | Throughout construction | R | W | Photo documentation CHAR(AMP) ITP Sign-off | 3.2 - Deer Fence/s | RI - ENG | Acceptance Criteria - As per typical deer fence detail | Applicable Standard - Per design drawings | Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval | Inspection Test: Frequency - Throughout construction | Verification Activity by: SubCon - R | Verification Activity by: Alliance - W | Verification Activity by: Client - | Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off | RI - SA
3.3 | Paling Fence/s | ENG |  | As per typical paling fence detail | Per design drawings | Visual Inspection/s CHAR(AMP) ENG Approval | Throughout construction | R | W | Photo documentation CHAR(AMP) ITP Sign-off | 3.3 - Paling Fence/s | RI - ENG | Acceptance Criteria - As per typical paling fence detail | Applicable Standard - Per design drawings | Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval | Inspection Test: Frequency - Throughout construction | Verification Activity by: SubCon - R | Verification Activity by: Alliance - W | Verification Activity by: Client - | Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off | Acceptance Criteria - Completely reviewed by all disciplines w/ document completely signed-off CHAR(AMP) issued for construction
3.4 | Electric Fence/s | ENG |  | As per typical electrification detail | Per design drawings | Visual Inspection/s CHAR(AMP) ENG Approval | Throughout construction | R | W | Photo documentation CHAR(AMP) ITP Sign-off | 3.4 - Electric Fence/s | RI - ENG | Acceptance Criteria - As per typical electrification detail | Applicable Standard - Per design drawings | Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval | Inspection Test: Frequency - Throughout construction | Verification Activity by: SubCon - R | Verification Activity by: Alliance - W | Verification Activity by: Client - | Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off | Applicable Standard - Ō2NL SA Interdisciplinary Review
3.5 | Stream-crossing Fences / Flood Gates | ENG |  | As per typical flood gate detail | Per design drawings | Visual Inspection/s CHAR(AMP) ENG Approval | Throughout construction | R | W | Photo documentation CHAR(AMP) ITP Sign-off | 3.5 - Stream-crossing Fences / Flood Gates | RI - ENG | Acceptance Criteria - As per typical flood gate detail | Applicable Standard - Per design drawings | Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval | Inspection Test: Frequency - Throughout construction | Verification Activity by: SubCon - R | Verification Activity by: Alliance - W | Verification Activity by: Client - | Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off | Inspection Test: Method - Review
4.1 | Survey As-built |  | ENG | Quality check on completed fence based on location vs project designation | Within project designation | ENG Approval | Upon completion of works | H | W | Survey Data CHAR(AMP) ITP Sign- off (ENG) | 4.1 - Survey As-built | RI - | Acceptance Criteria - Quality check on completed fence based on location vs project designation | Applicable Standard - Within project designation | Inspection Test: Method - ENG Approval | Inspection Test: Frequency - Upon completion of works | Verification Activity by: SubCon - H | Verification Activity by: Alliance - W | Verification Activity by: Client - | Verifying Records - Survey Data CHAR(AMP) ITP Sign- off (ENG) | Inspection Test: Frequency - Prior to Start; Every 6 months; change in working parameters or risks
4.2 | Stake-holder acceptance (where required) |  | SA | Documented satisfactory acceptance of boundary | Contractor Obligations | Comms | Upon completion of works | W | W | As-built Documentation CHAR(AMP) ITP Sign-off | 4.2 - Stake-holder acceptance (where required) | RI - | Acceptance Criteria - Documented satisfactory acceptance of boundary | Applicable Standard - Contractor Obligations | Inspection Test: Method - Comms | Inspection Test: Frequency - Upon completion of works | Verification Activity by: SubCon - W | Verification Activity by: Alliance - W | Verification Activity by: Client - | Verifying Records - As-built Documentation CHAR(AMP) ITP Sign-off | Verification Activity by: SubCon - R
Verification Activity by: Alliance - R
Verification Activity by: Client -
Verifying Records - Signed JSEA
1.3 - Ecological CHAR(AMP) Environmental walkthrough
RI - EMR
Acceptance Criteria - Ecological CHAR(AMP) environmental sign-off to proceed with works in the area / lot planned
Applicable Standard -
Inspection Test: Method - Area / Lot walkover
Inspection Test: Frequency - Prior to start of works
Verification Activity by: SubCon - H
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Documented correspondence / ITP Sign-off (EMR)
1.4 - Communication to stakeholders (where required)
RI - SA
Acceptance Criteria - Proper communications with stakeholder that fencing works relates to (e.g. balance land owner, lots sharing designation boundaries)
Applicable Standard - NZTA Contractor Obligations
Inspection Test: Method - Advance Comms / Letter Drop (as required)
Inspection Test: Frequency - Prior to start of works
Verification Activity by: SubCon - H
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Documented correspondence / ITP Sign-off (Comms)
1.5 - Valid Permits related to scope of works
RI - ENG/ SUP
Acceptance Criteria - Completely filled-out with accurate CHAR(AMP) up-to-date information of the site and scope of works necessary
Applicable Standard - Ō2NL SA Permits CHAR(AMP) Register
Inspection Test: Method - Review
Inspection Test: Frequency - Prior to start of works / Weekly as work continues
Verification Activity by: SubCon - H
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Permit Sign-off CHAR(AMP) Preliminary ITP Sign-off
1.6 - Extent of Fencing set-out
RI - ENG
Acceptance Criteria - Ensure fence line has been properly marked out and agreed with engineer in accordance with any property obligations and drawings
Applicable Standard - Contractor Obligations / Design Drawings
Inspection Test: Method - ENG Approval
Inspection Test: Frequency - Prior to start of works; any revision to IFC drawings/ data
Verification Activity by: SubCon - W
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - ITP Sign-off (ENG)
1.7 - Existing Fence Network
RI - ENG
Acceptance Criteria - Confirm limits of any existing fences or fence network that is affected by planned fencing works
Applicable Standard - Contractor Obligations / Design Drawings
Inspection Test: Method - ENG Approval
Inspection Test: Frequency - Prior to start of works
Verification Activity by: SubCon - W
Verification Activity by: Alliance - H
Verification Activity by: Client -
Verifying Records - Survey Data CHAR(AMP) ITP Sign- off (ENG)
2.1 - Timber (Posts, Stays, Battens, rails, palings)
RI - ENG
Acceptance Criteria - Finished treatment
Applicable Standard - O2NL Project specifications
Inspection Test: Method - ENG Approval
Inspection Test: Frequency - Prior to installation
Verification Activity by: SubCon - I
Verification Activity by: Alliance - R
Verification Activity by: Client -
Verifying Records - Copy of delivery docket
2.2 - Steel (Wire / Chain Link Fence)
RI - ENG
Acceptance Criteria - Standard galvanised high tensile steel wire
Applicable Standard - O2NL Project specifications
Inspection Test: Method - ENG Approval
Inspection Test: Frequency - Prior to installation
Verification Activity by: SubCon - I
Verification Activity by: Alliance - R
Verification Activity by: Client -
Verifying Records - Copy of delivery docket
2.3 - Steel Gates CHAR(AMP) Fittings (Fixings, fasteners, gudgeons, hinges, chains, locks, etc)
RI - ENG
Acceptance Criteria - Correct dimensions CHAR(AMP) galvanised treatment and all fittings are fit for purpose
Applicable Standard - O2NL Project specifications
Inspection Test: Method - ENG Approval
Inspection Test: Frequency - Prior to installation
Verification Activity by: SubCon - I
Verification Activity by: Alliance - R
Verification Activity by: Client -
Verifying Records - Copy of delivery docket
3.1 - 7-wire Fence/s
RI - ENG
Acceptance Criteria - As per typical 7-wire detail
Applicable Standard - Per design drawings
Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval
Inspection Test: Frequency - Throughout construction
Verification Activity by: SubCon - R
Verification Activity by: Alliance - W
Verification Activity by: Client -
Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off
3.2 - Deer Fence/s
RI - ENG
Acceptance Criteria - As per typical deer fence detail
Applicable Standard - Per design drawings
Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval
Inspection Test: Frequency - Throughout construction
Verification Activity by: SubCon - R
Verification Activity by: Alliance - W
Verification Activity by: Client -
Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off
3.3 - Paling Fence/s
RI - ENG
Acceptance Criteria - As per typical paling fence detail
Applicable Standard - Per design drawings
Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval
Inspection Test: Frequency - Throughout construction
Verification Activity by: SubCon - R
Verification Activity by: Alliance - W
Verification Activity by: Client -
Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off
3.4 - Electric Fence/s
RI - ENG
Acceptance Criteria - As per typical electrification detail
Applicable Standard - Per design drawings
Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval
Inspection Test: Frequency - Throughout construction
Verification Activity by: SubCon - R
Verification Activity by: Alliance - W
Verification Activity by: Client -
Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off
3.5 - Stream-crossing Fences / Flood Gates
RI - ENG
Acceptance Criteria - As per typical flood gate detail
Applicable Standard - Per design drawings
Inspection Test: Method - Visual Inspection/s CHAR(AMP) ENG Approval
Inspection Test: Frequency - Throughout construction
Verification Activity by: SubCon - R
Verification Activity by: Alliance - W
Verification Activity by: Client -
Verifying Records - Photo documentation CHAR(AMP) ITP Sign-off
4.1 - Survey As-built
RI -
Acceptance Criteria - Quality check on completed fence based on location vs project designation
Applicable Standard - Within project designation
Inspection Test: Method - ENG Approval
Inspection Test: Frequency - Upon completion of works
Verification Activity by: SubCon - H
Verification Activity by: Alliance - W
Verification Activity by: Client -
Verifying Records - Survey Data CHAR(AMP) ITP Sign- off (ENG)
4.2 - Stake-holder acceptance (where required)
RI -
Acceptance Criteria - Documented satisfactory acceptance of boundary
Applicable Standard - Contractor Obligations
Inspection Test: Method - Comms
Inspection Test: Frequency - Upon completion of works
Verification Activity by: SubCon - W
Verification Activity by: Alliance - W
Verification Activity by: Client -
Verifying Records - As-built Documentation CHAR(AMP) ITP Sign-off