## Project Structure
Folder Structure |  |  | Checklists
SITE QA
ROUGH-IN
|  | COOLROOM ONE | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
FITOFF
|  | COOLROOM ONE | STANDARD EQUIPMENT Fit off Checklist
VRF FCU Fit off Checklist
| PRE-ENERGISATION TESTS |  |  | VRF Condensing unit Rough In Checklist
AS3000 VERIFICATION TESTING DOCUMENT
|  | COOLROOM 1 | AS3000 MANDATORY TESTS | Central Controller Rough In checklist
| ENERGISATION/TESTING |  |  | VRF Condensing unit PBO Checklist
|  | COOLROOM 1 | Energisation and Testing from switchboard | VRF FCU PBO Rough-in Checklist
WC FCU Rough In checklist
| EQUIPMENT COMMISSIONING |  |  | Remote sensor Rough In checklist
|  | AC-T1-C-1 | Coolroom Commissioning Checklist | BMS Zone Sensor/AHPB Rough-in Checklist
AHPB Rough in Checklist
| HANDOVER |  |  | DOL FAN PBO Rough-in Checklist
|  | AS-INSTALLED MANUAL |  | VRF Condensing unit PBO Fit off Checklist
|  |  | AS-INSTALLED MANUAL | VRF FCU PBO Fit off Checklist
VSD FAN Fit off Checklist
EC FAN Rough-in Checklist
WC FCU Fit off checklist
Remote sensor Fit off checklist
BMS Zone Sensor/AHPB Fit off Checklist
BMS Zone Sensor Fit off checklist
Remote Sensor/AHPB Fit off Checklist
SPLIT AC Fit off Checklist
AHPB Fit off Checklist
SEF VSD FAN Rough-in Checklist
Circuit Energisation from switchboard checklist
Circuit Energisation from Isolator checklist
SEF VSD FAN Commissioning Checklist
VSD FAN PBO Commissioning Checklist
VRF Condensing unit PBO Commissioning Checklist
VRF FCU PBO Commissioning Checklist
VSD FAN Commissioning Checklist
EC FAN Commissioning Checklist
WC FCU Commissioning checklist
AHPB Commissioning Checklist
SPLIT AC Commissioning Checklist

## DELAP ITP
type | name | values
checklist | MSSB CONDITION
checkpoint | General condition (with photos)
checkpoint | Lockouts
checkpoint | Lamp test
checkpoint | GFA present and operational
checkpoint | Data outlet present for BMS
checkpoint | Drawings avaliable
checkpoint | Clearance to AS3000
checkpoint | Location of MSSB
type | name | values
checklist | EXISTING EQUIPMENT
checkpoint | Equipment ID
checkpoint | Circuit breaker/fuse and rating
checkpoint | Cable size/type
checkpoint | Starter- Type (DOL/VSD/EC)
checkpoint | AOM operation
checkpoint | Run/Fault light operation
checkpoint | AMP Rating
checkpoint | AMP Draw
checkpoint | Rotation
checkpoint | Location
checkpoint | Photo
checkpoint | Operational Y/N, comments

## Switchboard ITP
type | name | values | type | name | values
Checklist | Switchboard Installation |  | Checklist | Switchboard Fit-off
checkpoint | Wall Avaliable for Mounting Switchboard |  | checkpoint | All field cabling terminated
checkpoint | Switchboard Installed on Wall |  | checkpoint | Fire Signal supplied by others and terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Sub-mains supplied by others and terminated
|  |  | checkpoint | BMS cables installed and terminated
|  |  | checkpoint | All Field Tests completed
|  |  | checkpoint | Ready for Energisation
type | name | values
Checklist | Switchboard Energisation |  | type | name | values
checkpoint | All field cabling terminated |  | Checklist | Switchboard Commissioning
checkpoint | All field tests completed |  | checkpoint | All circuits operational
checkpoint | Power provided at Main Switch and tested |  | checkpoint | Power meter tested
|  |  | checkpoint | Fire Trip Tested
type | name | values
Checklist | BMS Cubicle Installation |  | type | name | values
checkpoint | Wall Avaliable for Mounting Switchboard |  | Checklist | BMS Cubicle Fit-off
checkpoint | Cubicle Installed on Wall |  | checkpoint | All BMS cabling terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Network cabling terminated
|  |  | checkpoint | Ready for power
|  |  | type | name | values
|  |  | Checklist | Switchboard Handover
type | name | values | checkpoint | Fire Trip tested for correct operation of all equipment
Checklist | BMS Cubicle Commissioning |  | checkpoint | All labels installed
checkpoint | BMS Cubicle powered up |  | checkpoint | As-installed Drawings and legend in MSSB
checkpoint | All Cards Online |  | checkpoint | All penetrations sealed
checkpoint | All labels, drawings etc installed |  | checkpoint | MSSB cleaned (photos)
checkpoint | BMS Cubicle cleaned out and ready for Handover |  | Checkpoint | Notes
type | name | values
Checklist | Fire Control Panel Installation
checkpoint | Wall Avaliable for Mounting Switchboard |  | type | name | values
checkpoint | Cubicle Installed on Wall |  | Checklist | Fire Control Panel Fit-off
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | All interconnecting cabling to MSSB installed and terminated
|  |  | checkpoint | Fire cabling by others installed and terminated
type | name | values
Checklist | Fire Control Panel Commissioning
checkpoint | All fire relays and points test with fire contractor
checkpoint | All labels, drawings etc installed
checkpoint | Fire Control Panel cleaned out and ready for Handover

## Rough-in ITP
type | name | values
checklist | Central Controller Rough In checklist
checkpoint | All transmission cabling installed
checkpoint | Central controller cable roughed in to correct wall position
type | name | values
checklist | Cable Tray Install Checklist
checkpoint | Hangars Installed
checkpoint | Cable Tray Installed
checkpoint | Bolted down, ready for rough-in
type | name | values
Checklist | STANDARD EQUIPMENT PBO Rough-in Checklist
checkpoint | Equipment installed in final position
checkpoint | Isolator installed by others
checkpoint | Control cabling roughed in
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
checkpoint | Equipment installed in final position
checkpoint | Power cabling roughed in
checkpoint | Control cabling roughed in
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
Checklist | Essential FAN Rough-in Checklist
checkpoint | Roof penetration marked out
checkpoint | Fire Rated Supply rouged-in
checkpoint | Fire Rated Control cable roughed-in
checkpoint | Stainless Steel cable ties installed
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
VRF Condensing unit Rough In Checklist
checkpoint | Condensing unit installed in final position
checkpoint | Power supply roughed in
checkpoint | Transmission/Interconnecting cabling Roughed In
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | VRF FCU/BB Rough-in Checklist
checkpoint | FCU/BB Installed
checkpoint | Transmission cabling Roughed In
checkpoint | Hard-wired controller Roughed In
checkpoint | Floor marked for plasterer
type | name | values
Checklist | SPLIT AC Rough-In Checklist
checkpoint | Area ready & accessible
checkpoint | Outdoor unit installed in final position
checkpoint | Power supply to Outdoor unit roughed in
checkpoint | Interconnecting cabling installed
checkpoint | Hard-wired controller roughed in
checkpoint | Floor marked for plasterer
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | Remote sensor Rough In checklist
checkpoint | Wall installed
checkpoint | Remote sensor cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Zone Sensor/AHPB Rough-in Checklist
checkpoint | Wall installed
checkpoint | 3 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | Remote Sensor/AHPB Rough-in Checklist
checkpoint | Wall installed
checkpoint | Remote sensor and 2 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Zone Sensor Rough In checklist
checkpoint | Wall installed
checkpoint | 1 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | AHPB Rough in Checklist
checkpoint | Wall installed
checkpoint | 2 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | DOL FAN Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Local switch roughed in
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | DOL FAN PBO Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Isolator installed by others
checkpoint | Local switch roughed in
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values

## Fitoff ITP
type | name | values
checklist | Central Controller Fit off checklist |  | Central Controller Fit off checklist
checkpoint | All transmission cabling and interfcae cards installed and fitoff
checkpoint | Central controller controller Fit off to correct wall position |  | VSD FAN PBO Fit off Checklist
VRF Condensing unit PBO Fit off Checklist
type | name | values | VSD FAN Fit off Checklist
Checklist | STANDARD EQUIPMENT Fit off Checklist |  | EC FAN Rough-in Checklist
checkpoint | Power supply terminated |  | Remote sensor Fit off checklist
checkpoint | Control cable fit off |  | BMS Zone Sensor Fit off checklist
checkpoint | Ready for AS3000 pre-energisation tests |  | Remote Sensor/AHPB Fit off Checklist
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | SPLIT AC Fit off Checklist
AHPB Fit off Checklist
VRF FCU PBO Fit off Checklist
type | name | values | VSD FAN Fit off Checklist
Checklist | VSD FAN/PUMP Fit off Checklist |  | EC FAN Rough-in Checklist
checkpoint | VSD installed |  | WC FCU Fit off checklist
checkpoint | Power supply terminated/Isolator installed |  | Remote sensor Fit off checklist
checkpoint | EMC cable fit off |  | BMS Zone Sensor/AHPB Fit off Checklist
checkpoint | Control cable fit off |  | BMS Zone Sensor Fit off checklist
checkpoint | Ready for energisation |  | Remote Sensor/AHPB Fit off Checklist
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | SPLIT AC Fit off Checklist
AHPB Fit off Checklist
type | name | values
Checklist | EC FAN Fit off Checklist
checkpoint | Power supply terminated
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | SEF VSD FAN Fitoff Checklist
checkpoint | VSD installed
checkpoint | Power supply terminated
checkpoint | EMC cable fit off
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
VRF Condensing unit Fitoff Checklist
checkpoint | Condensing unit installed
checkpoint | Isolator and power supply installed
checkpoint | Power supply fit off
checkpoint | Transmission cabling Fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | VRF FCU Fit off Checklist
checkpoint | VRF Indoor unit installed
checkpoint | Isolator and power supply installed
checkpoint | Power supply fit off
checkpoint | Wall plastered/painted
checkpoint | Hard-wired controller fit off both ends
checkpoint | Transmission cabling Fit off
checkpoint | Interface card installed
checkpoint | OA Damper installed and wired
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | SPLIT AC Fit off Checklist
checkpoint | Outdoor unit installed in final position and piped
checkpoint | Power supply to condensing unit Fit off
checkpoint | Interconnecting cabling Fit off
checkpoint | Local thermostat Fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | WC FCU Fit off checklist
checkpoint | FCU installed in final location
checkpoint | Power supply fit off
checkpoint | Wall sensors fit-off
checkpoint | All control points fit-off (Valves, sensors etc.)
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | Remote sensor Fit off checklist
checkpoint | Wall plastered/painted
checkpoint | Remote sensor cable Fit off on wall
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Control Point Wall Mounted off Checklist
checkpoint | Wall plastered/painted
checkpoint | Fit off on wall
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Control Point Field off Checklist
checkpoint | Control Point fitoff
checkpoint | Any penetrations sealed
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
Checklist | DOL FAN PBO Fit-off Checklist
checkpoint | Fan Fitoff
checkpoint | Local switch fitoff
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean

## AS3000 TESTS
type | name | values
checklist | AS3000 MANDATORY TESTS |  | Circuit Energisation from switchboard checklist
checkpoint | Continuity
checkpoint | Insulation resistance
checkpoint | Polarity
checkpoint | Correct circuit connects
checkpoint | Fault loop
checkpoint | Operation of RCD's
checkpoint | All cabling re-terminated, ready for energisation

## Energisation ITP
type | name | values
checklist | Energisation and Testing from switchboard |  | Circuit Energisation from switchboard checklist
checkpoint | Power cable terminated at switchboard
checkpoint | Power cable terminated at Equipment
checkpoint | All AS3000 Tests complete and passed
checkpoint | Circuit energised
checkpoint | Voltage Tested at equipment
checkpoint | Amp Draw
checkpoint | Overload setting
checkpoint | Operation/Rotation tested with local controls
checkpoint | All labels installed at equipment
checkpoint | Ensure all rubbish and materials have been picked up and area is clean (photo)
type | name | values
checklist | Circuit Energisation from Isolator checklist
checkpoint | Isolator installed in correct position
checkpoint | Power cable terminated by others
checkpoint | Power cable terminated at Equipment
checkpoint | All AS3000 Tests complete and passed
checkpoint | Circuit energised by others
checkpoint | Voltage Tested at equipment

## Equipment COmmissioning
type | name | values
checklist | Main Controller BMS |  | v | name | values
checkpoint | Controller and cards online |  | Checklist | Supermarket Plantroom Fan Commissioning
checkpoint | Cat5 connected to network |  | checkpoint | Plantroom Temp reading
|  |  | checkpoint | Plantrrom PB tested
type | name | values | checkpoint | Refrigeration interlock tested with Ref. contractor
checklist | Central Controller Commissioning checklist |  | checkpoint | Plantroom fan operation tested
checkpoint | Power supply tested |  | checkpoint | All labels installed
checkpoint | Central controller online
|  |  | type | name | values
v | name | values | Checklist | Coolroom Commissioning Checklist
Checklist | VSD/EC FAN Commissioning Checklist |  | checkpoint | Controller setpoint
checkpoint | VSD programmed to equipment specs |  | checkpoint | Probe reading
checkpoint | AOM operation |  | checkpoint | Solenoid tested
checkpoint | I/O's tested |  | checkpoint | Lights operational
checkpoint | Speed tested |  | checkpoint | Fans operational
|  |  | checkpoint | Notes
type | name | values
Checklist | DOL FAN Commissioning Checklist
checkpoint | VSD programmed to equipment specs
checkpoint | AOM operation
checkpoint | I/O's tested
checkpoint | Speed tested
checkpoint | Notes
type | name | values
Checklist
checkpoint | AOM operation
checkpoint | Field sensors checked (zone, supply etc)
checkpoint | Cool/Heat stages tested
checkpoint | Economy cycle tested
checkpoint | Minimum OA tested
checkpoint | Notes
type | name | values
VRF Condensing unit Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested Voltage
checkpoint | AMP Draw Tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | VRF FCU Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested Voltage
checkpoint | AMP Draw Tested
checkpoint | Controller Online
checkpoint | Heat tested
checkpoint | Cool Tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | EC FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | AOM, local switch tested
checkpoint | Run light tested
checkpoint | Fault light tested
checkpoint | Speed tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | WC FCU Commissioning checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested
checkpoint | Space temp Tested
checkpoint | Supply air temp Tested
checkpoint | Cooling Valve Tested
checkpoint | Heating Valve Tested
checkpoint | Air DP Tested
checkpoint | SAF Enable Tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | AHPB Commissioning
checkpoint | AHPB operating
checkpoint | Neon working
checkpoint | Label installed
type | name | values
Checklist | SPLIT AC Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply to condensing unit Voltage
checkpoint | Power on indoor unit
checkpoint | Local controller operational
checkpoint | Cool Tested
checkpoint | Heat Tested
checkpoint | AMP draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Fan rotation tested
checkpoint | Local switch tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | FAN PBO Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Fan rotation tested
checkpoint | Local switch tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | SEF VSD FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Start relay tested
checkpoint | Firemans Start tested
checkpoint | Firemans Stop tested
checkpoint | Run Proof tested
checkpoint | Fault Tested
checkpoint | Speed tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Fire label and padlock installed

## HANDOVER ITP
type | name | values
Checklist | Switchboard Handover
checkpoint | Fire Trip tested for correct operation of all equipment
checkpoint | All labels installed
checkpoint | As-installed Drawings and legend in MSSB
checkpoint | All penetrations sealed
checkpoint | MSSB cleaned (photos)
Checkpoint | Notes
type | name | values
Checklist | AS-INSTALLED MANUAL
checkpoint | Electrical Certificate
checkpoint | As-installed Drawings
checkpoint | Legend
checkpoint | Thermal scan