## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-012 – Concrete Culvert | itp |  |  |  | Yes | ITP-012 - Concrete Culvert | 6ada54ce-a983-44b6-b9d5-103a4e50c27f
section | 1.1.0 Pre-construction approvals
checkpoint | 1.1.1 - Construction Environmental Management Plan
note | Method/Description - Document Review
note | Test frequency - Prior to work starting
note | Contractor - H
note | Verifying Records Checklists, Test and Supplier Certificates - Signed CEMP
checkpoint | 1.1.2 - Construction Work Plan
note | Method/Description - Document Review
note | Test frequency - Prior to work starting
note | Contractor - H
note | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.1.3 - IANZ accredited testing organisation
note | Method/Description - Document Review
note | Test frequency - Once prior to works commencing
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - IFC's specification
note | Method/Description - Document Review
note | Test frequency - Once prior to works commencing
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - IFC specifications or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - IFC drawings
note | Method/Description - Document Review
note | Test frequency - Once prior to works commencing
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Approved Drainage Strings
note | Method/Description - Document Review
note | Test frequency - Every new Drainage Line and prior to work commencing
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - IFC Cover Form
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.7 - Approval of stockpile location
note | Method/Description - Document Review & Approval
note | Test frequency - Prior to works commencing
note | Contractor - H
note | Designer - R
note | Verifying Records Checklists, Test and Supplier Certificates - ?
section | 1.2.0 Material compliance
checkpoint | 1.2.1 - Materials - pipes and fittings
note | Method/Description - Confirm pipe diameter, class and jointing type as shown on the drawings and that pipes are in correct and good condition.
note | Test frequency - Each delivery to site
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check Sheet
checkpoint | 1.2.2 - Materials – pipes and pre-cast units (wingwalls)
note | Method/Description - Specification compliance – manufacturer’s certificate to TNZ F/3 for pipe and pre-cast units
note | Test frequency - Each delivery to site
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Compliance Cettifcates
checkpoint | 1.2.3 - Materials – Grading for Bedding, Haunch and Sides Zones AP20
note | Method/Description - Confirm the material for bed, haunch, side and overlay zones meet the requirements of AS/NZS 3725:2007 table 6.
note | • NZS4402 Supplement No 1:1988 - Test 2.8.1 (or similar approved)
note | • Determination of the particle size distribution Standard method by wet sieving
note | Test frequency - 1 per source then 1 per 500 m3
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.4 - Materials – Compaction Curves Bedding, Haunch and Sides Zones AP20
note | Method/Description - Establish the optimum moisture content and minimum and maximum dry density.
note | • NZS4402 Supplement No 1:1988 - Test 4.1.1 or similar approved
note | Test frequency - 3 no. tests per source with minimum 5 points
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 1.2.5 - Materials - Structural Fill and for Overlay Zones (AP65)
note | Method/Description - As Per MMA-CON-CMA-ITP-31067
note | Test frequency - As Per MMA-CON-CMA-ITP-31067
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Reports
checkpoint | 1.2.6 - Material - Rip Rap
note | Method/Description - As per MMA-DES-DNG-E1-10686
note | Test frequency - 1 per source then 1 per 500 m3
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
section | 1.3.0 Geosynthetics
checkpoint | 1.3.3 - Visual inspection - geotextiles
note | Method/Description - To inspect geotextile and is the proper type and no tears, rips or other signs of deterioration.
note | Test frequency - Check each lot (1 roll)
note | Contractor - H
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.4 - Geotextiles
note | Method/Description - Specification compliance – manufacturer’s certificate to TNZ F/7 2003
note | Test frequency - Check each lot (1 roll)
note | Contractor - H
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Manufactures Certifcate
section | 2.1.0 Trench Excavation
checkpoint | 2.1.1 - Trench Subgrade
note | Method/Description - Testing trench foundation material to assess is undercut is required. Scala penetrometer test as per NZS4402.6.5.2:1988 for non-cohesive materials. Table 18
note | Test frequency - 2 nos. scala penetrometer tests / 5m of trench
note | • 1 per ancillary structure
note | Contractor - W
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 2.1.2 - Trench Benching
note | Method/Description - 1.5m benches to be constructed strating from rock face
note | Test frequency - Daily
note | Contractor - H
note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Check List
section | 2.2.0 Pipe Bedding and Construction
checkpoint | 2.2.1 - Construction of embedment, bed, haunch and side zones using AP20
note | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991;
note | Test frequency - 3no NDM test per 10 m max centres tests on combined lifts upto 300mm lift and minimum of test at the bottom layer, middle of pipe and top of pipe
note | Contractor - W
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 2.2.2 - Construction of Overlay Zone
note | Method/Description - Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991; Undrained shear Strength
note | Test frequency - 1no NDM and 1no Shear Vane Test per 20m max canters at 300mm lifts
note | Contractor - W
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test Report
checkpoint | 2.2.3 - Construction of pipe
note | Method/Description - Visual test prior to backfill above the side zones – line and level, correct installation, and joints are all sealed.
note | Test frequency - Review every 10m and witness every 25m
note | Contractor - W
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report
checkpoint | 2.2.4 - Construction of Wingwalls
note | Method/Description - Foundation and bedding testing as per pipes, using AP65 as opposed to AP20. Visual inspection of joints between pipe and wingwall
note | Test frequency - Each Wingwall
note | Contractor - W
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Test report, Onsite Checksheet
checkpoint | 2.2.5 - Construction of Antiseep Collars
note | Method/Description - Antiseep collars to be embeded 200mm horizontaly into side of trench and 400mm below base of trench. To be located every second pipe joint. Concrete strength >=20MPa
note | Test frequency - Each Anti Seep Collar
note | Contractor - W
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - DSR Inspection (Pre-Pour), Pre-Pour Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.6 - Construction of Cut Off Toes
note | Method/Description - Cut off Toe to be embeded 1m (or note 4) from top of wingwall base, to be consructed as per IFC Drawings
note | Test frequency - Cut Off Toe
note | Contractor - W
note | Designer - H
note | Verifying Records Checklists, Test and Supplier Certificates - Pre-Pour Checksheet, Detail Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.7 - Construction of Inlet/Outlet Channels
note | Method/Description - DSR to inpect geotextiles before rip - rap is laid. Max drop heights to be adhered to when placing rip-rap
note | Test frequency - Each Channels
note | Contractor - W
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Geotextile Installation Check Sheet
checkpoint | 2.2.8 - Fish Passage
note | Method/Description - 25% embedment depth with meandering low flow path from voild filled riprap. Spat ropes for CU-17
note | Test frequency - Review every 10m and witness every 25m
note | Contractor - W
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checksheet
checkpoint | 2.2.9 - Construction of Safety Rail
note | Method/Description - Constructed as per IFC Drawings
note | Test frequency - Each Fence
note | Contractor - W
note | Designer - W
note | Verifying Records Checklists, Test and Supplier Certificates - Onsite Checksheet
section | 3.0 Post Construction
checkpoint | 3.1 - Survey/as-builts
note | Method/Description - As built survey of coordinates and invert levels, structures, and pipe ends
note | Test frequency - Every 25m
note | Contractor - H
note | Designer - R
note | Verifying Records Checklists, Test and Supplier Certificates - As-Built
checkpoint | 3.2 - Post Construction CCTV inspection
note | Method/Description - Check conformance with the specification and assess the asset condition post construction
note | Test frequency - To be completed following pipe construction but prior to spat rope installation
note | Contractor - H
note | Designer - R
note | Verifying Records Checklists, Test and Supplier Certificates - CCTV log Report as per the standard