## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP024 - Line Marking | itp |  |  |  |  | FH-ZU2-QU-ITP024 - Line Marking - Rev 0A
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex.
label | Reference Documents - Current revisions in Aconex
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Linemarking Plan Approval
label | Frequency - Prior to commencing works
label | Acceptance Criteria - A linemarking plan showing which lines are to be removed and which lines are to be applied needs to be approved by the Contract Administrator prior to commencement.
label | Reference Documents - FH Internal
label | Inspection/Test Method - Aconex Correspondence
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS.
label | Reference Documents - PSP, EMP, TMP, WMS, SWMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Plant and Equipment
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Plant and equipment used in the works are appropriate to achieve specification requirements.
label | Reference Documents - Beca Spec 002 15.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint-no-status | 1.4 - Materials
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The paint to be used shall be a premixed synthetic latex-based paint (such as WATTYL AIRPAVE or approved equivalent).
label | Reference Documents - Beca Spec 002 15.4.1
label | Aconex ref: FHPL-TRANSMIT-001678
label | Inspection/Test Method - Aconex Correspondence
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project Engineer, Principal’s Representative
label | Checked by: Principal’s Representative - FHPL-TRANSMIT-001678
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Material Handling
label | Frequency - Prior / During works
label | Acceptance Criteria - The paint Is to be packaged in 20 litre containers that are of durable construction without sharp edges. Paint containers are to be clearly labelled “Airport Pavement Marking Paint” as well as being labelled with the following: Manufacturer’s name, Colour, Batch number and Date.
label | Reference Documents - Beca Spec 002 15.4.2
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.6 - Survey and setting out
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor shall carry out the setting out of the pavement Markings as shown on the drawings. This shall be approved by the Principal’s Representative.
label | Reference Documents - Beca Spec 002 15.7
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Construction
checkpoint | 2.1 - Removal of Existing Line Marking
label | Frequency - Each Lot
label | Acceptance Criteria - Existing pavement markings, at the locations shown on the Drawings, shall be removed by water blasting or other approved means that is non-destructive to the existing pavement surface.
label | Reference Documents - Beca Spec 002 15.5
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Surface preparation
label | Frequency - Each Lot
label | Acceptance Criteria - The surface of the asphalt or concrete pavement in the areas to be painted shall be thoroughly cleaned prior to the application of the pavement marking paint. This shall be approved by the Principal’s Representative.
label | Reference Documents - Beca Spec 002 15.6
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Weather Conditions
label | Frequency - Each Lot
label | Acceptance Criteria - Pavement marking shall not proceed during wet weather or when the pavement surface is wet or when rain is likely or during high winds.
label | Reference Documents - Beca Spec 002 15.10
label | Inspection/Test Method - Verify & Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.4 - Application
label | Frequency - Each Lot
label | Acceptance Criteria - The paint must be applied in two even coats to provide the required minimum total dry film thickness for the two different paints are:
label | – Dulux Roadmaster dry film thickness (210µm)
label | – WATTYL Airpave dry film thickness (60µm).
label | ○ The second coat is to be applied no less than three days following the initial coat.
label | Reference Documents - Beca Spec 002 15.8 / Manufacture rs Specs
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.5 - Application Rate and Conformity of Application
label | Frequency - Each Lot
label | Acceptance Criteria - Daily records of paint usage and the area covered shall be maintained by the Contractor.
label | Reference Documents - Beca Spec 002 15.12
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed / Daily Records
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 3.0 - Post Construction
checkpoint | 3.1 - Records
label | Frequency - Each Lot
label | Acceptance Criteria - Finished pavement markings shall conform to the following tolerances:
label | – Location of pavement markings ±10mm
label | – Width of any line or line forming an alpha/numeric symbol ±5mm
label | – Length of any line and the spacing of broken lines ±50mm
label | – Dimensions of any alpha/numeric symbol ±10mm
label | Reference Documents - Beca Spec 002 15.9
label | Inspection/Test Method - Verify
label | Record of conformity - Survey
label | SCP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: