## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | FH-ZU2-QU-ITP024 - Line Marking - Rev 0A | itp | ITP024 - Line Marking
| section | 1.0 - Preliminary Activities
| checkpoint | 1.3 - Plant and Equipment
| note | Frequency - Prior to commencing works
| note | Acceptance Criteria - Plant and equipment used in the works are appropriate to achieve specification requirements.
| note | Reference Documents - Beca Spec 002 15.3
| note | Inspection/Test Method - Verify
| note | Record of conformity - This ITP Signed
| note | IP
| note | Responsibility - Project / Site Engineer
| date | Date Completed:
| checkpoint-no-status | 1.4 - Materials
| note | Frequency - Prior to commencing works
| note | Acceptance Criteria - The paint to be used shall be a premixed synthetic latex-based paint (such as WATTYL AIRPAVE or approved equivalent).
| note | Reference Documents - Beca Spec 002 15.4.1
| note | Aconex ref: FHPL-TRANSMIT-001678
| note | Inspection/Test Method - Aconex Correspondence
| note | Record of conformity - This ITP signed
| note | HP
| note | Responsibility - Project Engineer, Principal’s Representative
| note | Checked by: Principal’s Representative - FHPL-TRANSMIT-001678
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT