## Sub Base & Stabilised Basecours
Inspection Test Plan - ITP Action Plan
Project |  | B1001F - Devil's Elbow Culvert |  |  | CPS Approver | Signature | Project Manager | Tony King
ITP Name |  | Sub Base & Stabilised Basecourse |  |  |  |  | Project Engineer | Arvinder Singh
ITP Document No |  | B1001-02-608-00000-CO-IT-TREC-0F0003 |  |  |  | Name & Date | Site Engineer | Jamie Anderson
CWP Document No |  | B1001-02-608-00000-CO-WP-TREC-0F0002 |  |  | Quality Approver | Signature | Quality Engineer | Subash KC
Status |  | Approved |  | 2024-07-24 |  |  | CPS Engineer | Greg Bailey
Revision | [5 empty] | J Addis 24/7/24 | CPS Manager | Dave Hooker
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Conformance Criteria | Inspection / Test Method (submission, visual inspection, testing, measure, review) | Records | Construction Assignee | CPS Assignee | Date(s)
1 | Pre-Construction
1.1 | Material Compliance | WITNESS | i) Has the underlying layer been tested and results acceptable? ii) Has the material used in this layer been formally accepted for use? | Prior to commencement | Subbase material test Records | Visual Inspection | Photos | Site Engineer
1.2 | Compaction NDM | HOLD | NDM test | Post Construction | Design specification ; Mean ≥ 98 % Minimum ≥ 95% | Visual Inspection | Lab report | Site Engineer | CPS Engineer
1.3 | Surface level, thickness shape and visual inspection | HOLD | Arrange for a set out survey to be carried out & check against design drawings | Post Construction | Visual inspection | String sheet / Survey | COR | Site Engineer | CPS Engineer
2 | Material Compliance
2.1 | AP40 material | HOLD | Material review for works | Prior to commencement | Weathering Test | Document Review | Lab report | Site Engineer | CPS Engineer
2.2 | AP40 material | HOLD | Material review for works | Prior to commencement | Crushing Resistance | Document Review | Lab report | Site Engineer | CPS Engineer
2.3 | AP40 material | HOLD | Material review for works | Prior to commencement | PSD, broken face | Document Review | Lab report | Site Engineer | CPS Engineer
2.4 | AP40 material | HOLD | Material review for works | Prior to commencement | MDD sand Equivalent | Document Review | Lab report | Site Engineer | CPS Engineer
3 | Construction 1
3.1 | Survey set out | HOLD | Install offset pegs and mark out the extent of stabilisation | Prior to commencement | CPS approval | Measurement | COR / survey | Site Engineer | CPS Engineer
3.2 | Weather conditions | MONITOR | Ambient Temperature (C&L) Material to be stabilised (BE&FBS) Wind | Prior to spreading | Measurement Ambient Temperatures: Cement: > 5°C | Measurement | Site Diary / Subcontractor QA | Site Engineer
3.3 | Stabilising Agents | MONITOR | Cement ,GP | Per batch | Confirm specification | on site monitor | Subcontractor QA | Site Engineer
3.3 | Cement application - Mat test | MONITOR | Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | Every 400 m2 every 150m for a 2.4m width | ±0.50kg/m² of specified rate | Measurement | Subcontractor QA | Site Engineer
3.4 | Cement application - Average Usage Test | MONITOR | Within ±2.5% of specified rate | On-going measurement by computer/load cells concrete | Within ±2.5% of specified rate | Measurement | Subcontractor QA | Site Engineer
3.5 | Stabilisation depth | HOLD | Maximum variation is -5mm and +15mm | In first 20m and then every 50m | In first 20m and then every 50m | Measurement | Subcontractor QA | Site Engineer | CPS Engineer
3.6 | Moisture Content Check | MONITOR | Visual check | Every 50m | Every 50m walking behind the stabilising the plant | On site Monitor | Subcontractor QA | Site Engineer
3.7 | Compaction NDM | WITNESS | NDM test | 5 per 1000m2 | Mean ≥ 98 % ; Minimum ≥ 95% MDD greater from Plateau or MDD lab report | On site testing | Lab Report | Site Engineer
3.8 | Finished Basecourse layer | HOLD | Surface shape , level and crossfall | Post construction | Submission | Visual inspection | COR | Site Engineer | CPS Engineer
4 | Post-Construction Closeout | [6 empty] | Construction Assignee(s) | Construction Assignee(s) | CPS Assignee
4.1 | Final Walkover (Snags) | HOLD | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Completed report | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Snag List signed by attendees | Quality Manager
4.2 | Survey As-builts | HOLD | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | All RFI, NCRs and site changes must be recorded. Signed and dated | Drawings Survey as-built | As-built Drawings. Redline Markups | Site Engineer
4.3 | Quality Assurance Deliverables | WITNESS | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Ensure all QA is uploaded into ConQA / Procore | Document Review | As-builts, NCR's and RFI's | Quality Manager
4.4 | Final Approvals | HOLD | Signoffs by Project Manager, Quality Manager and CPS Manager | At the completion of the CWP | Ensure all parties have signed and approved ITP | Document Review | Signatures | Project Manager | Quality Manager | CPS Manager
Note on D3: e.g. B1004A - White Pines Bush North
Note on K10: CPS Engineer must always be assigned to Hold Points

## Drop Down Lists
ACTION | Construction Assignee | CPS Assignee
HOLD | Site Engineer | CPS Engineer
WITNESS | Project Engineer | Geotechnical Engineer
MONITOR | Project Manager | Specialist
| Sub-Contractor | Designer
| Third-Party | Third-Party