## struct
resource | resource | resource | resource | resource | resource | resource | resource | resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
[9 empty] | step |  |  | Tier 1: Site QA
Authority Main to Meter Installation | [8 empty] | checklist |  |  | Tier 2: Authority Water Connection
[9 empty] | step |  |  | Tier 2: In-Ground Services
[9 empty] | step |  |  | Tier 3: Basement Level
Drainage Installation (In-ground) | [8 empty] | checklist |  |  | Tier 4: Drainage Installation (In-ground)
Water Service Installation (In-ground) | [8 empty] | checklist |  |  | Tier 4: Water Service Installation (In-ground)
Gas Service Installation (In-ground) | [8 empty] | checklist |  |  | Tier 4: Gas Service Installation (In-ground)
[9 empty] | step |  |  | Tier 3: Ground Level
Drainage Installation (In-ground) | [8 empty] | checklist |  |  | Tier 4: Drainage Installation (In-ground)
Water Service Installation (In-ground) | [8 empty] | checklist |  |  | Tier 4: Water Service Installation (In-ground)
Gas Service Installation (In-ground) | [8 empty] | checklist |  |  | Tier 4: Gas Service Installation (In-ground)
[9 empty] | step |  |  | Tier 2: Penetrations
Penetration Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Ground Level
Penetration Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 1
Penetration Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 2
Penetration Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 3
Penetration Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 4
Penetration Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 5
Penetration Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 6
Penetration Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Roof
[9 empty] | step |  |  | Tier 2: Stacks & Vents
Stack & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Basement Level
Stack & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Ground Level
Stack & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 1
Stack & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 2
Stack & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 3
Stack & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 4
Stack & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 5
Stack & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 6
Stack & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Roof
[9 empty] | step |  |  | Tier 2: Downpipes & Overflows
Downpipe & Overflow Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Basement Level
Downpipe & Overflow Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Ground Level
Downpipe & Overflow Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 1
Downpipe & Overflow Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 2
Downpipe & Overflow Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 3
Downpipe & Overflow Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 4
Downpipe & Overflow Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 5
Downpipe & Overflow Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 6
Downpipe & Overflow Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Roof
[9 empty] | step |  |  | Tier 2: Water Mains/Risers
Water Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Basement Level
Water Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Ground Level
Water Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 1
Water Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 2
Water Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 3
Water Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 4
Water Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 5
Water Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 6
Water Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Roof
[9 empty] | step |  |  | Tier 2: Gas Mains/Risers
Gas Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Basement Level
Gas Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Ground Level
Gas Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 1
Gas Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 2
Gas Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 3
Gas Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 4
Gas Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 5
Gas Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Level 6
Gas Service Installation (Mains/Risers) | [8 empty] | folder-with-checklists |  |  | Tier 3: Roof
[9 empty] | step |  |  | Tier 2: Wastes & Vents (Apts Only)
[9 empty] | step |  |  | Tier 3: Ground Level
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Lwr)
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Lwr)
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.01
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.02
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.03
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.04
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.05
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.06
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.07
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.08
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.09
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.10
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.11
[9 empty] | step |  |  | Tier 3: Level 1
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Upr)
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Upr)
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.01
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.02
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.03
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.04
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.05
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.06
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.07
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.08
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.09
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.10
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.11
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.12
[9 empty] | step |  |  | Tier 3: Level 2
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.01
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.02
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.03
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.04
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.05
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.06
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.07
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.08
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.09
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.10
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.11
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.12
[9 empty] | step |  |  | Tier 3: Level 3
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.01
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.02
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.03
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.04
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.05
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.06
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.07
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.08
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.09
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.10
[9 empty] | step |  |  | Tier 3: Level 4
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.01
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.02
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.03
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.04
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.05
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.06
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.07
[9 empty] | step |  |  | Tier 3: Level 5
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.01
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.02
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.03
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.04
[9 empty] | step |  |  | Tier 3: Level 6
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.01
Waste & Vent Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.02
[9 empty] | step |  |  | Tier 2: Water Rough-Ins (Apts Only)
[9 empty] | step |  |  | Tier 3: Ground Level
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Lwr)
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Lwr)
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.01
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.02
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.03
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.04
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.05
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.06
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.07
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.08
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.09
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.10
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.11
[9 empty] | step |  |  | Tier 3: Level 1
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Upr)
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Upr)
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.01
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.02
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.03
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.04
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.05
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.06
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.07
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.08
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.09
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.10
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.11
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.12
[9 empty] | step |  |  | Tier 3: Level 2
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.01
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.02
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.03
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.04
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.05
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.06
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.07
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.08
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.09
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.10
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.11
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.12
[9 empty] | step |  |  | Tier 3: Level 3
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.01
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.02
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.03
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.04
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.05
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.06
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.07
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.08
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.09
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.10
[9 empty] | step |  |  | Tier 3: Level 4
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.01
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.02
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.03
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.04
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.05
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.06
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.07
[9 empty] | step |  |  | Tier 3: Level 5
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.01
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.02
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.03
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.04
[9 empty] | step |  |  | Tier 3: Level 6
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.01
Water Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.02
[9 empty] | step |  |  | Tier 2: Gas Rough-Ins (Apts Only)
[9 empty] | step |  |  | Tier 3: Ground Level
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Lwr)
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Lwr)
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.01
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.02
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.03
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.04
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.05
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.06
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.07
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.08
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.09
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.10
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: G.11
[9 empty] | step |  |  | Tier 3: Level 1
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Upr)
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Upr)
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.01
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.02
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.03
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.04
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.05
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.06
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.07
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.08
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.09
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.10
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.11
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.12
[9 empty] | step |  |  | Tier 3: Level 2
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.01
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.02
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.03
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.04
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.05
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.06
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.07
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.08
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.09
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.10
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.11
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.12
[9 empty] | step |  |  | Tier 3: Level 3
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.01
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.02
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.03
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.04
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.05
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.06
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.07
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.08
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.09
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.10
[9 empty] | step |  |  | Tier 3: Level 4
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.01
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.02
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.03
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.04
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.05
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.06
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.07
[9 empty] | step |  |  | Tier 3: Level 5
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.01
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.02
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.03
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.04
[9 empty] | step |  |  | Tier 3: Level 6
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.01
Gas Service Installation (Rough-ins) | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.02
[9 empty] | step |  |  | Tier 2: Fixtures & Tapware (Apts Only)
[9 empty] | step |  |  | Tier 3: Ground Level
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: T1 (Lwr)
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: T2 (Lwr)
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.01
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.02
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.03
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.04
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.05
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.06
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.07
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.08
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.09
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.10
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.11
[9 empty] | step |  |  | Tier 3: Level 1
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: T1 (Upr)
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: T2 (Upr)
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.01
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.02
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.03
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.04
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.05
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.06
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.07
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.08
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.09
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.10
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.11
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.12
[9 empty] | step |  |  | Tier 3: Ground Level
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: T1 (Lwr)
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: T2 (Lwr)
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.01
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.02
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.03
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.04
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.05
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.06
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.07
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.08
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.09
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.10
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: G.11
[9 empty] | step |  |  | Tier 3: Level 1
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: T1 (Upr)
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: T2 (Upr)
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.01
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.02
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.03
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.04
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.05
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.06
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.07
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.08
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.09
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.10
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.11
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 1.12
[9 empty] | step |  |  | Tier 3: Level 2
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.01
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.02
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.03
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.04
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.05
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.06
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.07
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.08
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.09
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.10
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.11
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 2.12
[9 empty] | step |  |  | Tier 3: Level 3
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.01
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.02
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.03
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.04
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.05
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.06
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.07
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.08
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.09
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 3.10
[9 empty] | step |  |  | Tier 3: Level 4
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 4.01
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 4.02
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 4.03
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 4.04
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 4.05
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 4.06
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 4.07
[9 empty] | step |  |  | Tier 3: Level 5
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 5.01
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 5.02
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 5.03
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 5.04
[9 empty] | step |  |  | Tier 3: Level 6
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 6.01
Toilet & Cistern Installation | Wash Basin & Tapware Installation | Shower & Tapware Installation | Bath & Tapware Installation | Kitchen Sink & Tapware Installation | Washer Machine Installation | Laundry Trough & Tapware Installation | Tundish Installation | Hose Tap Installation | folder-with-checklists |  |  | Tier 4: 6.02
[9 empty] | step |  |  | Tier 2: Plant & Equipment Installation
[9 empty] | step |  |  | Tier 3: Basement Level
Plant & Equipment Installation | [8 empty] | checklist |  |  | Tier 4: Sewer Pump Station
Plant & Equipment Installation | [8 empty] | checklist |  |  | Tier 4: Rain Water Harvest Tank (25KL)
Plant & Equipment Installation | [8 empty] | checklist |  |  | Tier 4: Rain Water Pressure Pump
Plant & Equipment Installation | [8 empty] | checklist |  |  | Tier 4: Storm Water Detention Tank (40KL)
Plant & Equipment Installation | [8 empty] | checklist |  |  | Tier 4: Storm Water Pump Station
Plant & Equipment Installation | [8 empty] | checklist |  |  | Tier 4: Stormwater Filter
[9 empty] | step |  |  | Tier 3: Roof Level
Plant & Equipment Installation | [8 empty] | checklist |  |  | Tier 4: Hot Water Generating Plant
[9 empty] | step |  |  | Tier 2: Testing (General Plumbing)
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 3: Basement Level
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 3: Ground Level
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 3: Level 1
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 3: Level 2
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 3: Level 3
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 3: Level 4
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 3: Level 5
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 3: Level 6
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 3: Roof Level
[9 empty] | step |  |  | Tier 2: Testing (Apts Only)
[9 empty] | step |  |  | Tier 3: Ground Level
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: T1 (Lwr)
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: T2 (Lwr)
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.01
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.02
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.03
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.04
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.05
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.06
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.07
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.08
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.09
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.10
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: G.11
[9 empty] | step |  |  | Tier 3: Level 1
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: T1 (Upr)
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: T2 (Upr)
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.01
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.02
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.03
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.04
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.05
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.06
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.07
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.08
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.09
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.10
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.11
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 1.12
[9 empty] | step |  |  | Tier 3: Level 2
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.01
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.02
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.03
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.04
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.05
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.06
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.07
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.08
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.09
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.10
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.11
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 2.12
[9 empty] | step |  |  | Tier 3: Level 3
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.01
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.02
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.03
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.04
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.05
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.06
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.07
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.08
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.09
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 3.10
[9 empty] | step |  |  | Tier 3: Level 4
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 4.01
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 4.02
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 4.03
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 4.04
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 4.05
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 4.06
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 4.07
[9 empty] | step |  |  | Tier 3: Level 5
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 5.01
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 5.02
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 5.03
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 5.04
[9 empty] | step |  |  | Tier 3: Level 6
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 6.01
Testing Drainage Pipework (Air Test) | Testing Drainage Pipework (Water Test) | Testing Water Pipework (Water Test) | Testing Gas Service (Air Test) | [5 empty] | folder-with-checklists |  |  | Tier 4: 6.02
[9 empty] | step |  |  | Tier 2: Commissioning (Plant & Equipment)
[9 empty] | step |  |  | Tier 3: Basement Level
Commission Drainage Pump Station | [8 empty] | checklist |  |  | Tier 4: Sewer Pump Station
Commission Water Storage Tank | [8 empty] | checklist |  |  | Tier 4: Rain Water Harvest Tank (25KL)
Commission Rain Water Pressure Pump Set | [8 empty] | checklist |  |  | Tier 4: Rain Water Pressure Pump
Commission Water Storage Tank | [8 empty] | checklist |  |  | Tier 4: Storm Water Detention Tank (40KL)
Commission Drainage Pump Station | [8 empty] | checklist |  |  | Tier 4: Storm Water Pump Station
Add New Task | [8 empty] | checklist |  |  | Tier 4: Stormwater Filter
[9 empty] | step |  |  | Tier 3: Roof Level
Commission Hot Water Generating Plant | [8 empty] | checklist |  |  | Tier 4: Hot Water Generation Plant
[9 empty] | step |  |  | Tier 2: Commissioning (Apts Only)
[9 empty] | step |  |  | Tier 3: Ground Level
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Lwr)
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Lwr)
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.01
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.02
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.03
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.04
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.05
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.06
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.07
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.08
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.09
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.10
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: G.11
[9 empty] | step |  |  | Tier 3: Level 1
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Upr)
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Upr)
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.01
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.02
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.03
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.04
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.05
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.06
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.07
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.08
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.09
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.10
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.11
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.12
[9 empty] | step |  |  | Tier 3: Level 2
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.01
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.02
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.03
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.04
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.05
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.06
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.07
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.08
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.09
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.10
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.11
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.12
[9 empty] | step |  |  | Tier 3: Level 3
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.01
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.02
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.03
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.04
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.05
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.06
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.07
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.08
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.09
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.10
[9 empty] | step |  |  | Tier 3: Level 4
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.01
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.02
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.03
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.04
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.05
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.06
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.07
[9 empty] | step |  |  | Tier 3: Level 5
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.01
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.02
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.03
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.04
[9 empty] | step |  |  | Tier 3: Level 6
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.01
Commission Fixture Group | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.02
[9 empty] | step |  |  | Tier 2: Water Meter Installation
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Basement Level
[9 empty] | step |  |  | Tier 3: Ground Level
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Lwr)
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Lwr)
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.01
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.02
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.03
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.04
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.05
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.06
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.07
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.08
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.09
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.10
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: G.11
[9 empty] | step |  |  | Tier 3: Level 1
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: T1 (Upr)
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: T2 (Upr)
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.01
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.02
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.03
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.04
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.05
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.06
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.07
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.08
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.09
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.10
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.11
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 1.12
[9 empty] | step |  |  | Tier 3: Level 2
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.01
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.02
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.03
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.04
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.05
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.06
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.07
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.08
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.09
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.10
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.11
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 2.12
[9 empty] | step |  |  | Tier 3: Level 3
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.01
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.02
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.03
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.04
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.05
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.06
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.07
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.08
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.09
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 3.10
[9 empty] | step |  |  | Tier 3: Level 4
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.01
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.02
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.03
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.04
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.05
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.06
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 4.07
[9 empty] | step |  |  | Tier 3: Level 5
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.01
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.02
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.03
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 5.04
[9 empty] | step |  |  | Tier 3: Level 6
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.01
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 4: 6.02
Water Meter Installation | [8 empty] | folder-with-checklists |  |  | Tier 3: Roof Level