## Sheet1
1.1 | Documentation | Issued drawings / Site copy drawings | Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks. | S | S |  | 1.1 - Documentation | Ref docs - Issued drawings / Site copy drawings | Acceptance criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks. | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | 1.1 - Documentation
1.2 | Lot Traceability | Spec. 0161 Quality [Cl 7.3] | Prepare a lot map for traceability of the work area. | S | S |  | 1.2 - Lot Traceability | Ref docs - Spec. 0161 Quality [Cl 7.3] | Acceptance criteria - Prepare a lot map for traceability of the work area. | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Ref docs - Issued drawings / Site copy drawings
1.3 | Set out | Drawings | Setout structure to the location and levels on the drawings. This shall be presented for inspection by the superintendent. | S | S |  | 1.3 - Set out | Ref docs - Drawings | Acceptance criteria - Setout structure to the location and levels on the drawings. This shall be presented for inspection by the superintendent. | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Acceptance criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
1.4 | Underlying Lot Conformance | Underlying Lot ITP | Underlying services and/or assets have been installed prior to commencing works over and/or above. Refer underlying lot ITP(s) | S | S |  | 1.4 - Underlying Lot Conformance | Ref docs - Underlying Lot ITP | Acceptance criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above. Refer underlying lot ITP(s) | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Acceptance
1.5 | Site Checklist(s) |  | Have Site checklist(s) been signed and uploaded? | S | S | ☐ Site Checklist(S) | 1.5 - Site Checklist(s) | Ref docs - | Acceptance criteria - Have Site checklist(s) been signed and uploaded? | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Site Checklist(S) | HPP CON Key - S
2.1 | Excavation |  | Excavate to the depth nominated on the drawings and remove any loose material at the base. Ensure excavation is carried out to a width which will not impede external formwork. | S | S |  | 2.1 - Excavation | Ref docs - | Acceptance criteria - Excavate to the depth nominated on the drawings and remove any loose material at the base. Ensure excavation is carried out to a width which will not impede external formwork. | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | HPP QA Key - S
2.2 | Unsuitable Material | Spec. 1112 Earthwork s [Cl 4.6] | Any Unsuitable Material to be removed to the depth as directed by the Superintendent HOLD POINT | H | H |  | 2.2 - Unsuitable Material | Ref docs - Spec. 1112 Earthwork s [Cl 4.6] | Acceptance criteria - Any Unsuitable Material to be removed to the depth as directed by the Superintendent HOLD POINT | Acceptance | HPP CON Key - H | HPP QA Key - H | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
2.3 | Compaction - Foundation | Spec. 1112 Earthwork s [Cl 4.7, 4.13] Spec 0161 [CL 7.2] | Foundation (including any unsuitable replacement) to be compacted to a relative compaction of 97% modified to a depth of 200mm below foundation level Test Frequency = 1 per 500m2 | S | S | ☐ Test reports | 2.3 - Compaction - Foundation | Ref docs - Spec. 1112 Earthwork s [Cl 4.7, 4.13] Spec 0161 [CL 7.2] | Acceptance criteria - Foundation (including any unsuitable replacement) to be compacted to a relative compaction of 97% modified to a depth of 200mm below foundation level Test Frequency = 1 per 500m2 | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Test reports | 1.2 - Lot Traceability
2.4 | Foundation Inspection | Spec. 1112 Earthwork s [4.7] | Foundation to be inspected by the Superintendent prior to placing blinding HOLD POINT | H | H |  | 2.4 - Foundation Inspection | Ref docs - Spec. 1112 Earthwork s [4.7] | Acceptance criteria - Foundation to be inspected by the Superintendent prior to placing blinding HOLD POINT | Acceptance | HPP CON Key - H | HPP QA Key - H | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Ref docs - Spec. 0161 Quality [Cl 7.3]
2.5 | Blinding | Spec. 1354 Stormwate r Drainage Structures [Cl 3.6] | Blinding (N15) for Reinforced Concrete Bases to be a 100mm thick mass concrete layer or as otherwise shown on the drawings. Unreinforced bases can be poured directly on the earth | S | S |  | 2.5 - Blinding | Ref docs - Spec. 1354 Stormwate r Drainage Structures [Cl 3.6] | Acceptance criteria - Blinding (N15) for Reinforced Concrete Bases to be a 100mm thick mass concrete layer or as otherwise shown on the drawings. Unreinforced bases can be poured directly on the earth | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Acceptance criteria - Prepare a lot map for traceability of the work area.
2.6 | Mating Concrete Surface Preparation | Spec. 0002 [CL 3.9] | Construction joints prepared and free of loose material Dowelled joints prepared and bond breaker applied for expansion joints if applicable | S | S |  | 2.6 - Mating Concrete Surface Preparation | Ref docs - Spec. 0002 [CL 3.9] | Acceptance criteria - Construction joints prepared and free of loose material Dowelled joints prepared and bond breaker applied for expansion joints if applicable | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Acceptance
3.1 | Formwork | Spec. 0002 Concrete supply, constructio n, and grouting [Cl 4.0] Drawings | Formwork installed as per drawings and adequately supported. Completed formwork to be inspected by the Superintendent prior to concrete placement Formwork engineers inspection certificate complete and received Survey report to be received prior to ordering concrete. HOLD POINT Before Placing Concrete | H | H | ☐ Pre-pour inspection | 3.1 - Formwork | Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 4.0] Drawings | Acceptance criteria - Formwork installed as per drawings and adequately supported. Completed formwork to be inspected by the Superintendent prior to concrete placement Formwork engineers inspection certificate complete and received Survey report to be received prior to ordering concrete. HOLD POINT Before Placing Concrete | Acceptance | HPP CON Key - H | HPP QA Key - H | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Pre-pour inspection | HPP CON Key - S
3.2 | Steel reinforcement | Spec. 0002 Concrete supply, constructio n, and grouting [Cl 5.0] Drawings | Reinforcement installed as per drawings, ensuring sufficient lap length and cover is achieved on all bars. Inspection per layer installed. Concrete pre-pour inspection complete. HOLD POINT Before Placing Concrete | H | H | ☐ Pre-pour inspection | 3.2 - Steel reinforcement | Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 5.0] Drawings | Acceptance criteria - Reinforcement installed as per drawings, ensuring sufficient lap length and cover is achieved on all bars. Inspection per layer installed. Concrete pre-pour inspection complete. HOLD POINT Before Placing Concrete | Acceptance | HPP CON Key - H | HPP QA Key - H | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Pre-pour inspection | HPP QA Key - S
3.3 | Reinforcement Splice Lengths | Spec. 0002 Concrete supply, constructio n, and grouting [Cl 5.7] | Where splicing of reinforcement is not shown on drawings min. lap lengths shown below shall be adopted. (SPT-0002 Table 6) | S | S |  | 3.3 - Reinforcement Splice Lengths | Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 5.7] | Acceptance criteria - Where splicing of reinforcement is not shown on drawings min. lap lengths shown below shall be adopted. (SPT-0002 Table 6) | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.4 | Pit CHAR(AMP) Pipe Connections | Spec. 1354 Stormwate r Drainage Structures [Cl 3.3] Spec. 0002 Concrete supply, constructio n, and grouting [Cl 2.6] Drawings | Inlet and outlet pipes to be integrally cast into foundation/pit walls and the joint waterproofed as per design requirements. Embedded pipes to be adequately restrained against flotation HOLD POINT | H | W | ITP for associated pit/pipe reviewed for conformance | 3.4 - Pit CHAR(AMP) Pipe Connections | Ref docs - Spec. 1354 Stormwate r Drainage Structures [Cl 3.3] Spec. 0002 Concrete supply, constructio n, and grouting [Cl 2.6] Drawings | Acceptance criteria - Inlet and outlet pipes to be integrally cast into foundation/pit walls and the joint waterproofed as per design requirements. Embedded pipes to be adequately restrained against flotation HOLD POINT | Acceptance | HPP CON Key - H | HPP QA Key - W | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ITP for associated pit/pipe reviewed for conformance | 1.3 - Set out
3.5 | Installation of Core Holes, Voids, HD Bolts and Embedments | Spec. 0002 Concrete supply, constructio n, and grouting [CL 2.6, 7.1, 7.2, 7.3] | Firmly Fixed in position in all directions Reinforcement displaced where necessary, bars requiring cutting approved by superintendent Integrity of surface treatments maintained (galvanising, painting etc) Threads covered | S | S |  | 3.5 - Installation of Core Holes, Voids, HD Bolts and Embedments | Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [CL 2.6, 7.1, 7.2, 7.3] | Acceptance criteria - Firmly Fixed in position in all directions Reinforcement displaced where necessary, bars requiring cutting approved by superintendent Integrity of surface treatments maintained (galvanising, painting etc) Threads covered | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Ref docs - Drawings
3.7 | Earthing for Concrete Structures | Drawings Spec. 0002 Concrete supply, constructio n, and grouting [CL 2.6] | Earthing installed for concrete structures as per provided Drawings HOLD POINT | H | W | ☐ UGL Earthing FIC | 3.7 - Earthing for Concrete Structures | Ref docs - Drawings Spec. 0002 Concrete supply, constructio n, and grouting [CL 2.6] | Acceptance criteria - Earthing installed for concrete structures as per provided Drawings HOLD POINT | Acceptance | HPP CON Key - H | HPP QA Key - W | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ UGL Earthing FIC | Acceptance criteria - Setout structure to the location and levels on the drawings. This shall be presented for inspection by the superintendent.
3.8 | Concrete Mix and properties |  | Concrete compressive strength required (28 days) = MPA Approved Concrete mix ID = Slump = mm | S | S | ☐ Material dockets ☐Concrete pour records | 3.8 - Concrete Mix and properties | Ref docs - | Acceptance criteria - Concrete compressive strength required (28 days) = MPA Approved Concrete mix ID = Slump = mm | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Material dockets ☐Concrete pour records | Acceptance
3.9a | Concrete Supply Temperature - GT Foundation Only | Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.1.2] Thermal Analysis Report | Temperature of concrete at the time of placement must be minimum 10°C and maximum 25°C. Ambient air temperature at the time of placement must be between 5oC and 30oC. | S | S | ☐ Material dockets ☐Concrete pour records | 3.9a - Concrete Supply Temperature - GT Foundation Only | Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.1.2] Thermal Analysis Report | Acceptance criteria - Temperature of concrete at the time of placement must be minimum 10°C and maximum 25°C. Ambient air temperature at the time of placement must be between 5oC and 30oC. | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Material dockets ☐Concrete pour records | HPP CON Key - S
3.9b | Concrete Supply Temperature – Other foundations | Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.1.2] | Temperature of concrete at the time of placement must be minimum 10°C and maximum 30°C. Ambient air temperature at the time of placement must be between 5oC and 32oC. If ambient temperature is between 32oC and 38oC, seek approval from superintendent to proceed by taking special precautions noted in the specification. | S | S | ☐ Material dockets ☐Concrete pour records | 3.9b - Concrete Supply Temperature – Other foundations | Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.1.2] | Acceptance criteria - Temperature of concrete at the time of placement must be minimum 10°C and maximum 30°C. Ambient air temperature at the time of placement must be between 5oC and 32oC. If ambient temperature is between 32oC and 38oC, seek approval from superintendent to proceed by taking special precautions noted in the specification. | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Material dockets ☐Concrete pour records | HPP QA Key - S
3.1 | Concrete Placement | Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.1.4] | Ensure elapsed time between batching and discharge of the mix does not exceed 1.5 hours. Concrete placed in layers ≤ 300mm thick and adequately vibrated avoiding over-vibration. Concrete thoroughly compacted – one internal vibrator per 10m3 concrete placed per hour | S | S | ☐ Material dockets ☐Concrete pour records | 3.1 - Concrete Placement | Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.1.4] | Acceptance criteria - Ensure elapsed time between batching and discharge of the mix does not exceed 1.5 hours. Concrete placed in layers ≤ 300mm thick and adequately vibrated avoiding over-vibration. Concrete thoroughly compacted – one internal vibrator per 10m3 concrete placed per hour | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Material dockets ☐Concrete pour records | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.11 | Concrete Slump Testing |  | Slump Test - One per batch of concrete Slump within tolerances specified in AS 1379 Testing to be executed by a NATA accredited test facility | S | S | ☐ Concrete pour record | 3.11 - Concrete Slump Testing | Ref docs - | Acceptance criteria - Slump Test - One per batch of concrete Slump within tolerances specified in AS 1379 Testing to be executed by a NATA accredited test facility | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Concrete pour record | 1.4 - Underlying Lot Conformance
3.12 | Concrete Compressive Strength Testing | Drawings | Compressive Strength Testing - 2 x 7day and 2 x 28day per 50m3 Testing to be executed by a NATA accredited test facility | S | S | ☐ Concrete pour record | 3.12 - Concrete Compressive Strength Testing | Ref docs - Drawings | Acceptance criteria - Compressive Strength Testing - 2 x 7day and 2 x 28day per 50m3 Testing to be executed by a NATA accredited test facility | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Concrete pour record | Ref docs - Underlying Lot ITP
3.13 | Surface finish | Spec. 0319 Minor Concrete Works [Cl 4.2] Drawings | Concrete surfaces shall be true and even, free from honeycombed surface depressions or rejections. Formed surfaces conform with surface finish requirements of AS3610 for the surface class nominated. WITNESS POINT 1 day prior | W | W |  | 3.13 - Surface finish | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.2] Drawings | Acceptance criteria - Concrete surfaces shall be true and even, free from honeycombed surface depressions or rejections. Formed surfaces conform with surface finish requirements of AS3610 for the surface class nominated. WITNESS POINT 1 day prior | Acceptance | HPP CON Key - W | HPP QA Key - W | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Acceptance criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above. Refer underlying lot ITP(s)
3.14 | Surface Treatments |  | Any surface treatments to be applied are approved for use and appropriate dose rates have been determined | S | S |  | 3.14 - Surface Treatments | Ref docs - | Acceptance criteria - Any surface treatments to be applied are approved for use and appropriate dose rates have been determined | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Acceptance
3.15 | Joints | As per drawings | As per design drawings. Sawn joints to commence as soon as the concrete has hardened sufficiently. | S | S |  | 3.15 - Joints | Ref docs - As per drawings | Acceptance criteria - As per design drawings. Sawn joints to commence as soon as the concrete has hardened sufficiently. | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | HPP CON Key - S
3.16 | Curing | Spec. 0319 Minor Concrete Works [Cl 4.13] | From completion of finishing cure continuously with an approved method for a min period of 7 days or as directed by the Superintendent. a. Ordinary Portland cement concrete – 7 days b. High early strength concrete – 3 days c. Concrete with cement or pozzolan materials – 10 days | S | S |  | 3.16 - Curing | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.13] | Acceptance criteria - From completion of finishing cure continuously with an approved method for a min period of 7 days or as directed by the Superintendent. a. Ordinary Portland cement concrete – 7 days b. High early strength concrete – 3 days c. Concrete with cement or pozzolan materials – 10 days | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | HPP QA Key - S
3.17 | Stripping of formwork | Spec. 0002 Concrete supply, constructio n, and grouting [Cl 4.4.5] |  | S | S |  | 3.17 - Stripping of formwork | Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 4.4.5] | Acceptance criteria - | Acceptance | HPP CON Key - S | HPP QA Key - S | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.18 | Concrete Repair (If required) | Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.7] | Defective concrete shall be repaired or replaced. The materials and techniques of repair shall be examined and approved by the Superintendent prior to the commencement of repairs. | H | H | ☐ Grout Placement Checklist ☐ Approved Aconex Corro for Repair Methodology | 3.18 - Concrete Repair (If required) | Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.7] | Acceptance criteria - Defective concrete shall be repaired or replaced. The materials and techniques of repair shall be examined and approved by the Superintendent prior to the commencement of repairs. | Acceptance | HPP CON Key - H | HPP QA Key - H | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Grout Placement Checklist ☐ Approved Aconex Corro for Repair Methodology | 1.5 - Site Checklist(s)
Ref docs -
Acceptance criteria - Have Site checklist(s) been signed and uploaded?
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Site Checklist(S)
2.1 - Excavation
Ref docs -
Acceptance criteria - Excavate to the depth nominated on the drawings and remove any loose material at the base. Ensure excavation is carried out to a width which will not impede external formwork.
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
2.2 - Unsuitable Material
Ref docs - Spec. 1112 Earthwork s [Cl 4.6]
Acceptance criteria - Any Unsuitable Material to be removed to the depth as directed by the Superintendent HOLD POINT
Acceptance
HPP CON Key - H
HPP QA Key - H
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
2.3 - Compaction - Foundation
Ref docs - Spec. 1112 Earthwork s [Cl 4.7, 4.13] Spec 0161 [CL 7.2]
Acceptance criteria - Foundation (including any unsuitable replacement) to be compacted to a relative compaction of 97% modified to a depth of 200mm below foundation level Test Frequency = 1 per 500m2
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Test reports
2.4 - Foundation Inspection
Ref docs - Spec. 1112 Earthwork s [4.7]
Acceptance criteria - Foundation to be inspected by the Superintendent prior to placing blinding HOLD POINT
Acceptance
HPP CON Key - H
HPP QA Key - H
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
2.5 - Blinding
Ref docs - Spec. 1354 Stormwate r Drainage Structures [Cl 3.6]
Acceptance criteria - Blinding (N15) for Reinforced Concrete Bases to be a 100mm thick mass concrete layer or as otherwise shown on the drawings. Unreinforced bases can be poured directly on the earth
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
2.6 - Mating Concrete Surface Preparation
Ref docs - Spec. 0002 [CL 3.9]
Acceptance criteria - Construction joints prepared and free of loose material Dowelled joints prepared and bond breaker applied for expansion joints if applicable
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.1 - Formwork
Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 4.0] Drawings
Acceptance criteria - Formwork installed as per drawings and adequately supported. Completed formwork to be inspected by the Superintendent prior to concrete placement Formwork engineers inspection certificate complete and received Survey report to be received prior to ordering concrete. HOLD POINT Before Placing Concrete
Acceptance
HPP CON Key - H
HPP QA Key - H
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Pre-pour inspection
3.2 - Steel reinforcement
Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 5.0] Drawings
Acceptance criteria - Reinforcement installed as per drawings, ensuring sufficient lap length and cover is achieved on all bars. Inspection per layer installed. Concrete pre-pour inspection complete. HOLD POINT Before Placing Concrete
Acceptance
HPP CON Key - H
HPP QA Key - H
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Pre-pour inspection
3.3 - Reinforcement Splice Lengths
Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 5.7]
Acceptance criteria - Where splicing of reinforcement is not shown on drawings min. lap lengths shown below shall be adopted. (SPT-0002 Table 6)
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.4 - Pit CHAR(AMP) Pipe Connections
Ref docs - Spec. 1354 Stormwate r Drainage Structures [Cl 3.3] Spec. 0002 Concrete supply, constructio n, and grouting [Cl 2.6] Drawings
Acceptance criteria - Inlet and outlet pipes to be integrally cast into foundation/pit walls and the joint waterproofed as per design requirements. Embedded pipes to be adequately restrained against flotation HOLD POINT
Acceptance
HPP CON Key - H
HPP QA Key - W
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ITP for associated pit/pipe reviewed for conformance
3.5 - Installation of Core Holes, Voids, HD Bolts and Embedments
Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [CL 2.6, 7.1, 7.2, 7.3]
Acceptance criteria - Firmly Fixed in position in all directions Reinforcement displaced where necessary, bars requiring cutting approved by superintendent Integrity of surface treatments maintained (galvanising, painting etc) Threads covered
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.7 - Earthing for Concrete Structures
Ref docs - Drawings Spec. 0002 Concrete supply, constructio n, and grouting [CL 2.6]
Acceptance criteria - Earthing installed for concrete structures as per provided Drawings HOLD POINT
Acceptance
HPP CON Key - H
HPP QA Key - W
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ UGL Earthing FIC
3.8 - Concrete Mix and properties
Ref docs -
Acceptance criteria - Concrete compressive strength required (28 days) = MPA Approved Concrete mix ID = Slump = mm
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Material dockets ☐Concrete pour records
3.9a - Concrete Supply Temperature - GT Foundation Only
Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.1.2] Thermal Analysis Report
Acceptance criteria - Temperature of concrete at the time of placement must be minimum 10°C and maximum 25°C. Ambient air temperature at the time of placement must be between 5oC and 30oC.
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Material dockets ☐Concrete pour records
3.9b - Concrete Supply Temperature – Other foundations
Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.1.2]
Acceptance criteria - Temperature of concrete at the time of placement must be minimum 10°C and maximum 30°C. Ambient air temperature at the time of placement must be between 5oC and 32oC. If ambient temperature is between 32oC and 38oC, seek approval from superintendent to proceed by taking special precautions noted in the specification.
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Material dockets ☐Concrete pour records
3.1 - Concrete Placement
Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.1.4]
Acceptance criteria - Ensure elapsed time between batching and discharge of the mix does not exceed 1.5 hours. Concrete placed in layers ≤ 300mm thick and adequately vibrated avoiding over-vibration. Concrete thoroughly compacted – one internal vibrator per 10m3 concrete placed per hour
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Material dockets ☐Concrete pour records
3.11 - Concrete Slump Testing
Ref docs -
Acceptance criteria - Slump Test - One per batch of concrete Slump within tolerances specified in AS 1379 Testing to be executed by a NATA accredited test facility
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Concrete pour record
3.12 - Concrete Compressive Strength Testing
Ref docs - Drawings
Acceptance criteria - Compressive Strength Testing - 2 x 7day and 2 x 28day per 50m3 Testing to be executed by a NATA accredited test facility
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Concrete pour record
3.13 - Surface finish
Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.2] Drawings
Acceptance criteria - Concrete surfaces shall be true and even, free from honeycombed surface depressions or rejections. Formed surfaces conform with surface finish requirements of AS3610 for the surface class nominated. WITNESS POINT 1 day prior
Acceptance
HPP CON Key - W
HPP QA Key - W
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.14 - Surface Treatments
Ref docs -
Acceptance criteria - Any surface treatments to be applied are approved for use and appropriate dose rates have been determined
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.15 - Joints
Ref docs - As per drawings
Acceptance criteria - As per design drawings. Sawn joints to commence as soon as the concrete has hardened sufficiently.
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.16 - Curing
Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.13]
Acceptance criteria - From completion of finishing cure continuously with an approved method for a min period of 7 days or as directed by the Superintendent. a. Ordinary Portland cement concrete – 7 days b. High early strength concrete – 3 days c. Concrete with cement or pozzolan materials – 10 days
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.17 - Stripping of formwork
Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 4.4.5]
Acceptance criteria -
Acceptance
HPP CON Key - S
HPP QA Key - S
Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3.18 - Concrete Repair (If required)
Ref docs - Spec. 0002 Concrete supply, constructio n, and grouting [Cl 8.7]
Acceptance criteria - Defective concrete shall be repaired or replaced. The materials and techniques of repair shall be examined and approved by the Superintendent prior to the commencement of repairs.
Acceptance
HPP CON Key - H
HPP QA Key - H
Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ☐ Grout Placement Checklist ☐ Approved Aconex Corro for Repair Methodology