## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP048 - ALER 3 General Fitout & Finishes | itp |  |  |  |  | FH-ZU2-QU-ITP048 - ALER 3 General Fitout & Finishes - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex or ACC.
label | Reference Documents - Current Revisions in Aconex or ACC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Check all materials & shop drawings have been approved for use
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Ensure all materials & shop drawings have been reviewed & approved by BECA.
label | Reference Documents - Materials Schedule Drawing Package 030
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Register
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.4 - Material inspections (off-site)
label | Frequency - Prior to commencing works
label | Acceptance Criteria - WITNESS POINT
label | ○ Give notice for inspection of fabricated window assemblies at the factory ready for delivery.
label | Reference Documents - ZULU- BECA-001- SPC-00005, 0451
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP Signed, Inspection Report
label | WP
label | Responsibility - Project / Site Engineer / Principals Representative
date | Date Completed:
checkpoint | 1.5 - Material inspections (on-site)
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Complete a material inspection for deliveries of the following items:
label | ○ Roofing
label | ○ Light Steel Framing
label | ○ Glazing
label | ○ Insulation/sarking
label | Reference Documents - FH Quality Procedures
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.6 - Survey Set out
label | Frequency - Each Lot
label | Acceptance Criteria - Confirm survey set out has been completed on site prior to commencement of works
label | Reference Documents - Survey Process
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 2.0 - Construction
checkpoint | 2.1 - Roofing
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Check for installation of the following against manufacturers specification, project drawings and AS/NZS standards:
label | — Roofing battens
label | — Insulation Blanket
label | — Sarking/vapour barrier
label | — Roofing Sheets
label | — Gutter Hail/Leaf Guards
label | — Eaves Soffits
label | ○ Notice shall be given for inspection of roofing supports prior to covering up or concealing
label | Reference Documents - Drawing set 030, AS 1562.1, ZULU- BECA-001- SPC-00005, 0423
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITC, Compliance Certificate
label | WP
label | Responsibility - Project / Site Engineer / Principals Representative
date | Date Completed:
checkpoint | 2.2 - Glazing
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Installation of all windows as per the project drawings and manufacturer specifications.
label | ○ Check windows are plumb, correctly sealed and securely fixed.
label | ○ Give notice for inspection of the following:
label | — Openings prepared to receive Windows in precast walls
label | — Commencement of Window installation
label | ○ Certification required confirming that window assemblies conform to AS 2047 (2014)
label | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0451, AS 2047
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITC, Compliance Certificate
label | WP
label | Responsibility - Project / Site Engineer / Principals Representative
date | Date Completed:
checkpoint | 2.3 - External & Internal Door & Jambs
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Installation of the following
label | — Door frames/jambs
label | — Hang doors
label | — Locks, latches & handles
label | — Fire Doors – as per certifiers requirements
label | ○ Check for
label | — Plumbness
label | — Securely affixed
label | — Proper function
label | — As per drawing sizing & locations
label | — Adequate clearance bottom of doors
label | — Sealing installed as required
label | ○ Give notice for inspection of door frames in place prior to any joinery/trim being installed.
label | Reference Documents - Drawing Set 030, ZULU- BECA-001- SPC-00005, 0455
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITC
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 2.4 - Wall & Partition Framing
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Installation of Light Steel Framing to the project drawings and as per manufacturers specification.
label | — Max Stud Spacing of 600 mm
label | — Damp Proof Course as required
label | ○ Give notice for inspection of the following
label | — Set out prior to construction
label | — Wall & Partition framing prior to plastering/lining
label | — Framed & lines partitions ready to receive framed and glazed components
label | — Completion of installation Certification required confirming that the erected frame conforms to the documented project requirements.
label | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0342
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITC, Compliance Certificate
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 2.5 - Fireproofing – Fyrchek Panels / Ceilings
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Ensure the following during installation:
label | — Butt joints flat with no visible gaps
label | — Junction with floors and ceilings straight and true, and allow for a 10mm fire caulking gap
label | ○ Expansion joints, taped joints and setting per spec and manufacturers requirements
label | ○ Give notice for inspections of the following:
label | — Control/construction joints completed and ready for fire- stopping
label | ○ Finished Fire Stopping prior to concealment
label | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0511, 0182, Gyprock – The Red Book
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITP, Fireproofing Certificate
label | HP*
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 2.6 - Suspended Ceiling
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Installation of the suspended wall system as per manufacturers specifications and to the project drawings.
label | ○ Ensure ceiling height is correct.
label | ○ Give notice so that inspections can be made of the following:
label | — Suspension system before installation of lining
label | — Ceiling assembly before installing of fittings and site painting
label | — Completed Ceiling
label | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0532
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITC
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 2.7 - Insulation
label | Frequency - Each Lot
label | Acceptance Criteria - Install all wall insulation prior to plastering/wall lining.
label | ○ Ensure adequately placed and secured.
label | Reference Documents - Drawing set 030
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.7 - Plastering & lining
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Installation of the following as per manufacturers specification:
label | — Wall Plastering to steel frames
label | — Ceiling lining to suspended ceiling
label | ○ Expansion joints, taped joints and setting per spec and manufacturers requirements
label | ○ Give notice for inspection of finished surface prior to applying sealer or finish coatings or decorative paper
label | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0511
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITC
label | WP
label | Responsibility - Project / Site Engineer Principal’s Representative
date | Date Completed:
checkpoint | 2.8 - Fireproofing – Penetrations
label | Frequency - Each Lot
label | Acceptance Criteria - Ensure the following for all penetrations in fire rated rooms:
label | — Penetrations are sealed and approved
label | — Fire collars are installed as per manufacturer specs
label | — Verify door jambs are filled in or packed
label | — 500mm run for junction seals
label | — 500x500mm area for penetration seals
label | ○ Give notice for inspections of the following:
label | — Service penetrations completed and ready for fire-stopping
label | — Finished Fire Stopping prior to concealment
label | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0182, Gyprock – The Red Book
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITP, Fireproofing Certificate
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 2.9 - Joinery/Fixing
label | Frequency - Each Lot
label | Acceptance Criteria - Installation of the following in accordance with project drawings and as per manufacturers specifications:
label | — Skirting
label | — Architraves
label | — Cabinets (if applicable)
label | — Door Handles
label | — Grabrails
label | — Toilet fixtures such as soap dispensers, toilet roll holder, paper towel dispenser etc
label | — Door close speeds set
label | — Kick plates
label | Reference Documents - Drawing set 030
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITC
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 3.0 - Finishes
checkpoint | 3.1 - Painting
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Painting off required components as per specified colour & paint.
label | ○ New unpainted interior surfaces: To AS/NZS 2311 (2017) Table 5.1.
label | ○ New unpainted exterior surfaces: To AS/NZS 2311 (2017) Table 5.2
label | ○ Give notice for inspection of: Opaque finishing stages:
label | — Completion of surface preparation.
label | — After application of final coat. Clear finishing stages:
label | — Before surface preparation of timber.
label | — Completion of surface preparation.
label | — After application of final coat.
label | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0671p
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITC
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 3.2 - Flooring
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Ensure all flooring surface is level and falls to drains have the required grades prior to installation of flooring.
label | ○ Installation of the following strictly according to manufacturer’s specifications and project drawings:
label | — Vinyl Flooring
label | — Resin Based Flooring Give inspection for the following: Resin based Flooring
label | — Completion of substrate preparation
label | — Substrate joints, thresholds and perimeter walls
label | — Completed priming of base.
label | — Completion of each coat in the flooring system
label | — Completed application Resilient Flooring
label | — Substrate immediately before fixing resilient finishes or underlay
label | — Trial set outs before execution
label | — Completed underlay, if any
label | — Finished surface before applying sealers or polishes, if any
label | — Completed installation
label | Reference Documents - Drawing set 030, Materials Schedule, ZULU- BECA-001- SPC-00005, 0657, 0651
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, BE ITC
label | WP
label | Responsibility - Project / Site Engineer / Principal’s Representative
date | Date Completed:
checkpoint | 3.3 - Furniture
label | Frequency - Each Lot
label | Acceptance Criteria - Delivery and installation of approved furniture.
label | ○ Installed on site as per manufacturers specifications.
label | Reference Documents - Drawing Set 030, Aconex DCWC Mgt-GCOR- 010265
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.4 - Mirror
label | Frequency - Each Lot
label | Acceptance Criteria - Installation of bathroom mirror as per drawings and manufacturer specification.
label | ○ Correct adhesive used and allowed to cure for minimum period whilst mirror is supported.
label | Reference Documents - Drawing Set 030
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.5 - Eye Wash Station
label | Frequency - Each Lot
label | Acceptance Criteria - Installation of eye wash station as per drawings and manufacturer specification.
label | Reference Documents - Drawing Set 030
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.6 - Installation of Small Kitchenette
label | Frequency - Each Lot
label | Acceptance Criteria - Installation of kitchenette as per drawings and manufacturer specification.
label | Reference Documents - Drawing Set 030
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: