## Sheet1
type | name
checklist | Bonding Installation
section | Information
checkpoint-no-status | Bonding Installation Check Sheet
label | Project: P.0597875 - AIAL WP1
textbox | Area
textbox | Drawing reference
section | Pre-Installation
checkpoint | 1.01 Review drawings and ensure all earthing conductors installed as per relevant drawing. (Hold Point)
section | Installation
checkpoint | 2.01 Confirm conductor size as per drawing.
checkpoint | 2.02 Confirm all required links are in place.
checkpoint | 2.03 Confirm all bolted connections are torqued and correct fixings are used.
checkpoint | 2.04 Confirm all cables are terminated correctly (i.e. correct lugs, ferrules etc.).
checkpoint | 2.05 Confirm labelling installed and correct.
checkpoint | 2.06 Confirm one lug per bolted connection.
checkpoint | 2.07 Complete testing. Ensure test sheet complete.
section | Completion of works
checkpoint | 3.01 Supervisor to update, collate, check documents, drawings and results then record.
section | Documentation
checkpoint | 4.01 Verify all drawings “As built” status.
checkpoint | 4.02 Verify that all necessary documentation has been signed by the appropriate persons.
checkpoint | 4.03 Collate and Deliver final reports.
section | Signoff
signoff | Supervisor
signoff | Project Engineer
signoff | Client