## Sheet1
type | name
checklist | Fibre Optic Cabling
section | Information
checkpoint-no-status | Fibre Optic Cabling Check Sheet
label | Project: P.0597875 - AIAL WP1
textbox | Area
textbox | Drawing reference
textbox | Cable number
section | Planning
checkpoint | 1.01 Review the existing cable tray layout and plan the routing of the fibre optic cables to minimize the bends. (Hold Point)
checkpoint | 1.02 Check the specifications of the fibre optic cables to be installed, including length, type, and any specific handling requirements. (Hold Point)
checkpoint | 1.03 Ensure all the necessary cable pulling tools are in good condition.
checkpoint | 1.04 All staff and subcontractor briefed HSE & install methodology.
checkpoint | 1.05 Ensure that the installation area is clear of potential hazards.
checkpoint | 1.06 Verify that the team members are equipped with appropriate PPE such as gloved, safety glasses, hard hats, and harnesses.
checkpoint | 1.07 Inspect the existing cable trays for any damage or debris that could hinder the installation.
section | Install
checkpoint | 2.01 Unroll the fiber optic cables carefully to prevent twists and kinks.
checkpoint | 2.02 Verify the integrity of the cable sheath and ensure that it is free from any damage or defects.
checkpoint | 2.03 Attach pulling grips to the fiber optic cables and secure them properly.
checkpoint | 2.04 Use appropriate pulling tension to avoid damaging the cables during installation.
checkpoint | 2.05 Ensure that the cables are properly supported along the entire length of the cable tray.
checkpoint | 2.06 Ensure at least 3-meter cable slack is available at each end to perform splicing and termination.
section | Confirmation of install
checkpoint | 3.01 Cables identified by a permanent marker at each end clearly.
checkpoint | 3.02 Cables installed in vertical cable tray are secured to the cable tray at least every 1.5 m.
checkpoint | 3.03 Ensure the cable has no joints or connectors.
section | Splicing and termination
checkpoint | 4.01 Follow the manufacturer's guidelines for splicing and terminating the fiber optic cables.
checkpoint | 4.02 Use appropriate splicing tools and techniques to achieve low signal loss and ensure reliable connections.
section | Testing and verification
checkpoint | 5.01 Conduct thorough testing using appropriate equipment to verify the integrity and performance of the installed fiber optic cables.
checkpoint | 5.02 Check for any signal loss, attenuation, or other issues that could affect the transmission quality.
section | Documentation
checkpoint | 6.01 Record the test results.
checkpoint | 6.02 Submit the ITPs to client.