## Sheet1
type | name
checklist | HV Cable Jointing
section | Information
checkpoint-no-status | HV Cable jointing Check Sheet
label | Project: P.0597875 - AIAL WP1
textbox | Area
textbox | Drawing reference
textbox | HV Cable number
section | Pre-Installation
checkpoint | 1.01 All staff briefed on safety requirements and installation procedure. Ensure permits are valid and all parties are notified.
checkpoint | 1.02 Verify drawings is the latest revision .
checkpoint | 1.03 Confirm correct cable joint kits supplied. Ensure voltage level, bushing type, indoor/outdoor, correct diameter.
checkpoint | 1.04 Termination pit dimensions suitable for cable joint.
checkpoint | 1.05 Termination pit free of water, and adequate access provided.
checkpoint | 1.06 Existing cable correctly identified, isolated and or spiked and communicated to all parties.
checkpoint | 1.07 Pre-joint cable test carried out and results recorded (Hold Point)
checkpoint | 1.08 Ensure Cable Jointers ITP's Template received and verified. (Witness)
checkpoint | 1.09 Circuit breaker on either end are isolated of the relavant cable and LOTO procedure is applied. (Hold Point)
checkpoint | 1.10 Ensure cable is de-energised. Prove-Test-Prove. Confirm with the relavant party that the work can proceed. (Hold Point)
section | Installation
checkpoint | 2.01 Ensure the cable is cut at the correct location.
checkpoint | 2.02 Ensure correct phase rotation matched for new and existing cable. Cable core identified by a label or marked.
checkpoint | 2.03 Ensure HV cables are supported/clamped as necessary.
checkpoint | 2.04 Ensure either side of the cable has a straight section for cable jointing and ensure no weight/pressure on the joint positions.
checkpoint | 2.05 Prepare the cable joint in accordance with the instructions provided by the manufacturer joint kit.
checkpoint | 2.06 GPS location captured (if required).
checkpoint | 2.07 Photographic evidence taken and recorded. (Hold Point)
section | Confirmation of the installation
checkpoint | 3.01 Cable jointers completed and signed ITP received. (Hold Point)
checkpoint | 3.02 Correct back fill carried out as per specifications. (Witness)
checkpoint | 3.03 Termination chamber closed, sealed and no tools or detritus left inside. (If applicable) Confirmation
checkpoint | 3.02 Correct back fill carried out as per specifications (If applicable). (Witness)
checkpoint | 3.03 Termination chamber closed, sealed and no tools or detritus left inside. (If applicable)
section | Signoff
signoff | Supervisor
signoff | Project Engineer
signoff | Client