## Sheet1
type | name
checklist | LV Cable installation
section | Information
checkpoint-no-status | LV Cable installation Check Sheet
label | Project: P.0597875 - AIAL WP1
textbox | Area
textbox | Drawing reference
textbox | Cable number
section | Pre-Installation
checkpoint | 1.01 All staff briefed on safety requirements and installation procedure. (Hold Point)
checkpoint | 1.02 Verify drawings latest revision. (Hold Point)
checkpoint | 1.03 Ensure ducting/trenches installed by others is checked prior to use. (Hold Point)
section | Installation
checkpoint | 2.01 Ensure cable drums are set up correctly and level - Jacks must be suitable for the load & size of drum. (Witness)
checkpoint | 2.02 Ensure cable drums are set up in a location clear of personel and traffic.
checkpoint | 2.03 Ensure any edges to trays are smooth and chamfered or protected.
checkpoint | 2.04 Minimise the amount of 'drag' across the ground when installing cables (ensure enough personnel are present).
checkpoint | 2.05 Ensure pulling tensions and bending radius' are not exceeded during installation.
checkpoint | 2.06 Ensure that cables are grouped in a manner to reduce magnetic interference where possible.
checkpoint | 2.07 Ensure cables are supported along entire length.
checkpoint | 2.08 Confirm each cable is labelled appropirately at either end and enough length left for termination. (Monitor)
checkpoint | 2.09 Confirm no damage has occurred to cabling during installation. (Monitor)
checkpoint | 2.1 Ensure ends of cables are taped/capped until terminations unertaken.
checkpoint | 2.11 Mark up "As built" drawings. (Monitor)
section | Signoff
signoff | Supervisor
signoff | Project Engineer
signoff | Client