## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP 04 - Pavement Layers | itp
section | Details
checkpoint | 1 - Subgrade (Existing Surface)
label | SPECIFICATION REFERENCE - Civil Works Specification Section 2, Clause 14.1
label | ACTIVITY/TASK - Proof Roll Witnessed by Principal's Representative.
label | INSPECTION BY - UCCL/MEL
label | TASK TIMING OR TASK FREQUENCY - Prior to commencing with the AP65 subbase layer.
label | ACCEPTANCE CRITERIA - Acceptance of subgrade by Principal's Representative.
label | UCCL - H
label | CLIENT - H
holdpoint | HOLD POINT
checkpoint | 2 - Subbase Material Testing
label | SPECIFICATION REFERENCE - Civil Works Specification Section 2, Clause 14.4.2
label | ACTIVITY/TASK - Material Test Certificates
label | INSPECTION BY - UCCL/MEL
label | TASK TIMING OR TASK FREQUENCY - Prior to placing AP65 subbase layer on site.
label | ACCEPTANCE CRITERIA - Material meets specification. Material acceptance by Principal's Representative.
label | UCCL - S
label | CLIENT - A
checkpoint | 3 - Subbase Compaction (Under Containers)
label | SPECIFICATION REFERENCE - MELNZ-CI-000133
label | ACTIVITY/TASK - Clegg Testing - Minimum Clegg Impact Value (CIV) of 25.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to placing Fibre Concrete under containers. Minimum 2 tests under each container.
label | ACCEPTANCE CRITERIA - Minimum CIV 25 achieved. Acceptance by Principal's Representative.
label | UCCL - W
label | CLIENT - W
checkpoint | 4 - Subbase Compaction (Inner Zone Between Containers)
label | SPECIFICATION REFERENCE - MELNZ-CI-000133
label | ACTIVITY/TASK - Clegg Testing - Minimum Clegg Impact Value (CIV) of 25.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - Prior to placing Basecourse layer.
label | ACCEPTANCE CRITERIA - Minimum CIV 25 achieved. Acceptance by Principal's Representative.
label | UCCL - W
label | CLIENT - W
checkpoint | 5 - Subbase Compaction (Site Roads)
label | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 7.6
label | ACTIVITY/TASK - NDM Testing
label | INSPECTION BY - UCCL/MEL
label | TASK TIMING OR TASK FREQUENCY - Minimum 5 No. NDM Tests per area. Compaction to achieve average > 95% MDD with minimum value > 92%.
label | ACCEPTANCE CRITERIA - Compaction achieves average > 95% MDD achieved with minimum value > 92%.
label | UCCL - H
label | CLIENT - H
holdpoint | HOLD POINT
checkpoint | 6 - Subbase Tolerances
label | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 5.1
label | ACTIVITY/TASK - Strings.
label | ○ Survey setout/as-builts
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of Subbase layer prior to placing Basecourse layer.
label | ACCEPTANCE CRITERIA - Line and level within tolerances.
label | UCCL - S
label | CLIENT - A
checkpoint | 7 - Kerb and Channel
label | ACTIVITY/TASK - Kerb and channel installation
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of kerb and channel installation.
label | ACCEPTANCE CRITERIA - Kerb and channel meets specification.
label | UCCL - W
label | CLIENT - W
checkpoint | 8 - Basecourse Material Testing
label | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.5.
label | ACTIVITY/TASK - Material Test Certificates
label | INSPECTION BY - UCCL/MEL
label | TASK TIMING OR TASK FREQUENCY - Prior to placing AP40 Basecourse layer on site.
label | ACCEPTANCE CRITERIA - Material meets specification. Material acceptance by Principal's Representative.
label | UCCL - S
label | CLIENT - A
checkpoint | 9 - Basecourse Compaction Compaction (Inner Container Zones)
label | ACTIVITY/TASK - NDM Testing
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - NDM Testnig each area. Compaction to achieve average > 95% MDD with minimum value > 92%.
label | ACCEPTANCE CRITERIA - Compaction achieves average > 95% MDD achieved with minimum value > 92%.
label | UCCL - W
label | CLIENT - W
checkpoint | 10 - Basecourse Compaction (Site Roads)
label | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.5. TNZ B/02 Clause 7.6.
label | ACTIVITY/TASK - NDM Testing
label | INSPECTION BY - UCCL/MEL
label | TASK TIMING OR TASK FREQUENCY - Minimum 5 No. NDM Tests per area. Compaction to achieve average > 98% MDD with minimum value > 95%.
label | ACCEPTANCE CRITERIA - Compaction achieves average > 98% MDD achieved with minimum value > 95%.
label | UCCL - H
label | CLIENT - H
holdpoint | HOLD POINT
checkpoint | 11 - Basecourse Tolerances
label | SPECIFICATION REFERENCE - Civil Works Specification Section 2 Clause 14.4. TNZ B/02 Clause 5.1.
label | ACTIVITY/TASK - Strings.
label | ○ Survey setout/as-builts.
label | INSPECTION BY - UCCL
label | TASK TIMING OR TASK FREQUENCY - On completion of Basecourse layer prior to placing Basecourse layer.
label | ACCEPTANCE CRITERIA - Line and level within tolerances.
label | UCCL - W
label | CLIENT - W
checkpoint | 12 - AC Material Specification
label | ACTIVITY/TASK - Specification as agreed between Principal and Contractor.
label | INSPECTION BY - UCCL/MEL
label | TASK TIMING OR TASK FREQUENCY - Prior to using the material on site
label | ACCEPTANCE CRITERIA - Specification as agreed between Principal and Contractor prior to works commencing.
label | UCCL - H
label | CLIENT - H
holdpoint | HOLD POINT
checkpoint | 13 - AC Pavement Testing
label | ACTIVITY/TASK - Testing as agreed between Principal and Contractor.
label | INSPECTION BY - UCCL/MEL
label | TASK TIMING OR TASK FREQUENCY - On completion of AC pavement layer.
label | ACCEPTANCE CRITERIA - Testing as agreed between Principal and Contractor prior to works commencing.
label | UCCL - H
label | CLIENT - H
holdpoint | HOLD POINT