## Master List Templates
Id | Type | Name | Values | Prompting Name
2988931c-6f0b-41d2-b708-0310a761e33e | checklist | General Precast QA |  | General Precast QA
7d564968-ed41-46a4-ae8e-d58af860aa0e | section | Pre install Lifting and quality checks
41aa8d0b-5078-4216-90f4-6604e53aadf9 | checkpoint | Birth cert provided
747b9038-5754-4e82-971c-5c0f82e2e5a2 | checkpoint | Panel visual inspection (any damage, check colour and quality) take photo
1d796b45-fbb9-405c-93ab-5b375df1443a | checkpoint | Can panel be lifted as per rigging details provided in shop drawing
c32404bc-e319-462b-a042-2fd716288663 | checkpoint | Do strong-backs, fall protection need to be installed prior to lift
da1a7f4e-303c-44fc-b024-abbb988f6203 | section | Post install check
8395f3b4-2625-4450-9915-82c9f9db4327 | checkpoint | Set out check Grid/Level/Plumb
8f6337b0-baa4-4aea-ac26-f57f61a54da2 | checkpoint | Shims set to correct height
819b1800-1913-4d48-ae14-41db3925a99a | checkpoint | Props signed off and installed correctly with all pins and clips in
5d23d035-eb06-46e5-abc7-80f5bab0b0f3 | checkpoint | Base checked and ready for Grouting
dd11b226-1c2a-4d9b-9c11-3cd34f69d818 | checkpoint | Check quality, any cracks, damage
69be4a0c-6322-5e33-967d-0013130b21d9 | checklist | Job Details Checklist |  | Job Details Checklist
51bf5cc3-529c-5727-8f24-9698eaef6d5b | checkpoint | Project details entered below
c1f6ab7e-f81e-589e-b78e-492c1f38c907 | textbox | Job File Number
fc3160a1-3708-54e1-8dd2-5ce70a30df0f | textbox | Project Name
49a3fb09-ed91-5ef3-b0f6-342e5d559882 | textbox | Site Address
c2e2d2b9-425b-5bbc-92b9-7efd8b02f2a7 | textbox | Main Contractor
9e583952-527a-5180-828e-fe444e9d9782 | textbox | Main Contractor POC
e0d71164-cbf5-5047-a285-5aa1b4f3104c | textbox | Structural Engineer
1592197d-fe31-50fc-b8f1-19b76276f5bc | textbox | Architect
bca707e6-e3e1-4bb9-abf2-f925e9412bd4 | checklist | Job Details Checklist (V1) |  | Job Details Checklist
35294a2e-3be7-4de2-9c7c-9f8053ed87c1 | section | Details
ef6e723c-5af9-475f-8928-3e5379f737e7 | checkpoint | Project details entered below
47c73c88-9ef0-52e5-885f-1f4cff71c349 | textbox | Project Name
85158d6b-aac1-50e4-b769-0d840c9c7b86 | textbox | Site Address
36d546d9-0f7e-54d0-94c4-0bd6167fceec | textbox | Main Contractor
5dc3c97a-35cd-527f-91f8-22dfc6de0ff0 | textbox | Main Contractor POC
ca9692b8-08b7-520e-8975-ddcf19bcb2e0 | textbox | Rigging/dogging by
0b532558-25ae-5e91-96c6-d1557a7137ed | textbox | Crane supplier & crane used
e06d7fa0-c34d-53dc-aadb-b1dfb0dc3c42 | checklist | Precast Install QA |  | Precast Install QA
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
3a0365f7-d8cf-5281-8449-db2471d5f49b | checkpoint | Details Complete
4ec70be5-8d6b-57c4-baf8-2f8722b72b17 | textbox | Watpac supervisor
24040c42-3857-59a3-a7e7-15a98c70d254 | textbox | Precast Supplier
27a57b5c-a429-5084-b0e0-7239d052fc4a | textbox | Rigging Company
8720b5f3-d8d6-5910-bfbf-b44db0bf47cc | textbox | Riggin Supervisor
c60f3148-12f6-515e-866d-e0ab88b61739 | textbox | Crane Supplier
39d7520b-e0dc-5e25-89a1-76358c8e9154 | section | Lifting and Quality Checks
ffbd54f5-383b-5ce6-9d6d-55a05a688db9 | checkpoint | Birth Cert (QA) Provided
3dc30cb7-3137-54b6-b2ca-1071b32a1f82 | checkpoint | Panel Visual inspection (any damage, check coulour and quality) take photo
97bd35b9-751b-56a4-9db7-2dd00d291344 | checkpoint | Can the panel be lifted as per rigging details provided in shop drawing?
021a33db-f5e4-5a4c-89ab-c3aaf0c75bd5 | checkpoint | Do strongbacks, fall protection need to be installed prior to lift?
aceff255-bd31-5ea7-a334-5fa5c48cb46e | section | Post install check
fac19dbd-dc32-504c-adc3-05fff6877cf6 | checkpoint | Set out check - Grid / level / plumb
c0bea680-01a9-56f6-950e-76597a47dd7d | checkpoint | All Bracekts installed with correct number of fixings, washers, packing shims etc
dc1fdd4f-9bc8-5c62-bbc8-d56dd23fb5dc | checkpoint | Grouting
67c2cd5d-6d13-59e5-817b-5f770fe7ee6b | checkpoint | Propping signed off temp works engineer
ad3ae2b9-0e1a-4d48-a0d5-e1a052001027 | checkpoint | Grouting
cb33a6de-3ddb-5030-a945-c1b3b2eec332 | checkpoint | Ready/OK to pour upper level
e60f0a55-bbd6-51e9-9b67-25f060f334f8 | checklist | Precast Panel QA |  | Precast Panel QA
0a6f879a-f7c0-5fb8-a0ee-b01fa0ff8553 | section | Precast Element Details
f790a491-9898-5ece-b858-71a5143647dc | checkpoint | Concrete Details Complete
9a9f7793-1730-56fc-ad72-cac4a3914488 | textbox | Concrete Volume
7a06bc19-3510-5a04-a45f-8ecb34cc16cb | textbox | Concrete Strength
cdb07bb6-0d0a-5c53-9c35-e272ae7f9fbb | textbox | Enter Drawing Revision Number
91d7836b-9319-5abe-9fcd-ad70b55e2c2f | textbox | Cast Date
f82127a1-976e-5098-b036-4e64fa49e86b | textbox | Admixture Required
514a3ffb-c729-5bcb-b232-f399880cc36e | section | Formwork Set Up Checks
ca09864a-dea5-57bf-a14f-7906b27ff390 | checkpoint | Length/Width/Thickness/Cutouts/Diagonals
ed2ed9e3-7b68-5bac-a3ff-641c772a7683 | checkpoint | Edge Details & Rebates
a7f6eec0-ce53-5038-8356-701f6d265c83 | checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
eb669ff0-5050-545a-b015-12ea82406b40 | checkpoint | MF roughening's
8dd19059-36e1-5713-8a2d-69de3add5555 | checkpoint | Sides Straight & Magnets Fastened
a0519a85-85fc-5ade-b8de-701b9f1a3087 | checkpoint | Mould Face Clean
0893047f-442e-5cf2-8203-15ebaedb0fec | section | Prepour Checks
9f00b6d8-0b61-5c62-9331-88dc85cf3d35 | checkpoint | Mould Cleaned & Oiled
9f8fde18-6c88-55d7-b038-3d02ccf8403c | checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
1cc09221-6314-5edf-bfdf-46726ac443b4 | checkpoint | Check covers on all sides, MF and TF
448b247e-8856-5758-8008-4274631a93b0 | checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
c100af67-4eef-52e1-86dc-57626e02f0c3 | checkpoint | Starters (Size, Grade, Setout and Length)
9db6f847-9383-52b3-b5ff-b5f4f84e595a | checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
9b6e3edc-dfe4-5262-98f0-960d691a3111 | checkpoint | Lifters
bea24c24-ca23-575f-bcb4-babd519b4b83 | checkpoint | Tie wire Trimmed
68823ead-2cec-500c-90ed-8b41c6d502c8 | checkpoint | Panel fully clean
24b19991-6ee4-5a4b-915e-d0fad604df1c | checkpoint | General Photos Attached
7a0a347f-51db-5be3-888b-97db9cd91e17 | checkpoint | Concrete Docket Attached
dd6bbf6b-a743-5395-9969-8341ce437a0e | checkpoint | Shop Drawing Checked Off (attach photo)
6e622356-d5be-55cc-a9f4-debde1802f08 | section | Demould Inspection
20d807eb-8c7f-55ca-8c90-ce4e9fff50ad | checkpoint | Demould Inspection complete
1d916d8e-45c7-556e-9d23-ce8e00d53783 | section | Loading Out
6512bd27-8753-5a74-aae2-6cdbb5ad5bc1 | checkpoint | Photo take of Panel on Truck
db97e532-caec-56ff-862c-f0c514e9bef3 | checkpoint | No remedial work required on site
16c198a1-27aa-5160-8050-8e0776d13cc9 | section | Test Results, Certificates and Documentation
4773d614-8475-5887-bc13-fd99b673c2bd | checkpoint | Upload reinforcing detail sheets
9a2fc81c-6997-5c2a-8260-315579b91828 | checkpoint | Upload Photo of Reinforcing Cast # Tracking
9b196911-f702-5ae6-9c7b-e579b8e8ab7b | checkpoint | Upload Concrete test results
f925bf1c-dce4-46a0-b2cd-dc4f50beceaa | checklist | Precast Panel QA (V1) |  | Precast Panel QA (V1)
669ee94a-3b66-4038-8df8-a2d2437c4af8 | section | Precast Element Details
18a67b45-b448-4eb8-a4a5-9eac5ae99f70 | checkpoint | Concrete Details Complete
75301615-a6af-50f5-8e26-e8ba92c8ddaf | textbox | Concrete Volume
1a8d9e05-33f0-513f-8959-b29bc21a9062 | textbox | Concrete Strength
8934d94e-5947-50c0-a747-c19b797c198c | textbox | Enter Drawing Revision Number
f8a4bdb9-8b61-54a4-a687-782eaedf23f8 | textbox | Cast Date
09ce230b-97aa-51f7-8b6d-7d8080e02913 | textbox | Admixture Required
dcb3a255-3f3c-4ffe-babd-8c6cf13502e0 | section | Formwork Set Up Checks
b37ed67c-0764-4e33-a6f8-533596c04a1d | checkpoint | Length/Width/Thickness/Cutouts/Diagonals
92779e6d-d3a2-42a3-9ae0-a76e8a459fa3 | checkpoint | Edge Details & Rebates
147b3bb9-6e35-4e06-b0d4-10a65be5792e | checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
ce2601f7-bc8d-45fa-9300-9fc9f18fe237 | checkpoint | MF roughening's
6e71c84e-40c9-4072-958f-f85f91ffd656 | checkpoint | Sides Straight & Magnets Fastened
274474b3-e62c-4fc1-945a-2a67b1fc7065 | checkpoint | Mould Face Clean
4e4c3fae-d749-4f34-b20f-7e1940dcb7da | section | Prepour Checks
cdff2892-536c-4ab0-b84c-9829f7a97df7 | checkpoint | Mould Cleaned & Oiled
b12e7460-9959-4f0d-a231-67296a4864a2 | checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
1b698d56-8b0a-4712-b061-2768301bafa9 | checkpoint | Check covers on all sides, MF and TF
2e9b945e-0925-48cd-882b-f9ca2a4d114a | checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
97730527-c49e-43b7-b1b4-429a0dd01632 | checkpoint | Starters (Size, Grade, Setout and Length)
f80308b3-1796-4aaf-b37d-2fc51365947d | checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
6b4b15f8-aaf8-4f7f-bb71-3068b786545a | checkpoint | Drossbach Locations and Length
9aa65505-66bb-4834-8651-0d3fc9578d47 | checkpoint | Lifters
8eae7d59-8184-4c44-8af2-ffa1c86288f1 | checkpoint | Tie wire Trimmed
34f8fe9f-c23a-4542-b6ef-878c2648cd2c | checkpoint | Panel fully clean
722cc99e-e178-4228-9bbd-4a8445ce6fdf | checkpoint | Panel tag installed
4a6849ec-b2c5-4dd1-8037-3f2215131087 | checkpoint | General Photos Attached
b269f506-c902-4b7c-845e-4e6cba278976 | checkpoint | Shop Drawing Checked Off (attach photo)
627f40e0-922e-48cc-998d-7fa77161988d | section | Demould Inspection
4f323124-9b35-415c-9f17-f85ba40630be | checkpoint | Off Site Claim Photos Taken (attach photo with principles details )
450203c2-2ff7-44d5-b12f-ba2b192e5a99 | checkpoint | Demould Inspection complete
0062989c-6d59-41b0-86a0-51283e25f349 | section | Loading Out
e5f9ccaf-d7d6-4f38-8381-dd8baa35eb96 | checkpoint | Photo take of Panel on Truck
b09d2b6f-8f23-454d-be52-7a85e94a0fff | checkpoint | No remedial work required on site
3fd82cb4-4a1f-4811-aa84-260a47f75f22 | section | Test Results, Certificates and Documentation
1248d001-bff5-4c2f-a59f-3199f98d541c | checkpoint | Upload reinforcing detail sheets
ed677a5b-9100-4bbd-85d1-2bc10dfa85d0 | checkpoint | Concrete Docket Attached
0d92247b-ca56-4040-bc5d-f56a1922a66e | checkpoint | Upload Concrete test results
ad1bc9d5-0cb3-4f62-9b91-5d83dc6f2226 | checkpoint | Upload Photo of Reinforcing Cast # Tracking