## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
5d3f9eb5-d6b3-4aa1-8a9a-8e256ec208e7 | checklist | ITP - Clearing and Grubbing | itp | ITP - Clearing and Grubbing
b1342eda-2f49-4cb2-811b-6c5ea611c7d8 | section | Clearing and Grubbing
df0f18cc-daba-4c27-8caf-8ca89e1518a8 | checkpoint | Clearing Requirements
d978475e-e284-5d4e-8153-a93d29aa9a63 | note | Acceptance Criteria and Frequency - Where an area of the premises are required to be cleared, the clearing includes the removal of all artificial obstructions including fences, rubbish unnecessary structures, building foundations, obsolete pipelines and the like plants (including stumps and boulders) other than the plants required to be retained as shown on the approved drawings;
dd600f0f-9bdc-597f-8157-ed4abc794c49 | note | Reference - LCC SS 1 Part 2.1
985c1622-5234-57d3-bf4e-e2e3f269d4e5 | note | Item Check - Check and Verify
d19d8bea-36b4-4222-ba1e-7f31a1f45bdf | checkpoint | Extent of clearing and grubbing
7cb7beb4-fe65-5364-9cfe-6b7a7b5a6351 | note | Acceptance Criteria and Frequency - The extent of the cleared area is limited to the minimum area of the premises to be occupied by the completed earthworks or 1 metre on each side of the completed earthworks or the minimum area of the premises required to safely install a service.
9e8f8840-a574-5a3b-8eaa-cebae75ecf06 | note | ○ Grubbing, being the removal from the ground of trees, roots and stumps to a depth of 300mm below the surface of the ground, is carried out across the entire cleared area, any area which is identified as an area not to be disturbed, is to be fenced off.
b6bf9272-7ddc-57e0-8e7d-a2208ac06d0b | note | Reference - LCC SS 1 Part 2.2 & 3.1
c02f9a7a-cc3a-5e0a-941c-b6bfd7a64407 | note | Item Check - Check and Verify
12c61f8e-8ed5-4beb-b22c-573fef013e40 | checkpoint | Removal of material from the premises
1269e4cd-d671-5797-885a-2e6b3867e501 | note | Acceptance Criteria and Frequency - Cleared plants are disposed of by mulching and reusing the mulch on the premises as far as possible.
e86f4eb8-5a95-5092-a158-d2287d76acf0 | note | ○ All material, other than plant material that is mulched and reused on the premises, is removed from the premises to a place approved by the local government, no material is to be burnt on site
783cee84-4a40-5917-ac48-fa1a1c5525a5 | note | Reference - LCC SS 1 Part 2.4
7bc2832b-528f-5f75-ba07-9aef3767bb6b | note | Item Check - Check and Verify
6dd411f5-1714-4eb8-92e8-70d497487b75 | checkpoint | Fauna Habitat Logs
b2f204d9-710f-5fb5-af1c-50ef4f1d84cc | note | Acceptance Criteria and Frequency - Hollow timber which is identified as being suitable for fauna habitat logs shall be relocated to areas clear of construction activities as follows:
cb33396a-2ffd-59a3-b957-0c66baea68c1 | note | a) behind batters
8d3f6914-c048-57be-b89e-1990dfb05341 | note | b) behind proposed safety barriers but not within any hazard free zone, and
a3a15378-a2ab-5dff-82ce-47139425650a | note | c) areas at least 9 m clear of carriageways.
0610756f-334a-5526-91d4-17e02e71c50b | note | ○ Fauna habitat log density shall not exceed 20 m length per 100 m² area. Logs shall not be placed in waterways or in any area where they are likely to be struck by errant vehicles.
b1c96f89-0233-5137-8eaf-f684793052bf | note | Reference - MRTS04 Clause 7.2.5
f4fd28b5-ea20-5cb4-9953-389e8a318f00 | note | Item Check - Check and Verify
0b8bd99f-e32a-406c-8344-5b4109e42ae4 | checkpoint | Additional Requirements:
e1499f5e-0dc6-5700-812c-1875ff8ee37f | note | Acceptance Criteria and Frequency - Within the limits of the clearing and grubbing, but clear of earthworks operations, any existing local irregularities of the natural surface are trimmed so as not to cause a hazard to errant vehicles. The surface is lightly compacted when necessary to provide a surface consistent with that existing prior to the Works
3cfa1550-5448-5db6-bc02-819f6da76624 | note | Reference - MRTS04 Clause 7.2.8
34dbb050-1b68-5cd4-b8d4-0565986de23e | note | Item Check - Check and Verify
849e6e0b-477b-4e87-8ff4-7d1069a8ed8a | checkpoint | Final Sign off and Approval - Conformance with the Specification
cb7d3153-989b-5863-be6c-37ab9dbe38ab | textbox | Name of Cient's Representative
c8d3b2f0-fffc-587e-b8ac-6fdd6212d718 | date | Date
decc910e-9143-57de-83b6-072719889c78 | textbox | Name of Contractor's Representative
b4158449-d985-5d6b-b52f-b0f674b0a868 | date | Date
9f533f84-bde7-42c0-8e6b-200ffbf4d496 | signoff | Signature
21d43408-d727-4be2-8bb8-e5caef57ce2a | section | Final Sign Offs (to be completed at closure of Lot)
ac434884-e6e9-4d02-b4ce-95737d06581a | checkpoint | Closure of Lot
37107856-4ae6-4862-81b0-d72e4faee00c | signoff | Closure of Lot Sign Off
1dbfffca-d0a3-4639-9826-82921c534e4a | checklist | ITP - Conduits and Pits - Rev1 | itp | ITP - Conduits and Pits
fc6d3432-0eae-4df2-8f60-d143c46471c8 | section | Conduits and Pits
493f959a-2db6-499d-b749-679102c0bf97 | checkpoint | General
73e49ef5-2baa-5632-bc44-aa9ba83c7c76 | note | Acceptance Criteria and Frequency - A construction procedure for the installation of all conduits and pits shall be submitted to the Administrator at least 14 days prior to the commencement of installation. No excavation activity associated with the installation of conduits and pits shall commence until the expiration of the 14-day period.
09370e4b-449d-5517-9e0d-60ea798e1273 | note | Reference - MRTS 91 Clause 5.3
948230cd-78e5-5781-a0a7-2da5c50fd88b | note | Item Check - Witness Point & Hold Point
5b06434a-9287-4e64-86d2-8364263bf294 | signoff | HOLD POINT
4619ca28-74f1-4152-9893-4a825edb4d4a | checkpoint | Asbestos Assessment
48352898-8507-5b52-b7b4-e0bf6c8a65ef | note | Acceptance Criteria and Frequency - Asbestos is suspected or found in existing installation, work at this site must be stopped immediately, and the finding must be reported to the principal immediately for their decision and instruction on the work to be carried out at the site.
e2586e25-79f1-5864-a35f-38a1dd4ee056 | note | Reference - MRTS 91 Clause 6.1
10e7c1a5-495e-5ed0-b76f-69f1db678ee4 | note | Item Check - Hold Point
a81f364a-0852-41a8-b114-f724327173be | signoff | HOLD POINT
7cdfa583-59e6-4a1f-981e-6b61d1fa3096 | checkpoint | Material Certification
d6c60ed3-690b-5b66-befd-a766450428a8 | note | Acceptance Criteria and Frequency - All materials must comply strictly with the requirements of this Technical Specification. For all materials, a certificate of such compliance shall be provided to the Administrator before the materials are incorporated into the works
f04deb58-1dfb-50e4-bf6f-d7315e32ee25 | note | Reference - MRTS 91 Clause 7.1
c36de2be-4ff7-56dc-9cc5-8f06791a4285 | note | Item Check - Hold Point
bdc8de39-6692-420b-8ec9-b0bb8e61b6c2 | signoff | HOLD POINT
152a2373-c8db-4716-a8c9-f23fae533fe7 | checkpoint | Excavation for underground conduits and pits
532cfb35-eec2-55c8-ab98-cbd7add6bf4f | note | Acceptance Criteria and Frequency - Conduit runs and pit locations shall be set out and notice of such set out shall be provided to the principal at least 48 hours prior to the commencement of excavation. Construction shall not commence before the expirations of the period of notice.
08a27d2e-c57e-5e83-a82a-445fb76d5ea7 | note | Reference - MRTS 91 Claus 8.1
5400cbfe-92dc-5cbc-a5db-79d3f9a4b6f4 | note | Item Check - Witness Point & Hold Point
4dbfa992-afac-4add-b144-a71052155941 | signoff | HOLD POINT
bc2465c5-754c-402b-bc01-a7b2b51916c3 | checkpoint | Bottom of trench
f9f7e3fa-2bdd-59d6-8afe-b3c5dd750dd7 | note | Acceptance Criteria and Frequency - The bottom of the trench shall be compacted as per Standard Drawing 1149 to form a firm uniform surface free from loose material.
f317dbf8-141e-59cf-a9c5-23b0b1a2457b | note | Reference - MRTS 91 Clause 8.4
b119df8f-8706-5e93-906f-9e3b926dbeb9 | note | Item Check - Witness Point
8418fd45-0e53-4b9a-b599-6cee8615b12c | checkpoint | Boring and Jacking
8c596e21-140b-53b0-a2ef-58254ced9422 | note | Acceptance Criteria and Frequency - Work shall not commence until it has been demonstrated to the Administrator that the proposed equipment can accurately install the conduit in accordance with MRTS140 Horizontal Directional Drilling (HDD) and Standard Drawing 1149 Installation of Underground Electrical and Communication.
f5468f6c-100a-5be2-99b8-bc0d1a18fca7 | note | Reference - MRTS 91 Clause 8.7
0bee0273-396e-51d5-ae38-198185ed0bef | note | Item Check - Hold Point
a4402be0-b8c4-4131-9aec-2a417ec6f52d | signoff | HOLD POINT
04f155f4-bb50-4ee7-a0b4-7b62f16331a6 | checkpoint | Installation of conduits
7f8401a1-8bb6-5290-8e39-11a2ef9a3892 | note | Acceptance Criteria and Frequency - The installation of conduits shall conform to the requirements of Standard Drawing 1149. The installation of communications conduits shall also comply with the requirements of AS/CA S009. Prior to installation, the Contractor shall inspect all conduit and conduit fittings to ensure that they are free of any defects that could damage the cables during installation. Conduits to be installed without dips/low points to ensure that drainage at pits operates as intended.
6bafc17d-05dc-5cc5-bc5c-5f8d5ec934e8 | note | ○ The conduits are not to be lower than the pit it connects to unless approved by the Principal. Road crossing installed by ‘boring’ conduit to be installed level to facilitate correct drainage of conduit.
e36dbdb8-2770-5740-8356-91fb9cceb36f | note | Reference - MRTS 91 Clause 9.1
363e3b51-d6d5-5352-9cd6-0e775b6172d9 | note | Item Check - Hold Point
bf233863-f4fe-40eb-b037-8645d48eeedc | signoff | HOLD POINT
dae8f498-afb7-49ad-b7dc-3b47334d5ba2 | checkpoint | Mandrel
19a637e8-2bb9-552f-9df0-47c480d7fd2f | note | Acceptance Criteria and Frequency - After installation and backfilling, the conduit and conduit fittings shall be proved by drawing a mandrel having a diameter of at least 95% of the internal diameter of the conduit. The mandrel shall have a length sufficient to allow it to pass around any bends in the conduit, but not shorter than 95% of the diameter of the conduit being tested
e5254fbd-35c6-5d40-b694-c2830fb0d686 | note | Reference - MRTS 91 Clause 9.1
14594fe3-3af3-579f-b65d-d0c36a7e6b9a | note | Item Check - Hold Point
215ab9bf-c001-411d-8e20-157442203101 | signoff | HOLD POINT
abaf12bf-5cf1-4598-98ff-363782b86132 | checkpoint | Draw rope
56ff7ac5-b176-53d9-8e22-61fa6b47786f | note | Acceptance Criteria and Frequency - Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
18dcc28c-3f9e-590a-af25-a9310bcffe0f | note | Reference - MRTS 91 Clause 9.13
ccd6f017-b274-5218-bb53-9595885aebca | note | Item Check - Witness point
884b1b67-1919-4004-9668-00cf27e3b42e | checkpoint | Vermin proofing of conduits
65271a6d-38b6-53bb-bf30-79297d0422cd | note | Acceptance Criteria and Frequency - Any alternative proposed conduit sealing system shall be fit for purpose, and a proprietary system, and shall be submitted to the Administrator for consideration and approval prior to commencement of the installation of any cabling.
fd8e6510-c1cc-5e2d-afc8-17644863a463 | note | Reference - MRTS 91 Clause 10.9
cd8e5a03-0fb8-51c3-b6c9-f3e85bff8799 | note | Item Check - Hold Point
dc664b92-7e50-4510-94d6-bfaf7c8984cc | signoff | HOLD POINT
b89cfd70-7eb5-4d22-93f9-9cec3d44f122 | checkpoint | Bedding of pit
d94f9ea3-e296-553c-a1d9-c50869daeba4 | note | Acceptance Criteria and Frequency - The bottom of an excavation for a pit shall be compacted to at least 95% relative compaction.
9481ffcf-2967-5fc3-b9ec-bf4aa51de8e0 | note | Reference - MRTS 91 Clause 10.4
4bccd447-09d7-5b8e-a11a-79d0d3367bc3 | note | Item Check - Hold Point
5edd734c-9d5e-4912-a7b2-5aa4f5487dc9 | signoff | HOLD POINT
189e40f0-d77a-417b-a887-c71d74ae10aa | checkpoint | Compact bedding material
0ed28512-9f4a-533b-983a-a437cf8e8cbc | note | Acceptance Criteria and Frequency - Compact bedding material to density index 60.
024ef54e-f843-5394-902c-f68f164d7c28 | note | Reference - MRTS 91 Clause 10.4
ae57de4d-8d1c-5231-8fdc-1de09b5d9f0e | note | Item Check - Check & Verify
aaaf38f1-4f5e-4c59-97cb-6962b951eda2 | checkpoint | Drainage Holes
c1e1263e-df24-5f4f-8349-8dcec96fce48 | note | Acceptance Criteria and Frequency - The lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level.
a14e93ef-705f-5ba6-bddc-6ab894c96e73 | note | Reference - MRTS 91 Clause 10.11
600a19b2-b01c-521a-a5f8-a9307e1506fa | note | Item Check - Witness Point
7fe9c3db-eaa3-4e9a-af15-b87a4b44e40b | checkpoint | Backfilling
2a94436b-8a55-5c1e-bbf9-02ba5e0863cf | note | Acceptance Criteria and Frequency - Backfilling of trenches for conduits shall not commence until the conduit system has been inspected by the Administrator
45b03652-4d3a-5b83-8251-9304119f9827 | note | ○ Backfilling shall not commence until all the conformance and As Constructed survey requirements have been met as specified in Clause 11 and 12 of MRTS91, and notice of such works provided to the Administrator
0ecc313f-8082-5a71-bbfb-09de25961ff2 | note | Reference - MRTS 91 Clause 13.1
b186b632-1320-5b28-8764-cceeb3e053f9 | note | Item Check - Hold Point
66423c3b-9a28-472c-94fb-8151edb775ef | signoff | HOLD POINT
84fca69b-9559-4263-8a76-6880f82e8eab | checkpoint | Final Sign off and Approval - Conformance with the Specification
e66bda51-d60d-59dc-8dda-72d9a32c672f | textbox | Name of Cient's Representative
9b78bce6-3fef-5ae3-9ca9-9c3155009bd6 | date | Date
710c6514-94bf-5d41-a00f-46f441a6cde6 | textbox | Name of Contractor's Representative
79a01e51-3f73-5f08-b181-9095c5ac8976 | date | Date
c72bde2a-4a39-4e32-b6f8-6db295e18390 | signoff | Signature
70525dee-5350-41da-bc5a-be446435d6f6 | section | Final Sign Offs (to be completed at closure of Lot)
4e678367-2280-4c0d-beb8-b41fbd65bb6e | checkpoint | Closure of Lot
c11e58f3-0f09-4e7f-a75a-78db2923363b | signoff | Closure of Lot Sign Off
4a7eb5b2-1b9e-42fc-9751-421baa4ab5f1 | checklist | ITP - Contractor's Site Facilites | itp | ITP - Contractor's Site Facilites
4a24fcb8-a376-44a4-bc1f-b8bfeb06e1fd | section | Contractor's Site Facilites
c5a3c52e-3dca-4ad9-8490-47a530795cbc | checkpoint | General
481819e0-e889-50ed-90ff-19e06c743b4d | note | Acceptance Criteria and Frequency - The Contractor shall provide properly constructed toilets, drinking water, eating and washing facilities at the Contractor’s site facilities for the use of personnel and connect to town sewer where possible and shall comply with AS 1547 On-site domestic wastewater management.
4c54ad4d-8b84-5a0d-a062-966d33985f7d | note | Reference - MRTS 28 Clause 4.3 & MRTS 28 Clause 3, Clause 8
6971f177-9a10-5824-b5cf-50e71a0c881d | note | Item Check - Check and Verify
36e61bcc-93ac-44d5-aebd-5a3d25987696 | checkpoint | Site Security
a11a0a54-fee1-5e2e-94a6-142f75a78b3b | note | Acceptance Criteria and Frequency - The Contractor shall be responsible for the security of the buildings, construction plant and machinery.
a69efaf9-4304-54b6-87c2-22f3e8cf0025 | note | ○ The Contractor shall also take all necessary precautions to make the area safe to the public, including provision of signs outlining relevant project contact details, safety requirements and any other relevant details on the main entry gate.
0710d83d-644f-5823-a492-432648e268af | note | Reference - MRTS 28 Clause 4.3
1dc5c372-23dc-517f-962c-e0dbf9d50de5 | note | Item Check - Check and Verify
df300288-2762-47ff-bd4f-7e16254c01a2 | checkpoint | Visibility to the public
bc8742ef-b69e-5972-8162-f50f868294e4 | note | Acceptance Criteria and Frequency - External lights on the facilities and camps should be positioned or shielded to minimise light overflow onto neighbouring properties.
2b032233-9937-5acd-9acc-1f9a4d19d1a1 | note | Reference - MRTS 28 Clause 4.5.2
04847910-4407-56f6-b2c1-43d377f66497 | note | Item Check - Check and Verify
05f06fd6-d7b0-4e65-88d6-b73183061b24 | checkpoint | Noise
8c15a605-7283-597a-b8cc-d299a77098e0 | note | Acceptance Criteria and Frequency - Noise generated from the site facilities shall be kept to a minimum and the Contractor shall construct noise amelioration devices around the site facilities to bring the noise levels within specified criteria.
57e2e724-9271-52c1-b622-0d99ae10fe79 | note | Reference - MRTS 28 Clause 4.5.3
e7d90a2a-9587-5473-9bd7-da3d2f6cc081 | note | Item Check - Check and Verify
04e87243-57ed-494e-876e-0ac7ee2e5e61 | checkpoint | Dust Suppression
cbb28059-306f-5d81-912d-c78175e99271 | note | Acceptance Criteria and Frequency - Adequate precautions are taken to minimise dust or dust-related conditions during any activity which may affect the safety and general comfort of any person. Regular applications of water are applied to any roads or structures whilst completing earthworks
e8cd41bd-91c8-5213-873b-318f3f708e7d | note | Reference - MRTS 28 Clause 4.5.4
4a0364bf-b155-56d9-afea-3d0286513fb9 | note | Item Check - Check and Verify
608ae181-85b3-47b3-8d5f-723eb8fb3ee2 | checkpoint | Temporary road safety barriers
c700b1ee-cb28-501b-8715-75dc6bbb56cd | note | Acceptance Criteria and Frequency - Temporary Road Safety Barriers (TRSB) shall be used to contain and redirect errant vehicles so as to reduce the likelihood of them entering the work site
09808e3f-3720-5484-8ad4-2ef5be666562 | note | ○ Provision shall be made for TRSB At locations where work is to be close to traffic, and in accordance with Worker safety requirements in MUTCD Part 3;
2902710e-c91c-53a9-b67d-44a9f6e7e2fc | note | ○ Only those TRSB which are included in the Transport and Main Roads – Road Safety Barrier Systems, End Treatments and other related Road Safety Devices shall be used
4b79bcea-d414-5827-a66b-82c552e2d4f8 | note | ○ All TRSB and end treatments shall be installed in accordance with the department's Standard Drawings and/or the manufacturer's specifications
1e940c55-c0c9-55a0-b0a0-4c8299db6264 | note | Reference - MRTS02 Cl 6.5.11 & Annexure 2.1
a5736224-a613-53aa-bc97-833d822e8708 | note | Item Check - Check and Verify
3e389d38-c735-455a-844c-3ed2b1e58963 | checkpoint | Temporary line marking
2301a1f3-bc5a-50e2-9d81-2bea33921b44 | note | Acceptance Criteria and Frequency - Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
b06506ba-4cc7-5523-a22d-54701f0f1904 | note | Reference - LCC SS 10 Part 2.8.4
0314e44e-487b-5823-818a-bb6ea99774f0 | note | Item Check - Check and Verify
abde7b9c-5649-48f2-b1c0-180e1a5390a5 | checkpoint | Access
b8a46151-1810-50c2-ae32-4009a04462af | note | Acceptance Criteria and Frequency - The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
fa91f66a-4bf6-5464-88f6-c320ac0db922 | note | Reference - MRTS 28 Clause 4.5.6
d4b3caf2-49fe-5ee2-a73c-3773d750f4fb | note | Item Check - Check and Verify
f81245c4-8519-495b-a54d-3b3bd0664c10 | checkpoint | Final Sign off and Approval - Conformance with the Specification
9a367eed-5169-546a-b65e-38bd71ca7398 | textbox | Name of Cient's Representative
fbf8c67c-dcf3-5d26-8415-05e8c1be213f | date | Date
5969564f-4a6a-555b-92a5-e137546aa219 | textbox | Name of Contractor's Representative
d603a70c-6e25-544d-9617-7be1b5e5d327 | date | Date
aaf5683a-54ff-493b-b620-cae41eb49015 | signoff | Signature
132bf029-0f47-4d34-9310-301266e9de86 | section | Final Sign Offs (to be completed at closure of Lot)
ee4d0179-250c-472c-8971-140ce8d2acf4 | checkpoint | Closure of Lot
b9097b63-5259-47e7-aa0b-f70356c8aa80 | signoff | Closure of Lot Sign Off
c1bf6d23-279d-48f2-81ff-eca0c7b461af | checklist | ITP - Dense Grade Asphalt - Rev1 | itp | ITP - Dense Grade Asphalt
1340b2ef-652c-4961-bde7-7b90ba2f04b9 | section | Dense Grade Asphalt
7bfbfa6a-3b7c-4b6f-9f97-f3b1c0ebfe13 | checkpoint | Submission of Asphalt Quality Plan
cdaf703e-f4fd-5c32-85b0-94f96f225ae8 | note | Acceptance Criteria and Frequency - The Contractor must develop an Asphalt Quality Plan (AQP) for the asphalt work to the Administrator for consideration at least seven days prior to work commencing and must be implemented.
86f47269-9f4b-546e-8787-5a7d7271f715 | note | Reference - MRTS30 Cl 5.2
accbc5c2-26ca-5850-8d6c-3844d6c4b9b2 | note | Item Check - Milestone
232a2a1b-776b-444a-aca4-f46075cbf7c9 | checkpoint | Submission of Asphalt Quality Plan
3f7c6da7-2635-5a30-b91e-91f034636105 | note | Acceptance Criteria and Frequency - For dense graded asphalt, the tensile strength ratio (TSR) must be ≥ 80% when determined in accordance with ATM 232 and the average tensile strength of the freeze / thaw group must be:
c9a29adf-fa66-5946-ad72-8d859a04309f | note | a) ≥ 500 kPa for mixes containing SBS based polymer modified binder (e.g., A10E, A15E and A20E), and
ecc620d3-9fd1-55ca-aa4e-e9ba14ffe30c | note | b) ≥ 600 kPa for mixes containing all other binders.
df7d5afc-3ba4-5ecc-b90d-f2c3b18f8479 | note | Reference - MRTS 30 Cl 7.2.5
b5d3dc92-90fd-54b2-bde7-9e97b9eaf765 | note | Item Check - Hold Point
f776c086-36f2-409a-b60f-8e20c611011f | signoff | HOLD POINT
dff2c023-c14a-4e76-9d7f-a95728d8a685 | checkpoint | Nomination of registered mix designs
4f24552f-c23e-5b8d-9668-9b1d4f2bbdc5 | note | Acceptance Criteria and Frequency - At least seven days before asphalt is to be incorporated into the Works, the Contractor shall submit to the Administrator a copy of the mix design certificate(s) for each nominal size and type of asphalt mix to be incorporated into the Works.
f814dc11-4667-586d-b792-1445d7269232 | note | Reference - MRTS30 Cl 7.3.3
b26f6eea-13e0-50a0-913b-3d3283755d89 | note | Item Check - Milestone
86808759-1e74-4739-9583-d294a508f398 | checkpoint | Asphalt Mix Properties
b6810e00-1d24-5183-8d30-b3de51d61cb7 | note | Acceptance Criteria and Frequency - The properties of asphalt mix must comply with Table 2.6.1 - Asphalt mix properties of LCC spec No. 13 Part 2.6.1 when tested in accordance with column 3, asphalt shall aslo comply with MRTS 30.
ba2a2c5e-64f9-5691-ac24-40700b86c19d | note | Reference - LCC SS 13 Part 2.6 & MRTS 30
3597da63-27d0-5f6d-99a8-6cd6239b59cb | note | Item Check - Check and Verify
ec84a1e6-0fae-4c68-b7fa-1219842050fd | checkpoint | General
ac08c297-c538-5119-90ad-e15a78f6dfe8 | note | Acceptance Criteria and Frequency - All asphalt shall be placed in accordance with design drawings and as per drawings GW001 & LS001
aac28447-ca46-5e8f-aef6-a46f55b942c4 | note | Reference - General
28580898-190f-537a-a190-6d2cb6de7b87 | note | Item Check - Ckeck and Verify
34128b95-6dee-4a32-bd0e-dd13098cb88e | checkpoint | Production of Asphalt
77a3208f-fc63-5ab1-8d5f-aaed85916c2c | note | Acceptance Criteria and Frequency - Asphalt shall be produced by a registered asphalt manufacturer from the nominated asphalt plant in accordance with the nominated mix design for the Works. Asphalt shall not be incorporated into the Works until the Contractor has demonstrated to the Administrator that the underlying lots conform to the specified requirements
94a2fb3d-45c7-590e-8b19-3dacbf24c251 | note | Reference - MRTS30 Cl 7.4.1
7ef20bcd-617a-5061-8c59-a1c2daafe424 | note | Item Check - Hold Point 2
76f7f314-4b10-4903-a71b-d27546da336b | signoff | HOLD POINT
c5093155-2afe-4ac6-9ab9-67f503c47344 | checkpoint | Production of Asphalt
852146e7-5554-56dd-934f-bb73e61b216d | note | Acceptance Criteria and Frequency - For asphalt placed over pavement constructed by others, the surface on which asphalt will be placed shall be tested for perceptible surface deformation by ‘proof rolling’ in the presence of the Administrator.
bcc77259-9b04-56d2-82a2-0abf50498443 | note | Reference - MRTS30 Cl 8.2.2
23253f38-6892-5d64-adfb-09531b88b6ee | note | Item Check - Witness Point 1
8b8b36c8-9461-4619-982a-93014812983d | checkpoint | Preparation
e864dedc-396f-5671-bc80-44941e5b7cfa | note | Acceptance Criteria and Frequency - Unless otherwise approved by the Administrator, asphalt shall not be placed over pavement exhibiting significant perceptible surface deformation.
10a081b5-1703-5cd3-a811-7324fc71798c | note | Reference - MRTS30 Cl 8.2.2
ff912142-d7fe-5cdc-8ac4-87a61af60455 | note | Item Check - Hold Point 4
2315ddb5-2812-430a-87a1-30ae1550e876 | signoff | HOLD POINT
ec28ac07-896a-47fc-bae8-8cd1a2588110 | checkpoint | Preparation of pavement
4bda2a29-6584-5527-8818-01ec438a5f8c | note | Acceptance Criteria and Frequency - Existing substrate shall not be wet and shall be swept thouroughly to remove and loose or deleterious material
8452231b-912b-5b75-b56f-2f32ba9ef434 | note | Reference - MRTS30 Cl 8.2.2
6387315c-ec78-565c-86e6-b934c471eb83 | note | Item Check - Check and Verify
24eb727e-71e3-4e14-9f0b-8b7a9ab44e84 | checkpoint | Application of Asphalt - Temperature
9db7f562-7474-5e9d-95c4-fabfa285b3b6 | note | Acceptance Criteria and Frequency - The asphalt mix temperature is controlled so that it is between 135C and 175C when loaded into the delivery truck, the mix temperature is between 110C and 165C immediately behind the paver with compaction commencing before the temperature of the mix falls below a minimum of 95C.
a87cdbaf-dc57-54bf-a739-fed83c8bbc64 | note | Reference - LCC SS 13 Part 3.1.1&2
49302707-51b0-56cd-8303-dc8ffc93a0d7 | note | Item Check - Check and Verify
412aabde-6833-4b24-ae81-c23abe2eb69f | checkpoint | Asphalt Compaction
d62ba957-755d-5745-8774-b2865a860aa3 | note | Acceptance Criteria and Frequency - Compaction is commenced as soon as possible after spreading, and is completed in the shortest possible time except in the event of significant deformation or an irregularity occurring under the action of the roller in which case, rolling is delayed
51178f8d-4055-5de8-8a71-ee4ee1c4c2ee | note | ○ For compaction testing, a lot is the same as for a production lot and compaction testing is undertaken in accordance with Q302A, Q302B, Q306B and Q314.
e96cc620-3799-55cb-a4a9-de772854ebde | note | ○ After completion of each job, core samples are taken from the compacted asphalt at the rate of one core per 1000m2 of asphalt laid, but with a minimum of three cores per job, asphalt compaction shall be greater than 95%
ca15c10a-0268-533a-b636-24328b238529 | note | Reference - LCC SS 13 Part 3.4 & 3.5
79084078-0f82-5bf2-8037-a8b790ee9aee | note | Item Check - Hold Point
8b8b2b8c-920a-4915-8f92-17500c35e3cc | signoff | HOLD POINT
98911e25-53f8-4458-ada0-92301a3005d7 | checkpoint | Final Sign off and Approval - Conformance with the Specification
896cdd71-5b24-577d-b3aa-978e528b79c6 | textbox | Name of Cient's Representative
687226e5-a7d7-5f21-86ed-8dd5507eaf95 | date | Date
76b35c58-23bf-5cfe-b568-f88ee4f6d0ef | textbox | Name of Contractor's Representative
1d1ec42a-c5a3-5ac4-8ec0-311d5cf6bb12 | date | Date
46fe451d-0199-42d1-92de-ff97ed61951e | signoff | Signature
2b71cc11-6386-40ec-9925-b19b5ba717de | section | Final Sign Offs (to be completed at closure of Lot)
d80a01da-d1c5-4bdf-a4dd-5674e1ac695f | checkpoint | Closure of Lot
3b106906-a214-4c1b-b003-099eb59dd8be | signoff | Closure of Lot Sign Off
2a91ea37-7e7e-4c39-a455-bf355806e9c1 | checklist | ITP - Environmental Management Systems | itp | ITP - Environmental Management Systems
14bf52e4-97f5-4575-b53e-3e43f96381ea | section | Environmental Management Systems
a2ee131f-de70-4394-b72b-07bd05968178 | checkpoint | Environmental Inspection
227a7810-b7e2-56f4-a455-c89fbff65d61 | note | Acceptance Criteria and Frequency - Enviromental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements all Inspection to be documented in donesafe. The Contractor’s Environmental Representative shall undertake and document Weekly Site Inspections.
51b6f269-ba78-5fbe-b4b5-b90eb874111d | note | Reference - Internal
ee1095b7-3ddb-52dd-bf15-386b4faf5b69 | note | Item Check - Check and Verify
b68e6229-4868-4501-876b-a5eca76ecc6b | checkpoint | Management Plan
a4df2792-75e2-5dce-8716-94d22b4f510e | note | Acceptance Criteria and Frequency - Environmental Management Plan (Construction) submitted in accordance with Conditions of Contract.
7626ef77-c27d-503a-b0ea-35bffad2cde3 | note | Reference - MRTS51 Cl 6.3
e3ee9990-9a40-576f-a7ce-86fd61d805f0 | note | Item Check - Hold Point 1
5ffe688e-c6a7-4e33-8931-091ad3c034da | signoff | HOLD POINT
a6fecea1-5455-41a9-a185-a86dda25519f | checkpoint | Approval Environmental Management Plan
dceab9c4-0a9c-5f10-b908-912d05538b45 | note | Acceptance Criteria and Frequency - Works shall not commence until the Environmental Management Plan (Construction) has been assessed for suitability by the Administrator and approved.
b105e31e-7cc6-5402-b8a4-acbd9f855da8 | note | Reference - MRTS51 Cl 6.3
23f4bf9a-8102-5dbf-9b56-61454d5e31a2 | note | Item Check - Check and Verify
a9e6dc02-d6a1-45ac-ae52-a81d33a40f74 | checkpoint | Amendments
6b707525-93cc-5232-93aa-c57e699c3091 | note | Acceptance Criteria and Frequency - Amendments to the Environmental Management Plan (Construction) to be submitted on a monthly bases for assessment of suitability by the Administrator.
667398c6-c347-598b-ad89-22f4da01d03f | note | Reference - MRTS51 Cl 6.4
f9606c07-cfca-5e6b-9130-0d1fe366286d | note | Item Check - Hold Point 2
913cce82-6225-4be4-9aba-e941ff2d79e0 | signoff | HOLD POINT
24be4d1f-7d63-43b5-85b8-27bcd6c0dc38 | checkpoint | Noise Monitoring
02a756fa-ed10-51db-af2c-d0b7b95db8d5 | note | Acceptance Criteria and Frequency - Noise monitoring shall be undertaken as per the contract specifications
87cf794b-fbe4-5a80-8128-91ed1e3513a6 | note | Reference - Internal
c0804000-ac2e-5570-b8b3-7cdd5cd6987f | note | Item Check - Check and Verify
cbb8a5aa-813f-4da8-bf22-7869c6267061 | checkpoint | Water quality
66126643-a9b7-5e5c-94b9-01c9bd7c821c | note | Acceptance Criteria and Frequency - Water quality monitoring undertaken as per requirements in MRTS52 and otherwise specified in contract
c84c4d04-c580-5fbc-9114-f403aa47a753 | note | Reference - MRTS51 Cl 8.2
40756f9d-c9cb-565b-8a76-2d925d786a60 | note | Item Check - Check and Verify
9c210669-65f6-4134-89f1-b4d09147e4a5 | checkpoint | Erosion and Sediment Control
339b9789-438e-5d67-825f-f9940e92dfb5 | note | Acceptance Criteria and Frequency - Requirements relating to Erosion and Sediment Control are contained within MRTS52
d5918a03-b9e5-5802-9584-924677ce639a | note | Reference - MRTS51 Cl 8.3
032c504c-0d42-551d-b1cc-31c4a25a28d2 | note | Item Check - Check and Verify
e92edb9e-be5a-42fb-bc25-d745b3b76291 | checkpoint | Areas of cultural significance
435a23ae-e84d-53de-bc06-b715e1a58833 | note | Acceptance Criteria and Frequency - Areas of cultural significance have been identified and are managed as per Clause 3 of Annexure MRTS51.1.
22dd63ee-fbe2-5ce3-bbe0-6dd504b919f3 | note | Reference - MRTS51.1 Cl 2.2
c969b93b-958d-5f13-b388-c0f86ef79991 | note | Item Check - Check and Verify
69572d8b-0130-405c-8dde-818955de6c7e | checkpoint | Dilapidation Report
24a012d0-cdab-5a7d-9453-079176dc8183 | note | Acceptance Criteria and Frequency - A copy of the condition/dilapidation survey for vibration has been given to the Administrator before any works that cause vibration start (5 days) - Condition surveys to be undertaken at the Locations listed in Cl 5.5 of the annexure
1e8fb9b8-28e4-54c9-90a9-475e4928f94c | note | Reference - MRTS51 Cl Clause 8.6.2.3
39fb74e7-a6b6-5e63-9872-ac5ab94fcdf8 | note | Item Check - Check and Verify
7b6e9419-895a-4322-b1be-27cbbf432dc9 | checkpoint | Air Quality
bcf8ea74-e964-5a51-aae9-3c9f74d530ab | note | Acceptance Criteria and Frequency - Construction activities have not resulted in air quality impacts that cause environmental nuisance or harm. Burning material not permitted on site
9f69be3a-3ec2-5229-950e-c7ee9ee448e2 | note | Reference - MRTS51 Cl Clause 8.7.3
f4930e07-f3d4-53ab-9ca6-d0d03e71bb81 | note | Item Check - Check and Verify
053fd544-27a9-41c3-9051-08e6ef0627d6 | checkpoint | Acid Sulphate Soil
ba515ed2-d6e0-5683-88d1-99b0ce2e0f68 | note | Acceptance Criteria and Frequency - Acid Sulphate Soils have been managed as per the requirements of MRTS04
d9db009d-a9c7-5e58-b750-72b1743448e7 | note | Reference - MRTS51 Cl 8.8
611ed662-d1d0-5932-8c5a-925858f2769e | note | Item Check - Check and Verify
c891e45c-daa6-4d07-84b4-fae1c81561b9 | checkpoint | Contaminated sites
bf758b39-5ed8-5ff3-95ad-0e98e45d203e | note | Acceptance Criteria and Frequency - Contaminated sites (contaminated soils, waste dumps, unexploded ordinances ) within the worksite have been addressed as per requirements of MRTS04.
12b3850a-434b-5608-840d-cdac318f0994 | note | Reference - MRTS51 Cl 8.9.5
50c7ceaa-5669-5b4c-9ff7-ab4d386d53f9 | note | Item Check - Check and Verify
cd093383-bd86-4b72-a59e-153fc40bf6e3 | checkpoint | Fauna
c146bd0e-e46e-52c9-81b1-4f47636682fa | note | Acceptance Criteria and Frequency - No harm caused to native fauna. Areas of significance and related management requirements are stated in contract. Contact details for emergency wildlife care shall be included on project emergency contact list.
4bf90a89-31d3-5021-aa30-c7ac73d94a11 | note | Reference - MRTS51 Cl 8.10.1
cde064c8-b89a-5aaa-b25f-0b84c258fcaf | note | Item Check - Check and Verify
727fbb49-138c-4c4b-ac27-5d47aad9d590 | checkpoint | Vegitation
05b50347-7586-536f-95ee-39b50d1e42f4 | note | Acceptance Criteria and Frequency - Management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
73bbcb17-80cd-58c8-8443-c5985d5f839c | note | Reference - MRTS51 Cl 8.11.1
c276a6ba-654e-5e80-bfa1-61a97a73884a | note | Item Check - Check and Verify
b61713c9-fe7c-4aed-abb1-d73358606cbe | checkpoint | Pest Management
185a8202-a3c2-5ceb-b53c-cb4fdb5fbc0c | note | Acceptance Criteria and Frequency - All declared pest known to occur within the worksite and any associated management requirements are stated in the contract have been managed and prevented from spreading on and off site
142d6edd-57af-54e9-b212-485b164c5df2 | note | Reference - MRTS51 Cl8.12.2
fbd5f6b6-354a-5303-854a-2809893150d2 | note | Item Check - Check and Verify
02859bb6-9b4e-4dfd-bdae-632940638888 | checkpoint | Chemicals & Fulels
cb3368b0-da4b-5caf-a31e-ec89d9f0f229 | note | Acceptance Criteria and Frequency - All chemicals and fuels within the worksite are contained so as not to cause environmental nuisance or harm.
07b7fa7a-dee4-5409-b6c2-71d0dba46e62 | note | ○ Spill kits response equipment are available on site for use in emergency
0fb12c24-07cc-5693-b777-ffc3cc9fa93f | note | Reference - MRTS51 8.14.3
1b000230-ca0a-55b0-b418-ddd75812b4af | note | Item Check - Check and Verify
5ab9aa91-dbcb-44f7-a57e-1dc7b8a5dda9 | checkpoint | Final Sign off and Approval - Conformance with the Specification
f197d31f-c2ae-5634-8d89-962c3bcde8bc | textbox | Name of Cient's Representative
512c37c3-0c7c-5575-9d4c-557e2a2518fc | date | Date
185d4106-a46d-5340-9b1c-345b8603be95 | textbox | Name of Contractor's Representative
c41abceb-282d-57d7-a61f-486c4cb6800a | date | Date
20283edc-9ced-420e-a6ef-818e3aeb48ec | signoff | Signature
3ceced24-9c1d-445b-9484-ba90632e0630 | section | Final Sign Offs (to be completed at closure of Lot)
9c23e5f9-a8df-4c95-86a6-f2a385c44e37 | checkpoint | Closure of Lot
282cc7f3-3b9b-41f3-8997-4d2e146ec215 | signoff | Closure of Lot Sign Off
f3b1c754-85f6-4157-a98f-73a42eaff7ec | checklist | ITP - General Excavation - Rev1 | itp | ITP - General Excavation
2892542e-69fd-45fb-92a4-c537ea0d6ead | section | General Excavation
8379e25e-74c0-489d-9278-e8caa5bea4c1 | checkpoint | Lot Boundries
cf6efc64-37dd-576a-9191-4a7d839446dc | note | Acceptance Criteria and Frequency - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
70b044ee-b31a-5ea1-b696-e8e5101a7410 | note | Reference - General
77ee455d-1ad0-5a5b-b092-68679728aa61 | note | Item Check - Check and Verify
4f1e56a9-749f-4092-962b-c52cef720912 | checkpoint | Services:
fe19f851-56c1-5eca-80de-03c4820a105f | note | Acceptance Criteria and Frequency - All services identified – shall be marked, potholed and/or protected as required
fef1f3be-681d-5bfb-8953-6968822cb88c | note | ○ Permit to excavate issued by Project Engineer
d7334c5d-ea60-5c3c-92e3-cda2a6fa7320 | note | Reference - DBYD
89e59b21-1eab-5eb4-945b-b439ec1badd2 | note | Item Check - Check and Verify
7f46f2a4-1a0c-47ae-a0a0-9b8b193f50c2 | checkpoint | Testing Frequencies
68360ed2-8c89-5de8-8baa-be215598f7a1 | note | Acceptance Criteria and Frequency - The minimum testing frequencies shall be as stated in Tables A.1 and A.2 of Appendix A.
0c8d6575-502e-5c5d-a2ff-8a81eb27917d | note | Reference - MRTS04 Clause 5.6
67dbd82c-97cf-583f-ae0c-b1e187c6a6fa | note | Item Check - Check and Verify
d34e6100-8c27-4b96-9917-b563a63d3e5a | checkpoint | Erosion Sediment Control
671713a4-7308-5bc0-951a-45f3976ca04b | note | Acceptance Criteria and Frequency - Erosion and sediment controls in place
82cfd33c-0e89-5931-9393-f0e2973d1717 | note | ○ Due care taken to ensure native fauna is not harmed
964d4250-5486-5614-abc4-67108d9f665a | note | ○ Vibration and Air quality to be monitored as a direct result of construction activities
782ab8ea-bb06-5f5b-9af4-855b060703a0 | note | Reference - MRTS51 Cl 10.3
a1a83ba3-b26c-5114-8397-5756ddb74620 | note | Item Check - Check and Verify
93087127-518f-4d55-8c4b-3ea64602a448 | checkpoint | Excavation Cutting
74f6472b-a169-5300-a053-920a9a2a7398 | note | Acceptance Criteria and Frequency - The bottom of excavations shall be trimmed to the tolerances specified in Clause 6 and any loose material removed from the surface.
59e1ab03-ec2f-5375-a8d5-33d33e752067 | note | ○ The existing soil is compacted to 95 percent relative dry density standard compaction, for a depth of 300mm below the sub-grade and care is taken to ensure that the topsoil and organic material is removed and replaced with approved selected material for a depth of 500mm and compacted to 95 percent relative dry density standard compaction where the sub-grade passes through the natural surfaceat the ends of the excavation or anywhere in cross-section.
eb3678c7-b0ce-5fd1-bec6-9d7e8d0a74f6 | note | Reference - LCC SS No.1 Part 9.1
d08609c6-ab9d-5649-9ce4-6550c23c98e3 | note | Item Check - Check and Verify
c0793aee-e335-4bf1-a307-f344c68501bf | checkpoint | Unsuitable Material in Excavtion
124a23d5-3006-50f5-ac7f-b6e43804523a | note | Acceptance Criteria and Frequency - Unsuitable material below the level of the sub-grade in an excavation is:
13b4fec8-ba26-543b-a4a8-08c490412ff0 | note | (a) removed and run to spoil in accordance with section 12.1 of Specification 1,or replaced with select backfill in accordance with section 8.3–Selected gravel fill or selected backfill of this standard specification;
c8f57375-3134-5f8a-aff8-4d83b8f068a5 | note | (b) compacted to 95 percent relative dry density standard compaction
77ea9c61-1621-5f7f-9928-1c78fa2b9dc6 | note | Reference - LCC SS No.1 Part 9.3
3d063b14-3b71-51cc-9688-70fdd01c65ca | note | Item Check - Check and Verify
e972a7c2-9716-4153-98b8-754aac90599b | checkpoint | Unsuitable Material Below Lines of Cuttings
2f8c9cb7-e9fe-5db7-83d3-06cc2bf0f91c | note | Acceptance Criteria and Frequency - Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4.
16d6f513-4771-5fa9-8a32-9de675e61e8f | note | ○ Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate fill material as specified on the drawings or in accordance with Clause 18 and 19.
2cd1f027-bf5b-562c-be26-2ac0c67400e6 | note | Reference - MRTS04 Clause 13.3.2.2
bd1306e9-f284-5227-956d-b3bd5f5a8840 | note | Item Check - Check and Verify
f7d2b245-7cda-4146-81df-0a4a394b5b90 | checkpoint | Finished Cut Surface Survey
861f7f35-28dc-59a5-9613-5bad03e77371 | note | Acceptance Criteria and Frequency - Once Works are completed to Subgrade Level (including all Subgrade treatments), an As Constructed Survey of the bottom of the excavated area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
348577e8-dfa8-5024-872a-0d766b7e0713 | note | Reference - MRTS04 Clause 13.3.2.1
2c0ed882-b9fb-59f3-a120-769bd4c094e6 | note | Item Check - Check and Verify
cdf09901-03b8-41fc-88cc-4c578a5d08ae | checkpoint | Lot Acceptance
d8cddd4c-279e-5906-9945-1dab0a3ca568 | note | Acceptance Criteria and Frequency - Lot closure requires all relevant information to be attached to the Conformance Report this includes a Lot Plan, Survey Report, Hold Points/Approvals & any supporting documentation
a4d11478-96b0-5755-879b-e05c6b39e6e8 | note | Item Check - Check and Verify
7f6dbd34-a5ff-4ff3-8935-a7b5e416d389 | checkpoint | Final Sign off and Approval - Conformance with the Specification
ac494123-09b8-58cb-8d32-8c59a74061c9 | textbox | Name of Cient's Representative
cf7c9efb-1b55-581e-bc39-f2b867d082c2 | date | Date
f0d4cf47-5168-5955-9af7-2dc73753e1f7 | textbox | Name of Contractor's Representative
eef06bfc-ab64-5824-b609-f684fdf1a983 | date | Date
51ae1ed5-e5bf-42c0-98f3-bb0fa9914552 | signoff | Signature
cd09e5cc-5b0a-4a4f-9cb7-76fdbeefac68 | section | Final Sign Offs (to be completed at closure of Lot)
3c191d8e-fc52-404e-b7ac-a915d3420a2a | checkpoint | Closure of Lot
551b5bfc-11ee-4325-ace7-18c88f63a1d1 | signoff | Closure of Lot Sign Off
a74a3e8e-b503-47b5-bfd6-464b753f0ec2 | checklist | ITP - Geotextiles for paving applications - Rev1 | itp | ITP - Geotextiles for paving applications
d3eb40b2-9d73-4004-a1c3-995dc8d02041 | section | Geotextiles for paving applications
0b775983-2fe0-47fc-878f-9c2c1a9562d4 | checkpoint | Geotextile Filtration & Strength Class
3cb3e574-1461-5c83-964c-3794fecf7211 | note | Acceptance Criteria and Frequency - Geotextile to be used as specified in approved drawings
50618b82-9711-54a2-b5e6-aef174c002a0 | note | Reference - Drawing Notes
1c7107da-6e97-50cf-abdc-312281a38dbe | note | Item Check - Check and Verify
554c4f80-253b-45f0-b258-559fa9f1afe2 | checkpoint | Storage, packaging and identification on site
9289e40f-711a-5b39-9dfb-badd45c14df9 | note | Acceptance Criteria and Frequency - Geotextiles shall be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation.
381418bb-6088-5458-ab1d-0eb6eb4fab8f | note | ○ Geotextiles shall not be stored directly on the ground or in any manner in which they may be affected by heat. The method of storage shall be in accordance with any other recommendations set by the manufacturer.
5d3cac75-914f-595d-8ae3-95f2726e03ed | note | ○ The protected geotextile rolls shall be clearly labelled showing manufacturer, type of geotextile and batch number identification number
e0d90530-8c61-5be8-aa76-84cd4d4a171b | note | Reference - MRTS27 Clause 7
c7b6975f-c9ee-51e0-a392-ca7b3288f639 | note | Item Check - Check and Verify
c05c27d6-97b7-432c-b959-ff43af7d614f | checkpoint | Geotextile Construction Procedure
73d6f6b2-35fa-5343-a4c8-cad7ce4b02ab | note | Acceptance Criteria and Frequency - A construction procedure detailing all work described in this Technical Specification shall be prepared. The construction procedure shall be consistent with the guidelines set out in the Transport and Main Road’s Pavement Rehabilitation Manual April 2012, Sections 4.4.6 to 4.4.6.8.
0d1daee4-4cf5-5d6e-9f48-fb93461339bd | note | ○ The proposed construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of any works related to the placement of paving geotextile(s)
57617689-0685-592a-8cc7-edf6a72cce16 | note | Reference - MRTS57 Clause 5.2
a98df849-0970-5d86-b57a-2df3d9e648f1 | note | Item Check - Milestone
aaf4c814-065f-475d-b62c-3dd3de048801 | checkpoint | Approval of construction Procedure
26508fe6-95eb-5771-bb47-72052b37da82 | note | Acceptance Criteria and Frequency - No works related to the placement of paving geotextile(s) shall commence until the construction procedures have been approved by the Administrator and the Administrator has given the Contractor permission to proceed.
90115d92-848c-538c-bf42-0f9f42900b96 | note | Reference - MRTS57 Clause 5.2
07d6a995-0881-5f91-9432-695d525caeb3 | note | Item Check - Hold Point 1
51000204-232e-40aa-a240-b9b12a8d8b7f | signoff | HOLD POINT
8977221a-527f-478e-8217-613664981a57 | checkpoint | Ordering - Technical Data
c7efa944-a4a1-507f-bec7-babac399df13 | note | Acceptance Criteria and Frequency - At least 14 days prior to the proposed ordering date of any geotextile, the Contractor shall submit to the Administrator a copy of the proposed manufacturer’s technical data sheet and a sample of the proposed geotextile from the manufacturer demonstrating compliance with this Technical Specification
9d8d8c85-830a-5963-9beb-dae9258d3ff2 | note | Reference - MRTS57 Cl 8.2
4ca904ce-f43e-546e-8fcd-830a7eeb2ce5 | note | Item Check - Milestone
182f5adc-b6cb-44a4-b697-a667d90a12ff | checkpoint | Ordering
b1b10230-21a1-5dfc-914e-c44b08baa6a8 | note | Acceptance Criteria and Frequency - The Contractor shall not order any geotextile prior to the acceptance of that geotextile by the Administrator.
0ea73930-c20b-59fb-9f05-41c57337f807 | note | Reference - MRTS57 Cl 8.2
a0e2ed6e-8b9c-5cbb-9266-0c16401ed12a | note | Item Check - Hold Point 2
4c4c87d1-d191-4964-8813-c145c7b84f00 | signoff | HOLD POINT
7a6509b4-9cbb-495e-8f4b-2a08d64b62d1 | checkpoint | Delivery
25ff7904-cd7f-5d99-8d58-45bd8d5878a1 | note | Acceptance Criteria and Frequency - With each batch of geotextile incorporated in the Works, a certificate of compliance stating that the geotextile complies with all the requirements of this Technical Specification as appropriate to the application, together with test results reported on NATA endorsed test documents, shall be included in the Quality Records
40ea8ecd-59f0-5c04-bd20-c221e1c9cf1d | note | Reference - MRTS57 Cl 8.4
39ef91e7-6119-5495-8a93-e7159f967a34 | note | Item Check - Check and Verify
9b07eea2-a6b3-48ea-ad5c-7f3230e59416 | checkpoint | Surface Temperature
a4bcfc8b-06b8-5f4c-8b85-428b361b640f | note | Acceptance Criteria and Frequency - Spraying of bitumen or placement of geotextile shall not commence until the temperature of the surface of the pavement is above the temperature specified in MRTS11 Sprayed Bituminous Surfacing
e6cec66d-9be0-54bf-92ff-032b7a02c328 | note | Reference - MRTS57 Cl 9.3
454932d5-5155-5780-9285-47a73ac1b540 | note | Item Check - Witness Point
bb380b40-2390-471a-a7f6-facf3322960d | checkpoint | Final Sign off and Approval - Conformance with the Specification
010d678f-50dc-5dc9-9e60-73ac9308f0e8 | textbox | Name of Cient's Representative
83b44fb4-8d59-5305-a14c-df6d6abcb241 | date | Date
515d1042-6441-556c-88b0-dfe438e54d36 | textbox | Name of Contractor's Representative
b69d525f-cf65-5815-9adf-557cf970d09d | date | Date
2a96c334-5cac-419c-be55-b7dbbc4cd586 | signoff | Signature
0e4ceeda-fb1b-494e-81ac-cd8df1c2e166 | section | Final Sign Offs (to be completed at closure of Lot)
2415199c-7021-4a2b-8ad9-36a2cef4f9f2 | checkpoint | Closure of Lot
41f83979-849d-42fb-9134-70cc6cf0e1ad | signoff | Closure of Lot Sign Off
704a64ee-55ed-47a1-b419-aa4d2153b57b | checklist | ITP - Hand Placed Concrete - Rev1 | itp | ITP - Hand Placed Concrete
fc87b703-144b-4b4b-8131-868ac66f31d5 | section | Hand Placed Concrete
40351798-57d2-41c3-9645-9727ef4d9dcc | checkpoint | Design location
2043ed91-3fcb-58f9-8359-388af080b147 | note | Acceptance Criteria and Frequency - All concrete works are to be installed in location and noted on a lot map attached to this document and accordance with the specified drawings:
8e984588-4183-589b-954f-17b49696519e | textbox | Specified Drawing:
840ac1de-38bd-5aef-be80-766282bafec3 | note | Reference - IFC Design Drawings
88540946-582b-58e2-94f4-f61900d34454 | note | Item Check - Check and Verify
d9998c20-ca99-46ba-a846-3239a22e7fd7 | checkpoint | Concrete Mix Design Submission
7c326a14-a567-55cf-a2a6-ac7d36235dff | note | Acceptance Criteria and Frequency - All mix designs shall be submitted to the administrator prior to works beginning if insufficient testing history is available for the specified mix from an approved supplier, preliminary mixes for all grades of concrete are designed, made and tested.
fe834b56-2b43-5fe9-8b42-3e4598c989ae | note | Reference - LCC SS No. 7 Part 2.3
09474e64-2031-52ab-845a-27fe38d91277 | note | Item Check - Milestone
8b1a89b8-b3c9-4f0d-83ac-96270d76452e | checkpoint | Concrete Mix Design Approval
da4e8fe8-9200-5272-9d20-e0d7cf86e597 | note | Acceptance Criteria and Frequency - Concrete Mix designs are approved prior to the usage in any works.
8b69ff13-12d5-594d-9619-415853cb8b1d | note | Reference - LCC SS No. 7 Part 2
b21a8cfd-a429-5ecf-9bd8-d452c7fd1fbd | note | Item Check - Hold Point
1e00e4e2-081d-4bf9-9bab-f2dfa26d40ed | signoff | HOLD POINT
3dfd57eb-eee9-436e-bd4b-944d68bca895 | checkpoint | Concrete Mix Design Approval
337c15f7-dd73-5111-a966-a1c99537fd18 | note | Acceptance Criteria and Frequency - Where the bottom of an excavation is free of rock or a rock bar the existing soil is compacted to 95 percent relative dry density standard compaction, for a depth of 300mm below the sub-grade
76295e41-baa8-5141-91f7-7cfb20663b91 | note | Reference - LCC SS No. 1 Part 9.1.1
8be4bc48-792c-56c6-8201-d32d7b861827 | note | Item Check - Check and Verify
704d8f51-ded8-441a-92ac-b90feee80c3f | checkpoint | Formwork Approval
9221c04a-6151-58b6-8420-909cf1cccb64 | note | Acceptance Criteria and Frequency - All steel reinforcement that will be used in concrete works shall be inspected and approved by the local government prior to the placement of concrete, all formwork shall be inspected and checked against formwork checklist. When forms appear to be unsatisfactory in any way, either before or during the placing of concrete, the work does not proceed until the defects have been corrected to the approval of the local government.
9eb78f71-867d-5979-89bf-c24a2e4c9443 | note | Reference - LCC SS No. 7 Part 5.3.11
24d8622c-e35e-5c74-b370-3d18055523b2 | note | Item Check - Hold Point
79a537a1-c35e-4896-89df-89319f425a54 | signoff | HOLD POINT
1012d201-3d45-4586-9362-57d2a79e4467 | checkpoint | Footpath Contraction Joint
02806d66-d4af-5cba-928b-0e81deb81f1b | note | Acceptance Criteria and Frequency - Contraction joints:
635128d4-aa04-5ae1-ba58-82af2c043fd2 | note | (a) are provided at centres matching the width of the footpath and not more than 3.0 metres;
0cfc1cfe-441f-54b8-a19d-ede6587378ff | note | (b) are formed by a jointing tool;
5f64912c-72f9-50d7-8b14-220e14afffcb | note | (c) do not exceed 35mm in depth or 6mm in width;
b352d687-190a-5d36-a89f-58f787c12bd4 | note | (d) are at right angles to the edge of the path.
d3750bbb-dafd-5427-8be9-845c3178fdf8 | note | Reference - LCC SS No. 8 Part 3.1.4
9d1e442c-9266-5a0c-b71b-9438659524a8 | note | Item Check - Check and Verify
2e2da9f6-c37a-497a-8d6d-247bdeb1141d | checkpoint | Footpath Expansion Joint
678aa56b-7fe2-5ed3-8163-91d31cf0d4c6 | note | Acceptance Criteria and Frequency - Expansion joints:
b2b52dd3-38fb-53fa-9cad-cc855e621aaa | note | (a) are placed at 15 metre centres except for 2.0m footpath which can be 16m to match dimension multiplier;
b39e3136-d25d-5163-9bde-7bb480953cb2 | note | (b) are at right angles to the edge of the path;
a5e9d489-8ce8-5c97-8672-5f9a37e7caed | note | (c) extend for the full depth of the concrete path and are 10mm in width.
f1785f08-ab2c-5de5-a890-6cf8d14419f1 | note | ○ All expansion joints shall be as per LCC specifcations or where specified in standard darwings.
8dd9adc7-e43e-52df-adc1-6d701f746241 | note | Reference - LCC SS No. 8 Part 3.1.5
5b25cbff-307a-5e1a-bb61-739d9a159766 | note | Item Check - Check and Verify
78d22673-e9b8-43fb-a89b-fa87d1f77e49 | checkpoint | Slump & Testing
5a6c7ef5-f0d3-5b27-be05-7d424afeb4fe | note | Acceptance Criteria and Frequency - All concrete poured on site shall be slump tested by a NATA certified testing contractor, all slump testing values shall be recorded by a pour record sheet and provided to the administrator with the submission of the lot. All slump values shall comply with table 2.4.1 under Standard Specification 7. All concrete shall be tested for strength, concrete is sampled and tested in accordance with AS 1012.1-1993 Methods of testing concrete - Sampling of fresh concrete, by an approved NATA registered laboratory and the results are provided to the local government.
6928adf0-50a3-5af6-9765-6c1cbbed08b5 | note | Reference - LCC SS No. 7 Part 2.4
609dae68-3ee7-585c-88f4-c401c5f22d7d | note | Item Check - Check and Verify
913e9778-8ec4-47f1-8d20-942ef8ee1ca5 | checkpoint | Temperature and Timing
3a90c25f-5e76-5986-a17b-8649db763fc7 | note | Acceptance Criteria and Frequency - Where the ambient temperature is likely to exceed 30°C, all practical precautions are taken to maintain the concrete at a temperature not exceeding 30°C at the time of placing to prevent shrinkage, settlement and presetting cracks. No concrete with a temperature higher than 30°C is placed unless otherwise approved by the local government.
9dbb79e9-38b2-50eb-93ad-f8cf4e73b855 | note | ○ Ready mixed concrete is placed and compacted within 1 hour 15 minutes of charging the mixer for concrete temperatures up to 30°C and within 30 minutes of charging the mixer.
661f4b66-8386-5360-a069-ef356369d806 | note | Reference - LCC SS No. 7 Part 4.2&4.3
11e5e91d-1794-5e62-8f9f-c9c22b59d858 | note | Item Check - Check and Verify
810bd2c8-7788-4ec9-aab4-769bbd8ad69b | checkpoint | Finishing
82d39f7a-1c79-50b0-aabb-872a4e07277b | note | Acceptance Criteria and Frequency - All surfaces of concrete that are exposed to view in the completed structure are finished such that:
8f0d1c5e-e35b-5e35-802f-5d135426842e | note | (a) Immediately after the removal of forms, all fins and other projections are ground off, all pockets and honeycombs are cleaned and filled with a stiff cement mortar having the same proportion of cement and sand as the original concrete, and the surface of the patch is ground flush;
0facc25d-110b-54fa-816a-4e55fe5aeb37 | note | (b) Decks are roughened slightly by brooming or other approved method before initial set;
624b1c1d-d244-5d8d-92db-35320dda6a3b | note | (c) Kerb and channel, invert crossings, vehicle crossings and industrial crossings are finished with an approved steel finishing tool;
82c4053b-479f-5653-b3b1-cb40c80853fa | note | (d) Footpaths and pram ramps are finished with a wooden float and broomed.
1e4559d5-5a8f-5296-804d-5a4d7ccb3057 | note | Reference - LCC SS No. 7 Part 6.1.2
e681281f-b191-5542-9221-bbaaf0fa8dde | note | Item Check - Check and Verify
c99cc001-30a3-4284-a266-fd296cf8d6bf | checkpoint | Curing
2b02549c-4a41-54a6-94a1-739ec6630a9e | note | Acceptance Criteria and Frequency - Concrete surfaces are kept moist by spraying with an approved curing compound, or water sprays or wet sand in which case the surfaces are kept moist 24 hours a day for the full period specified without any breaks at weekends or holidays. Curing is commenced immediately on completion of the finishing of exposed surfaces or within 30 minutes of removal of the forms from other surfaces.
17ae0b15-40ae-5a29-8121-fb1f4e2bada7 | note | Reference - LCC SS No. 7 Part 6.3
c2e197e9-b7e8-5a6f-8252-f75618ce8a4e | note | Item Check - Check and Verify
a50ea8d6-8bb0-48b0-bc0a-cdc848587ae1 | checkpoint | Dimension Tolerances
479624b0-777e-50a2-bb53-a4922854dea2 | note | Acceptance Criteria and Frequency - Where tolerances are not stated in the approved drawings for any individual structure or feature thereof, deviations from established lines, grades and dimensions are not greater than the tolerances listed in Table 6.4.1–Tolerances of this standard specification and are applied to the completed work.
d1fc102e-94f8-59cb-8735-90b4564bb869 | note | ○ Size of member or thickness of slab: +7mm, -0
03d541d4-6532-5715-9670-187e6d61a80c | note | ○ Cover of Concrete Over Reinforcement: +7mm, -3mm
176e6cda-6cf1-525b-8cbd-9c52035ccf5e | note | ○ Contract dimensions:
2de9aef3-6308-54bd-a9c6-e9bf57ac2ee8 | note | – 0-20meters: +7mm
e8ee63d2-e27d-5ad0-b45a-fbfd38e874f4 | note | – Over 20meters: +13mm
f0bf2453-c8ba-5308-877e-aafdeb0313e9 | note | Reference - LCC SS No. 7 Part 6.4
e3aedaa8-523c-5518-b8d7-5be047fca807 | note | Item Check - Check and Verify
15a62e7a-1e1d-45d4-a03f-a79983b3b23d | checkpoint | Added Water
f11bf61b-9b64-5265-a5d3-8d795ecbc21c | note | Acceptance Criteria and Frequency - No extra water is added to the concrete on site unless:
cc919ec1-fbc6-5a82-9ec3-16f5ba11f827 | note | (a) the amount of the water being added is measured and recorded;
a261c265-eef9-5077-b0c0-1a44737cd1b3 | note | (b) the concrete is thoroughly remixed and a slump test taken to ensure the consistency is still within the specified limits in this standard specification.
6bae9942-e9a3-554e-9dd8-f2dadbc354c1 | note | Reference - LCC SS No.7 Part 2.4
df8174be-a5a6-53d7-905b-43ee18b8b80f | note | Item Check - Check and Verify
2ffa8612-f22d-4163-89c1-b44763bb1310 | checkpoint | Final Sign off and Approval - Conformance with the Specification
94a67222-01ce-53e3-9a46-6b7fda45689e | textbox | Name of Cient's Representative
55881841-746b-52cd-8b9f-4fce821037e8 | date | Date
40cc8c52-92b5-5ed7-ac1c-5546074f6954 | textbox | Name of Contractor's Representative
4a5591ee-b100-5a25-bdf7-e4e943a75607 | date | Date
b41c6de6-6752-412d-8ab6-fb25dc25afed | signoff | Signature
c660d486-9ce8-4b11-b92d-d77c9b1e97ea | section | Final Sign Offs (to be completed at closure of Lot)
3d017957-0dd2-410c-917a-0fe046fad799 | checkpoint | Closure of Lot
f08e1483-eb73-48fd-9b5f-d09f0584de0e | signoff | Closure of Lot Sign Off
173a0985-c0ff-4a27-965b-607d2b52309f | checklist | ITP - Installation of Kerb and Channel - Rev1 | itp | ITP - Installation of Kerb and Channel
9790714c-84b0-4ef6-8df5-63c79b0b81c5 | section | Installation of Kerb, Channel & Kerb and Channel
54ad559e-71e8-4b24-8766-5fc030667b84 | checkpoint | Kerb type
faf1aa33-ace5-54f7-8b02-39e2810170e3 | note | Acceptance Criteria and Frequency - Kerb and channel complies with standard drawing number R-0080 and is one of the following profiles: B1, B2, SM5, M3, Median and Invert, and must be wet mix unless otherwise approvd by local government
35dcc80e-6561-5303-a9bf-584d00449ac8 | note | Reference - LCC SS No.8 Part 2.1
38a73c1d-efb8-51f6-83e5-8b283335f5fa | note | Item Check - Check and Verify
eb48f68b-a4a3-4a6b-8e4b-5dc0a9d28636 | checkpoint | Design and Set-Out Locations
cd650ffa-f14c-50a7-b38e-d071e4f2d46b | note | Acceptance Criteria and Frequency - Concrete for kerb and kerb and channel is 32 MPa strength grade complying with the requirements of AS 1379-2007:
51f76c8e-a00c-5582-9286-201768b38401 | note | ○ The slump values of the concrete are machine finished (wet kerb)—12mm minimum—40mm maximum.
0fc36e6c-9423-5190-94d1-55502737f094 | note | Reference - LCC SS No.8 Part 2.3
d5111b06-7e29-52ff-99c8-e548051aab0f | note | Item Check - Check and Verify
b2a203bc-3c30-4597-9640-41190830ce54 | checkpoint | Compaction of Materials
207075fe-76c4-504f-b5eb-00fe5acbe090 | note | Acceptance Criteria and Frequency - Where pavement thickness exceeds 175mm in depth, the pavement extends under the kerb where the pavement thickness does not exceed 175mm in depth, the kerb and channel is firmly bedded on 100mm road base aggregate compacted to 95 percent modified dry density as required under AS 1289.0-2000 Methods of testing soils for engineering purposes - General requirements and list of methods. No concrete is placed until the foundations have been approved by the local government.
b8a59043-fabc-543f-b547-14d57725980a | note | Reference - LCC SS No.8 Part 2.2
ef534311-21df-5c42-bd85-0d118ede6edc | note | Item Check - Hold Point
e5213e6e-15c6-487e-9388-59daff224803 | signoff | HOLD POINT
8d7939ef-d0cf-45c7-b52c-ec4b2c4a1ea5 | checkpoint | Joining existing Kerb
a4490ea6-145a-5134-b6c1-7981fdce2e23 | note | Acceptance Criteria and Frequency - The concrete kerb or kerb and channel joins neatly with the existing kerb or kerb and channel over a minimal transitional length of 2 metres
cec094c6-3d4b-5642-9323-cd14aa56453a | note | Reference - LCC SS No.8 Part 2.5
df15df1d-c1bc-5141-aefc-3523ba84d43e | note | Item Check - Check and Verify
c58d169f-a3f9-43e4-b0f9-debf8da8ca56 | checkpoint | Expansion Joints
3f66ff61-fb0b-5cf1-9a38-3e6035a35d46 | note | Acceptance Criteria and Frequency - In the case of kerb, a joint is cut and cork jointing is inserted every 20 metres with a cut joint midway between cork joints and jointing is placed in such a manner as to dissect the kerb for its full thickness.
d24ada71-997b-5bc4-9def-485f95466559 | note | Reference - LCC SS No.8 Part 2.4
397ac0e0-8cda-5b0f-b07c-9452260ef992 | note | Item Check - Check and Verify
8e762a2e-5f11-4adc-9d4f-ca86fd231751 | checkpoint | Contraction Joints
5b55d087-0a69-5085-854f-3cd421be8460 | note | Acceptance Criteria and Frequency - A contraction joint is provided at 4 metre centres which is finished square and at right angles to the section of kerb or kerb and channel. The kerb or kerb and channel at a contraction joint is guillotined to the full depth of the concrete and re-finished with a jointing tool to form neat joint lines not exceeding 3mm in width and 6mm in depth
83033990-e15e-51dd-bad3-6b68f32a737a | note | Reference - LCC SS No.8 Part 2.4
588c58d3-fc9f-5970-aa47-6b74a82ce5f6 | note | Item Check - Check and Verify
f064d53a-5b17-42d7-9f5d-54219cdaab69 | checkpoint | Tolerances
f0a5b37b-c20d-5707-9911-cde413c9a45f | note | Acceptance Criteria and Frequency - The horizontal and vertical alignments of kerb, channel and/or kerb and channel shall not vary from those specified by more than ± 10 mm provided that the difference between the deviations from the correct levels at any two points 30 metres apart does not exceed 30mm.
1edd0d20-7829-5783-a3e9-16ed8b74b937 | note | ○ Crossfall is maintained within +/- 0.50 percent of the design
ed396b63-3bc1-5b5b-9c13-3bb1b2126a15 | note | Reference - LCC SS No.8 Part 2.4
d455529a-4f20-5be3-91ac-a99c73cd3812 | note | Item Check - Check and Verify
54e60b9a-57c7-4778-bf1c-774512efe2c5 | checkpoint | Water Test
dc337ecc-dc01-56ae-8a6b-c3b322ea7eb1 | note | Acceptance Criteria and Frequency - Notwithstanding the allowable tolerances, the invert of the channel is finished true to grade and alignment and channelling in which water is found to pond is not accepted and is removed immediately
2c229c5c-4a14-583d-a701-9f158c0789e2 | note | Reference - LCC SS No.8 Part 2.4.10
f9f75ff8-5bd2-5a66-827f-794c9abd97b6 | note | Item Check - WITNESS POINT
52f5a5bc-1ac1-46b7-a788-c224ec6791f4 | checkpoint | Final Sign off and Approval - Conformance with the Specification
2103e188-0041-5a8a-885f-1d4232466561 | textbox | Name of Cient's Representative
46431aeb-3497-5efe-9ca6-13a16be8f98c | date | Date
b11a42fd-e0e4-50d1-bfd8-b9929af6b52a | textbox | Name of Contractor's Representative
fbb3481a-ec65-5bf2-b7cd-030ca43c6c90 | date | Date
5a46c52a-da85-4b73-89e2-15cf031efd3e | signoff | Signature
18f119c1-ae50-4ad2-ad0b-408715801dd3 | section | Final Sign Offs (to be completed at closure of Lot)
4aa8dede-0b94-42b4-b1f1-654aa08407e2 | checkpoint | Closure of Lot
0027c2ec-d11f-4f54-aa2c-8bc48c1199af | signoff | Closure of Lot Sign Off
9043e72c-2f31-416c-b7d2-1834590e45bd | checklist | ITP - Landscaping - Rev1 | itp | ITP - Landscaping
9fd30ffb-4cf4-4f4b-9aea-eabe9d142e52 | section | Topsoil & Turf
54f95345-3cfb-4016-8ef8-a8d3aee254c9 | checkpoint | Soil Type
2fe920fd-6435-5b88-b0be-59310ae53cd6 | note | Acceptance Criteria and Frequency - Alll topsoil imported to site shall comply wiht the following below
962abaaf-6a31-5c4f-86fa-7c11cd21be9b | note | (a) is a fine soil type in accordance with Table 6.2.1–Soil type by texture of this standard specification;
ff9275e5-118e-5cea-ab58-d8c8886bf922 | note | (b) is friable;
33db5823-6ddf-52cd-a471-271a1808d8d8 | note | (c) is moderately free draining;
9785a1ae-8554-5e4e-9017-c9c2fe4c538a | note | (d) complies with AS 4419–2003 Soils for landscaping and garden use;
cd007d65-0952-537b-920d-6ff6680f9d37 | note | (e) is free of fire ants;
c1496bf1-38ee-5026-90a5-bb8319809957 | note | (f) is free from Nut Grass (Cyperus rotundus);
6c8af66d-32e9-5bf5-ad29-1a33044c9c0b | note | Reference - LCC SS No. 2 Part 6.2.1
21f6c367-f03b-5ccc-8449-f2237d3987aa | note | Item Check - Check and Verify
e8532e71-d1c3-4f25-9af8-44340a4b891c | checkpoint | Topsoil Provider
e4112bb8-4d92-5bde-9698-f1dd4da6fe94 | note | Acceptance Criteria and Frequency - Soil is imported from a source approved by the local government or is provided from material upon the premises where approved by the local government.
4ad87737-11b4-50ca-a554-81f6a6678357 | note | ○ Soil from the premises which is improved to comply with Table 6.2.1–Soil type by texture of this standard specification by the use of additives such as Gypsum, may be used as topsoil where approved by the local government.
1f92ac4f-61a1-5a56-ab52-9089dee37f99 | note | Reference - LCC SS No. 2 Part 6.2.2&3
0e997d2a-4024-56f2-9de3-cbe036244f86 | note | Item Check - Hold Point
ce68acfc-e89c-4b11-b0db-c549bbdc214a | signoff | HOLD POINT
1997230e-0f54-4cd6-99b4-166a765da03c | checkpoint | Spreading Topsoil
6f58026a-1bd7-5877-bb01-9d1b4ae61781 | note | Acceptance Criteria and Frequency - Soil is spread such that:
daf21908-8080-5d42-a9d1-0ce02983ddc3 | note | (a) the finished surface of the soil is smooth, free of lumps and free draining;
07baf405-fba5-59e1-a391-77924958d21f | note | (b) the finished surface levels allows for the settling and spreading of mulch;
5c77b8bc-92ff-54f5-9243-244d34da7c5a | note | (c) the soil is lightly compacted over the prepared sub-grade;
839922e1-29b2-5d9b-bfae-f20a370d4789 | note | (d) in a grassed area the edge of the soil is feathered into undisturbed ground.
1957cf2b-deea-5f3a-9f5a-6642e6d81fa0 | note | Reference - LCC SS No. 2 Part 6.2.5
bec6f81a-e86c-592a-815e-0d3f58b8204b | note | Item Check - Check and Verify
49bb7e2c-ed32-40de-bc13-9604cfff957c | checkpoint | Topsoil Finish
90205315-706f-578e-bc44-f0335383c798 | note | Acceptance Criteria and Frequency - Where soil is next to a kerb, a path, a mowing strip or other hard paved surface:
3361760b-4ff9-5cb8-a784-970f780b7507 | note | (a) the soil is finished flush for a seeded grass area and bevelled below the abutting finished grade to allow for turf or mulch;
d44f4dae-c6c7-5f9b-abda-e39d2d6306d2 | note | (b) the finished grade of the mulch is approximately 10mm below the abutting finished surface level;
05c31716-a210-5f6d-ae6b-31595e8f07b1 | note | (c) the finished surface level of the turf is flush with the abutting finished surface level;
b0de02b3-65cc-5356-a0df-c4ef48303439 | note | (d) the finished surface level of a grass area, turf and a garden bed adjacent to a building or other structure is 125mm below the weepholes in the building or the structure.
1fd2b1af-e55f-589d-af87-f4b436be9414 | note | Reference - LCC SS No. 2 Part 6.2.6
9ff8fd15-6a00-5752-82fb-343dc11fba61 | note | Item Check - Check and Verify
372812b1-7a01-4c16-b132-fcce78413b7d | checkpoint | Topsoil Depth
d57c6fb0-6100-5b69-b50b-94aee5f243e1 | note | Acceptance Criteria and Frequency - Topsoil depth is 75mm as per contract drawing GW001
c9d97ab8-9bb0-5e4b-9055-97cb75fa70a8 | note | Reference - Contract Drawings
117190ba-3c2d-55f8-9e83-7a9b461c8fa9 | note | Item Check - Check and Verify
927db4db-06a8-4128-9682-bdde0cdedbbb | checkpoint | Fertiliser
2efe4240-115e-53f3-8306-5353a71fd28a | note | Acceptance Criteria and Frequency - Fertiliser is to be applied as per manufacturer's specification to ensure healthy long term growth.
e6c0a7ec-24cd-5e0e-826c-dfb48b5cb6ef | note | Reference - LCC SS No. 2 Part 6.4.1
d1327423-e34d-568b-8735-8ca71020ae93 | note | Item Check - Check and Verify
d3832854-54e5-4ba9-8fb5-e71bffb1b25b | checkpoint | Turfed Area
30d70d28-8cd8-59fd-b0a3-4b11aa3b6f35 | note | Acceptance Criteria and Frequency - A turf roll has a minimum soil thickness of 20mm.
86993059-e1ef-544f-9428-9d6e4bd6eb4a | note | (2) The turf is delivered to the premises within 24 hours of being cut.
243ad3c4-601f-51d7-ab84-b8448598f3d2 | note | (3) The turf is laid within 36 hours of being cut.
8c5d1d48-e6e7-57a4-b4b7-a6046ff4c905 | note | (4) Where the laying of the turf is delayed, the turf is:
e6a99d0d-da83-5763-8d81-4554471ddd32 | note | (a) protected and watered to maintain its condition;
bd0c303b-8a0d-50c2-a2c4-25827a5c746a | note | (b) not allowed to dry out at any stage from cutting to laying.
c4d139c9-3d55-53ef-89df-ad30fb271c14 | note | Reference - LCC SS No. 2 Part 6.4.3
15c0bc54-958d-5f8e-93f3-0ea020139e8f | note | Item Check - Check and Verify
8620647b-c555-4d7d-88c2-0515a586c390 | section | Maintenance
de9fe89a-634d-403c-b8a8-7478220cad8e | checkpoint | General Maintenance
cb3e3c34-6245-5e7a-bcd0-c728ed470274 | note | Acceptance Criteria and Frequency - The premises is to be kept free of weeds and rubbish and any damaged, defective or stolen landscaping item is to be repaired or replaced.
ff1b52fe-ae3f-59a5-ac62-5c48c95fa02e | note | Reference - LCC SS No.3 Part 7.1
37628314-3559-5d44-a7fe-7bcfb61ba4e4 | note | Item Check - Check and Verify
76026e8c-331b-4ee3-a807-6f7406fc6893 | checkpoint | Maintenance Period
eaa02f19-9fd0-5aad-83cb-6ad0ca1551cf | note | Acceptance Criteria and Frequency - All turfef areas are maintained through the maintenance period such that at the end of the establishment period a turfed area has 100 percent of turf coverage, the plant estabblishment period is a minimum period of 12 weeks from the date that PC is approved.
47868576-22cf-5c3b-b207-fd51cdb58aea | note | Reference - LCC SS No.3 Part 7.3
82e29511-2615-5df4-9bdd-424c87351050 | note | Item Check - Check and Verify
cd83b992-61db-4dff-948c-18e0236ab917 | checkpoint | Maintenance of Turf
d283b9d0-57a6-5395-ab72-764d97cd9ea5 | note | Acceptance Criteria and Frequency - A grassed area is maintained during the maintenance period by:
69dfbf79-ed89-5df0-9918-5fbd3b694a60 | note | (a) mowing grass to 50mm height when grass has grown no higher than 75mm and removing grass clippings from the landscape area or as otherwise approved by the local government;
14ff4a30-a8ea-5833-8bfb-8924066f5b09 | note | (b) applying water at regular intervals to ensure ongoing healthy growth
d7bc6a57-ce52-50f7-9f24-bff6716e58fe | note | Reference - LCC SS No.3 Part 7.4.2
78df162d-bd3a-5951-9637-d98b3872f35d | note | Item Check - Check and Verify
7517668d-4ca6-446a-81c2-68ae360fffb9 | checkpoint | Maintenance Program
21fc98de-2cd0-5989-beb7-38e857f7572a | note | Acceptance Criteria and Frequency - The Maintenance Program is to be prepared by the Contractor and submitted to the Superintendent for approval prior to commencement of work under the Contract and is to contian details about the frequency which the contractor proposes to carry out its obligation under section 7.4 SS 2
0e52bfe7-e00c-5cac-829d-4d513dd7f19a | note | Reference - LCC SS No.7 Part 8.3.4
efca10b6-f51b-5aee-b750-1ed8a3641696 | note | Item Check - Milestone/ Hold Point
dfa3f3df-0df1-46c2-bb33-74b04ffa188c | signoff | HOLD POINT
ffdb3097-41be-4394-8e6b-a22fd867861a | checkpoint | Final Sign off and Approval - Conformance with the Specification
2ae0e6a1-7bbd-529c-ada8-274bfbe5966b | textbox | Name of Cient's Representative
b8335759-a310-5fb1-b311-ad2271bd4c92 | date | Date
414bb2cc-f8a7-5425-8e89-5135726e0189 | textbox | Name of Contractor's Representative
212dfcee-5129-5090-a65c-20f106fab5f7 | date | Date
cf1b43e1-0d4a-4eff-ac90-25a1f753391d | signoff | Signature
c862864b-dfe5-403b-9017-05e82c26680d | section | Final Sign Offs (to be completed at closure of Lot)
f70383b3-9220-4a1e-bfed-660c47fd754a | checkpoint | Closure of Lot
ac687c21-3402-4b94-bdda-691b9408a263 | signoff | Closure of Lot Sign Off
9c56cbaa-ca57-44a7-85cb-cf2d9367b2e1 | checklist | ITP - Linemarking | itp | ITP - Linemarking
f2391c43-0279-4a77-acf6-9ea407598030 | section | Linemarking
0a7db2e1-5cdc-4160-9be4-6b3a19bf68c0 | checkpoint | General
c68e2fc8-2186-5298-a66a-6c1df0a91fbe | note | Acceptance Criteria and Frequency - The Contractor shall provide properly constructed toilets, drinking water, eating and washing facilities at the Contractor’s site facilities for the use of personnel and connect to town sewer where possible and shall comply with AS 1547 On-site domestic wastewater management.
09f85f8e-c0ba-51b0-b375-ecfccf6906f5 | note | Item Check - Check and Verify
10f2dcf9-bf77-46e2-960f-5379db91e7a9 | checkpoint | Site Security
dfc20f9b-d288-5ace-b584-7be5446a2c85 | note | Acceptance Criteria and Frequency - The Contractor shall be responsible for the security of the buildings, construction plant and machinery.
2892c41b-b6bb-5d83-9ad4-e9bfcd450d6f | note | ○ The Contractor shall also take all necessary precautions to make the area safe to the public, including provision of signs outlining relevant project contact details, safety requirements and any other relevant details on the main entry gate.
d95c5036-b343-5761-86df-775a664cbe5e | note | Item Check - Check and Verify
2d7faca5-41d8-412c-8a87-070077344996 | checkpoint | Visibility to the public
7ce4fc23-292d-5bcf-9cea-f629ec725ddd | note | Acceptance Criteria and Frequency - External lights on the facilities and camps should be positioned or shielded to minimise light overflow onto neighbouring properties.
2d368114-f196-50fc-9d35-02f1e6d0da99 | note | Item Check - Check and Verify
e96308b3-1af9-40d2-9ba4-c78e6dbbdf60 | checkpoint | Noise
fcf75a11-02d8-5466-a9cc-bcc55fc01fb4 | note | Acceptance Criteria and Frequency - Noise generated from the site facilities shall be kept to a minimum and the Contractor shall construct noise amelioration devices around the site facilities to bring the noise levels within specified criteria.
ac579c85-acb0-5559-8d66-a4cb2fdf0025 | note | Item Check - Check and Verify
372d46f1-2ad9-48ab-bbfe-8d67ab2deb53 | checkpoint | Dust Suppression
99661851-7d2b-5104-b44b-7d7dc2835452 | note | Acceptance Criteria and Frequency - Adequate precautions are taken to minimise dust or dust-related conditions during any activity which may affect the safety and general comfort of any person. Regular applications of water are applied to any roads or structures whilst completing earthworks
ac0fc598-e2f4-5924-8df3-3931832a3e08 | note | Item Check - Check and Verify
25e42595-ae0a-431c-add1-95786f0dae75 | checkpoint | Temporary road safety barriers
3d17f8a5-612d-529b-b95c-6700c56f11fc | note | Acceptance Criteria and Frequency - Temporary Road Safety Barriers (TRSB) shall be used to contain and redirect errant vehicles so as to reduce the likelihood of them entering the work site
b3318957-eb59-5134-ae32-7b8b23211afa | note | ○ Provision shall be made for TRSB At locations where work is to be close to traffic, and in accordance with Worker safety requirements in MUTCD Part 3;
6e5b51a9-6691-5d0f-a14d-c3a9b12c2a31 | note | ○ Only those TRSB which are included in the Transport and Main Roads – Road Safety Barrier Systems, End Treatments and other related Road Safety Devices shall be used
ab1ec2f4-1cda-5839-b7c9-392823f5a213 | note | ○ All TRSB and end treatments shall be installed in accordance with the department's Standard Drawings and/or the manufacturer's specifications
fb2e5ae3-67bc-5956-a744-8c78db74c1a0 | note | Item Check - Check and Verify
54552f30-4041-4f07-a4ec-465c28dd3793 | checkpoint | Temporary line marking
e463f098-6c24-54f7-b347-6ee118e43238 | note | Acceptance Criteria and Frequency - Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
3fb6f143-6a89-583d-9a96-b301fee2ce37 | note | Item Check - Check and Verify
d13c6936-0626-4cbf-be3d-d10a3de544f7 | checkpoint | Access
13361f46-14c5-5461-8d01-9aeaa55f84c6 | note | Acceptance Criteria and Frequency - The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
af00e0b4-93c5-59f4-a257-acf520569f7b | note | Item Check - Check and Verify
c8200c85-eb84-4a82-9de1-2539b99f2cfe | checkpoint | Final Sign off and Approval - Conformance with the Specification
19e81cb8-c4de-539e-aa5f-a976f1ca534c | textbox | Name of Cient's Representative
4db5a311-8b20-5e25-849c-e99df3d2734d | date | Date
47d7b145-a1ca-54c0-8300-261509a927f3 | textbox | Name of Contractor's Representative
28c2ef85-cc34-545c-9e70-72745c262d6c | date | Date
03c308a4-cc9f-4eea-a986-254f23914bab | signoff | Signature
40a83092-ef12-4746-8132-1816cac4253a | section | Final Sign Offs (to be completed at closure of Lot)
8def33cd-2caa-4b3e-9ad1-1f70cd1739f8 | checkpoint | Closure of Lot
8cdaf66d-b02d-4803-a292-a7b62e8d243f | signoff | Closure of Lot Sign Off
b59e2ad6-7771-4986-ba78-68cc1a10614f | checklist | ITP - Placement of Plant Mixed Foamed Bitumen | itp | ITP - Placement of Plant Mixed Foamed Bitumen
4a7d235c-6b7a-4886-8397-5f4383190363 | section | Details
df4340f0-5fa5-4a8f-99bf-7df8fd2cbe25 | checkpoint | Approval of Construction Procedure
762ab85b-6c9a-56b1-b11c-f930a7bdfab1 | note | Acceptance Criteria and Frequency - No stabilisation works shall be commenced until the construction procedure for the stabilisation works including all required compliance test results is acceptable to, and approved by, the Administrator.
d7e3610b-4c63-573e-9f0c-350e25e61cd5 | note | Reference - MRTS09 Clause 5.2.2
b89d2778-af63-579c-944c-81ef487e2fed | note | Item Check - Hold Point 1
2311ef6e-ab41-402a-b171-1ebb95363571 | signoff | HOLD POINT
d1ef867a-47ef-49a1-bb8d-95eed1916067 | checkpoint | Compliance of Materials and Sources
c777168a-a324-5f25-81c5-dd47297d09df | note | Acceptance Criteria and Frequency - No material shall be incorporated into the works unless it has been demonstrated to the Administrator’s satisfaction that all the material to be used in this Contract comply with all the requirements of this Technical Specification and the Contract.
6987051a-4497-54fe-a600-6ad2c46a171a | note | Reference - MRTS09 Clause 7.1
da6840b6-66b6-511f-b42a-1b4ebc1f6a2d | note | Item Check - Hold Point 2
5aaa828c-4968-4a53-af96-223976dde1df | signoff | HOLD POINT
631e9eee-2e88-4467-8c17-5db4c8a47bca | checkpoint | Construction Permitted to Proceed
1567ccee-547b-520c-b927-97c2b7ad7041 | note | Acceptance Criteria and Frequency - Prior to acceptance (Clause 9.10), manufacturing stabilised materials and construction of a stabilised layer shall not proceed until the Administrator is satisfied that the requirements covered by Clause 8.1 to Clause 8.9.5.5.3 have been adhered to by the Contractor.
c4fb2e9b-b3cc-57c6-a2b0-021d5f58cdae | note | Reference - MRTS09 Clause 8
20f06660-c0a1-5022-8f37-349dbba10ae6 | note | Item Check - Hold Point 3
93552237-fccc-4046-b6f8-3e4a6366538c | signoff | HOLD POINT
f9cb1e23-285c-494f-9b60-ed80a547bc52 | checkpoint | Survey of Services, Utilities and Drainage
9bba2abc-f968-5850-a716-64a234e2a927 | note | Acceptance Criteria and Frequency - A survey of the Site to determine the location and depth of services, utilities, buildings and drainage components shall be carried out prior to commencement of construction. Works shall not commence until the survey has been completed and a copy of the report provided to the Administrator.
fe4dd027-2b9e-532e-b0e4-bbc18443367c | note | Reference - MRTS09 Clause 8.3
8ccd64ca-1530-5525-907f-aa25d6f3e74f | note | Item Check - Hold Point 5
26090d0e-d628-40fa-a3de-396f66b63761 | signoff | HOLD POINT
45ea0a55-a4a0-4bad-a8aa-ed40480ce9d2 | checkpoint | Allowable Time for Placement, Compaction and Trimming
9e164832-36a1-5f76-a748-ea9437d17962 | note | Acceptance Criteria and Frequency - The time after discharge from the truck within which placement, compaction and trimming of the stabilised layer shall be completed is the difference between the allowable working time (8 hours) and the allowable stockpile time (5 Hours).
233854cc-3c53-5d81-a77b-f36a4608cd9a | note | ○ The maximum allowable time for placement, compaction and trimming shall be 3 hours.
26e6669f-8a02-59ec-ad2f-43aa8068d044 | note | Reference - MRTS09 Clause 8.5
9e64e722-e7dd-52dc-a354-74e2198d758d | note | Item Check - Check and Verify
4c71a13a-344e-4a96-9512-1e003e4a0de1 | checkpoint | Allowable Working Time
da483f20-c630-5270-8569-1fc65ccbd286 | note | Acceptance Criteria and Frequency - The allowable working time is measured from the commencement of incorporation (i.e. mixing) of the foamed bitumen into the material to be stabilised, to the completion of compaction and trimming of the stabilised materials (excluding static multi-tyre rolling).
7d95cffb-6c49-5162-8cca-22fec76b0fff | note | ○ The maximum allowable working time is 8 hours.
05fc5b7b-2b60-56e1-8936-fb6d74eb94ca | note | Reference - MRTS09 Clause 8.6
193101e1-4fab-5e5e-a6a6-267e18d24980 | note | Item Check - Check and Verify
db8c4770-a860-404f-a646-58c26d62afe6 | checkpoint | Preparation of Surface
fe00efc2-86c9-549e-b031-0fbf8b3e07c1 | note | Acceptance Criteria and Frequency - Where a stabilised layer is to be placed on the surface of a granular pavement or bituminous sealed pavement, the Contractor shall carry out the works detailed in this clause and Clause 8.8.9.3:
45fe3c69-1fbf-588f-bd56-466e72657df5 | note | — Where a stabilised layer is to be laid over pavement with a bituminous surfacing, the bituminous surfacing shall be lightly scarified or pre-milled.
ac294ef6-da58-5e58-aa03-717b467cf767 | note | — The Contractor shall ensure the surface onto which a stabilised layer is to be constructed is well compacted, trimmed and prepared before material for the overlying stabilised layer is placed.
f132b0df-1f8e-52d1-a027-126adcd998e0 | note | — The prepared surface shall be swept with a road broom until the larger particles in the surface of the pavement are slightly exposed but ensuring excessive erosion of the surrounding finer material does not occur.
6b59c174-ed96-585c-acdf-b47d8bb96743 | note | Reference - MRTS09 Clause 8.8.9.1
46fcc2b6-2da3-5960-808d-f785fb6055fb | note | Item Check - Witness Point 3
289b9c45-1baa-4d96-b9ea-cb2d01dc2a24 | checkpoint | Subgrade Approval
b6da81df-6401-5cb0-a0d7-b05852237cb8 | note | Acceptance Criteria and Frequency - Prior to placement of any bitumenous product the subgrade surface shall be proof rolled and show no deformation.
62e84437-b9c1-5fd8-9240-bfffa8bd00db | textbox | Corresponding Subgrade Lot:
84acd5f5-558b-5210-98de-29a5ea15cfaf | note | Reference - Internal check
f703c686-d691-523f-81ad-9f563cc40517 | note | Item Check - Check and Verify
c8e0f082-d247-4855-8a07-9bfc8714dce0 | checkpoint | Layer Thickness
55664170-2e18-56f3-b2d6-d0f2ea6b4238 | note | Acceptance Criteria and Frequency - Individual compacted layer thicknesses shall be chosen to suit the construction process and the requirements of the Contract. Unless otherwise approved by the Administrator, the compacted layer thicknesses shall be in accordance with Table 8.8.10
2b7d3f0d-7462-5dec-a23e-dbfb4e9a0530 | note | ○ Minimum thickness: 125mm
ad3a815b-20a8-568c-afa9-54fc67517554 | note | ○ Maximum thickness: 300mm
975c1c29-485a-5803-8afe-c2107025a081 | note | Reference - MRTS09 Clause 8.8.10
b07cd061-e55b-550d-8798-95b4a1b3461a | note | Item Check - Check and Verify
858139ba-13dd-449b-ba73-4406fe3bf817 | checkpoint | Placement
fca95358-0a61-5a1a-9eef-f164a1763635 | note | Acceptance Criteria and Frequency - The stabilised material shall be produced, transferred and spread in one concurrent operation. The stabilised material will be spread with a grader, it shall be manned by a final trim operator. After placement, the layer shall be compacted and trimmed in accordance with this Technical Specification to produce a tight dense surface that has properties that are within the required tolerances.
40228905-768f-5a4d-8ef4-d733506fa1d3 | note | Reference - MRTS09 Clause 8.8.11
b043f2a0-c267-5802-963b-f50289e676b0 | note | Item Check - Check and Verify
f5dfbad7-14e8-4585-b829-6d428b841a33 | checkpoint | Compaction
ee1bcf6a-508b-5bf6-9a16-27fd7470755f | note | Acceptance Criteria and Frequency - Compaction shall be completed within the allowable working time (refer to Clauses 8.4, 8.5 and 8.6). This shall be carried out using an appropriate roller(s) that is capable of achieving relatively uniform compaction over the depth of each stabilised layer. For a layer of 200mm the minimum roller requirements are a smooth drum roller with a multi-tyre
2e756069-443a-53f8-9ffb-0e9b8d21a4ef | note | Reference - MRTS09 Clause 8.8.12
c28af2fb-7eb0-5504-b08a-afec7bc019a3 | note | Item Check - Check and Verify
07fe0ae0-0649-4ed1-9d35-9069ef021472 | checkpoint | Joining new work to existing Pavements and structures
d5260da9-c320-53df-a207-3e25d395ae5e | note | Acceptance Criteria and Frequency - Existing pavements shall be excavated as shown or described in the drawings or Contract to provide a clean, vertical surface at the joint line against which the stabilised layer / material is to be placed, and the stabilised material shall be compacted so that the completed layer is neatly finished to match adjacent pavements and structures.
9e28b1a2-5860-5a8b-b25b-bc26cb560e43 | note | Reference - MRTS09 Clause 8.8.16
6a928dbd-687c-5d13-a0ea-3432865a93a0 | note | Item Check - Check and Verify
70a31bf4-bbc7-45f1-a76c-5e20237930e6 | checkpoint | Proof Roll of Final Surface
9ff92dd9-e0bd-5a9e-ac51-a3e09c0b50f7 | note | Acceptance Criteria and Frequency - Each stabilised layer shall be tested for perceptible surface deformation by ‘proof rolling’ the stabilised layer, in the presence of the Administrator and all areas of the stabilised layers shall be ‘proof rolled’, including all trafficked lanes, shoulders and other areas
e2c900e3-8da0-5826-b118-00f33a13c669 | note | Reference - MRTS09 Clause 9.8.2
22e6cfa2-95cd-527b-a73b-30e46649fcef | note | Item Check - Witness Point 4
6e715be5-18f0-430b-a507-b465f1408bfd | checkpoint | Compaction Standard
57846a4c-d708-5a87-a7a7-0ed07074474a | note | Acceptance Criteria and Frequency - The minimum characteristic value of the relative compaction results for the full thickness of the stabilised layer shall be 102% Standard Compaction
8787484b-39d5-5ac8-bfd2-6e0e4378c9ac | note | Reference - MRTS09 Clause 8.9.4
ef1d3541-2cab-5720-9b1b-94a82eeb8e78 | note | Item Check - Check and Verify
aae4191e-303b-4134-87aa-2b3d96eff84b | checkpoint | Acceptance of Final Surface
693f0e4f-eb6c-5e13-8ea3-fc321ab633fa | note | Acceptance Criteria and Frequency - No stabilised pavement lot shall be covered by a subsequent layer of pavement or by a surfacing until all compliance testing has been completed and the layer has been presented to the Administrator for permission to proceed
e8efb167-1ae6-5297-81f3-faeaecfd5471 | note | Reference - MRTS09 Clause 9.8.3
90d74f6b-b810-5d40-afcc-f84aac8eda86 | note | Item Check - Hold Point 10
efc347ca-eac7-409c-997f-d1c89e1e76e7 | signoff | HOLD POINT
b146d35e-920b-4d10-a7f0-c038470e0d9c | checkpoint | Final Sign off and Approval - Conformance with the Specification
224e995f-8db4-5d58-9610-396f20f5d6e2 | textbox | Name of Cient's Representative
0ebb97ff-f9f8-5fc3-839c-713db7fa8349 | date | Date
32ab7832-9d34-5eee-a541-de0e4621df02 | textbox | Name of Contractor's Representative
e8081794-7766-5b49-9ef8-d411cb5d7dac | date | Date
42fcf8bf-c773-4a96-992d-4a68d20b57d1 | signoff | Signature
009a71d2-e9d9-4454-af96-87528dbe696e | section | Final Sign Offs (to be completed at closure of Lot)
14e3e5d1-bd8c-438f-bd14-66ef6b4c649d | checkpoint | Closure of Lot
198e2cd5-0e79-476e-afa1-3a00c2b775c7 | signoff | Closure of Lot Sign Off
66862c87-7270-4647-88c3-a832b0b01b82 | checklist | ITP - Precast Concrete Channel Drain | itp | ITP - Precast Concrete Channel Drain
5bb46709-500b-468a-b9dd-0f5d280ea22c | section | Precast Concrete Channel Drain
9e3f4652-628c-4b71-8ee5-e9d14742e775 | checkpoint | General
f31e826f-8ee3-569d-ac1c-125c35851481 | note | Acceptance Criteria and Frequency - Precast and/or preformed trough components shall be installed in the locations and in accordance with the details specified in the drawings and excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
902ddcab-a1e2-591b-a578-b86aad4c9f44 | note | Reference - General
295c0775-8f29-575a-990d-c5e5353b9f7d | note | Item Check - Check and Verify
88f6d6ab-bf3f-4567-8f2c-3f37112fec17 | checkpoint | Bedding of drainage trough components
53188f38-7e6d-54a2-945e-c92f070433a7 | note | Acceptance Criteria and Frequency - Foundation bedding materials shall be placed in accordance with Clause 19 of MRTS04 General Earthworks. The foundation bedding shall provide continuous, even support to the drainage trough components
d495f45c-2a00-5cf6-bf8d-d317d107eeda | note | Reference - MRTS 03 Cl 12.3.2
d6e23c44-a009-572f-baac-6bbae702dfd5 | note | Item Check - Check and Verify
b8476bdf-9747-439d-bd85-fd11acae98d0 | checkpoint | Precast concrete drain assembly
942831d8-37d1-530b-82ec-a63daacda48d | note | Acceptance Criteria and Frequency - Drainage trough components shall be assembled in accordance with the manufacturer’s drawings and recommendations.
202152f2-cd4d-57eb-a39a-ca1ed267e7ac | note | Reference - MRTS 03 Cl 12.3.3
78322a71-5638-5226-a589-68f8aee183e7 | note | Item Check - Check and Verify
f6330d24-5f25-4f34-8584-4c5e9924b56d | checkpoint | Laying drainage trough components
0166180a-595d-502d-bfd2-9f11f3e32fc6 | note | Acceptance Criteria and Frequency - Drainage trough components shall be laid with the tops flush with the finished batter the laying of drainage trough components shall commence at the outlet end of the trough and progress to the inlet end.
310f9084-01a4-5119-9fce-4bff55923f52 | note | ○ Where necessary, components shall be selected and arranged to give satisfactory fit the ends of components shall be free of any foreign matter at the time of jointing, when butt and flush joints are specified, the drainage trough components shall abut one another.
7528e2ec-eddf-52c6-90e9-c4cde634c341 | note | Reference - MRTS 03 Cl 12.3.4
68fcb1b3-2bb6-5692-9cae-8b3947a85506 | note | Item Check - Check and Verify
519ed722-02a5-41bc-b012-c404ea078521 | checkpoint | Drainage trough bandages
812da7e9-5b1e-5436-ab35-9e708f18d62f | note | Acceptance Criteria and Frequency - Bandage covers shall be applied to the outer surfaces of butt and flush joints. Bandage covers shall consist of:
c965fdfd-2035-5022-b5e1-02752a850938 | note | a) one layer of non-woven fabric, or
69049125-ddc8-504a-aab5-a83c6ddff037 | note | b) three layers of woven fabric.
3c171231-c623-55db-bfb5-e2a9fff0fe72 | note | ○ Fabric covers shall have a width sufficient to overlap adjacent components by not less than 45 mm and shall not be applied until the ambient temperature exceeds 15°C. Fabric covers shall not be wrinkled and shall adhere to the outer surfaces of the adjacent components. The ends of the fabric in the covers shall be secured in accordance with the manufacturer’s recommendations.
848b37b3-2d73-56c5-8d4a-b07fcb8d29ca | note | Reference - MRTS 03 Cl 12.3.4
9c9df9d9-702f-5a8f-bb0e-f365e99b9e88 | note | Item Check - Check and Verify
9e410e6c-f7ba-4971-8353-a2420a3617d0 | checkpoint | Cutting Draianage trough components
a62e7843-f2a8-5f29-9e9a-df364303f88a | note | Acceptance Criteria and Frequency - Where the cutting of precast drainaage components is required the following actions shall be taken:
08a8d6ae-e9eb-5be3-9ea5-2fe1afec709d | note | ○ Cutting operations shall provide neat end surfaces, the cut surfaces of concrete drainage trough components shall be given two coats of a surface tolerant epoxy.
cd0d12ab-aa20-57ef-afc8-5d821fe4946a | note | ○ The cut surfaces of corrugated steel drainage trough components shall be given two coats of zinc-rich organic priming paint as specified in AS 3750.9. The coats shall have a combined thickness at least equivalent to the galvanised coating thickness. Each coat shall overlap adjacent uncut surfaces by not less than 25 mm.
b8a70ae2-f87b-5bc4-8a0f-14be3b5e7638 | note | Reference - MRTS 03 Cl 12.3.5
2a3d0703-ac12-5696-b435-5f45dea17653 | note | Item Check - Check and Verify
bc6b686e-1a48-4001-8d41-ec4891968004 | checkpoint | Installing holding down anchors
8d0bf5d1-f11f-54e6-901b-9ebe7312f8ff | note | Acceptance Criteria and Frequency - Holding down anchors shall be installed in accordance with the requirements specified in the Standard Drawings and the manufacturer’s recommendations as relevant
1f56ce19-dce6-59be-9d9f-ae15607c71db | note | Reference - MRTS 03 Cl 12.3.6
c684833c-91b8-502c-bf68-550ce449fda7 | note | Item Check - Check and Verify
1164b301-5333-4f39-881b-7b93ca8d8956 | checkpoint | Water Test
ea5c8ccc-6a48-5636-9d76-48c4ad78cbe7 | note | Acceptance Criteria and Frequency - Where the longitudinal grade of channels is less than 1%, a test shall be carried out by discharging water into the channel to check uniformity of flow along the channel. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel. The test shall be carried out as soon as possible after the concrete in the channel has hardened.
b561d97b-de1e-5628-a5ae-7a5eb21d8f0e | note | Reference - MRTS 03 Cl 18.5
5cea108c-65b2-53da-b798-481e4d9ccf4b | note | Item Check - Witness Point 1
00f0b0fc-b79b-44dc-824c-d209d9f36dc2 | checkpoint | Final Sign off and Approval - Conformance with the Specification
70f89dd1-5b4f-5617-86cf-403b4cbd3b53 | textbox | Name of Cient's Representative
8ab05a7e-af67-5e67-9734-2949103e7d31 | date | Date
e4a49396-7e23-51a0-ae82-c773d9e9d0d8 | textbox | Name of Contractor's Representative
56db3792-2cd1-5014-89d7-56e5097ed220 | date | Date
8218a0d1-a3cd-4ecc-8413-d192fdcf83f7 | signoff | Signature
6b467762-80c0-4d2e-874d-ab2564219840 | section | Final Sign Offs (to be completed at closure of Lot)
4adcfd6a-54de-431a-8a12-b7b2c166eb00 | checkpoint | Closure of Lot
acf4b351-4619-43b3-9394-8b048d5eaf6b | signoff | Closure of Lot Sign Off
b7da5cbc-010b-4e11-9388-d92bad977e3a | checklist | ITP - Reinforced Concrete Pipe - Rev1 | itp | ITP - Reinforced Concrete Pipe
f5d677ed-82e9-4e78-b232-3141e227e938 | section | Reinforced Concrete Pipe Works
7694cee0-b210-4425-b81d-a051d470f1e0 | checkpoint | General
ddb94ccc-e36b-595a-9a02-18fdff84cca5 | note | Acceptance Criteria and Frequency - All reinforced concrete pipes and pit shall be as per drawings unless an alternitive is approved, all pipes shall be laid in location and to levels specified in drawings.
990176e2-66ae-5061-b993-90dfa999cc21 | note | ○ Drawings specify
dc46f25b-637b-5d17-9dc3-859671266ce5 | note | Reference - General
5dfd69f5-bcdd-5ef9-851e-c7fd04241575 | note | Item Check - Check and Verify
be5f74da-2540-4205-b414-c9deb4072606 | checkpoint | Material Conformance
2c8d8fc1-8ed5-55bc-a51c-e53343a80aa8 | note | Acceptance Criteria and Frequency - Unless otherwise noted on the approved drawings all pipes are Class 2 and comply with the requirements of AS 4058–2007 and all matrial conformnace data shall be included in the lot submission to the administrator.
9a29dc34-dadd-58eb-95a5-590cd15e6caa | note | Reference - LCC SS No.3 Part 2.1
82b6c189-542c-500e-8c9a-efd8cf630b25 | note | Item Check - Check and Verify
4ba3f01e-32bc-42c6-9d95-d2d71115aff7 | checkpoint | Construction
075ef688-8a29-5b11-bf8f-70862c22235a | note | Acceptance Criteria and Frequency - All RCP will be constructed as per IPWEA-STD-DS-030 which covers excavation, bedding material and backfilling
9c9e71e8-0bad-5ee7-91be-f5f5575f4984 | note | ○ Bottom of excavation shall be compacted to a 95% standard compaction unless insitu material is rock for all excavations.
5ca35146-b41a-528b-9f2a-ac2e2daebf46 | note | ○ Backfill material shall be either 5 or 10mm aggregate.
34c04ba8-b578-580e-98cf-d2e277c21d7b | note | Reference - LCC SS No.3 Part 6.3
1a47d613-003a-5a6d-822f-0ffbe87108ca | note | Item Check - Check and Verify
437ccfaa-4ef9-4091-b410-a1c62fdf87d4 | checkpoint | Pipe Laying
0c9a21e5-fa34-5eaf-b90e-420d84d6f1f6 | note | Acceptance Criteria and Frequency - Pipes are laid true to line and grade, and are free draining and firmly bedded and are laid from the discharge end upstream to the following tolerances:
21b4cbdd-1617-5bf6-9be3-2fac12782f77 | note | – invert levels - ±50mm;
bbb8ac9c-7589-5c5b-b176-9a509ff91cc1 | note | – gully locations - within 300mm of design.
0dcd18f3-da1d-560a-bb5b-4004d46deeee | note | ○ For pipes up to and including 600mm diameter, the socketed end of the pipe is laid upstream and a shallow excavation is made under the socket of each pipe so that the pipe fully rests for its full length of barrel upon the bedding material in the trench.
06fb3e23-8408-589b-9934-af79a50c2f34 | note | Reference - LCC SS No.3 Part 4.2
bb8e9227-afce-5205-824e-02a94efcce51 | note | Item Check - Check and Verify
dffbe2c4-1830-4545-9da4-a3f1a230f3f1 | checkpoint | Construction - Backfilling
3236e555-9f0b-55fb-ae97-a01c83c68ea4 | note | Acceptance Criteria and Frequency - Pipe is not to be backfilled without being inspected and approved by administrator.
7a42f4ca-92e7-583d-8380-df5b6037f081 | note | Reference - LCC SS No.3 Part 5.1
5d5c76e9-820b-57a2-a0a0-de1290b0e787 | note | Item Check - Hold Point
56ead252-913d-45f0-a563-31e1aeb4f89c | signoff | HOLD POINT
445d6773-0cc1-44cc-96d7-3e9f50c5aa94 | checkpoint | Backfilling Material
9ad8c4b2-0a6e-5a67-a049-6e73fb941959 | note | Acceptance Criteria and Frequency - Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in part 4 of Standard specification 3 and conforms with table 4.1.1 Bedding Material
d7558804-858e-55e4-8bd3-327a296792ee | note | Reference - LCC SS No.3 Part 4.1
24b47b9d-a23d-52c1-adce-71591e9820d7 | note | Item Check - Hold Point/ Witness Point
f2595b55-ff3e-449b-8cec-e104eceb756c | signoff | HOLD POINT
ac0d221a-3c78-424b-8e9c-9f86dd53a3ae | checkpoint | Backfilling Under Proposed Pavements
9ed1c894-3dfb-5165-ad1e-37d013d0b19e | note | Acceptance Criteria and Frequency - backfilled with approved material of minimum 4 day soaked California bearing ratio of 15 and compacted to 100 percent standard compaction.
f4d63cc1-85cd-5d63-9f22-a7a8b490fab6 | note | Reference - LCC No.3 Part 5.2.1.(a)
fdfb6d88-7676-544f-87e9-8dfa1b08c146 | note | Item Check - Check and Verify
41ba5873-bd09-4da3-b3b3-0f37200480d8 | checkpoint | Bedding
8ef6c5e3-4868-5e41-bc5a-5a494741c850 | note | Acceptance Criteria and Frequency - The pipe bedding or box culvert bedding and the lower layers of backfill up to a point 300mm above the crown of the pipe or box culvert are carefully packed and rammed solidly in layers of 150mm, to 95 percent standard compaction as determined by AS 1289.1.1 - 2001 and Amendment 1- 2002 and Amendment 2 - 2008 Methods of testing soils for engineering purposes - General requirements and list of methods.
33a97d5b-a47e-5e03-9176-ed6d84db04b3 | note | Reference - LCC SS No3 Part 5.5
aa82279a-03a5-5390-9aba-0aa5678481be | note | Item Check - Check and Verify
1350055b-9d6e-4869-8994-24eaed14415f | checkpoint | Pipe Laying Compliance Testing
4530fee1-04aa-56a0-8ed8-81ae3980d433 | note | Acceptance Criteria and Frequency - All pipes lines are subject to internal inspection and approval, the inspection of all pipes is carried out using a remote controlled video camera and is submitted to the local government before being accepted on-maintenance. A report on the findings of a remote controlled video camera inspection is to be submitted to the local government in an electronic format suitable for utilisation in “Sewer Rat” compatible applications. Pipes must not show clearly visible cracks of more than one millimetre for a length of 300mm or more on the inside.
9a903f54-54e2-5b83-aa40-753f82d5afad | note | Reference - LCC SS No.3 Part 4.4
16ee5aff-e132-56d7-88fd-85ec2851b21b | note | Item Check - Hold Point
fdfa6706-0378-4008-aae3-e3a46ea51873 | signoff | HOLD POINT
93708d47-6c24-4c20-a06c-81cdd44dc420 | section | Insitu Gully Pit Works
ef8c7c25-a259-41b6-be91-934deda809aa | checkpoint | General
6b9941cf-95a0-513f-bb2d-fa50c03ff4f8 | note | Acceptance Criteria and Frequency - A drainage structure includes all work and materials necessary for the construction of gullies, inlet pits and manholes, including excavation, concrete rendering and all necessary frames, curves, gratings, precast units and surrounds, precast troughs, chambers, lintels and shafts for side entry gullies, as specified in the approved drawings and standard drawings.
b6b06191-cd8a-5da5-8f8f-3d3cd4b9e3bb | note | ○ IPWEA-STD-DS-60
fa618c96-480d-549d-b39e-509f65a5a9e1 | note | Reference - LCC SS No.3 Part 6.1
7f138571-7434-56b9-b381-9d3f8a57b329 | note | Item Check - Check and Verify
ff125cbf-dd9a-46e7-8790-e2b4c99d9c1a | checkpoint | Materials - Gully Pit
7e3dc528-47de-5cdc-acff-2ac178d9b871 | note | Acceptance Criteria and Frequency - All materials used in insitu drainage structure will the N32 class concrete or otherewise specified.
cfe07c1e-c753-5b98-a3a4-4e3e07d50e39 | textbox | Concrete mix used -
be356185-82c9-531c-899e-e4a8e4467163 | note | Reference - LCC SS No.3 Part 6.2
0b18123b-1cb2-5bda-8968-d0d75b5f6a9d | note | Item Check - Check and Verify
aca57f99-d13b-4545-be8d-d8fa5b4c0037 | checkpoint | Formwork Approval
6d3cdc62-c58c-5648-bdbd-a2c2f7d639a1 | note | Acceptance Criteria and Frequency - All concrete is placed in dry conditions and no concrete is placed until the formwork, falsework, and reinforcing materials have been inspected and approved by the local government.
e4349d31-879e-5e81-aeca-6db72fa0c6e5 | note | Reference - LCC SS No.7 Part 4.1.1
f362051e-1730-52b0-bf44-bec581a6c4e6 | note | Item Check - Hold Point
2e84fb45-9281-4f42-b59c-e940d55ec0de | signoff | HOLD POINT
0608ded7-cd03-4359-804e-cd7be78ae4e4 | checkpoint | Construction of Gully Pit
e1ebfcc0-4000-5a41-a542-f21ca1d99c16 | note | Acceptance Criteria and Frequency - Where the sides of the excavation are deemed to be in solid ground shafts may be constructed without the use of backforms, where concrete is placed without backforms the specified wall thickness is increased by 50mm minimum and not greater than 300mm of the design thickness. The finished concrete surface shall have smooth even and neat edges and will be shaped per the design intent.
93da4af4-042b-51b6-869f-0f150c2bee04 | note | Reference - LCC SS No.3 Part 6.3
57cb8042-9fed-508e-a43b-894fb46b0518 | note | Item Check - Check and Verify
32a46035-f141-4e6b-b1d6-af4befe99a67 | checkpoint | Subsoil Drainage
fc340267-9f11-5bd5-8f52-7278934fc4a2 | note | Acceptance Criteria and Frequency - Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub−soil drainage pipe is laid in the bedding material.
1daaf833-2265-5fd3-a7b3-7e3af1ebdda1 | note | (2) The sub−soil drainage pipe is:
155d69cf-41cc-5828-96d7-34900f0496c6 | note | (a) Class 400 perforated corrugated PVC pipe Type 1 that complies with AS 2439.1−2007 Perforated plastics drainage and effluent pipe and fittings—Perforated drainage pipe and associated fittings and AS 2439.2−2007 Perforated plastics drainage and effluent pipe and fittings—Perforated effluent pipe and associated fittings for sewerage applications;
5d37d20d-d59d-59ce-b25e-2a97956bcfd2 | note | (b) fitted with an approved geotextile filter sock where sand bedding is used.
7b38d760-075d-51cc-9d20-61b53b9027d3 | note | Reference - LCC SS No3 Part 3.2
ef5f7def-19be-54ce-aec6-a518be8b7d27 | note | Item Check - Check and Verify
5058e2ac-081c-4f68-9a7f-de608d59d860 | checkpoint | Final Sign off and Approval - Conformance with the Specification
43252244-9d05-585d-ada5-b3b05bca0fd5 | textbox | Name of Cient's Representative
7441126d-66fc-5f13-8fc1-527fb055b7ec | date | Date
92768728-e1d0-5d35-8342-75e0e38f5514 | textbox | Name of Contractor's Representative
3a47900b-44e6-55c1-befa-054384f4948d | date | Date
6c6563ea-6bf3-43b7-93ac-fc7f8418e8c7 | signoff | Signature
3ee6b7d9-fe04-475d-be5b-77c35501d689 | section | Final Sign Offs (to be completed at closure of Lot)
8e7303e0-b27c-4e65-965c-c3c3bde37cbf | checkpoint | Closure of Lot
1d952ef2-93e4-43c9-8300-c0b338c0f6ac | signoff | Closure of Lot Sign Off
8e6045fc-dbae-4b49-96de-ce2fa959dd80 | checklist | ITP - Sprayed Bitumen Surfacing | itp | ITP - Sprayed Bitumen Surfacing
2241d54d-f800-4b74-8616-b2af94b1df20 | section | Sprayed Bitumen Surfacing
009f47fa-e76f-407f-a95c-9dd00aa3064b | checkpoint | Construction Procedure
c6324c2f-2608-550c-beb8-a7476873e2c8 | note | Acceptance Criteria and Frequency - Procedures shall be submitted to the Administrator not less than seven days prior to their use, and procedures shall not be implemented until permission to use has been granted by the Administrator.
24ebb54a-2c78-5975-b0d4-ffa757fa6ee1 | note | Reference - MRTS12 Cl 5.2
1452a065-ab70-5b8e-85a2-cdb57e391694 | note | Item Check - Hold Point 1
fb0a4ef7-2474-42de-9349-1d67ebc9907a | signoff | HOLD POINT
6bf1b892-d406-4f3f-b3b4-7172c28f1795 | checkpoint | Plant Required
65f47a33-1fc7-5ad3-b9a3-442a5922c8b5 | note | Acceptance Criteria and Frequency - The Contractor shall have on the Site and in use as required the plant necessary for the performance of the particular operation. The respective minimum requirements for the plant listed in Table 9 shall apply. Not less than seven days prior to sealing operations, the Contractor shall submit details of all plant to be used in the operations.
c4ed9e90-cb8a-5422-8beb-dcb5eea1b4e6 | note | Reference - MRTS12 Cl 9
85388bbd-eaf8-53fb-9b5d-94285a22ef0a | note | Item Check - Hold Point 4
6810cee1-e4aa-494e-bf84-eef961691fb9 | signoff | HOLD POINT
a6342721-b575-4cf4-a47c-ed033dbcb801 | checkpoint | Surface Preparation
3bca88f8-888a-565e-92b1-4c87789a8990 | note | Acceptance Criteria and Frequency - Any surface that is to be sprayed shall be prepared in a manner that all foreign and loose material, including lenses of pavement material, are removed from the surface, the surface is swept with a road broom until the larger particles in the surface of the pavement are slightly exposed without dislodgement and excessive erosion of the surrounding finer material, a light watering is carried out just prior to spraying; or all foreign and loose material is removed from the surface; the surface is swept with a road broom;
422def0b-8dc6-57b4-abde-4a76c0452654 | note | Reference - LCC SS 14 Part 4.1.3
9a769790-b12a-52d8-bc9b-52a012840939 | note | Item Check - Check & Verify
aa8d8a7e-27a3-4ae3-abf8-3fdde7ae772c | checkpoint | Pavement Surface Temperature
6e8828e8-d744-56d5-881a-a979f08c3009 | note | Acceptance Criteria and Frequency - Spraying shall not commence until the temperature on the surface of the pavement is above the temperature given in Clause 4.2 of the Annexure MRTS12.1 or, if not so given, above 20ºC for at least one hour before spraying commences.
3b14bcb8-2a93-5286-9b86-073db558e4b4 | note | Reference - LCC SS 14 Part 6.1.1
44cf3aa3-99b7-54c4-b67f-16dde74815d6 | note | Item Check - Check & Verify
a70c0673-edc1-4b53-b6c7-46ed595e6f6b | checkpoint | Spraying Temperature
0731a013-6fd1-51cb-9b6b-fef02b19a65f | note | Acceptance Criteria and Frequency - Bituminous emulsion shall be sprayed at a temperature consistent with the requirements detailed in Table 12.5
80e03b51-19ce-513f-b766-e9a88e726548 | note | – – – – – – – – – – – – – – – – –
f22a823e-9e25-57f1-a4b8-76688a3cc225 | note | Table 12.5 - Spraying temperature range
bef20879-5f34-5f9c-9968-c05d62a57390 | note | Material ¦¦ Spraying Temperature Range
9b071ace-f264-5ebb-a55d-f95fc5d51a6e | note | – – – – – – – – – – – – – – – – –
d147515c-4e82-53eb-a966-93cf58a79efb | note | Bituminous emulsion - 60% bitumen content ¦¦ Ambient
588060a6-ab47-5453-be1a-342438a0b4f9 | note | Bituminous emulsion - 67% bitumen content ¦¦ Minimum - 30°C, Maximum - 80°C
28aa27ea-4ea9-5d4d-8cc1-362cad642d3c | note | Modified Bituminous emulsion ¦¦ As shown in Clause 1.2 of Annexure MRTS12.1
621cd138-5fa1-5ce2-8a19-f8e59137e3d9 | note | – – – – – – – – – – – – – – – – –
529ea402-fa26-59f1-9db5-0e26b3663370 | note | Reference - MRTS 12 Cl 12.5
513b925e-da11-5201-b08a-666bb6feb1f9 | note | Item Check - Witness Point 2
1d65c9ca-254e-4130-a1a5-6137790e7b99 | checkpoint | General Standards
9f027caa-9c23-5fa4-9144-12c4c10b30d8 | note | Acceptance Criteria and Frequency - Emulsion primers only to be used where approved by administrator and shall be used according to the manufacturers specifications.
ae67fe9a-a33b-5d10-b497-28a810beef4c | note | Reference - LCC SS 14 Part 4.1.3
60e82d9e-1b5a-5135-a992-f918e0c382f5 | note | Item Check - Check & Verify
188f7baa-b6af-4664-9275-5f1747e71f04 | checkpoint | Details of spraying operations
49ea8794-af4d-580d-8a56-6b89a90d060d | note | Acceptance Criteria and Frequency - After each spray run, all details of the sealing operations are recorded on a bituminous materials spraying record sheet. The bituminous materials spraying record sheet is signed by the local government and a copy of the completed bituminous materials spraying record sheet is provided to the local government at the end of each day's operation.
e4261676-9688-5dca-91f8-53268f27c571 | note | Reference - LCC SS 14 Part 10.1.1
80f7dfb1-d535-5468-8602-a255871eabc7 | note | Item Check - Witness Point
c1dd5631-58cb-4264-82f7-5a3559403830 | checkpoint | Final Sign off and Approval - Conformance with the Specification
9e7b0c5a-3913-598b-ae1e-4acfe109d9b2 | textbox | Name of Cient's Representative
b866e326-e28c-5ec4-b3a5-4c6cf2ae7294 | date | Date
22d84f8f-c1c1-5dae-99e6-0823f6234ae6 | textbox | Name of Contractor's Representative
0211fa22-3e3f-565e-8e93-de82279df363 | date | Date
d6937649-cde2-40c7-95e5-de3d934a3a56 | signoff | Signature
fd6f5fe6-3105-423a-86f7-22d36789d56e | section | Final Sign Offs (to be completed at closure of Lot)
7fbdd2ba-35f3-403e-97c6-9f61cf822790 | checkpoint | Closure of Lot
b6bf8c92-1678-4405-af94-911dfe358c8b | signoff | Closure of Lot Sign Off
41c247b8-0486-43c1-8239-53b40a880a40 | checklist | ITP - Subgrade Treatment | itp | ITP - Subgrade Treatment
436a474d-030b-4288-b82f-a50739e168a9 | section | Subgrade Treatment
c019dcb8-a3eb-494f-be4f-a65c3117ddaa | checkpoint | Lot Boundries
6a59ecfd-2b1e-5059-bda9-d1f1c20a1be1 | note | Acceptance Criteria and Frequency - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
166bb212-5ba6-57de-9868-ad2ca397d9c7 | note | Reference - MRTS 04 Cl 5.6
505cf800-b146-56d7-a834-ea1353409789 | note | Item Check - Check and Verify
f43c2bda-dad6-406f-9d5c-0ef78343ad01 | checkpoint | Proof Roll
735636cb-1b1c-5f41-8c17-d43217c14960 | note | Acceptance Criteria and Frequency - At the completion of earthworks to Subgrade Level, the Contractor shall test for perceptible surface deformation by undertaking proof rolling, Work on the pavement does not commence until the subgrade has been inspected and approved by the local government
923a8115-814e-5179-874c-570583fa1020 | note | Reference - LCC SS No.6 Part 4.1
21d81615-680d-56c5-aedb-c5d6e4df0265 | note | Item Check - Hold Point
36421285-2219-493b-9182-de79f2daa9bf | signoff | HOLD POINT
818c8056-62c7-42a4-aff2-24a5e30ab3f7 | checkpoint | Testing - Compaction
4184a9ec-fdc2-5e43-85ca-bb84de2d153e | note | Acceptance Criteria and Frequency - Subgrade shall be compacted and tested for a standard conpaction of 95% as per table 6.1.1
f8582035-0357-5736-8c0b-fefc0cb6aa11 | note | Reference - LCC SS No. 6 Part 6.1
5e1d93c1-bf66-51d2-9b04-52a916ce2680 | note | Item Check - Test Reports
174281eb-d974-539a-9c7d-302c480fa17c | note | ○ 1 per 500m2
7671a923-244d-5c5f-984a-3eb906cca080 | note | ○ 4 per Lot
f3697a88-c242-4df1-a0a6-14cf36d7be8e | checkpoint | Geometrics - Survey
f93d3a12-8a07-5c40-842e-cb7c6abe3c80 | note | Acceptance Criteria and Frequency - The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings,by more than the tolerance stated in Table 5.1.1 unless specified otherwise.
c83842be-34c1-5346-873b-69ee464beb7b | note | ○ Subgrade Level tolerances as per table 5.1.1:- 30mm and +10mm
daf0a64c-5410-5955-b5ca-dfed229631f1 | note | Reference - LCC SS No. 6 Part 5.1
544330fb-256e-5555-a244-a1d82cb62350 | note | Item Check - Survey, 20m intervals
4ac84b61-45ea-498a-b434-ebdce0524b70 | checkpoint | Final Sign off and Approval - Conformance with the Specification
98b407a1-bcb2-54da-a73f-81626902ae84 | textbox | Name of Cient's Representative
fa524987-2b8a-57c3-b554-3f93e2ea3261 | date | Date
d6340e5f-55da-5b78-a986-13ac20cd7f28 | textbox | Name of Contractor's Representative
92f4194e-77a9-5fd5-849b-f40bbbd7f801 | date | Date
1c025e4d-c29b-4cf1-bc20-2b78fd3d3240 | signoff | Signature
200fd4a6-c9b7-4139-9e8d-f57a99d21f91 | section | Final Sign Offs (to be completed at closure of Lot)
d2854152-0bea-486b-9c2f-5acb07a5931b | checkpoint | Closure of Lot
3c450ab1-9c33-46a3-8072-8126f41aa690 | signoff | Closure of Lot Sign Off
769bc303-6e67-4f4f-828a-eca039fd7d21 | checklist | ITP - Subsoil Drains - Rev1 | itp | ITP - Subsoil Drains
766b5fbf-4db4-4d5b-8d9e-3e2d46113126 | section | Subsoil Drains
f22c20af-f557-491e-bd8e-84ebeda811e8 | checkpoint | Material Requirements - Standard subsoil drains
94d88664-ebd1-56fc-b981-89ef0822bd7a | note | Acceptance Criteria and Frequency - A sub-soil drainage pipe is a class 400 perforated corrugated PVC pipe Type 1 in accordance with AS 2439.1-2007 Perforated plastics drainage and effluent pipe and fittings - Perforated drainage pipe and associated fittings.
3413f472-63bf-500e-aa81-5f7b9b9c93c8 | note | ○ The diameter of a sub-soil drainage pipe is a minimum of 100mm and the perforations do not exceed 1.1mm in width and 7.4mm in length.
30bf2fcb-8e72-55f8-8939-e0ec128bdc47 | note | Reference - LCC SS 12 Part 2.5
2b9ecf36-5982-51f8-8676-e834d9274e4e | note | Item Check - Check and Verify
cceb198b-242f-463b-9e54-3a3937e4e238 | checkpoint | Longitudinal subsoil drain in pavement
f214af88-5b26-5504-816a-6451792f840b | note | Acceptance Criteria and Frequency - Where a kerb and channel is constructed a sub-soil drainage pipe is constructed
49f46f0a-6844-5523-8388-d833eaabc43f | note | Ss12-2
45c74ca8-f762-5e08-ac50-f98bd0310d32 | note | (a) immediately below the back of the kerb in accordance with standard drawing IPWEAQ R-0140,
02747f26-5842-529b-acc1-1f37e771cdec | note | (b) at least 150mm below the finished sub-grade level
d4023798-e942-51bd-9c49-796b0d2a339a | note | Reference - LCC SS 12 Part 2.2
c612792a-9029-5ec4-8eef-43f230f7eb43 | note | Item Check - Check and Verify
124288d7-6f29-4248-a766-2422560f4284 | checkpoint | Subsoil Drain Excavation
8c755a8f-635a-51bf-93ab-e7e6b8972fe9 | note | Acceptance Criteria and Frequency - A trench for a sub-soil drainage pipe is excavated to 50mm below the invert level of the sub-soil drainage pipe and have a gradient which is specified in the approved drawings or which is a minimum of 1 percent.
fdb81515-8b98-55ac-8758-0c8038728a45 | note | ○ The excavated trench is to be a minimum of 100mm wider than the outside diameter of the sub-soil drainage pipe.
11787540-591b-59e1-98e2-6b91ea7231c5 | note | Reference - LCC SS 12 Part 2.4
622c1df2-edd1-5e8c-a1b7-8c9cfb1c1b96 | note | Item Check - Check and Verify
f2cdfeb9-d161-420b-a7a7-ff82edf0eece | checkpoint | Filter Material
280a5054-a5a5-53c7-a474-1f5107f5e931 | note | Acceptance Criteria and Frequency - Fileter material shall be either 5mm or 10mm drainage aggregate as per standard drawing IPWEA - RS - 140
06658740-22cb-5b17-9e59-b2abb40e5f5c | note | Reference - IPWEA-RS-030
efeaf81a-e067-57bb-b822-41cbe6c4f1d7 | note | Item Check - Check and Verify
c4b98dd5-7bcd-4263-a590-c17f3fe09135 | checkpoint | Subsoil drain outlet
1ad2a2ca-f603-5935-afe8-82ebf9eac6dc | note | Acceptance Criteria and Frequency - A sub-soil drainage pipe: shall be connected to a gully pit, as specified in standard drawing IPWEAQ R-0140; or discharges to a culvert head wall or an open channel below the edge of the road shoulder or at the edge of an embankment.
71472633-97d3-5674-b3e3-dcfc4fc084c1 | note | (a) If a sub-soil drainage pipe is not connected into a gully pit or a culvert headwall, a concrete headwall is provided to the sub-soil drainage pipe.
dc6d7069-383a-568e-b7e9-54f64450a9c6 | note | (b) The headwall is at least 100mm thick and extends for a minimum of 150mm on all sides of the pipe.
6cdcfe12-4d8c-5787-910e-b8974bc7dc48 | note | (c) Where the outlet is through a batter, the surface of the headwall conforms to the batter slope.
182f2d51-07a2-586e-b284-200a36a68c0c | note | Reference - LCC SS 12 Part 4.3
eb9b0632-098a-5b1e-81a1-4b2794130ab3 | note | Item Check - Check and Verify
3d72b9c6-5e41-4440-a292-2f15f457a203 | checkpoint | Poor Ground Conditions
389cd66e-90fb-5a55-95a5-8d557d1a0394 | note | Acceptance Criteria and Frequency - Add below:
c9b57a86-118c-5c4d-a91f-08cf0f93bac1 | note | (1) Where the excavation encounters ground water or other poor ground conditions, the depth of the bedding and surround material is increased to provide adequate support for the pipe as approved by the local government.
f56162d9-9773-56a6-8c50-fe018e8cd361 | note | (2) If poor trench conditions exist, the pipe, or structure is supported by rock ballast which is:
ad0a7664-9bda-5236-805f-fd05b56a8b01 | note | (a) sound igneous or metamorphic material that does not disintegrate in water;
5c25f216-8689-5203-b87d-84034c3d6840 | note | (b) of a 50mm nominal size;
a1c264d2-898b-59dc-be57-db40763227e2 | note | (c) completely wrapped in a non−woven geotextile fabric 1.9mm minimum thickness;
b7165fe2-a0ca-54d7-b884-e65fd6ec2949 | note | (d) tamped into place.
ad4cc5f7-6824-5308-aebd-37b650e66233 | note | Reference - LCC SS 3 Part 3.3
b947c52a-b259-5323-88a5-f6df0049953f | note | Item Check - Check and Verify
5bf11cfc-bfdc-419b-a1e3-6fe7af359da6 | checkpoint | Final Sign off and Approval - Conformance with the Specification
9f1224c1-d630-5ded-b4e6-fb02adab1955 | textbox | Name of Cient's Representative
9481793a-313c-5772-bd9b-90d7a5b084df | date | Date
708ee893-d309-5709-85f3-85c4ad2eb977 | textbox | Name of Contractor's Representative
2a063165-5600-593f-95c3-95d595dc48bf | date | Date
e4293ddc-f7cf-4e08-83e1-280a3f2753de | signoff | Signature
cdc3ddfd-61e6-4adf-b622-11ef51763881 | section | Final Sign Offs (to be completed at closure of Lot)
b560e0b4-5acd-4e39-95dd-b2a182257849 | checkpoint | Closure of Lot
7ca9c45a-20db-4b67-8471-19d56f87119f | signoff | Closure of Lot Sign Off
f7a87631-f453-4c3d-9429-f508e8f7651e | checklist | ITP - Traffic Management on Site | itp | ITP - Traffic Management on Site
918a114c-0cc6-4cde-9964-63c854628d66 | section | Traffic Management on Site
ea40f1b4-dd53-43e5-a169-b370bde27b08 | checkpoint | Nominated traffic officer training/experience requirements
dd44044a-7297-5820-a219-09c0a8583792 | note | Acceptance Criteria and Frequency - The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
e5d1a949-a3af-53d0-a31f-38f984ebeaad | note | Reference - MRTS02 Cl 5.2.
3f58332d-f2d0-5d8b-925c-95ed5f9380b6 | note | Item Check - Check and Verify
fb748777-6799-4725-8296-7285bfb3daea | checkpoint | Traffic management plan submission and approval
296e4a71-fc93-5415-bad7-4057f24dcac7 | note | Acceptance Criteria and Frequency - A traffic management plan for the works is provided to the local governement and approved prior to the commencement of work and complies with the MUTCD, any changes to the TMP will be provided
3302fdec-1621-5815-9193-b1703959efa6 | note | Reference - LCC SS 10 Part 2.1.1
1c184dfc-b6e3-5f5b-98b3-23500288ff27 | note | Item Check - Hold Point
d4a1233b-d774-48eb-94cf-39bc4b48d444 | signoff | HOLD POINT
dc5944ac-1052-44d4-bcd4-8da65f515a60 | checkpoint | Traffic guidance scheme submission and consideration
51711ae6-36e4-55ce-9e82-0bca589a7f79 | note | Acceptance Criteria and Frequency - All TGS's prepared by a suitably qualified person and submitted and approved by the Administrator
d3f0ee8f-3f81-5437-9a95-bf46f2cdf522 | note | Reference - MRTS02 Cl 6.2
aaf15612-13b0-516a-96da-666cba34b673 | note | Item Check - Hold Point 2
1844a20f-ea2a-469e-85bd-99ac13d0a53d | signoff | HOLD POINT
70d68aa2-61e7-4b48-9862-09bd39c76218 | checkpoint | Traffic Management Plan Alterations
4c400b4b-abd8-5854-9e88-263ba432a755 | note | Acceptance Criteria and Frequency - Any variation to the traffic management plan made during the work, is provided to the Administrator
f0465fe0-a309-5dfb-9055-237318b50ec2 | note | Reference - LCC SS 10 Part 2.1.3
14a8ea2c-ade1-5b45-a32b-8748e8a2ab29 | note | Item Check - Milestone
6e0617ca-a73a-45bd-b86e-1b24f38d7566 | checkpoint | Dust Suppression
7d91b5bd-3cdd-5e97-8cb0-0be96fc5ec50 | note | Acceptance Criteria and Frequency - Adequate precautions are taken to minimise dust or dust-related conditions during any activity which may affect the safety and general comfort of any person. Regular applications of water are applied to any roads or structures whilst completing earthworks
6aceb2f1-689d-5776-bb5d-122db54d329e | note | Reference - LCC SS 10 Part 2.5
b77532d7-904e-5156-86c3-bb454f422774 | note | Item Check - Check and Verify
7cc9f7cb-2c97-4de4-8f83-9e101d51d586 | checkpoint | Temporary road safety barriers
fde95329-a1bd-5566-ac52-f271abb88475 | note | Acceptance Criteria and Frequency - Temporary Road Safety Barriers (TRSB) shall be used to contain and redirect errant vehicles so as to reduce the likelihood of them entering the work site
eb1313bf-fdcf-5c74-9873-d1e50e84915b | note | ○ Provision shall be made for TRSB At locations where work is to be close to traffic, and in accordance with Worker safety requirements in MUTCD Part 3;
7df26c60-1855-57b3-b8fb-19977a43bfe7 | note | ○ Only those TRSB which are included in the Transport and Main Roads – Road Safety Barrier Systems, End Treatments and other related Road Safety Devices shall be used
8c483858-b810-572d-8293-a1076f70c377 | note | ○ All TRSB and end treatments shall be installed in accordance with the department's Standard Drawings and/or the manufacturer's specifications
2c7ea9a7-01e5-57f9-a68f-6b1496b1f7ba | note | Reference - MRTS02 Cl 6.5.11 & Annexure 2.1
a109b98a-0837-5f36-a769-4168413b051d | note | Item Check - Check and Verify
2ff13c46-993b-4112-8e3d-de149f77234b | checkpoint | Temporary line marking
cdd3784b-5425-5f57-8a4e-f705f6ae22ed | note | Acceptance Criteria and Frequency - Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
db756f5e-6295-5783-9bc8-9ff1296179fe | note | Reference - LCC SS 10 Part 2.8.4
58159248-ffc8-5c1f-9006-82abf99d34f8 | note | Item Check - Check and Verify
b6b4a424-2df8-4a2a-b7bf-62081c0236ee | checkpoint | Traffic Mmanement inspection reporting
2b07646c-a31d-5237-b5dd-c2f4e33643f8 | note | Acceptance Criteria and Frequency - The officer undertaking the Traffic Management Inspection shall provide a report to the Contractor for its action. The Contractor shall forward to the Administrator, within one week of the receipt of the report, the reports and findings, together with documentation of any actions taken in regard to the findings.
1e8df092-57e5-51d0-bbcb-ce536c67cdd5 | note | Reference - MRTS02 Cl 7.5
3b885d1f-10df-5409-94b3-c8a2f4b4afc5 | note | Item Check - Milestone
fdacce37-2e01-4a3d-8568-65b216986dca | checkpoint | Final Sign off and Approval - Conformance with the Specification
c2bd5d80-6c4d-57c8-bf3d-ba8d420adddf | textbox | Name of Cient's Representative
708278c8-842e-535d-ac3e-bce070e781d6 | date | Date
57d8a6da-f383-5b5b-a8f6-1b44479a0ea2 | textbox | Name of Contractor's Representative
3e218190-8b8c-5ee2-b742-57c8bc76883a | date | Date
71c841ff-abe6-4e37-b002-c2088b4c5d8d | signoff | Signature
551f5d80-f32e-4ddb-9352-9b67c5a1ff58 | section | Final Sign Offs (to be completed at closure of Lot)
584b390e-1dd1-47b9-a9ef-f79770053f1e | checkpoint | Closure of Lot
0100b43c-2e43-4d15-82f0-10fe89707d1d | signoff | Closure of Lot Sign Off
b50d72db-0038-47be-b656-6a49b96d04be | checklist | ITP - Unbound Pavement | itp | ITP - Unbound Pavement
6a270558-8594-4271-b02a-f8d4afd73b0b | section | Unbound Pavement
0d049799-3260-46f9-81bd-608803dd4036 | checkpoint | Acceptance of Construction Procedures for unbound pavement Works
e046805c-708a-5aa4-a9b4-5bf1fcf68039 | note | Acceptance Criteria and Frequency - No unbound pavement Works shall commence until all relevant construction procedures have been accepted by the Administrator
f9dcc579-f292-5f09-9250-77f17f6b9630 | note | Reference - MRTS05 Cl 5.2.1
c6c2c747-9cde-5de3-b6ae-a6ec1daf01ab | note | Item Check - Hold Point 1
fa6c65ca-33ad-4653-9603-45dce39756af | signoff | HOLD POINT
c0418d1b-f9b5-4f50-a1d2-a530fa1ceeda | checkpoint | Submit Construction Procedure for aggregate production
8c954929-e9a6-5037-be6c-3194ac1a95a2 | note | Acceptance Criteria and Frequency - The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the Works
70440abd-2910-5dd6-af3e-e7086af381b0 | note | Reference - MRTS05 Cl 5.2.2
268cbc6d-6013-5441-b45b-0a13e0f53ef1 | note | Item Check - Milestone
49e58f30-b78c-4219-9667-2ea1adba4c66 | checkpoint | Unbound Pavement construction procedure
6daa4d42-5632-581d-a021-f371a67cf848 | note | Acceptance Criteria and Frequency - The Unbound Pavement Construction Procedure shall be submitted to the Administrator at least 14 days prior to the commencement of unbound pavement Works.
a0c88527-a9ef-5285-b988-cbfb491d2e81 | note | Reference - MRTS05 Cl 5.2.3
c45a5ac4-dcca-5fb2-9929-1e357b311f0b | note | Item Check - Milestone
ebb529ea-5037-487a-bd7d-5ff3eff5136a | checkpoint | Supplier Registration and source Material assessment
4ad3d36f-06c6-555a-8cad-fcc126e04df1 | note | Acceptance Criteria and Frequency - The written permission of the Administrator is required prior to material being supplied to or used in the Works from any source nad the current TMR registration certificate for all sources to be used in the works shall be submitted to the administror 7 days prior to works beginning
53a0e8c8-2877-53f5-adc9-13dec39396a4 | note | Reference - MRTS05 Cl 6.1
f54322ad-f331-5b2c-8fcd-993486cb3132 | note | Item Check - Hold Point 2
cf54e0bc-bc35-43ac-932d-cb48be479369 | signoff | HOLD POINT
e5a6cc63-5db6-4721-b646-baf8d6586686 | checkpoint | Compaction
985cbd22-f220-592e-8e13-5c054e6a9784 | note | Acceptance Criteria and Frequency - Type 2.1 material shall be compacted to 100% modified compaction
4d880302-1298-5be7-aab3-027b62b93e4d | note | Reference - MRTS05 CL 8.4.3(a)
2c74caeb-37d6-50cf-a4b7-d44ab64dd76c | note | Item Check - Check and Verify
96c1a81f-e9ac-48f7-aa4c-bfcf21fa73c4 | checkpoint | Alignment, Grade and Crossfall Tolerance for base course
4784e74c-aa6a-5f51-b248-28f5fc4f207a | note | Acceptance Criteria and Frequency - Tolerances for base cousre pavement are as follows:
9ff4bbe2-712a-5931-85e1-d16d7d6e6878 | note | ○ Design Level: +15mm -10mm
6cd32d26-217b-57ab-b721-4ad49615da39 | note | ○ Thickness tolerance: +15mm -15mm
dc26b07d-137e-537c-a565-ba8e5e59818d | note | ○ Shape Tolerance: 15mm in 3 meters maximum
212d5eb0-dee4-5a31-bb5a-212313f13849 | note | Reference - LCC SS 6 Part 5.1.1
ddfa46e8-2b28-514f-91b8-80e74de973ce | note | Item Check - Check and Verify
065461ed-c52e-4b8a-8233-a96aa8bc8f48 | checkpoint | Proof Rolling
f004149f-269e-59b0-808e-8cfe2428797d | note | Acceptance Criteria and Frequency - Each unbound pavement layer shall be tested for perceptible surface deformation by ‘proof rolling’ the pavement, in the presence of the Administrator. All areas of unbound pavements shall be ‘proof rolled’, including all trafficked lanes, shoulders and other areas
c886aa69-1807-536a-bdb1-2ed87f2d17f7 | note | Reference - MRTS05 Cl 9.4.7
92d22171-fdf2-5178-be1a-41da95a0bc79 | note | Item Check - Witness Point 2
ad26d32a-e357-4a01-a519-cbdaff69631e | checkpoint | Lot Acceptance
bf7c3edb-3771-528f-8df8-c6858c2c567e | note | Acceptance Criteria and Frequency - Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until:
8570331d-942b-57eb-8349-a1224e62a640 | note | a) all testing has been completed
34806ed3-61ac-505e-8442-9d2b4305e2cb | note | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
a7f53943-15ae-50b2-a801-6792de18bfb1 | note | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
1477ad14-efea-5063-b800-5221c7da7432 | note | d) the layer has been presented to the Administrator for inspection, and
f15a48d7-d0cc-54e8-a43a-0f73ccc1c6b5 | note | Reference - MRTS05 Cl 9.5.1 & LCC SS 6 4.2.1
f32af4c0-43e4-57ef-aa37-3640429e6e82 | note | Item Check - Hold Point 6
b6fb5e91-4b4b-41b4-bb52-0fefe6821f84 | signoff | HOLD POINT
efcf397b-4657-43a0-b61f-3b7442c866cd | checkpoint | Final Sign off and Approval - Conformance with the Specification
3802a762-fae6-5bd5-8a53-4a2b48efca99 | textbox | Name of Cient's Representative
badd30cf-970f-5660-8b3b-d8dc3ac1695c | date | Date
df0f1394-f0c7-5570-89c4-5ba2b27bf90c | textbox | Name of Contractor's Representative
25f68108-2e35-574c-a87a-77d188d71a16 | date | Date
96f9b32a-36dd-44fe-ad70-2120fdf557b2 | signoff | Signature
da65d897-46ba-4bb3-b608-fc709703f0ab | section | Final Sign Offs (to be completed at closure of Lot)
9a666d0b-9b49-455d-bec2-f3f12ee57b69 | checkpoint | Closure of Lot
8d35aea0-cead-4b27-9746-afb06d1d1ac7 | signoff | Closure of Lot Sign Off
f0728d9e-6046-4268-8848-29255b082801 | checklist | Ω (DEPRECATED) - Conduits and Pits ITP | itp | ITP - Conduits and Pits
fc6d3432-0eae-4df2-8f60-d143c46471c8 | section | Conduits and Pits
493f959a-2db6-499d-b749-679102c0bf97 | checkpoint | General
73e49ef5-2baa-5632-bc44-aa9ba83c7c76 | note | Acceptance Criteria and Frequency - A construction procedure for the installation of all conduits and pits shall be submitted to the Administrator at least 14 days prior to the commencement of installation. No excavation activity associated with the installation of conduits and pits shall commence until the expiration of the 14-day period.
09370e4b-449d-5517-9e0d-60ea798e1273 | note | Reference - MRTS 91 Clause 5.3
948230cd-78e5-5781-a0a7-2da5c50fd88b | note | Item Check - Witness Point & Hold Point
5b06434a-9287-4e64-86d2-8364263bf294 | signoff | HOLD POINT
4619ca28-74f1-4152-9893-4a825edb4d4a | checkpoint | Asbestos Assessment
48352898-8507-5b52-b7b4-e0bf6c8a65ef | note | Acceptance Criteria and Frequency - Asbestos is suspected or found in existing installation, work at this site must be stopped immediately, and the finding must be reported to the principal immediately for their decision and instruction on the work to be carried out at the site.
e2586e25-79f1-5864-a35f-38a1dd4ee056 | note | Reference - MRTS 91 Clause 6.1
10e7c1a5-495e-5ed0-b76f-69f1db678ee4 | note | Item Check - Hold Point
a81f364a-0852-41a8-b114-f724327173be | signoff | HOLD POINT
7cdfa583-59e6-4a1f-981e-6b61d1fa3096 | checkpoint | Material Certification
d6c60ed3-690b-5b66-befd-a766450428a8 | note | Acceptance Criteria and Frequency - All materials must comply strictly with the requirements of this Technical Specification. For all materials, a certificate of such compliance shall be provided to the Administrator before the materials are incorporated into the works
f04deb58-1dfb-50e4-bf6f-d7315e32ee25 | note | Reference - MRTS 91 Clause 7.1
c36de2be-4ff7-56dc-9cc5-8f06791a4285 | note | Item Check - Hold Point
bdc8de39-6692-420b-8ec9-b0bb8e61b6c2 | signoff | HOLD POINT
152a2373-c8db-4716-a8c9-f23fae533fe7 | checkpoint | Excavation for underground conduits and pits
532cfb35-eec2-55c8-ab98-cbd7add6bf4f | note | Acceptance Criteria and Frequency - Conduit runs and pit locations shall be set out and notice of such set out shall be provided to the principal at least 48 hours prior to the commencement of excavation. Construction shall not commence before the expirations of the period of notice.
08a27d2e-c57e-5e83-a82a-445fb76d5ea7 | note | Reference - MRTS 91 Claus 8.1
5400cbfe-92dc-5cbc-a5db-79d3f9a4b6f4 | note | Item Check - Witness Point & Hold Point
4dbfa992-afac-4add-b144-a71052155941 | signoff | HOLD POINT
bc2465c5-754c-402b-bc01-a7b2b51916c3 | checkpoint | Bottom of trench
f9f7e3fa-2bdd-59d6-8afe-b3c5dd750dd7 | note | Acceptance Criteria and Frequency - The bottom of the trench shall be compacted as per Standard Drawing 1149 to form a firm uniform surface free from loose material.
f317dbf8-141e-59cf-a9c5-23b0b1a2457b | note | Reference - MRTS 91 Clause 8.4
b119df8f-8706-5e93-906f-9e3b926dbeb9 | note | Item Check - Witness Point
8418fd45-0e53-4b9a-b599-6cee8615b12c | checkpoint | Boring and Jacking
8c596e21-140b-53b0-a2ef-58254ced9422 | note | Acceptance Criteria and Frequency - Work shall not commence until it has been demonstrated to the Administrator that the proposed equipment can accurately install the conduit in accordance with MRTS140 Horizontal Directional Drilling (HDD) and Standard Drawing 1149 Installation of Underground Electrical and Communication.
f5468f6c-100a-5be2-99b8-bc0d1a18fca7 | note | Reference - MRTS 91 Clause 8.7
0bee0273-396e-51d5-ae38-198185ed0bef | note | Item Check - Hold Point
a4402be0-b8c4-4131-9aec-2a417ec6f52d | signoff | HOLD POINT
04f155f4-bb50-4ee7-a0b4-7b62f16331a6 | checkpoint | Installation of conduits
7f8401a1-8bb6-5290-8e39-11a2ef9a3892 | note | Acceptance Criteria and Frequency - The installation of conduits shall conform to the requirements of Standard Drawing 1149. The installation of communications conduits shall also comply with the requirements of AS/CA S009. Prior to installation, the Contractor shall inspect all conduit and conduit fittings to ensure that they are free of any defects that could damage the cables during installation. Conduits to be installed without dips/low points to ensure that drainage at pits operates as intended.
6bafc17d-05dc-5cc5-bc5c-5f8d5ec934e8 | note | ○ The conduits are not to be lower than the pit it connects to unless approved by the Principal. Road crossing installed by ‘boring’ conduit to be installed level to facilitate correct drainage of conduit.
e36dbdb8-2770-5740-8356-91fb9cceb36f | note | Reference - MRTS 91 Clause 9.1
363e3b51-d6d5-5352-9cd6-0e775b6172d9 | note | Item Check - Hold Point
bf233863-f4fe-40eb-b037-8645d48eeedc | signoff | HOLD POINT
dae8f498-afb7-49ad-b7dc-3b47334d5ba2 | checkpoint | Mandrel
19a637e8-2bb9-552f-9df0-47c480d7fd2f | note | Acceptance Criteria and Frequency - After installation and backfilling, the conduit and conduit fittings shall be proved by drawing a mandrel having a diameter of at least 95% of the internal diameter of the conduit. The mandrel shall have a length sufficient to allow it to pass around any bends in the conduit, but not shorter than 95% of the diameter of the conduit being tested
e5254fbd-35c6-5d40-b694-c2830fb0d686 | note | Reference - MRTS 91 Clause 9.1
14594fe3-3af3-579f-b65d-d0c36a7e6b9a | note | Item Check - Hold Point
215ab9bf-c001-411d-8e20-157442203101 | signoff | HOLD POINT
abaf12bf-5cf1-4598-98ff-363782b86132 | checkpoint | Draw rope
56ff7ac5-b176-53d9-8e22-61fa6b47786f | note | Acceptance Criteria and Frequency - Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
18dcc28c-3f9e-590a-af25-a9310bcffe0f | note | Reference - MRTS 91 Clause 9.13
ccd6f017-b274-5218-bb53-9595885aebca | note | Item Check - Witness point
884b1b67-1919-4004-9668-00cf27e3b42e | checkpoint | Vermin proofing of conduits
65271a6d-38b6-53bb-bf30-79297d0422cd | note | Acceptance Criteria and Frequency - Any alternative proposed conduit sealing system shall be fit for purpose, and a proprietary system, and shall be submitted to the Administrator for consideration and approval prior to commencement of the installation of any cabling.
fd8e6510-c1cc-5e2d-afc8-17644863a463 | note | Reference - MRTS 91 Clause 10.9
cd8e5a03-0fb8-51c3-b6c9-f3e85bff8799 | note | Item Check - Hold Point
dc664b92-7e50-4510-94d6-bfaf7c8984cc | signoff | HOLD POINT
b89cfd70-7eb5-4d22-93f9-9cec3d44f122 | checkpoint | Bedding of pit
d94f9ea3-e296-553c-a1d9-c50869daeba4 | note | Acceptance Criteria and Frequency - The bottom of an excavation for a pit shall be compacted to at least 95% relative compaction.
9481ffcf-2967-5fc3-b9ec-bf4aa51de8e0 | note | Reference - MRTS 91 Clause 10.4
4bccd447-09d7-5b8e-a11a-79d0d3367bc3 | note | Item Check - Hold Point
5edd734c-9d5e-4912-a7b2-5aa4f5487dc9 | signoff | HOLD POINT
189e40f0-d77a-417b-a887-c71d74ae10aa | checkpoint | Compact bedding material
0ed28512-9f4a-533b-983a-a437cf8e8cbc | note | Acceptance Criteria and Frequency - Compact bedding material to density index 60.
024ef54e-f843-5394-902c-f68f164d7c28 | note | Reference - MRTS 91 Clause 10.4
ae57de4d-8d1c-5231-8fdc-1de09b5d9f0e | note | Item Check - Check & Verify
aaaf38f1-4f5e-4c59-97cb-6962b951eda2 | checkpoint | Drainage Holes
c1e1263e-df24-5f4f-8349-8dcec96fce48 | note | Acceptance Criteria and Frequency - The lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level.
a14e93ef-705f-5ba6-bddc-6ab894c96e73 | note | Reference - MRTS 91 Clause 10.11
600a19b2-b01c-521a-a5f8-a9307e1506fa | note | Item Check - Witness Point
7fe9c3db-eaa3-4e9a-af15-b87a4b44e40b | checkpoint | Backfilling
2a94436b-8a55-5c1e-bbf9-02ba5e0863cf | note | Acceptance Criteria and Frequency - Backfilling of trenches for conduits shall not commence until the conduit system has been inspected by the Administrator
0ecc313f-8082-5a71-bbfb-09de25961ff2 | note | Reference - MRTS 91 Clause 13.1
b186b632-1320-5b28-8764-cceeb3e053f9 | note | Item Check - Hold Point
66423c3b-9a28-472c-94fb-8151edb775ef | signoff | HOLD POINT
84fca69b-9559-4263-8a76-6880f82e8eab | checkpoint | Final Sign off and Approval - Conformance with the Specification
e66bda51-d60d-59dc-8dda-72d9a32c672f | textbox | Name of Cient's Representative
9b78bce6-3fef-5ae3-9ca9-9c3155009bd6 | date | Date
710c6514-94bf-5d41-a00f-46f441a6cde6 | textbox | Name of Contractor's Representative
79a01e51-3f73-5f08-b181-9095c5ac8976 | date | Date
c72bde2a-4a39-4e32-b6f8-6db295e18390 | signoff | Signature
70525dee-5350-41da-bc5a-be446435d6f6 | section | Final Sign Offs (to be completed at closure of Lot)
4e678367-2280-4c0d-beb8-b41fbd65bb6e | checkpoint | Closure of Lot
c11e58f3-0f09-4e7f-a75a-78db2923363b | signoff | Closure of Lot Sign Off
3e95cdaa-d402-4584-8bc1-8cd1c1017b17 | checklist | Ω (DEPRECATED) - Dense Grade Asphalt ITP | itp | ITP - Dense Grade Asphalt
1340b2ef-652c-4961-bde7-7b90ba2f04b9 | section | Dense Grade Asphalt
7bfbfa6a-3b7c-4b6f-9f97-f3b1c0ebfe13 | checkpoint | Submission of Asphalt Quality Plan
cdaf703e-f4fd-5c32-85b0-94f96f225ae8 | note | Acceptance Criteria and Frequency - The Contractor must develop an Asphalt Quality Plan (AQP) for the asphalt work to the Administrator for consideration at least seven days prior to work commencing and must be implemented.
86f47269-9f4b-546e-8787-5a7d7271f715 | note | Reference - MRTS30 Cl 5.2
accbc5c2-26ca-5850-8d6c-3844d6c4b9b2 | note | Item Check - Milestone
dff2c023-c14a-4e76-9d7f-a95728d8a685 | checkpoint | Nomination of registered mix designs
4f24552f-c23e-5b8d-9668-9b1d4f2bbdc5 | note | Acceptance Criteria and Frequency - At least seven days before asphalt is to be incorporated into the Works, the Contractor shall submit to the Administrator a copy of the mix design certificate(s) for each nominal size and type of asphalt mix to be incorporated into the Works.
f814dc11-4667-586d-b792-1445d7269232 | note | Reference - MRTS30 Cl 7.3.3
b26f6eea-13e0-50a0-913b-3d3283755d89 | note | Item Check - Milestone
86808759-1e74-4739-9583-d294a508f398 | checkpoint | Asphalt Mix Properties
b6810e00-1d24-5183-8d30-b3de51d61cb7 | note | Acceptance Criteria and Frequency - The properties of asphalt mix must comply with Table 2.6.1 - Asphalt mix properties of LCC spec No. 13 Part 2.6.1 when tested in accordance with column 3, asphalt shall aslo comply with MRTS 30.
ba2a2c5e-64f9-5691-ac24-40700b86c19d | note | Reference - LCC SS 13 Part 2.6 & MRTS 30
3597da63-27d0-5f6d-99a8-6cd6239b59cb | note | Item Check - Check and Verify
ec84a1e6-0fae-4c68-b7fa-1219842050fd | checkpoint | General
ac08c297-c538-5119-90ad-e15a78f6dfe8 | note | Acceptance Criteria and Frequency - All asphalt shall be placed in accordance with design drawings and as per drawings GW001 & LS001
aac28447-ca46-5e8f-aef6-a46f55b942c4 | note | Reference - General
28580898-190f-537a-a190-6d2cb6de7b87 | note | Item Check - Ckeck and Verify
34128b95-6dee-4a32-bd0e-dd13098cb88e | checkpoint | Production of Asphalt
77a3208f-fc63-5ab1-8d5f-aaed85916c2c | note | Acceptance Criteria and Frequency - Asphalt shall be produced by a registered asphalt manufacturer from the nominated asphalt plant in accordance with the nominated mix design for the Works. Asphalt shall not be incorporated into the Works until the Contractor has demonstrated to the Administrator that the underlying lots conform to the specified requirements
94a2fb3d-45c7-590e-8b19-3dacbf24c251 | note | Reference - MRTS30 Cl 7.4.1
7ef20bcd-617a-5061-8c59-a1c2daafe424 | note | Item Check - Hold Point 2
76f7f314-4b10-4903-a71b-d27546da336b | signoff | HOLD POINT
c5093155-2afe-4ac6-9ab9-67f503c47344 | checkpoint | Production of Asphalt
852146e7-5554-56dd-934f-bb73e61b216d | note | Acceptance Criteria and Frequency - For asphalt placed over pavement constructed by others, the surface on which asphalt will be placed shall be tested for perceptible surface deformation by ‘proof rolling’ in the presence of the Administrator.
bcc77259-9b04-56d2-82a2-0abf50498443 | note | Reference - MRTS30 Cl 8.2.2
23253f38-6892-5d64-adfb-09531b88b6ee | note | Item Check - Witness Point 1
8b8b36c8-9461-4619-982a-93014812983d | checkpoint | Preparation
e864dedc-396f-5671-bc80-44941e5b7cfa | note | Acceptance Criteria and Frequency - Unless otherwise approved by the Administrator, asphalt shall not be placed over pavement exhibiting significant perceptible surface deformation.
10a081b5-1703-5cd3-a811-7324fc71798c | note | Reference - MRTS30 Cl 8.2.2
ff912142-d7fe-5cdc-8ac4-87a61af60455 | note | Item Check - Hold Point 4
2315ddb5-2812-430a-87a1-30ae1550e876 | signoff | HOLD POINT
ec28ac07-896a-47fc-bae8-8cd1a2588110 | checkpoint | Preparation of pavement
4bda2a29-6584-5527-8818-01ec438a5f8c | note | Acceptance Criteria and Frequency - Existing substrate shall not be wet and shall be swept thouroughly to remove and loose or deleterious material
8452231b-912b-5b75-b56f-2f32ba9ef434 | note | Reference - MRTS30 Cl 8.2.2
6387315c-ec78-565c-86e6-b934c471eb83 | note | Item Check - Check and Verify
24eb727e-71e3-4e14-9f0b-8b7a9ab44e84 | checkpoint | Application of Asphalt - Temperature
9db7f562-7474-5e9d-95c4-fabfa285b3b6 | note | Acceptance Criteria and Frequency - The asphalt mix temperature is controlled so that it is between 135C and 175C when loaded into the delivery truck, the mix temperature is between 110C and 165C immediately behind the paver with compaction commencing before the temperature of the mix falls below a minimum of 95C.
a87cdbaf-dc57-54bf-a739-fed83c8bbc64 | note | Reference - LCC SS 13 Part 3.1.1&2
49302707-51b0-56cd-8303-dc8ffc93a0d7 | note | Item Check - Check and Verify
412aabde-6833-4b24-ae81-c23abe2eb69f | checkpoint | Asphalt Compaction
d62ba957-755d-5745-8774-b2865a860aa3 | note | Acceptance Criteria and Frequency - Compaction is commenced as soon as possible after spreading, and is completed in the shortest possible time except in the event of significant deformation or an irregularity occurring under the action of the roller in which case, rolling is delayed
51178f8d-4055-5de8-8a71-ee4ee1c4c2ee | note | ○ For compaction testing, a lot is the same as for a production lot and compaction testing is undertaken in accordance with Q302A, Q302B, Q306B and Q314.
e96cc620-3799-55cb-a4a9-de772854ebde | note | ○ After completion of each job, core samples are taken from the compacted asphalt at the rate of one core per 1000m2 of asphalt laid, but with a minimum of three cores per job, asphalt compaction shall be greater than 95%
ca15c10a-0268-533a-b636-24328b238529 | note | Reference - LCC SS 13 Part 3.4 & 3.5
79084078-0f82-5bf2-8037-a8b790ee9aee | note | Item Check - Hold Point
8b8b2b8c-920a-4915-8f92-17500c35e3cc | signoff | HOLD POINT
98911e25-53f8-4458-ada0-92301a3005d7 | checkpoint | Final Sign off and Approval - Conformance with the Specification
896cdd71-5b24-577d-b3aa-978e528b79c6 | textbox | Name of Cient's Representative
687226e5-a7d7-5f21-86ed-8dd5507eaf95 | date | Date
76b35c58-23bf-5cfe-b568-f88ee4f6d0ef | textbox | Name of Contractor's Representative
1d1ec42a-c5a3-5ac4-8ec0-311d5cf6bb12 | date | Date
46fe451d-0199-42d1-92de-ff97ed61951e | signoff | Signature
2b71cc11-6386-40ec-9925-b19b5ba717de | section | Final Sign Offs (to be completed at closure of Lot)
d80a01da-d1c5-4bdf-a4dd-5674e1ac695f | checkpoint | Closure of Lot
3b106906-a214-4c1b-b003-099eb59dd8be | signoff | Closure of Lot Sign Off
4adadce3-ef4b-4e6d-a8db-1362cf63fe29 | checklist | Ω (DEPRECATED) - General Excavation ITP | itp | ITP - General Excavation
2892542e-69fd-45fb-92a4-c537ea0d6ead | section | General Excavation
8379e25e-74c0-489d-9278-e8caa5bea4c1 | checkpoint | Lot Boundries
cf6efc64-37dd-576a-9191-4a7d839446dc | note | Acceptance Criteria and Frequency - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
70b044ee-b31a-5ea1-b696-e8e5101a7410 | note | Reference - MRTS 04 Cl 5.6
77ee455d-1ad0-5a5b-b092-68679728aa61 | note | Item Check - Check and Verify
4f1e56a9-749f-4092-962b-c52cef720912 | checkpoint | Services:
fe19f851-56c1-5eca-80de-03c4820a105f | note | Acceptance Criteria and Frequency - All services identified – shall be marked, potholed and/or protected as required
fef1f3be-681d-5bfb-8953-6968822cb88c | note | ○ Permit to excavate issued by Project Engineer
d7334c5d-ea60-5c3c-92e3-cda2a6fa7320 | note | Reference - DBYD
89e59b21-1eab-5eb4-945b-b439ec1badd2 | note | Item Check - Check and Verify
d34e6100-8c27-4b96-9917-b563a63d3e5a | checkpoint | Erosion Sediment Control
671713a4-7308-5bc0-951a-45f3976ca04b | note | Acceptance Criteria and Frequency - Erosion and sediment controls in place
82cfd33c-0e89-5931-9393-f0e2973d1717 | note | ○ Due care taken to ensure native fauna is not harmed
964d4250-5486-5614-abc4-67108d9f665a | note | ○ Vibration and Air quality to be monitored as a direct result of construction activities
782ab8ea-bb06-5f5b-9af4-855b060703a0 | note | Reference - MRTS51 Cl 10.3
a1a83ba3-b26c-5114-8397-5756ddb74620 | note | Item Check - Check and Verify
93087127-518f-4d55-8c4b-3ea64602a448 | checkpoint | Excavation Cutting
74f6472b-a169-5300-a053-920a9a2a7398 | note | Acceptance Criteria and Frequency - The bottom of excavations shall be trimmed to the tolerances specified in Clause 6 and any loose material removed from the surface.
59e1ab03-ec2f-5375-a8d5-33d33e752067 | note | ○ The existing soil is compacted to 95 percent relative dry density standard compaction, for a depth of 300mm below the sub-grade and care is taken to ensure that the topsoil and organic material is removed and replaced with approved selected material for a depth of 500mm and compacted to 95 percent relative dry density standard compaction where the sub-grade passes through the natural surfaceat the ends of the excavation or anywhere in cross-section.
eb3678c7-b0ce-5fd1-bec6-9d7e8d0a74f6 | note | Reference - LCC SS No.1 Part 9.1
d08609c6-ab9d-5649-9ce4-6550c23c98e3 | note | Item Check - Check and Verify
c0793aee-e335-4bf1-a307-f344c68501bf | checkpoint | Unsuitable Material in Excavtion
124a23d5-3006-50f5-ac7f-b6e43804523a | note | Acceptance Criteria and Frequency - Unsuitable material below the level of the sub-grade in an excavation is:
13b4fec8-ba26-543b-a4a8-08c490412ff0 | note | (a) removed and run to spoil in accordance with section 12.1 of Specification 1,or replaced with select backfill in accordance with section 8.3–Selected gravel fill or selected backfill of this standard specification;
c8f57375-3134-5f8a-aff8-4d83b8f068a5 | note | (b) compacted to 95 percent relative dry density standard compaction
77ea9c61-1621-5f7f-9928-1c78fa2b9dc6 | note | Reference - LCC SS No.1 Part 9.3
3d063b14-3b71-51cc-9688-70fdd01c65ca | note | Item Check - Check and Verify
e972a7c2-9716-4153-98b8-754aac90599b | checkpoint | Unsuitable Material Below Lines of Cuttings
2f8c9cb7-e9fe-5db7-83d3-06cc2bf0f91c | note | Acceptance Criteria and Frequency - Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4.
16d6f513-4771-5fa9-8a32-9de675e61e8f | note | ○ Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate fill material as specified on the drawings or in accordance with Clause 18 and 19.
2cd1f027-bf5b-562c-be26-2ac0c67400e6 | note | Reference - MRTS04 Clause 13.3.2.2
bd1306e9-f284-5227-956d-b3bd5f5a8840 | note | Item Check - Check and Verify
f7d2b245-7cda-4146-81df-0a4a394b5b90 | checkpoint | Finished Cut Surface Survey
861f7f35-28dc-59a5-9613-5bad03e77371 | note | Acceptance Criteria and Frequency - Once Works are completed to Subgrade Level (including all Subgrade treatments), an As Constructed Survey of the bottom of the excavated area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
348577e8-dfa8-5024-872a-0d766b7e0713 | note | Reference - MRTS04 Clause 13.3.2.1
2c0ed882-b9fb-59f3-a120-769bd4c094e6 | note | Item Check - Check and Verify
cdf09901-03b8-41fc-88cc-4c578a5d08ae | checkpoint | Lot Acceptance
d8cddd4c-279e-5906-9945-1dab0a3ca568 | note | Acceptance Criteria and Frequency - Lot closure requires all relevant information to be attached to the Conformance Report this includes a Lot Plan, Survey Report, Hold Points/Approvals & any supporting documentation
a4d11478-96b0-5755-879b-e05c6b39e6e8 | note | Item Check - Check and Verify
7f6dbd34-a5ff-4ff3-8935-a7b5e416d389 | checkpoint | Final Sign off and Approval - Conformance with the Specification
ac494123-09b8-58cb-8d32-8c59a74061c9 | textbox | Name of Cient's Representative
cf7c9efb-1b55-581e-bc39-f2b867d082c2 | date | Date
f0d4cf47-5168-5955-9af7-2dc73753e1f7 | textbox | Name of Contractor's Representative
eef06bfc-ab64-5824-b609-f684fdf1a983 | date | Date
51ae1ed5-e5bf-42c0-98f3-bb0fa9914552 | signoff | Signature
cd09e5cc-5b0a-4a4f-9cb7-76fdbeefac68 | section | Final Sign Offs (to be completed at closure of Lot)
3c191d8e-fc52-404e-b7ac-a915d3420a2a | checkpoint | Closure of Lot
551b5bfc-11ee-4325-ace7-18c88f63a1d1 | signoff | Closure of Lot Sign Off
aca94d15-3e55-48e5-8c3d-84c6fffa10e1 | checklist | Ω (DEPRECATED) - Geotextiles for paving applications ITP | itp | ITP - Geotextiles for paving applications
d3eb40b2-9d73-4004-a1c3-995dc8d02041 | section | Geotextiles for paving applications
0b775983-2fe0-47fc-878f-9c2c1a9562d4 | checkpoint | Geotextile Filtration & Strength Class
3cb3e574-1461-5c83-964c-3794fecf7211 | note | Acceptance Criteria and Frequency - Geotextile to be used as specified in approved drawings
50618b82-9711-54a2-b5e6-aef174c002a0 | note | Reference - Drawing Notes
1c7107da-6e97-50cf-abdc-312281a38dbe | note | Item Check - Check and Verify
554c4f80-253b-45f0-b258-559fa9f1afe2 | checkpoint | Storage, packaging and identification on site
9289e40f-711a-5b39-9dfb-badd45c14df9 | note | Acceptance Criteria and Frequency - Geotextiles shall be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation.
381418bb-6088-5458-ab1d-0eb6eb4fab8f | note | ○ Geotextiles shall not be stored directly on the ground or in any manner in which they may be affected by heat. The method of storage shall be in accordance with any other recommendations set by the manufacturer.
5d3cac75-914f-595d-8ae3-95f2726e03ed | note | ○ The protected geotextile rolls shall be clearly labelled showing manufacturer, type of geotextile and batch number identification number
e0d90530-8c61-5be8-aa76-84cd4d4a171b | note | Reference - MRTS27 Clause 7
c7b6975f-c9ee-51e0-a392-ca7b3288f639 | note | Item Check - Check and Verify
c05c27d6-97b7-432c-b959-ff43af7d614f | checkpoint | Geotextile Construction Procedure
73d6f6b2-35fa-5343-a4c8-cad7ce4b02ab | note | Acceptance Criteria and Frequency - A construction procedure detailing all work described in this Technical Specification shall be prepared. The construction procedure shall be consistent with the guidelines set out in the Transport and Main Road’s Pavement Rehabilitation Manual April 2012, Sections 4.4.6 to 4.4.6.8.
0d1daee4-4cf5-5d6e-9f48-fb93461339bd | note | ○ The proposed construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of any works related to the placement of paving geotextile(s)
57617689-0685-592a-8cc7-edf6a72cce16 | note | Reference - MRTS57 Clause 5.2
a98df849-0970-5d86-b57a-2df3d9e648f1 | note | Item Check - Milestone
aaf4c814-065f-475d-b62c-3dd3de048801 | checkpoint | Approval of construction Procedure
26508fe6-95eb-5771-bb47-72052b37da82 | note | Acceptance Criteria and Frequency - No works related to the placement of paving geotextile(s) shall commence until the construction procedures have been approved by the Administrator and the Administrator has given the Contractor permission to proceed.
90115d92-848c-538c-bf42-0f9f42900b96 | note | Reference - MRTS57 Clause 5.2
07d6a995-0881-5f91-9432-695d525caeb3 | note | Item Check - Hold Point 1
51000204-232e-40aa-a240-b9b12a8d8b7f | signoff | HOLD POINT
8977221a-527f-478e-8217-613664981a57 | checkpoint | Ordering - Technical Data
c7efa944-a4a1-507f-bec7-babac399df13 | note | Acceptance Criteria and Frequency - At least 14 days prior to the proposed ordering date of any geotextile, the Contractor shall submit to the Administrator a copy of the proposed manufacturer’s technical data sheet and a sample of the proposed geotextile from the manufacturer demonstrating compliance with this Technical Specification
9d8d8c85-830a-5963-9beb-dae9258d3ff2 | note | Reference - MRTS57 Cl 8.2
4ca904ce-f43e-546e-8fcd-830a7eeb2ce5 | note | Item Check - Milestone
182f5adc-b6cb-44a4-b697-a667d90a12ff | checkpoint | Ordering
b1b10230-21a1-5dfc-914e-c44b08baa6a8 | note | Acceptance Criteria and Frequency - The Contractor shall not order any geotextile prior to the acceptance of that geotextile by the Administrator.
0ea73930-c20b-59fb-9f05-41c57337f807 | note | Reference - MRTS57 Cl 8.2
a0e2ed6e-8b9c-5cbb-9266-0c16401ed12a | note | Item Check - Hold Point 2
4c4c87d1-d191-4964-8813-c145c7b84f00 | signoff | HOLD POINT
7a6509b4-9cbb-495e-8f4b-2a08d64b62d1 | checkpoint | Delivery
25ff7904-cd7f-5d99-8d58-45bd8d5878a1 | note | Acceptance Criteria and Frequency - With each batch of geotextile incorporated in the Works, a certificate of compliance stating that the geotextile complies with all the requirements of this Technical Specification as appropriate to the application, together with test results reported on NATA endorsed test documents, shall be included in the Quality Records
40ea8ecd-59f0-5c04-bd20-c221e1c9cf1d | note | Reference - MRTS57 Cl 8.4
39ef91e7-6119-5495-8a93-e7159f967a34 | note | Item Check - Check and Verify
9b07eea2-a6b3-48ea-ad5c-7f3230e59416 | checkpoint | Surface Temperature
a4bcfc8b-06b8-5f4c-8b85-428b361b640f | note | Acceptance Criteria and Frequency - Spraying of bitumen or placement of geotextile shall not commence until the temperature of the surface of the pavement is above the temperature specified in MRTS11 Sprayed Bituminous Surfacing
e6cec66d-9be0-54bf-92ff-032b7a02c328 | note | Reference - MRTS57 Cl 9.3
454932d5-5155-5780-9285-47a73ac1b540 | note | Item Check - Check and Verify
bb380b40-2390-471a-a7f6-facf3322960d | checkpoint | Final Sign off and Approval - Conformance with the Specification
010d678f-50dc-5dc9-9e60-73ac9308f0e8 | textbox | Name of Cient's Representative
83b44fb4-8d59-5305-a14c-df6d6abcb241 | date | Date
515d1042-6441-556c-88b0-dfe438e54d36 | textbox | Name of Contractor's Representative
b69d525f-cf65-5815-9adf-557cf970d09d | date | Date
2a96c334-5cac-419c-be55-b7dbbc4cd586 | signoff | Signature
0e4ceeda-fb1b-494e-81ac-cd8df1c2e166 | section | Final Sign Offs (to be completed at closure of Lot)
2415199c-7021-4a2b-8ad9-36a2cef4f9f2 | checkpoint | Closure of Lot
41f83979-849d-42fb-9134-70cc6cf0e1ad | signoff | Closure of Lot Sign Off
2eace4a6-9716-4136-86c2-7a0f1f2b6f28 | checklist | Ω (DEPRECATED) - Hand Placed Concrete ITP | itp | ITP - Hand Placed Concrete
fc87b703-144b-4b4b-8131-868ac66f31d5 | section | Hand Placed Concrete
40351798-57d2-41c3-9645-9727ef4d9dcc | checkpoint | Design location
2043ed91-3fcb-58f9-8359-388af080b147 | note | Acceptance Criteria and Frequency - All concrete works are to be intalled in location and noted on a lot map attached to this document and accordance with the specified drawings:
8e984588-4183-589b-954f-17b49696519e | textbox | Specified Drawing:
840ac1de-38bd-5aef-be80-766282bafec3 | note | Reference - IFC Design Drawings
88540946-582b-58e2-94f4-f61900d34454 | note | Item Check - Check and Verify
d9998c20-ca99-46ba-a846-3239a22e7fd7 | checkpoint | Concrete Mix Design Submission
7c326a14-a567-55cf-a2a6-ac7d36235dff | note | Acceptance Criteria and Frequency - All mix designs shall be submitted to the administrator prior to works beginning if insufficient testing history is available for the specified mix from an approved supplier, preliminary mixes for all grades of concrete are designed, made and tested.
fe834b56-2b43-5fe9-8b42-3e4598c989ae | note | Reference - LCC SS No. 7 Part 2.3
09474e64-2031-52ab-845a-27fe38d91277 | note | Item Check - Milestone
8b1a89b8-b3c9-4f0d-83ac-96270d76452e | checkpoint | Concrete Mix Design Approval
da4e8fe8-9200-5272-9d20-e0d7cf86e597 | note | Acceptance Criteria and Frequency - Concrete Mix designs are approved prior to the usage in any works.
8b69ff13-12d5-594d-9619-415853cb8b1d | note | Reference - LCC SS No. 7 Part 2
b21a8cfd-a429-5ecf-9bd8-d452c7fd1fbd | note | Item Check - Hold Point
1e00e4e2-081d-4bf9-9bab-f2dfa26d40ed | signoff | HOLD POINT
704d8f51-ded8-441a-92ac-b90feee80c3f | checkpoint | Formwork Approval
9221c04a-6151-58b6-8420-909cf1cccb64 | note | Acceptance Criteria and Frequency - All steel reinforcement that will be used in concrete works shall be inspected and approved by the local government prior to the placement of concrete, all formwork shall be inspected and checked against formwork checklist. When forms appear to be unsatisfactory in any way, either before or during the placing of concrete, the work does not proceed until the defects have been corrected to the approval of the local government.
9eb78f71-867d-5979-89bf-c24a2e4c9443 | note | Reference - LCC SS No. 7 Part 5.3.11
24d8622c-e35e-5c74-b370-3d18055523b2 | note | Item Check - Hold Point
79a537a1-c35e-4896-89df-89319f425a54 | signoff | HOLD POINT
1012d201-3d45-4586-9362-57d2a79e4467 | checkpoint | Footpath Contraction Joint
02806d66-d4af-5cba-928b-0e81deb81f1b | note | Acceptance Criteria and Frequency - Contraction joints:
635128d4-aa04-5ae1-ba58-82af2c043fd2 | note | (a) are provided at centres matching the width of the footpath and not more than 3.0 metres;
0cfc1cfe-441f-54b8-a19d-ede6587378ff | note | (b) are formed by a jointing tool;
5f64912c-72f9-50d7-8b14-220e14afffcb | note | (c) do not exceed 35mm in depth or 6mm in width;
b352d687-190a-5d36-a89f-58f787c12bd4 | note | (d) are at right angles to the edge of the path.
d3750bbb-dafd-5427-8be9-845c3178fdf8 | note | Reference - LCC SS No. 8 Part 3.1.4
9d1e442c-9266-5a0c-b71b-9438659524a8 | note | Item Check - Check and Verify
2e2da9f6-c37a-497a-8d6d-247bdeb1141d | checkpoint | Footpath Expansion Joint
678aa56b-7fe2-5ed3-8163-91d31cf0d4c6 | note | Acceptance Criteria and Frequency - Expansion joints:
b2b52dd3-38fb-53fa-9cad-cc855e621aaa | note | (a) are placed at 15 metre centres except for 2.0m footpath which can be 16m to match dimension multiplier;
b39e3136-d25d-5163-9bde-7bb480953cb2 | note | (b) are at right angles to the edge of the path;
a5e9d489-8ce8-5c97-8672-5f9a37e7caed | note | (c) extend for the full depth of the concrete path and are 10mm in width.
f1785f08-ab2c-5de5-a890-6cf8d14419f1 | note | ○ All expansion joints shall be as per LCC specifcations or where specified in standard darwings.
8dd9adc7-e43e-52df-adc1-6d701f746241 | note | Reference - LCC SS No. 8 Part 3.1.5
5b25cbff-307a-5e1a-bb61-739d9a159766 | note | Item Check - Check and Verify
78d22673-e9b8-43fb-a89b-fa87d1f77e49 | checkpoint | Slump & Testing
5a6c7ef5-f0d3-5b27-be05-7d424afeb4fe | note | Acceptance Criteria and Frequency - All concrete poured on site shall be slump tested by a NATA certified testing contractor, all slump testing values shall be recorded by a pour record sheet and provided to the administrator with the submission of the lot. All slump values shall comply with table 2.4.1 under Standard Specification 7. All concrete shall be tested for strength, concrete is sampled and tested in accordance with AS 1012.1-1993 Methods of testing concrete - Sampling of fresh concrete, by an approved NATA registered laboratory and the results are provided to the local government.
6928adf0-50a3-5af6-9765-6c1cbbed08b5 | note | Reference - LCC SS No. 7 Part 2.4
609dae68-3ee7-585c-88f4-c401c5f22d7d | note | Item Check - Check and Verify
913e9778-8ec4-47f1-8d20-942ef8ee1ca5 | checkpoint | Temperature and Timing
3a90c25f-5e76-5986-a17b-8649db763fc7 | note | Acceptance Criteria and Frequency - Where the ambient temperature is likely to exceed 30°C, all practical precautions are taken to maintain the concrete at a temperature not exceeding 30°C at the time of placing to prevent shrinkage, settlement and presetting cracks. No concrete with a temperature higher than 30°C is placed unless otherwise approved by the local government.
9dbb79e9-38b2-50eb-93ad-f8cf4e73b855 | note | ○ Ready mixed concrete is placed and compacted within 1 hour 15 minutes of charging the mixer for concrete temperatures up to 30°C and within 30 minutes of charging the mixer.
661f4b66-8386-5360-a069-ef356369d806 | note | Reference - LCC SS No. 7 Part 4.2&4.3
11e5e91d-1794-5e62-8f9f-c9c22b59d858 | note | Item Check - Check and Verify
810bd2c8-7788-4ec9-aab4-769bbd8ad69b | checkpoint | Finishing
82d39f7a-1c79-50b0-aabb-872a4e07277b | note | Acceptance Criteria and Frequency - All surfaces of concrete that are exposed to view in the completed structure are finished such that:
8f0d1c5e-e35b-5e35-802f-5d135426842e | note | (a) Immediately after the removal of forms, all fins and other projections are ground off, all pockets and honeycombs are cleaned and filled with a stiff cement mortar having the same proportion of cement and sand as the original concrete, and the surface of the patch is ground flush;
0facc25d-110b-54fa-816a-4e55fe5aeb37 | note | (b) Decks are roughened slightly by brooming or other approved method before initial set;
624b1c1d-d244-5d8d-92db-35320dda6a3b | note | (c) Kerb and channel, invert crossings, vehicle crossings and industrial crossings are finished with an approved steel finishing tool;
82c4053b-479f-5653-b3b1-cb40c80853fa | note | (d) Footpaths and pram ramps are finished with a wooden float and broomed.
1e4559d5-5a8f-5296-804d-5a4d7ccb3057 | note | Reference - LCC SS No. 7 Part 6.1.2
e681281f-b191-5542-9221-bbaaf0fa8dde | note | Item Check - Check and Verify
c99cc001-30a3-4284-a266-fd296cf8d6bf | checkpoint | Curing
2b02549c-4a41-54a6-94a1-739ec6630a9e | note | Acceptance Criteria and Frequency - Concrete surfaces are kept moist by spraying with an approved curing compound, or water sprays or wet sand in which case the surfaces are kept moist 24 hours a day for the full period specified without any breaks at weekends or holidays. Curing is commenced immediately on completion of the finishing of exposed surfaces or within 30 minutes of removal of the forms from other surfaces.
17ae0b15-40ae-5a29-8121-fb1f4e2bada7 | note | Reference - LCC SS No. 7 Part 6.3
c2e197e9-b7e8-5a6f-8252-f75618ce8a4e | note | Item Check - Check and Verify
a50ea8d6-8bb0-48b0-bc0a-cdc848587ae1 | checkpoint | Dimension Tolerances
479624b0-777e-50a2-bb53-a4922854dea2 | note | Acceptance Criteria and Frequency - Where tolerances are not stated in the approved drawings for any individual structure or feature thereof, deviations from established lines, grades and dimensions are not greater than the tolerances listed in Table 6.4.1–Tolerances of this standard specification and are applied to the completed work.
d1fc102e-94f8-59cb-8735-90b4564bb869 | note | ○ Size of member or thickness of slab: +7mm, -0
03d541d4-6532-5715-9670-187e6d61a80c | note | ○ Cover of Concrete Over Reinforcement: +7mm, -3mm
176e6cda-6cf1-525b-8cbd-9c52035ccf5e | note | ○ Contract dimensions:
2de9aef3-6308-54bd-a9c6-e9bf57ac2ee8 | note | – 0-20meters: +7mm
e8ee63d2-e27d-5ad0-b45a-fbfd38e874f4 | note | – Over 20meters: +13mm
f0bf2453-c8ba-5308-877e-aafdeb0313e9 | note | Reference - LCC SS No. 7 Part 6.4
e3aedaa8-523c-5518-b8d7-5be047fca807 | note | Item Check - Check and Verify
2ffa8612-f22d-4163-89c1-b44763bb1310 | checkpoint | Final Sign off and Approval - Conformance with the Specification
94a67222-01ce-53e3-9a46-6b7fda45689e | textbox | Name of Cient's Representative
55881841-746b-52cd-8b9f-4fce821037e8 | date | Date
40cc8c52-92b5-5ed7-ac1c-5546074f6954 | textbox | Name of Contractor's Representative
4a5591ee-b100-5a25-bdf7-e4e943a75607 | date | Date
b41c6de6-6752-412d-8ab6-fb25dc25afed | signoff | Signature
c660d486-9ce8-4b11-b92d-d77c9b1e97ea | section | Final Sign Offs (to be completed at closure of Lot)
3d017957-0dd2-410c-917a-0fe046fad799 | checkpoint | Closure of Lot
f08e1483-eb73-48fd-9b5f-d09f0584de0e | signoff | Closure of Lot Sign Off
cdd3d221-2550-4c20-bb97-3edc31d7388e | checklist | Ω (DEPRECATED) - Installation of Kerb, Channel & Kerb and Channel ITP | itp | ITP - Installation of Kerb, Channel & Kerb and Channel
9790714c-84b0-4ef6-8df5-63c79b0b81c5 | section | Installation of Kerb, Channel & Kerb and Channel
54ad559e-71e8-4b24-8766-5fc030667b84 | checkpoint | Kerb type
faf1aa33-ace5-54f7-8b02-39e2810170e3 | note | Acceptance Criteria and Frequency - Kerb and channel complies with standard drawing number R-0080 and is one of the following profiles: B1, B2, SM5, M3, Median and Invert, and must be wet mix unless otherwise approvd by local government
35dcc80e-6561-5303-a9bf-584d00449ac8 | note | Reference - LCC SS No.8 Part 2.1
38a73c1d-efb8-51f6-83e5-8b283335f5fa | note | Item Check - Check and Verify
eb48f68b-a4a3-4a6b-8e4b-5dc0a9d28636 | checkpoint | Design and Set-Out Locations
cd650ffa-f14c-50a7-b38e-d071e4f2d46b | note | Acceptance Criteria and Frequency - Concrete for kerb and kerb and channel is 32 MPa strength grade complying with the requirements of AS 1379-2007:
51f76c8e-a00c-5582-9286-201768b38401 | note | ○ The slump values of the concrete are machine finished (wet kerb)—12mm minimum—40mm maximum.
0fc36e6c-9423-5190-94d1-55502737f094 | note | Reference - LCC SS No.8 Part 2.3
d5111b06-7e29-52ff-99c8-e548051aab0f | note | Item Check - Check and Verify
b2a203bc-3c30-4597-9640-41190830ce54 | checkpoint | Compaction of Materials
207075fe-76c4-504f-b5eb-00fe5acbe090 | note | Acceptance Criteria and Frequency - Where pavement thickness exceeds 175mm in depth, the pavement extends under the kerb where the pavement thickness does not exceed 175mm in depth, the kerb and channel is firmly bedded on 100mm road base aggregate compacted to 95 percent modified dry density as required under AS 1289.0-2000 Methods of testing soils for engineering purposes - General requirements and list of methods.
8a5cd63d-25c3-5390-87e3-69cc993abdac | note | ○ No concrete is placed until the foundations have been approved by the local government.
b8a59043-fabc-543f-b547-14d57725980a | note | Reference - LCC SS No.8 Part 2.2
ef534311-21df-5c42-bd85-0d118ede6edc | note | Item Check - Hold Point
e5213e6e-15c6-487e-9388-59daff224803 | signoff | HOLD POINT
8d7939ef-d0cf-45c7-b52c-ec4b2c4a1ea5 | checkpoint | Joining existing Kerb
a4490ea6-145a-5134-b6c1-7981fdce2e23 | note | Acceptance Criteria and Frequency - The concrete kerb or kerb and channel joins neatly with the existing kerb or kerb and channel over a minimal transitional length of 2 metres
cec094c6-3d4b-5642-9323-cd14aa56453a | note | Reference - LCC SS No.8 Part 2.5
df15df1d-c1bc-5141-aefc-3523ba84d43e | note | Item Check - Check and Verify
c58d169f-a3f9-43e4-b0f9-debf8da8ca56 | checkpoint | Expansion Joints
3f66ff61-fb0b-5cf1-9a38-3e6035a35d46 | note | Acceptance Criteria and Frequency - In the case of kerb, a joint is cut and cork jointing is inserted every 20 metres with a cut joint midway between cork joints and jointing is placed in such a manner as to dissect the kerb for its full thickness.
d24ada71-997b-5bc4-9def-485f95466559 | note | Reference - LCC SS No.8 Part 2.4
397ac0e0-8cda-5b0f-b07c-9452260ef992 | note | Item Check - Check and Verify
8e762a2e-5f11-4adc-9d4f-ca86fd231751 | checkpoint | Contraction Joints
5b55d087-0a69-5085-854f-3cd421be8460 | note | Acceptance Criteria and Frequency - A contraction joint is provided at 4 metre centres which is finished square and at right angles to the section of kerb or kerb and channel. The kerb or kerb and channel at a contraction joint is guillotined to the full depth of the concrete and re-finished with a jointing tool to form neat joint lines not exceeding 3mm in width and 6mm in depth
83033990-e15e-51dd-bad3-6b68f32a737a | note | Reference - LCC SS No.8 Part 2.4
588c58d3-fc9f-5970-aa47-6b74a82ce5f6 | note | Item Check - Check and Verify
f064d53a-5b17-42d7-9f5d-54219cdaab69 | checkpoint | Tolerances
f0a5b37b-c20d-5707-9911-cde413c9a45f | note | Acceptance Criteria and Frequency - The horizontal and vertical alignments of kerb, channel and/or kerb and channel shall not vary from those specified by more than ± 10 mm provided that the difference between the deviations from the correct levels at any two points 30 metres apart does not exceed 30mm.
1edd0d20-7829-5783-a3e9-16ed8b74b937 | note | ○ Crossfall is maintained within +/- 0.50 percent of the design
ed396b63-3bc1-5b5b-9c13-3bb1b2126a15 | note | Reference - LCC SS No.8 Part 2.4
d455529a-4f20-5be3-91ac-a99c73cd3812 | note | Item Check - Check and Verify
54e60b9a-57c7-4778-bf1c-774512efe2c5 | checkpoint | Water Test
dc337ecc-dc01-56ae-8a6b-c3b322ea7eb1 | note | Acceptance Criteria and Frequency - Notwithstanding the allowable tolerances, the invert of the channel is finished true to grade and alignment and channelling in which water is found to pond is not accepted and is removed immediately
2c229c5c-4a14-583d-a701-9f158c0789e2 | note | Reference - LCC SS No.8 Part 2.4.10
f9f75ff8-5bd2-5a66-827f-794c9abd97b6 | note | Item Check - WITNESS POINT
52f5a5bc-1ac1-46b7-a788-c224ec6791f4 | checkpoint | Final Sign off and Approval - Conformance with the Specification
2103e188-0041-5a8a-885f-1d4232466561 | textbox | Name of Cient's Representative
46431aeb-3497-5efe-9ca6-13a16be8f98c | date | Date
b11a42fd-e0e4-50d1-bfd8-b9929af6b52a | textbox | Name of Contractor's Representative
fbb3481a-ec65-5bf2-b7cd-030ca43c6c90 | date | Date
5a46c52a-da85-4b73-89e2-15cf031efd3e | signoff | Signature
18f119c1-ae50-4ad2-ad0b-408715801dd3 | section | Final Sign Offs (to be completed at closure of Lot)
4aa8dede-0b94-42b4-b1f1-654aa08407e2 | checkpoint | Closure of Lot
0027c2ec-d11f-4f54-aa2c-8bc48c1199af | signoff | Closure of Lot Sign Off
691f1085-5175-4b41-91c2-c3eebdbad371 | checklist | Ω (DEPRECATED) - Landscaping ITP | itp | ITP - Landscaping
9fd30ffb-4cf4-4f4b-9aea-eabe9d142e52 | section | Topsoil & Turf
54f95345-3cfb-4016-8ef8-a8d3aee254c9 | checkpoint | Soil Type
2fe920fd-6435-5b88-b0be-59310ae53cd6 | note | Acceptance Criteria and Frequency - Alll topsoil imported to site shall comply wiht the following below
962abaaf-6a31-5c4f-86fa-7c11cd21be9b | note | (a) is a fine soil type in accordance with Table 6.2.1–Soil type by texture of this standard specification;
ff9275e5-118e-5cea-ab58-d8c8886bf922 | note | (b) is friable;
33db5823-6ddf-52cd-a471-271a1808d8d8 | note | (c) is moderately free draining;
9785a1ae-8554-5e4e-9017-c9c2fe4c538a | note | (d) complies with AS 4419–2003 Soils for landscaping and garden use;
cd007d65-0952-537b-920d-6ff6680f9d37 | note | (e) is free of fire ants;
c1496bf1-38ee-5026-90a5-bb8319809957 | note | (f) is free from Nut Grass (Cyperus rotundus);
6c8af66d-32e9-5bf5-ad29-1a33044c9c0b | note | Reference - LCC SS No. 2 Part 6.2.2
21f6c367-f03b-5ccc-8449-f2237d3987aa | note | Item Check - Check and Verify
e8532e71-d1c3-4f25-9af8-44340a4b891c | checkpoint | Topsoil Provider
e4112bb8-4d92-5bde-9698-f1dd4da6fe94 | note | Acceptance Criteria and Frequency - Soil is imported from a source approved by the local government or is provided from material upon the premises where approved by the local government.
4ad87737-11b4-50ca-a554-81f6a6678357 | note | ○ Soil from the premises which is improved to comply with Table 6.2.1–Soil type by texture of this standard specification by the use of additives such as Gypsum, may be used as topsoil where approved by the local government.
1f92ac4f-61a1-5a56-ab52-9089dee37f99 | note | Reference - LCC SS No. 2 Part 6.2.3
0e997d2a-4024-56f2-9de3-cbe036244f86 | note | Item Check - Hold Point
ce68acfc-e89c-4b11-b0db-c549bbdc214a | signoff | HOLD POINT
1997230e-0f54-4cd6-99b4-166a765da03c | checkpoint | Spreading Topsoil
6f58026a-1bd7-5877-bb01-9d1b4ae61781 | note | Acceptance Criteria and Frequency - Soil is spread such that:
daf21908-8080-5d42-a9d1-0ce02983ddc3 | note | (a) the finished surface of the soil is smooth, free of lumps and free draining;
07baf405-fba5-59e1-a391-77924958d21f | note | (b) the finished surface levels allows for the settling and spreading of mulch;
5c77b8bc-92ff-54f5-9243-244d34da7c5a | note | (c) the soil is lightly compacted over the prepared sub-grade;
839922e1-29b2-5d9b-bfae-f20a370d4789 | note | (d) in a grassed area the edge of the soil is feathered into undisturbed ground.
1957cf2b-deea-5f3a-9f5a-6642e6d81fa0 | note | Reference - LCC SS No. 2 Part 6.2.5
bec6f81a-e86c-592a-815e-0d3f58b8204b | note | Item Check - Check and Verify
49bb7e2c-ed32-40de-bc13-9604cfff957c | checkpoint | Topsoil Finish
90205315-706f-578e-bc44-f0335383c798 | note | Acceptance Criteria and Frequency - Where soil is next to a kerb, a path, a mowing strip or other hard paved surface:
3361760b-4ff9-5cb8-a784-970f780b7507 | note | (a) the soil is finished flush for a seeded grass area and bevelled below the abutting finished grade to allow for turf or mulch;
d44f4dae-c6c7-5f9b-abda-e39d2d6306d2 | note | (b) the finished grade of the mulch is approximately 10mm below the abutting finished surface level;
05c31716-a210-5f6d-ae6b-31595e8f07b1 | note | (c) the finished surface level of the turf is flush with the abutting finished surface level;
b0de02b3-65cc-5356-a0df-c4ef48303439 | note | (d) the finished surface level of a grass area, turf and a garden bed adjacent to a building or other structure is 125mm below the weepholes in the building or the structure.
1fd2b1af-e55f-589d-af87-f4b436be9414 | note | Reference - LCC SS No. 2 Part 6.2.6
9ff8fd15-6a00-5752-82fb-343dc11fba61 | note | Item Check - Check and Verify
372812b1-7a01-4c16-b132-fcce78413b7d | checkpoint | Topsoil Depth
d57c6fb0-6100-5b69-b50b-94aee5f243e1 | note | Acceptance Criteria and Frequency - Topsoil depth is 75mm as per contract drawing GW001
c9d97ab8-9bb0-5e4b-9055-97cb75fa70a8 | note | Reference - Contract Drawings
117190ba-3c2d-55f8-9e83-7a9b461c8fa9 | note | Item Check - Check and Verify
927db4db-06a8-4128-9682-bdde0cdedbbb | checkpoint | Fertiliser
2efe4240-115e-53f3-8306-5353a71fd28a | note | Acceptance Criteria and Frequency - Fertiliser is to be applied as per manufacturer's specification to ensure healthy long term growth.
e6c0a7ec-24cd-5e0e-826c-dfb48b5cb6ef | note | Reference - LCC SS No. 2 Part 6.4.1
d1327423-e34d-568b-8735-8ca71020ae93 | note | Item Check - Check and Verify
d3832854-54e5-4ba9-8fb5-e71bffb1b25b | checkpoint | Turfed Area
30d70d28-8cd8-59fd-b0a3-4b11aa3b6f35 | note | Acceptance Criteria and Frequency - A turf roll has a minimum soil thickness of 20mm.
86993059-e1ef-544f-9428-9d6e4bd6eb4a | note | (2) The turf is delivered to the premises within 24 hours of being cut.
243ad3c4-601f-51d7-ab84-b8448598f3d2 | note | (3) The turf is laid within 36 hours of being cut.
8c5d1d48-e6e7-57a4-b4b7-a6046ff4c905 | note | (4) Where the laying of the turf is delayed, the turf is:
e6a99d0d-da83-5763-8d81-4554471ddd32 | note | (a) protected and watered to maintain its condition;
bd0c303b-8a0d-50c2-a2c4-25827a5c746a | note | (b) not allowed to dry out at any stage from cutting to laying.
c4d139c9-3d55-53ef-89df-ad30fb271c14 | note | Reference - LCC SS No. 2 Part 6.4.3
15c0bc54-958d-5f8e-93f3-0ea020139e8f | note | Item Check - Check and Verify
8620647b-c555-4d7d-88c2-0515a586c390 | section | Maintenance
de9fe89a-634d-403c-b8a8-7478220cad8e | checkpoint | General Maintenance
cb3e3c34-6245-5e7a-bcd0-c728ed470274 | note | Acceptance Criteria and Frequency - The premises is to be kept free of weeds and rubbish and any damaged, defective or stolen landscaping item is to be repaired or replaced.
ff1b52fe-ae3f-59a5-ac62-5c48c95fa02e | note | Reference - LCC SS No.3 Part 7.1
37628314-3559-5d44-a7fe-7bcfb61ba4e4 | note | Item Check - Check and Verify
76026e8c-331b-4ee3-a807-6f7406fc6893 | checkpoint | Maintenance Period
eaa02f19-9fd0-5aad-83cb-6ad0ca1551cf | note | Acceptance Criteria and Frequency - All turfef areas are maintained through the maintenance period such that at the end of the establishment period a turfed area has 100 percent of turf coverage, the plant estabblishment period is a minimum period of 12 weeks from the date that PC is approved.
47868576-22cf-5c3b-b207-fd51cdb58aea | note | Reference - LCC SS No.3 Part 7.3
82e29511-2615-5df4-9bdd-424c87351050 | note | Item Check - Check and Verify
cd83b992-61db-4dff-948c-18e0236ab917 | checkpoint | Maintenance of Turf
d283b9d0-57a6-5395-ab72-764d97cd9ea5 | note | Acceptance Criteria and Frequency - A grassed area is maintained during the maintenance period by:
69dfbf79-ed89-5df0-9918-5fbd3b694a60 | note | (a) mowing grass to 50mm height when grass has grown no higher than 75mm and removing grass clippings from the landscape area or as otherwise approved by the local government;
14ff4a30-a8ea-5833-8bfb-8924066f5b09 | note | (b) applying water at regular intervals to ensure ongoing healthy growth
d7bc6a57-ce52-50f7-9f24-bff6716e58fe | note | Reference - LCC SS No.3 Part 7.4.2
78df162d-bd3a-5951-9637-d98b3872f35d | note | Item Check - Check and Verify
7517668d-4ca6-446a-81c2-68ae360fffb9 | checkpoint | Maintenance Program
21fc98de-2cd0-5989-beb7-38e857f7572a | note | Acceptance Criteria and Frequency - The Maintenance Program is to be prepared by the Contractor and submitted to the Superintendent for approval prior to commencement of work under the Contract and is to contian details about the frequency which the contractor proposes to carry out its obligation under section 7.4 SS 2
0e52bfe7-e00c-5cac-829d-4d513dd7f19a | note | Reference - LCC SS No.7 Part 8.3.4
efca10b6-f51b-5aee-b750-1ed8a3641696 | note | Item Check - Milestone/ Hold Point
dfa3f3df-0df1-46c2-bb33-74b04ffa188c | signoff | HOLD POINT
ffdb3097-41be-4394-8e6b-a22fd867861a | checkpoint | Final Sign off and Approval - Conformance with the Specification
2ae0e6a1-7bbd-529c-ada8-274bfbe5966b | textbox | Name of Cient's Representative
b8335759-a310-5fb1-b311-ad2271bd4c92 | date | Date
414bb2cc-f8a7-5425-8e89-5135726e0189 | textbox | Name of Contractor's Representative
212dfcee-5129-5090-a65c-20f106fab5f7 | date | Date
cf1b43e1-0d4a-4eff-ac90-25a1f753391d | signoff | Signature
c862864b-dfe5-403b-9017-05e82c26680d | section | Final Sign Offs (to be completed at closure of Lot)
f70383b3-9220-4a1e-bfed-660c47fd754a | checkpoint | Closure of Lot
ac687c21-3402-4b94-bdda-691b9408a263 | signoff | Closure of Lot Sign Off
7b21cca0-3a63-4228-b3e0-e41f46e28e3a | checklist | Ω (DEPRECATED) - Reinforced Concrete Pipe ITP | itp | ITP - Reinforced Concrete Pipe
f5d677ed-82e9-4e78-b232-3141e227e938 | section | Reinforced Concrete Pipe Works
7694cee0-b210-4425-b81d-a051d470f1e0 | checkpoint | General
ddb94ccc-e36b-595a-9a02-18fdff84cca5 | note | Acceptance Criteria and Frequency - All reinforced concrete pipes and pit shall be as per drawings unless an alternitive is approved, all pipes shall be laid in location and to levels specified in drawings.
990176e2-66ae-5061-b993-90dfa999cc21 | note | ○ Drawings specify
dc46f25b-637b-5d17-9dc3-859671266ce5 | note | Reference - General
5dfd69f5-bcdd-5ef9-851e-c7fd04241575 | note | Item Check - Check and Verify
be5f74da-2540-4205-b414-c9deb4072606 | checkpoint | Material Conformance
2c8d8fc1-8ed5-55bc-a51c-e53343a80aa8 | note | Acceptance Criteria and Frequency - Unless otherwise noted on the approved drawings all pipes are Class 2 and comply with the requirements of AS 4058–2007 and all matrial conformnace data shall be included in the lot submission to the administrator.
9a29dc34-dadd-58eb-95a5-590cd15e6caa | note | Reference - LCC SS No.3 Part 2.1
82b6c189-542c-500e-8c9a-efd8cf630b25 | note | Item Check - Check and Verify
4ba3f01e-32bc-42c6-9d95-d2d71115aff7 | checkpoint | Construction
075ef688-8a29-5b11-bf8f-70862c22235a | note | Acceptance Criteria and Frequency - All RCP will be constructed as per IPWEA-STD-DS-030 which covers excavation, bedding material and backfilling
9c9e71e8-0bad-5ee7-91be-f5f5575f4984 | note | ○ Bottom of excavation shall be compacted to a 95% standard compaction unless insitu material is rock for all excavations.
5ca35146-b41a-528b-9f2a-ac2e2daebf46 | note | ○ Backfill material shall be either 5 or 10mm aggregate.
34c04ba8-b578-580e-98cf-d2e277c21d7b | note | Reference - LCC SS No.3 Part 6.3
1a47d613-003a-5a6d-822f-0ffbe87108ca | note | Item Check - Check and Verify
437ccfaa-4ef9-4091-b410-a1c62fdf87d4 | checkpoint | Pipe Laying
0c9a21e5-fa34-5eaf-b90e-420d84d6f1f6 | note | Acceptance Criteria and Frequency - Pipes are laid true to line and grade, and are free draining and firmly bedded and are laid from the discharge end upstream to the following tolerances:
21b4cbdd-1617-5bf6-9be3-2fac12782f77 | note | – invert levels - ±50mm;
bbb8ac9c-7589-5c5b-b176-9a509ff91cc1 | note | – gully locations - within 300mm of design.
0dcd18f3-da1d-560a-bb5b-4004d46deeee | note | ○ For pipes up to and including 600mm diameter, the socketed end of the pipe is laid upstream and a shallow excavation is made under the socket of each pipe so that the pipe fully rests for its full length of barrel upon the bedding material in the trench.
06fb3e23-8408-589b-9934-af79a50c2f34 | note | Reference - LCC SS No.3 Part 4.2
bb8e9227-afce-5205-824e-02a94efcce51 | note | Item Check - Check and Verify
dffbe2c4-1830-4545-9da4-a3f1a230f3f1 | checkpoint | Construction - Backfilling
3236e555-9f0b-55fb-ae97-a01c83c68ea4 | note | Acceptance Criteria and Frequency - Pipe is not to be backfilled without being inspected and approved by administrator.
7a42f4ca-92e7-583d-8380-df5b6037f081 | note | Reference - LCC SS No.3 Part 5.1
5d5c76e9-820b-57a2-a0a0-de1290b0e787 | note | Item Check - Hold Point
56ead252-913d-45f0-a563-31e1aeb4f89c | signoff | HOLD POINT
445d6773-0cc1-44cc-96d7-3e9f50c5aa94 | checkpoint | Backfilling Material
9ad8c4b2-0a6e-5a67-a049-6e73fb941959 | note | Acceptance Criteria and Frequency - Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in part 4 of Standard specification 3 and conforms with table 4.1.1 Bedding Material
d7558804-858e-55e4-8bd3-327a296792ee | note | Reference - LCC SS No.3 Part 4.1
24b47b9d-a23d-52c1-adce-71591e9820d7 | note | Item Check - Hold Point/ Witness Point
f2595b55-ff3e-449b-8cec-e104eceb756c | signoff | HOLD POINT
ac0d221a-3c78-424b-8e9c-9f86dd53a3ae | checkpoint | Backfilling Under Proposed Pavements
9ed1c894-3dfb-5165-ad1e-37d013d0b19e | note | Acceptance Criteria and Frequency - backfilled with approved material of minimum 4 day soaked California bearing ratio of 15 and compacted to 100 percent standard compaction.
f4d63cc1-85cd-5d63-9f22-a7a8b490fab6 | note | Reference - LCC No.3 Part 5.2.1.(a)
fdfb6d88-7676-544f-87e9-8dfa1b08c146 | note | Item Check - Check and Verify
1350055b-9d6e-4869-8994-24eaed14415f | checkpoint | Pipe Laying Compliance Testing
4530fee1-04aa-56a0-8ed8-81ae3980d433 | note | Acceptance Criteria and Frequency - All pipes lines are subject to internal inspection and approval, the inspection of all pipes is carried out using a remote controlled video camera and is submitted to the local government before being accepted on-maintenance. A report on the findings of a remote controlled video camera inspection is to be submitted to the local government in an electronic format suitable for utilisation in “Sewer Rat” compatible applications. Pipes must not show clearly visible cracks of more than one millimetre for a length of 300mm or more on the inside.
9a903f54-54e2-5b83-aa40-753f82d5afad | note | Reference - LCC SS No.3 Part 4.4
16ee5aff-e132-56d7-88fd-85ec2851b21b | note | Item Check - Hold Point
fdfa6706-0378-4008-aae3-e3a46ea51873 | signoff | HOLD POINT
93708d47-6c24-4c20-a06c-81cdd44dc420 | section | Insitu Gully Pit Works
ef8c7c25-a259-41b6-be91-934deda809aa | checkpoint | General
6b9941cf-95a0-513f-bb2d-fa50c03ff4f8 | note | Acceptance Criteria and Frequency - A drainage structure includes all work and materials necessary for the construction of gullies, inlet pits and manholes, including excavation, concrete rendering and all necessary frames, curves, gratings, precast units and surrounds, precast troughs, chambers, lintels and shafts for side entry gullies, as specified in the approved drawings and standard drawings.
b6b06191-cd8a-5da5-8f8f-3d3cd4b9e3bb | note | ○ IPWEA-STD-DS-60
fa618c96-480d-549d-b39e-509f65a5a9e1 | note | Reference - LCC SS No.3 Part 6.1
7f138571-7434-56b9-b381-9d3f8a57b329 | note | Item Check - Check and Verify
ff125cbf-dd9a-46e7-8790-e2b4c99d9c1a | checkpoint | Materials - Gully Pit
7e3dc528-47de-5cdc-acff-2ac178d9b871 | note | Acceptance Criteria and Frequency - All materials used in insitu drainage structure will ne N32 class concrete or otherewise specified.
cfe07c1e-c753-5b98-a3a4-4e3e07d50e39 | textbox | Concrete mix used -
be356185-82c9-531c-899e-e4a8e4467163 | note | Reference - LCC SS No.3 Part 6.2
0b18123b-1cb2-5bda-8968-d0d75b5f6a9d | note | Item Check - Check and Verify
aca57f99-d13b-4545-be8d-d8fa5b4c0037 | checkpoint | Formwork Approval
6d3cdc62-c58c-5648-bdbd-a2c2f7d639a1 | note | Acceptance Criteria and Frequency - All concrete is placed in dry conditions and no concrete is placed until the formwork, falsework, and reinforcing materials have been inspected and approved by the local government.
e4349d31-879e-5e81-aeca-6db72fa0c6e5 | note | Reference - LCC SS No.7 Part 4.1.1
f362051e-1730-52b0-bf44-bec581a6c4e6 | note | Item Check - Hold Point
2e84fb45-9281-4f42-b59c-e940d55ec0de | signoff | HOLD POINT
0608ded7-cd03-4359-804e-cd7be78ae4e4 | checkpoint | Construction of Gully Pit
e1ebfcc0-4000-5a41-a542-f21ca1d99c16 | note | Acceptance Criteria and Frequency - Where the sides of the excavation are deemed to be in solid ground shafts may be constructed without the use of backforms, where concrete is placed without backforms the specified wall thickness is increased by 50mm minimum and not greater than 300mm of the design thickness. The finished concrete surface shall have smooth even and neat edges and will be shaped per the design intent.
93da4af4-042b-51b6-869f-0f150c2bee04 | note | Reference - LCC SS No.3 Part 6.3
57cb8042-9fed-508e-a43b-894fb46b0518 | note | Item Check - Check and Verify
5058e2ac-081c-4f68-9a7f-de608d59d860 | checkpoint | Final Sign off and Approval - Conformance with the Specification
43252244-9d05-585d-ada5-b3b05bca0fd5 | textbox | Name of Cient's Representative
7441126d-66fc-5f13-8fc1-527fb055b7ec | date | Date
92768728-e1d0-5d35-8342-75e0e38f5514 | textbox | Name of Contractor's Representative
3a47900b-44e6-55c1-befa-054384f4948d | date | Date
6c6563ea-6bf3-43b7-93ac-fc7f8418e8c7 | signoff | Signature
3ee6b7d9-fe04-475d-be5b-77c35501d689 | section | Final Sign Offs (to be completed at closure of Lot)
8e7303e0-b27c-4e65-965c-c3c3bde37cbf | checkpoint | Closure of Lot
1d952ef2-93e4-43c9-8300-c0b338c0f6ac | signoff | Closure of Lot Sign Off
633cf358-6c24-4d42-aec4-1ca1fb1a20ce | checklist | Ω (DEPRECATED) - Subsoil Drains ITP | itp | ITP - Subsoil Drains
766b5fbf-4db4-4d5b-8d9e-3e2d46113126 | section | Subsoil Drains
f22c20af-f557-491e-bd8e-84ebeda811e8 | checkpoint | Material Requirements - Standard subsoil drains
94d88664-ebd1-56fc-b981-89ef0822bd7a | note | Acceptance Criteria and Frequency - A sub-soil drainage pipe is a class 400 perforated corrugated PVC pipe Type 1 in accordance with AS 2439.1-2007 Perforated plastics drainage and effluent pipe and fittings - Perforated drainage pipe and associated fittings.
3413f472-63bf-500e-aa81-5f7b9b9c93c8 | note | ○ The diameter of a sub-soil drainage pipe is a minimum of 100mm and the perforations do not exceed 1.1mm in width and 7.4mm in length.
30bf2fcb-8e72-55f8-8939-e0ec128bdc47 | note | Reference - LCC SS 12 Part 2.5
2b9ecf36-5982-51f8-8676-e834d9274e4e | note | Item Check - Check and Verify
cceb198b-242f-463b-9e54-3a3937e4e238 | checkpoint | Longitudinal subsoil drain in pavement
f214af88-5b26-5504-816a-6451792f840b | note | Acceptance Criteria and Frequency - Where a kerb and channel is constructed a sub-soil drainage pipe is constructed:Standard specification No. 12 (Sub-soil drainage) Ss12-2
49f46f0a-6844-5523-8388-d833eaabc43f | note | (a) immediately below the back of the kerb in accordance with standard drawing IPWEAQ R-0140,
45c74ca8-f762-5e08-ac50-f98bd0310d32 | note | (b) at least 150mm below the finished sub-grade level
d4023798-e942-51bd-9c49-796b0d2a339a | note | Reference - LCC SS 12 Part 2.2
c612792a-9029-5ec4-8eef-43f230f7eb43 | note | Item Check - Check and Verify
124288d7-6f29-4248-a766-2422560f4284 | checkpoint | Subsoil Drain Excavation
8c755a8f-635a-51bf-93ab-e7e6b8972fe9 | note | Acceptance Criteria and Frequency - A trench for a sub-soil drainage pipe is excavated to 50mm below the invert level of the sub-soil drainage pipe and have a gradient which is specified in the approved drawings or which is a minimum of 0.5 percent. the excavated trench is to be a minimum of 100mm wider than the outside diameter of the sub-soil drainage pipe.
11787540-591b-59e1-98e2-6b91ea7231c5 | note | Reference - LCC SS 12 Part 2.4
622c1df2-edd1-5e8c-a1b7-8c9cfb1c1b96 | note | Item Check - Check and Verify
f2cdfeb9-d161-420b-a7a7-ff82edf0eece | checkpoint | Filter Material
280a5054-a5a5-53c7-a474-1f5107f5e931 | note | Acceptance Criteria and Frequency - Fileter material shall be either 5mm or 10mm drainage aggregate as per standard drawing IPWEA - RS - 140
06658740-22cb-5b17-9e59-b2abb40e5f5c | note | Reference - IPWEA-RS-140
efeaf81a-e067-57bb-b822-41cbe6c4f1d7 | note | Item Check - Check and Verify
c4b98dd5-7bcd-4263-a590-c17f3fe09135 | checkpoint | Subsoil drain outlet
1ad2a2ca-f603-5935-afe8-82ebf9eac6dc | note | Acceptance Criteria and Frequency - A sub-soil drainage pipe: shall be connected to a gully pit, as specified in standard drawing IPWEAQ R-0140; or discharges to a culvert head wall or an open channel below the edge of the road shoulder or at the edge of an embankment.
71472633-97d3-5674-b3e3-dcfc4fc084c1 | note | (a) If a sub-soil drainage pipe is not connected into a gully pit or a culvert headwall, a concrete headwall is provided to the sub-soil drainage pipe.
dc6d7069-383a-568e-b7e9-54f64450a9c6 | note | (b) The headwall is at least 100mm thick and extends for a minimum of 150mm on all sides of the pipe.
6cdcfe12-4d8c-5787-910e-b8974bc7dc48 | note | (c) Where the outlet is through a batter, the surface of the headwall conforms to the batter slope.
182f2d51-07a2-586e-b284-200a36a68c0c | note | Reference - LCC SS 12 Part 4.3
eb9b0632-098a-5b1e-81a1-4b2794130ab3 | note | Item Check - Check and Verify
5bf11cfc-bfdc-419b-a1e3-6fe7af359da6 | checkpoint | Final Sign off and Approval - Conformance with the Specification
9f1224c1-d630-5ded-b4e6-fb02adab1955 | textbox | Name of Cient's Representative
9481793a-313c-5772-bd9b-90d7a5b084df | date | Date
708ee893-d309-5709-85f3-85c4ad2eb977 | textbox | Name of Contractor's Representative
2a063165-5600-593f-95c3-95d595dc48bf | date | Date
e4293ddc-f7cf-4e08-83e1-280a3f2753de | signoff | Signature
cdc3ddfd-61e6-4adf-b622-11ef51763881 | section | Final Sign Offs (to be completed at closure of Lot)
b560e0b4-5acd-4e39-95dd-b2a182257849 | checkpoint | Closure of Lot
7ca9c45a-20db-4b67-8471-19d56f87119f | signoff | Closure of Lot Sign Off