## Table 1
Trade/Supply Item: | Hydraulics – Stormwater | Contractor: Head Contractor: | Fluid Contracting BESIX Watpac | Location of Works:
Reviewed by: Blake Newton Project Manager: Mick Patterson Contact: 0417 162 226 Date: 19/03/2025 |  | Applicable Standards Specifications, Design Documentation and AS/NZS Standards |  | INSPECTIONS & VERIFICATION
WORK ACTIVITY/ SEQUENCE | REFERENCE (Aust. Standard No., Contract Clause, DRW No, Manufacturers Recommendations, BCA, DA etc) | ACCEPTANCE CRITERIA (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc) |  | Subcon -tractor | Date |  | Initial | Witness (Subcon -tractor) | Date |  | Inital | Comments / Records Record changes required to meet specification e.g. variation #, RFI #, alternative (material, process etc) used, sample approved on (date), NCR #., test reports, survey data, written approvals (letter reference)
SCOPE OF WORK | Subcontract documentation, specifications, design documentation and issued for construction drawings | Check documents are current & for construction Check levels & falls |  | S |  |  |  | S
COMPETENCY | Recognised Australian Authorities | Trade registration |  | S |  |  |  | S
SET OUT | Subcontract documentation, specifications, design documentation and issued for construction drawings | Mark out pipe locations and co-ordinate with other trades. |  | S |  |  |  | S
PIPE SUPPORTS | Subcontract documentation and AS3500.2 Table 9.1 | Pipes to be supported as per AS3500.2 Table 9.1 |  | S |  |  |  | S
PIPE LAYING | Subcontract documentation AS3500.3 Clause 7.4.2 | Pipes to be laid in straight lines between changes of directions. Pipes are to be laid on base of crushed hard rock or coarse washed sand. |  | S |  |  |  | S
PIPING | Subcontract documentation | Check that all sealants & adhesives are compatible with pipe materials. Pipework selection and sizes as per specifications and for construction drawings and AS 3500. Verification that delivered products are as per specification & approved samples. |  | S |  |  |  | S
MARKING & LABELING | Subcontract documentation, specifications, design documentation and issued for construction drawings | Underground pipework to have identification tape installed. |  | S |  |  |  | S
PITS | Specifications, design documentation and issued for construction drawings | Pits to have smooth, seamless finish using steel trowel or concrete cast in steel frames. Design and for construction drawings |  | S |  |  |  | S
TESTING | Subcontract documentation and AS3500.3 section 10 | Hold/Witness point, invitation to inspect Hydrostatic Testing. |  | WS |  |  |  | S
BACKFILL COMPACTION | Subcontract documentation | Pipes are to be laid on base of crushed hard rock or coarse washed sand. The balance of the trench to be filled and compacted with selected removed spoil. |  | WS |  |  |  | S
FINAL TRIM/ CLEAN SITE | Area cleaned and fit for following trade commencement. | Final clean and grade site area affected by the Stormwater scope of works Excess spoil removed from site by as per contract terms |  | S |  |  |  | S
FINAL INSPECTION / COMPLETION | Subcontract documentation | Verify all inspections, complete records clean and flush entire installation. CCTV of all completed pipe work. Submission to be completed and submitted to BESIX Watpac. |  | WS |  |  |  | S
RECORD DRAWINGS | Subcontract documentation | Provide Requirement as per contract documentation including Dimensioned, Surveyed, Falls, Locations and Components. Provide verifications of testing. Hydraulic Consultant (LCI) invitation to inspect. |  | H |  |  |  | S
Note: Signatures & dates are required under “Inspections and Verification” column. Do not just tick! When preparing the ITP, consider consequences of failure such as cost of remedial work, effect on construction program, accessibility for rectification, disruption to use of building, consequential damage to other elements, threat to safety of workers & public, breach of legal or other regulatory requirements. | [5 empty] | H = Hold Point Work cannot proceed without verification/approval by another party |  |  |  | W = Witness A point where another party may inspect or test. (eg. contract requirements for |  |  | S =Sign-off Verification of quality of work, conformance with specification etc