## Table 1
Trade/Supply Item: | Hydraulics – Inground Sewer Drainage | Contractor: Head Contractor: | Fluid Contracting BESIX Watpac | Location of Works:
Reviewed by: Blake Newton Project Manager: Mick Patterson Contact: 0417 162 226 Date: 19/03/2025 |  | Applicable Standards Specifications, Design Documentation and AS/NZS Standards |  | INSPECTIONS & VERIFICATION
WORK ACTIVITY/ SEQUENCE | REFERENCE (Aust. Standard No., Contract Clause, Dwg No, Manufacturers Recommendations, BCA, DA etc) | ACCEPTANCE CRITERIA (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc) |  | Subcon -tractor | Date | Initial | Witness (Subcon -tractor) | Date |  | Initial | Comments / Records Record changes required to meet specification eg variation #, RFI #, alternative (material, process etc) used, sample approved on (date), NCR #., test reports, survey data, written approvals (letter reference)
SCOPE OF WORK | Subcontract documentation, For construction drawings | Check documents are current & for construction Check levels & falls |  | S |  |  | HS
COMPETENCY |  | Trade Registration |  |  |  |  | S
SET OUT | Subcontract documentation, For construction drawings | Mark out pipe locations and co-ordinate with other trades |  | W |  |  | S
EXCAVATION | Subcontract documentation | Excavate trenches to minimal size Grade Trenches to Falls Bed pipes on 10mm – blue metal |  | W |  |  | S
PIPEWORK | Subcontract documentation. Check that delivered products are as per specification & approved samples | UPVC Pipework Jointing methods as per specification. Note that all sealants have been checked for compatibility with materials |  | W |  |  | S
PITS | Subcontract documentation, For construction drawings | Adequate Protection Installation as per specification |  | W |  |  | S
SEWER CONNECTION | Subcontract documentation | Connection permit received Authority procedures followed |  | W |  |  | S
BACKFILL COMPACTION | Subcontract documentation. Hold/Witness point, all inground sewer to be inspected prior to backfill | Backfill pipe with 10mm blue metal then backfill with selected excavated material. Reference to adequate compaction in accordance with AS 1289 |  | S |  |  | S
FINAL TRIM/ CLEAN SITE | Area cleaned and fit for following trade commencement | Final clean and grade site area affected by the stormwater scope of works Excess Spoil removed from site by others |  | W |  |  | S
FINAL INSPECTION |  | Hydraulic Consultant (LCI) notification and witness point where required. Verify all inspections, complete records. CCTV inspection of all complete Sewer installations |  | S |  |  | HS
Note: Signatures & dates are required under “Inspections and Verification” column. Do not just tick ! When preparing the ITP, consider consequences of failure such as cost of remedial work, effect on construction program, accessibility for rectification, disruption to use of building, consequential damage to other elements, threat to safety of workers & public, breach of legal or other regulatory requirements. | [5 empty] | H = Hold Point Work cannot proceed without verification/approval by another party |  |  | W = Witness A point where another party may inspect or test. (eg. contract requirements for |  |  | S =Sign-off Verification of quality of work, conformance with specification etc