## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP No 07 - Hydraulics - Stormwater | [5 empty] | FCQA - ITP No 07 Rev. 002 - Hydraulics - Stormwater
section | Hydraulics - Stormwater
checkpoint | SCOPE OF WORK
label | REFERENCE - Subcontract documentation, specifications, design documentation and issued for construction drawings
label | ACCEPTANCE CRITERIA - Check documents are current & for construction Check levels & falls
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | COMPETENCY
label | REFERENCE - Recognised Australian Authorities
label | ACCEPTANCE CRITERIA - Trade registration
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | SET OUT
label | REFERENCE - Subcontract documentation, specifications, design documentation and issued for construction drawings
label | ACCEPTANCE CRITERIA - Mark out pipe locations and co-ordinate with other trades.
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | PIPE SUPPORTS
label | REFERENCE - Subcontract documentation and AS3500.2 Table 9.1
label | ACCEPTANCE CRITERIA - Pipes to be supported as per AS3500.2 Table 9.1
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | PIPE LAYING
label | REFERENCE - Subcontract documentation AS3500.3 Clause 7.4.2
label | ACCEPTANCE CRITERIA - Pipes to be laid in straight lines between changes of directions. Pipes are to be laid on base of crushed hard rock or coarse washed sand.
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | PIPING
label | REFERENCE - Subcontract documentation
label | ACCEPTANCE CRITERIA - Check that all sealants & adhesives are compatible with pipe materials.
label | ○ Pipework selection and sizes as per specifications and for construction drawings and AS 3500.
label | ○ Verification that delivered products are as per specification & approved samples.
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | MARKING & LABELING
label | REFERENCE - Subcontract documentation, specifications, design documentation and issued for construction drawings
label | ACCEPTANCE CRITERIA - Underground pipework to have identification tape installed.
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | PITS
label | REFERENCE - Specifications, design documentation and issued for construction drawings
label | ACCEPTANCE CRITERIA - Pits to have smooth, seamless finish using steel trowel or concrete cast in steel frames. Design and for construction drawings
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | TESTING
label | REFERENCE - Subcontract documentation and AS3500.3 section 10
label | ACCEPTANCE CRITERIA - Hold/Witness point, invitation to inspect Hydrostatic Testing.
label | SUBCONTRACTOR - WS
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | BACKFILL COMPACTION
label | REFERENCE - Subcontract documentation
label | ACCEPTANCE CRITERIA - Pipes are to be laid on base of crushed hard rock or coarse washed sand. The balance of the trench to be filled and compacted with selected removed spoil.
label | SUBCONTRACTOR - WS
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | FINAL TRIM/ CLEAN SITE
label | REFERENCE - Area cleaned and fit for following trade commencement.
label | ACCEPTANCE CRITERIA - Final clean and grade site area affected by the Stormwater scope of works
label | ○ Excess spoil removed from site by as per contract terms
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | FINAL INSPECTION / COMPLETION
label | REFERENCE - Subcontract documentation
label | ACCEPTANCE CRITERIA - Verify all inspections, complete records clean and flush entire installation.
label | ○ CCTV of all completed pipe work. Submission to be completed and submitted to BESIX Watpac.
label | SUBCONTRACTOR - WS
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | RECORD DRAWINGS
label | REFERENCE - Subcontract documentation
label | ACCEPTANCE CRITERIA - Provide Requirement as per contract documentation including Dimensioned, Surveyed, Falls, Locations and Components. Provide verifications of testing.
label | ○ Hydraulic Consultant (LCI) invitation to inspect.
label | SUBCONTRACTOR - H
label | WITNESS (SUBCONTRACTOR) - S
holdpoint | HOLD POINT
checklist | ITP No 13 - Hydraulics - Inground Sewer Drainage | [5 empty] | FCQA - ITP No 13 Rev. 002 - Hydraulics - Inground Sewer Drainage
section | Hydraulics - Inground Sewer Drainage
checkpoint | SCOPE OF WORK
label | REFERENCE - Subcontract documentation, For construction drawings
label | ACCEPTANCE CRITERIA - Check documents are current & for construction Check levels & falls
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - HS
holdpoint | HOLD POINT
checkpoint | COMPETENCY
label | ACCEPTANCE CRITERIA - Trade Registration
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | SET OUT
label | REFERENCE - Subcontract documentation, For construction drawings
label | ACCEPTANCE CRITERIA - Mark out pipe locations and co-ordinate with other trades
label | SUBCONTRACTOR - W
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | EXCAVATION
label | REFERENCE - Subcontract documentation
label | ACCEPTANCE CRITERIA - Excavate trenches to minimal size Grade Trenches to Falls
label | ○ Bed pipes on 10mm – blue metal
label | SUBCONTRACTOR - W
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | PIPEWORK
label | REFERENCE - Subcontract documentation.
label | ○ Check that delivered products are as per specification & approved samples
label | ACCEPTANCE CRITERIA - UPVC Pipework
label | ○ Jointing methods as per specification.
label | ○ Note that all sealants have been checked for compatibility with materials
label | SUBCONTRACTOR - W
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | PITS
label | REFERENCE - Subcontract documentation, For construction drawings
label | ACCEPTANCE CRITERIA - Adequate Protection Installation as per specification
label | SUBCONTRACTOR - W
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | SEWER CONNECTION
label | REFERENCE - Subcontract documentation
label | ACCEPTANCE CRITERIA - Connection permit received Authority procedures followed
label | SUBCONTRACTOR - W
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | BACKFILL COMPACTION
label | REFERENCE - Subcontract documentation.
label | ○ Hold/Witness point, all inground sewer to be inspected prior to backfill
label | ACCEPTANCE CRITERIA - Backfill pipe with 10mm blue metal then backfill with selected excavated material.
label | ○ Reference to adequate compaction in accordance with AS 1289
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | FINAL TRIM/ CLEAN SITE
label | REFERENCE - Area cleaned and fit for following trade commencement
label | ACCEPTANCE CRITERIA - Final clean and grade site area affected by the stormwater scope of works
label | ○ Excess Spoil removed from site by others
label | SUBCONTRACTOR - W
label | WITNESS (SUBCONTRACTOR) - S
checkpoint | FINAL INSPECTION
label | ACCEPTANCE CRITERIA - Hydraulic Consultant (LCI) notification and witness point where required.
label | ○ Verify all inspections, complete records.
label | ○ CCTV inspection of all complete Sewer installations
label | SUBCONTRACTOR - S
label | WITNESS (SUBCONTRACTOR) - HS
holdpoint | HOLD POINT