## Sheet1
SCOPE OF WORK | Subcontract documentation, specifications, design documentation and issued for construction drawings | Check documents are current CHAR(AMP) for construction Check levels CHAR(AMP) falls | S | S | SCOPE OF WORK | REFERENCE - Subcontract documentation, specifications, design documentation and issued for construction drawings | ACCEPTANCE CRITERIA - Check documents are current CHAR(AMP) for construction Check levels CHAR(AMP) falls | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | SCOPE OF WORK
COMPETENCY | Recognised Australian Authorities | Trade registration | S | S | COMPETENCY | REFERENCE - Recognised Australian Authorities | ACCEPTANCE CRITERIA - Trade registration | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | REFERENCE - Subcontract documentation, For construction drawings
SET OUT | Subcontract documentation, specifications, design documentation and issued for construction drawings | Mark out pipe locations and co-ordinate with other trades. | S | S | SET OUT | REFERENCE - Subcontract documentation, specifications, design documentation and issued for construction drawings | ACCEPTANCE CRITERIA - Mark out pipe locations and co-ordinate with other trades. | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | ACCEPTANCE CRITERIA - Check documents are current CHAR(AMP) for construction Check levels CHAR(AMP) falls
PIPE SUPPORTS | Subcontract documentation and AS3500.2 Table 9.1 | Pipes to be supported as per AS3500.2 Table 9.1 | S | S | PIPE SUPPORTS | REFERENCE - Subcontract documentation and AS3500.2 Table 9.1 | ACCEPTANCE CRITERIA - Pipes to be supported as per AS3500.2 Table 9.1 | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | SUBCONTRACTOR - S
PIPE LAYING | Subcontract documentation AS3500.3 Clause 7.4.2 | Pipes to be laid in straight lines between changes of directions. Pipes are to be laid on base of crushed hard rock or coarse washed sand. | S | S | PIPE LAYING | REFERENCE - Subcontract documentation AS3500.3 Clause 7.4.2 | ACCEPTANCE CRITERIA - Pipes to be laid in straight lines between changes of directions. Pipes are to be laid on base of crushed hard rock or coarse washed sand. | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | WITNESS (SUBCONTRACTOR) - HS
PIPING | Subcontract documentation | Check that all sealants CHAR(AMP) adhesives are compatible with pipe materials. Pipework selection and sizes as per specifications and for construction drawings and AS 3500. Verification that delivered products are as per specification CHAR(AMP) approved samples. | S | S | PIPING | REFERENCE - Subcontract documentation | ACCEPTANCE CRITERIA - Check that all sealants CHAR(AMP) adhesives are compatible with pipe materials. Pipework selection and sizes as per specifications and for construction drawings and AS 3500. Verification that delivered products are as per specification CHAR(AMP) approved samples. | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | COMPETENCY
MARKING CHAR(AMP) LABELING | Subcontract documentation, specifications, design documentation and issued for construction drawings | Underground pipework to have identification tape installed. | S | S | MARKING CHAR(AMP) LABELING | REFERENCE - Subcontract documentation, specifications, design documentation and issued for construction drawings | ACCEPTANCE CRITERIA - Underground pipework to have identification tape installed. | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | REFERENCE -
PITS | Specifications, design documentation and issued for construction drawings | Pits to have smooth, seamless finish using steel trowel or concrete cast in steel frames. Design and for construction drawings | S | S | PITS | REFERENCE - Specifications, design documentation and issued for construction drawings | ACCEPTANCE CRITERIA - Pits to have smooth, seamless finish using steel trowel or concrete cast in steel frames. Design and for construction drawings | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | ACCEPTANCE CRITERIA - Trade Registration
TESTING | Subcontract documentation and AS3500.3 section 10 | Hold/Witness point, invitation to inspect Hydrostatic Testing. | WS | S | TESTING | REFERENCE - Subcontract documentation and AS3500.3 section 10 | ACCEPTANCE CRITERIA - Hold/Witness point, invitation to inspect Hydrostatic Testing. | SUBCONTRACTOR - WS | WITNESS (SUBCONTRACTOR) - S | SUBCONTRACTOR -
BACKFILL COMPACTION | Subcontract documentation | Pipes are to be laid on base of crushed hard rock or coarse washed sand. The balance of the trench to be filled and compacted with selected removed spoil. | WS | S | BACKFILL COMPACTION | REFERENCE - Subcontract documentation | ACCEPTANCE CRITERIA - Pipes are to be laid on base of crushed hard rock or coarse washed sand. The balance of the trench to be filled and compacted with selected removed spoil. | SUBCONTRACTOR - WS | WITNESS (SUBCONTRACTOR) - S | WITNESS (SUBCONTRACTOR) - S
FINAL TRIM/ CLEAN SITE | Area cleaned and fit for following trade commencement. | Final clean and grade site area affected by the Stormwater scope of works Excess spoil removed from site by as per contract terms | S | S | FINAL TRIM/ CLEAN SITE | REFERENCE - Area cleaned and fit for following trade commencement. | ACCEPTANCE CRITERIA - Final clean and grade site area affected by the Stormwater scope of works Excess spoil removed from site by as per contract terms | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | SET OUT
FINAL INSPECTION / COMPLETION | Subcontract documentation | Verify all inspections, complete records clean and flush entire installation. CCTV of all completed pipe work. Submission to be completed and submitted to BESIX Watpac. | WS | S | FINAL INSPECTION / COMPLETION | REFERENCE - Subcontract documentation | ACCEPTANCE CRITERIA - Verify all inspections, complete records clean and flush entire installation. CCTV of all completed pipe work. Submission to be completed and submitted to BESIX Watpac. | SUBCONTRACTOR - WS | WITNESS (SUBCONTRACTOR) - S | REFERENCE - Subcontract documentation, For construction drawings
RECORD DRAWINGS | Subcontract documentation | Provide Requirement as per contract documentation including Dimensioned, Surveyed, Falls, Locations and Components. Provide verifications of testing. Hydraulic Consultant (LCI) invitation to inspect. | H | S | RECORD DRAWINGS | REFERENCE - Subcontract documentation | ACCEPTANCE CRITERIA - Provide Requirement as per contract documentation including Dimensioned, Surveyed, Falls, Locations and Components. Provide verifications of testing. Hydraulic Consultant (LCI) invitation to inspect. | SUBCONTRACTOR - H | WITNESS (SUBCONTRACTOR) - S | ACCEPTANCE CRITERIA - Mark out pipe locations and co-ordinate with other trades
SUBCONTRACTOR - W
WITNESS (SUBCONTRACTOR) - S
EXCAVATION
REFERENCE - Subcontract documentation
ACCEPTANCE CRITERIA - Excavate trenches to minimal size Grade Trenches to Falls Bed pipes on 10mm – blue metal
SCOPE OF WORK | Subcontract documentation, For construction drawings | Check documents are current CHAR(AMP) for construction Check levels CHAR(AMP) falls | S | HS | SCOPE OF WORK | REFERENCE - Subcontract documentation, For construction drawings | ACCEPTANCE CRITERIA - Check documents are current CHAR(AMP) for construction Check levels CHAR(AMP) falls | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - HS | SUBCONTRACTOR - W
COMPETENCY |  | Trade Registration |  | S | COMPETENCY | REFERENCE - | ACCEPTANCE CRITERIA - Trade Registration | SUBCONTRACTOR - | WITNESS (SUBCONTRACTOR) - S | WITNESS (SUBCONTRACTOR) - S
SET OUT | Subcontract documentation, For construction drawings | Mark out pipe locations and co-ordinate with other trades | W | S | SET OUT | REFERENCE - Subcontract documentation, For construction drawings | ACCEPTANCE CRITERIA - Mark out pipe locations and co-ordinate with other trades | SUBCONTRACTOR - W | WITNESS (SUBCONTRACTOR) - S | PIPEWORK
EXCAVATION | Subcontract documentation | Excavate trenches to minimal size Grade Trenches to Falls Bed pipes on 10mm – blue metal | W | S | EXCAVATION | REFERENCE - Subcontract documentation | ACCEPTANCE CRITERIA - Excavate trenches to minimal size Grade Trenches to Falls Bed pipes on 10mm – blue metal | SUBCONTRACTOR - W | WITNESS (SUBCONTRACTOR) - S | REFERENCE - Subcontract documentation. Check that delivered products are as per specification CHAR(AMP) approved samples
PIPEWORK | Subcontract documentation. Check that delivered products are as per specification CHAR(AMP) approved samples | UPVC Pipework Jointing methods as per specification. Note that all sealants have been checked for compatibility with materials | W | S | PIPEWORK | REFERENCE - Subcontract documentation. Check that delivered products are as per specification CHAR(AMP) approved samples | ACCEPTANCE CRITERIA - UPVC Pipework Jointing methods as per specification. Note that all sealants have been checked for compatibility with materials | SUBCONTRACTOR - W | WITNESS (SUBCONTRACTOR) - S | ACCEPTANCE CRITERIA - UPVC Pipework Jointing methods as per specification. Note that all sealants have been checked for compatibility with materials
PITS | Subcontract documentation, For construction drawings | Adequate Protection Installation as per specification | W | S | PITS | REFERENCE - Subcontract documentation, For construction drawings | ACCEPTANCE CRITERIA - Adequate Protection Installation as per specification | SUBCONTRACTOR - W | WITNESS (SUBCONTRACTOR) - S | SUBCONTRACTOR - W
SEWER CONNECTION | Subcontract documentation | Connection permit received Authority procedures followed | W | S | SEWER CONNECTION | REFERENCE - Subcontract documentation | ACCEPTANCE CRITERIA - Connection permit received Authority procedures followed | SUBCONTRACTOR - W | WITNESS (SUBCONTRACTOR) - S | WITNESS (SUBCONTRACTOR) - S
BACKFILL COMPACTION | Subcontract documentation. Hold/Witness point, all inground sewer to be inspected prior to backfill | Backfill pipe with 10mm blue metal then backfill with selected excavated material. Reference to adequate compaction in accordance with AS 1289 | S | S | BACKFILL COMPACTION | REFERENCE - Subcontract documentation. Hold/Witness point, all inground sewer to be inspected prior to backfill | ACCEPTANCE CRITERIA - Backfill pipe with 10mm blue metal then backfill with selected excavated material. Reference to adequate compaction in accordance with AS 1289 | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - S | PITS
FINAL TRIM/ CLEAN SITE | Area cleaned and fit for following trade commencement | Final clean and grade site area affected by the stormwater scope of works Excess Spoil removed from site by others | W | S | FINAL TRIM/ CLEAN SITE | REFERENCE - Area cleaned and fit for following trade commencement | ACCEPTANCE CRITERIA - Final clean and grade site area affected by the stormwater scope of works Excess Spoil removed from site by others | SUBCONTRACTOR - W | WITNESS (SUBCONTRACTOR) - S | REFERENCE - Subcontract documentation, For construction drawings
FINAL INSPECTION |  | Hydraulic Consultant (LCI) notification and witness point where required. Verify all inspections, complete records. CCTV inspection of all complete Sewer installations | S | HS | FINAL INSPECTION | REFERENCE - | ACCEPTANCE CRITERIA - Hydraulic Consultant (LCI) notification and witness point where required. Verify all inspections, complete records. CCTV inspection of all complete Sewer installations | SUBCONTRACTOR - S | WITNESS (SUBCONTRACTOR) - HS | ACCEPTANCE CRITERIA - Adequate Protection Installation as per specification
SUBCONTRACTOR - W
WITNESS (SUBCONTRACTOR) - S
SEWER CONNECTION
REFERENCE - Subcontract documentation
ACCEPTANCE CRITERIA - Connection permit received Authority procedures followed
SUBCONTRACTOR - W
WITNESS (SUBCONTRACTOR) - S
BACKFILL COMPACTION
REFERENCE - Subcontract documentation. Hold/Witness point, all inground sewer to be inspected prior to backfill
ACCEPTANCE CRITERIA - Backfill pipe with 10mm blue metal then backfill with selected excavated material. Reference to adequate compaction in accordance with AS 1289
SUBCONTRACTOR - S
WITNESS (SUBCONTRACTOR) - S
FINAL TRIM/ CLEAN SITE
REFERENCE - Area cleaned and fit for following trade commencement
ACCEPTANCE CRITERIA - Final clean and grade site area affected by the stormwater scope of works Excess Spoil removed from site by others
SUBCONTRACTOR - W
WITNESS (SUBCONTRACTOR) - S
FINAL INSPECTION
REFERENCE -
ACCEPTANCE CRITERIA - Hydraulic Consultant (LCI) notification and witness point where required. Verify all inspections, complete records. CCTV inspection of all complete Sewer installations
SUBCONTRACTOR - S
WITNESS (SUBCONTRACTOR) - HS