## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
59c41df3-b219-406b-b1de-58333e10f081 | checklist | 01.00 - Sprayed Bituminous Surfacing | itp | 01.00 - Sprayed Bituminous Surfacing
8399b5e0-d43c-48f6-ac9d-9a0a1868c492 | section | Details
6ba3557a-2b09-4f2b-893c-3c6b22d72b76 | checkpoint | 1 - Document Submissions
d7a85024-851f-576b-a387-92dd861ad363 | note | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
5621529c-47cb-5211-be54-8e5a95986a07 | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
a1e639e0-effa-560f-8ada-5c058ca1fa13 | note | Check Item - Check Item
1994c3a6-86e2-4ddc-b86a-a36c054b2d9d | checkpoint | 2 - Traffic and Safety Controls
f1068495-f3b3-5ce7-bc52-f6b394061180 | note | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
db196daa-fff9-54eb-a805-bec5780c5804 | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
c5b6f3ce-67a7-580c-bdb6-de3983d21d74 | note | Check Item - Check Item
ba46f4b9-959b-4d46-8a27-eb2d4c4fba97 | checkpoint | 3 - Construction Procedures
7abb3d09-db65-58a0-b2c7-e820af7c3dca | note | ○ The contractor shall documented procedures for all required processes in reference to Clause 5.2 MRTS11 to be submitted not less than 7days, these procedures and ITP shall not be implemented until permission has been granted
53c73024-a9f6-5785-a846-6251aed93e52 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
b8e62235-ccd6-5803-921e-ccdece14f739 | note | Check Item - MILESTONE/HOLD POINT
87e94b8a-51e6-5cc5-93e4-0b314fd17b7b | note | Reference - Clause 5.2 MRTS11
2604b244-df65-4edf-8378-21c61040b2de | signoff | HOLD POINT
5cbc1ee5-39cb-4932-ac97-0c29ee5d29f9 | checkpoint | 4 - Seal Design - Binder Substitution
324e9e59-c3b6-5152-b356-967ad286d73a | note | ○ The Contractor shall notify the Administrator of the binder class substitution not less than 14 days prior to the commencement of spraying.
1b0288b9-b9b3-5c6b-91e9-a016e872e545 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
fccc0256-53b4-50dd-8dcd-8c18d4e7b8c8 | note | Check Item - MILESTONE
b8aa40de-3399-5ec0-bb31-f3130b65412c | note | Reference - Clause 6.1.2 MRTS11
ab18cb4f-f64f-4b2b-8661-b49619450fd7 | checkpoint | 5 - Seal Design By Principal
9e921d46-fcb2-516a-b8c4-f6af995cd28a | note | Testing shall be completed by the Contractor at the test locations and minimum test frequencies detailed in Table 6.2. (Particle Size Distribution, Flakiness Index and Avegrade Least Dimension, Texture Depth and Ball Penetration.)
b9c9ea02-4b7b-570f-878a-25fd9deffcc0 | note | — Test results for the cover aggregate and texture depth has been submiteed at least 7 days
02707065-f7cc-54e7-9564-a7e86fe15a1f | note | — Ball penetration testing has been undertaken in accordance with Table 6.2 and Clause 10.1.2 and passed on to the Administrator on the day of testing.
33b8219a-c1b5-5ad0-83ea-072b976f4408 | note | — Spraying shall not commenced until Designed Spray Rate and Designed Spread Rate has been confirmed.
1a570477-59cf-57f3-8ad4-af5b4d23ae63 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
3f632746-89a3-55ea-a09b-876f3e3f325d | note | Check Item - MILESTONE/HOLD POINT
255b8d50-fd19-55dd-9ecd-ebb683f23074 | note | Reference - Clause 6.2 MRTS11
a8db9dcf-5e9f-4986-a4aa-8b6ab34f5d19 | signoff | HOLD POINT
5a9cf039-e2d1-4292-a3d9-cae27287393c | checkpoint | 6 - Seal Design By Contractor
9ebc0257-0afe-5296-81c6-25e39d49a1f0 | note | ○ Where the Contractor is nominated to undertake the Seal Design, the Contractor shall inspect each site and shall select inputs and associated design factors. The seal design reports shall include all inputs stipulated in the nominated clause.
a09d6438-357e-50d8-afdc-cebda67ddfc8 | note | Acceptance Criteria & Frequency (Project Specific) - Check
9bdb4b58-6c43-5a2e-8633-f01c838f0ed3 | note | Check Item - Check Item
a30a3fff-8cf0-5d27-8a2b-bb90daa93dd6 | note | Reference - Clause 6.3 MRTS11
aade6e0e-c8b1-42b2-bee8-14a9376ae08c | checkpoint | 7 - Seal Design Report
a1a5c722-5cd5-5cac-95c0-11929b1df8f9 | note | ○ A seal desin report shall be submited to the Administrator at least 7 days prior to commencing bituminous spraying operations. The Seal Design Report shall include the requirements of Clause 6.3.2 MRTS11. The Administrator shall have 3 days to consider the seal design report and spraying operations shall not commence until release of the hold point
a780ae13-1c0e-5c24-9c82-7d6fc14b703a | note | Acceptance Criteria & Frequency (Project Specific) - Approval
e6ffd372-a5b3-5706-b5e5-0e9f49976d50 | note | Check Item - MILESTONE/HOLD POINT
4f25330d-67cf-5ac3-8d48-d9ab533af854 | note | Reference - Clause 6.3.2 MRTS11
956b74d4-1b55-43bc-8932-a59626dd586c | signoff | HOLD POINT
c2c44968-e9fb-42d2-953e-9b128457db25 | checkpoint | 8 - Quarry Registration Certificate
5d615261-8991-56e1-97df-eed61b5f1727 | note | ○ Cover aggregate shall be supplied by a registered quarry comply with TMR Quarry Registration System. Certificate to be sent to the Administrator 7 days before material supply. Material from a quarry shall neither be supplied,nor used in the Works prior to written permission by the Administrator
4af4d360-6e18-595b-9baa-2272b0d079e9 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
bd69aae0-6955-5070-9e7d-2fd6fd792ca2 | note | Check Item - MILESTONE/HOLD POINT
36035c69-ec9e-5c7a-b0f4-3bfafe3957e6 | note | Reference - Clause 6 MRTS22
7a98709e-ce19-48b9-9772-2ef82322b9be | signoff | HOLD POINT
7b94246f-82e5-4680-a1f2-d50de954b2b9 | checkpoint | 9 - Cover Aggregate
0b1a4b08-3fa2-5279-9144-419f404f9ce8 | note | ○ Cover aggregate shall not be exposed to contaminant agents and to be handle to avoid any contamination / deleterious effects. It shall be protected with a light plastic or similar material to prevent the ingress of moisture and other contaminants.
91902fd1-325f-523f-b3bb-aaa19f75627b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
800a10ed-f483-5fc9-b153-b5b88389d899 | note | Check Item - WITNESS POINT
0b58d6d9-4189-5f8d-8044-d1d7abf8b073 | note | Reference - Clause 8.2 MRTS11
8c685385-ad30-420c-8d93-7f8c44c1cf81 | checkpoint | 10 - Bituminous Materials
4b2acb70-1d06-5aa2-a817-eb6b38333011 | note | ○ Binder shall be delivered to the Works in accordance with Clause 8 MRTS17 Bitumen or Clause 8 of MRTS18 Polymer Modified Binder. Temperature at delivery to site shall be measured and recorded.
43decdd7-9c8f-5f43-8923-3e0a311be503 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
599b5209-12e9-59fa-9de3-6b91cbd26ba3 | note | Check Item - WITNESS POINT
42517892-8cc3-5643-bf5e-1e7fe1ae8a6c | note | Reference - Clause 8.3.1 MRTS11
594765cb-e116-48ee-9da1-6d8515fc9300 | checkpoint | 11 - Bituminous Material Heating
3a735c2a-c5ca-5a02-9549-08e490bb56e2 | note | ○ Strict controls shall be applied to heating of bituminous material and in accordance to Austroads AP-G41Bitumen Sealing Safety Guide, the heating requirements shall strictly be observed.
9f5689ab-b8a7-5379-98e7-702db98191a9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a0ff16ca-aff3-56cf-9a01-bf16ff7ae6d0 | note | Check Item - WITNESS POINT
7019d946-ec0f-5ad7-86fb-8edd81a0ae98 | note | Reference - Clause 8.3.2 MRTS11
7a8a52b8-6774-44a3-a645-e282b8baf23f | checkpoint | 12 - Precoating Agents
a1989bb0-8485-5614-bce0-24c8d83c7129 | note | ○ Cover aggregate shall be precoated with one of the nominated approved products listed in Clause 2 of Annexure MRTS22.1. The Contractor shall submit to the Administrator details of the precoating agent procedures 7 days prior commencing.
5548c0de-502e-581a-bcf3-78e25833ff12 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
30a1b4fe-188a-5df9-af16-95f4dd5cbeed | note | Check Item - MILESTONE
0d5f518d-7f0d-5fe7-b303-52e0e74cf677 | note | Reference - Clause 7.1.4 MRTS22
47267c5d-7895-4595-a541-fa89228e0094 | checkpoint | 13 - Compliance Testing
5a921cd3-d9bf-5f1b-adff-35d5f1390a7a | note | ○ The Administrator shall receive at least 15 working days a preliminary sample of 40kg of each type of cover aggregate to be used in the contract as per the requirments of Clause 3 MRTS22.1
495142fd-ec1b-55d4-8940-81b17c17bba3 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
1383a8bc-79af-51a7-94dd-c97d0753f117 | note | Check Item - MILESTONE
959782e2-eadd-505b-94d5-547a88151a4b | note | Reference - Clause 8.1 MRTS22
c9c59c50-78dc-4ee5-920b-63c5660a84fa | checkpoint | 14 - Plant & Equipments
2a04f29e-7fcd-5779-8bf4-13fce68713f4 | note | ○ On site documentation of required plant will be provided no less than 3 days prior to sealing operations and shall satisfied as per Table 9. Additional plant requirements shall apply in accordance of Clause 5 MRTS11.1
6c500873-bf80-5787-aad2-188315e547e1 | note | Acceptance Criteria & Frequency (Project Specific) - Check
f8e3fc6c-b175-55ee-bd8a-b8e8d0ff3df1 | note | Check Item - HOLD POINT
85bfc9a0-57ed-5182-901e-d21a55b7d84f | note | Reference - Clause 9 MRTS11
dc1703fa-3821-4454-95ae-25439e3e8c8f | signoff | HOLD POINT
06082b6e-79e3-463b-b68b-6f4c56999fb4 | checkpoint | 15 - Initial Bituminous Treatments (No Existing Bitumen Treatment)
00127876-91a3-50a9-bc72-da85a1a59d76 | note | ○ All foreigh and loose material, including lenses of pavement material shall be removed from the surface. The surface shall be swept with a road broom. Where a Ball Penetration test result exceeds 3.0 mm, the surface shall not be sprayed until approved by Administrator.
12cd4c5e-3b2b-5d29-aad7-ba73c51e1453 | note | Acceptance Criteria & Frequency (Project Specific) - Verify
dba924a0-68a4-57ff-acc9-4beef8933cf5 | note | Check Item - HOLD POINT
00a39975-cce2-50e3-a171-cfa99cd314d7 | note | Reference - Clause 10.1.2 MRTS11
4b881aed-218e-46e3-9139-01afe9ba8be5 | signoff | HOLD POINT
a9cde142-ff94-4f49-9cbd-f1d1f7261b61 | checkpoint | 16 - Availability of Cover Aggregate
9ffcb689-e186-5f47-ae2e-5361cd6a2f24 | note | ○ Prior to commencement of bitumen spraying operations, the contractor shall provide the Administrator with evidence there is sufficient cover aggregate for the extent of bitumen spraying work to be undertaken that day.
fd7e02a3-0992-59b9-be19-9d92226858a9 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
84addef4-3def-54a4-959e-faf4fe3115b8 | note | Check Item - HOLD POINT
2ffb6caf-2cd9-552f-9f7c-de3a6439a279 | note | Reference - Clause 11.1 MRTS11
326d9b4e-d5cd-4660-87a9-901e84f3d341 | signoff | HOLD POINT
65bb6f93-2e81-477e-a3de-238a0f05dca0 | checkpoint | 17 - Pavement Surface Temperature
140dbc58-34d1-5680-b5d3-677499d9c85d | note | — Spraying shall not commence until the temperature of the pavement surface is above the temperature given in Clause 6.2 of Annexure MRTS11.1.
0d9393c2-5e0f-5194-beb0-a188d0649281 | note | ○ 10℃ for primes
9120a6e5-37c5-5410-9398-24fd3bbc6070 | note | ○ 15℃ for initial seals containing cutback bitumen (i.e AMC4 to AMC7)
5b36c16d-352b-526b-a401-fa1193011cfc | note | ○ 20℃ for bitumen and polymer modified binders
31836b6b-d02d-5800-93f0-73a2153d270a | note | — These limits do not apply to WP-A and SAMI treatments
2797c7d0-9e5f-5ab9-93b3-a6ae9dab930c | note | ○ placed over an existing seal or ashalt, and
b47288c0-1a15-52f9-87e6-4ced608824d4 | note | ○ overlaid with asphalt prior to trafficking.
7af25391-4440-5fcc-9b95-f3b268a4008f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
cd5bf17e-d73c-5f16-804c-a00bee14beec | note | Check Item - WITNESS POINT
a422fda7-9bf1-576c-be3a-8d32f2428c05 | note | Reference - Clause 11.2 MRTS11
56cd8f59-cd07-4f40-ac47-ffb8211322c0 | checkpoint | 18 - Spraying Requirements
b3798c74-a6b1-56ad-bdaf-b7f025d029ee | note | ○ Spraying shall not take place during rain of if rain is likely to fall prior to spreading cover aggregate and the completion of rolling. Further, spraying shall not take place during winds of greater than 30km/hr or during dust storms.
ec691f18-daad-5fd0-a3d4-7c169e1211e8 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
4613aec8-5c77-50f7-a56a-812f751401f8 | note | Check Item - Check Item
eaee0ccc-fd00-5153-aafc-54a5167123f5 | note | Reference - Clause 11.3 MRTS11
c0295a86-c0f4-4fc0-8b1e-2e8a7a308367 | checkpoint | 19 - Time Period Between Bituminous Treatments
850888a1-6a64-50c0-a0e9-b4fe33bfad80 | note | ○ The minimum period of time between bituminous treatments shall be applicable as per the requirements of Clause 11.4 MRTS11
d55dfe7c-ceef-5b4b-aec9-119666d87a1c | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
3fef2432-3b79-589e-ab1f-6f9c881ea415 | note | Check Item - Check Item
6951a13a-449e-50e2-a455-a5583fe9f849 | note | Reference - Clause 11.4 MRTS11
9e2a0250-3934-4d07-8295-48d8aa24c282 | checkpoint | 20 - Spraying
f8302350-8849-5158-93d8-16d1550d4c57 | note | ○ The spraybar nozzles used shall be appropriate for each spray run and shall comply with QSC. A copy of the Queensland Sprayer Certificate shall be provided.
fca1bb26-5ad1-56c8-b021-45e1cfddf9e4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e53df3c0-6a22-51ae-8456-7405a00f8bdd | note | Check Item - WITNESS POINT
87cb82cd-8e2c-5b11-8be6-e1e8f6027a1b | note | Reference - Clause 12.4 MRTS11
eeb86a83-b591-4a67-9581-83a41f67af94 | checkpoint | 21 - Cutting Back Binder
6eaf6e8f-de19-5c62-9bb6-b2b174fefe35 | note | ○ Incorporation of cutter oil into the binder shall be caried out in accordance with Clause 8.3.3. Prior to each operation, Seal Designer Delegate shall nominate the cutter oil adjustments, which shall be recorded.
357109a3-59f9-5f0e-bb96-03bffcd40f48 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
af8aa715-1169-51dd-bee4-38219993918e | note | Check Item - WITNESS POINT
8d72e26e-7104-5e70-bd8c-4adb1dd7d483 | note | Reference - Clause 12.7 MRTS11
fb66d070-7bde-4b32-b2a8-36ef229d318b | checkpoint | 22 - Spreading of Cover Aggregate
a75bdb02-e1e3-5c1b-b409-aab8224eaf6b | note | ○ Wet cover aggregate containing free surface water shall not be loaded into the aggregate spreader.
804c79ec-722c-5085-930f-db4453a38ac2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
39984898-e354-55ed-be33-7fe89e6d3ced | note | Check Item - WITNESS POINT
930929b0-a70e-570f-a10d-facba8b3d450 | note | Reference - Clause 14.1 MRTS11
f03cb991-006d-443f-b96e-ef237474cce3 | checkpoint | 23 - Time Limit for Cover Aggregate
86fb0028-d567-5158-a107-4a834ea77342 | note | Spreading of cover aggregate shall commence as soon as possible with the time limits specified below:
30e02066-0c74-5b35-8605-fd84d135171f | note | — primerseals: 15 minutes
4d7f3dbe-2c6b-5769-8e37-02e483022f4f | note | — Cutback Bitumen, Bitumen and Multigrade Bitumen: 10 minutes, or
b951f1bc-0a04-5c58-a8b3-4b4cad1df7a8 | note | — polymer modified binders including crumbed rubber binder: 5 minutes
0c237b62-6752-5f8c-8a0d-77469509f259 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
94adfbb4-a046-5dbd-ab41-21598ebb1f6a | note | Check Item - Check Item
f6a9cb2d-09d6-54aa-901c-50b2c3e9e48c | note | Reference - Clause 14.3 MRTS11
1e16a313-b0d2-4798-a33b-8f3b7147d35d | checkpoint | 24 - Early Traficking Requirements
7dd69fc9-8ddd-5023-bcbc-641f9c7e3133 | note | ○ The requirements of Clause 14.8 shall be complied and the road shall not be opened to traffic until the release of this Hold Point by the Administrator
23db8834-dbed-5b45-99fb-19fdd9db9038 | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
ba21734e-8092-5211-95c8-4781e0dde6bf | note | Check Item - HOLD POINT
29a89bbb-8192-567f-b8f7-c04550b436cc | note | Reference - Clause 14.8 MRTS11
c2049cd2-9c2f-4876-9631-fa34c3e2e61e | signoff | HOLD POINT
7e511f78-0737-4a04-b830-09c6db792875 | checkpoint | 25 - Delivery of Aggregate to Stockpile Site
1b414470-f24d-52a0-ad27-f35250b09b3b | note | ○ Prior to commencement of delivery of aggregate to any stockpile site, the Contractor shall obtain the Administrator’s authorisation to place aggregates on the stockpile site.
42fb4715-7ab6-594c-a2e9-d09c55fbc783 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
90f4c50b-18e4-5f96-9737-a1c44525b83b | note | Check Item - HOLD POINT/WITNESS POINT
b9b6fd2e-4ed0-5870-9e68-2959ef72407a | note | Reference - Clause 10 MRTS22
dfc0867f-111d-4225-abd4-2832a1439f34 | signoff | HOLD POINT
7179eb34-13c2-4ae5-96b1-96e5d9867f83 | checkpoint | Final Verification
91f5ab8f-f0bd-582a-b740-7614d415370c | note | Responsible Officer
ccff6600-1acf-56fe-bb6c-d11ef0c6fa81 | textbox | Print Name:
03c25a5b-fe17-5bd9-b2d6-7aa7464b5e0b | date | Date:
7be57330-abed-55fe-bf63-b60b26b6b726 | note | Verifying Authority
10906389-9758-5a09-9b4b-34f6a187e0a1 | textbox | Print Name:
edfd32aa-9b5b-582a-ac0d-305d1157365c | date | Date:
3b391222-ad4f-42d5-adaf-f8bcb9fe86ea | signoff | Signature
778fba19-7e22-4e0b-9fdc-4356b0fe3dd7 | section | Final Sign Offs (to be completed at closure of Lot)
29ad50df-cbaa-4f98-9c4d-3ff3ec543987 | checkpoint | Agreed Quantities
2658a2d8-19db-432a-b4bb-2f57957e7761 | signoff | Agreed Quantities Sign Off
49bd935b-4cd7-4ced-93a1-df52622e422e | checkpoint | Closure of Lot
2eb2930f-45dc-400d-8818-8a8c010535ce | signoff | Closure of Lot Sign Off
1f9eb5f1-afd9-4949-afb3-b65a2769e342 | checklist | 02.00 - Clearing and Grubbing | itp | 02.00 - Clearing and Grubbing
71feac3c-0c5e-4503-aa89-ea85628dc976 | section | Details
b71be695-4edb-4efc-9482-17cc479e5660 | checkpoint | 1 - Document Submission
566b7f73-345e-592d-bc1f-891bee7c85de | note | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
a365be23-e93d-505e-8d50-b531fa361ae7 | note | Acceptance Criteria & Frequency (Project Specific) - Safety Plan, Environmental Plan and Traffic Management Plan
9390acf2-9deb-5107-a50f-69d52345ffb0 | note | Check Item - Check Item
183d0ce1-e1e8-45d1-9bd2-b99e6eb4fa63 | checkpoint | 2 - Traffic and Safety Controls
574e6498-7b71-550e-bc8c-1b4e0ca3c0a8 | note | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
ca546234-bc93-5edc-8909-52195c579bfc | note | Acceptance Criteria & Frequency (Project Specific) - Traffic and safety Management plans
efd64a1e-6871-5002-a48a-142d8a3d50b3 | note | Check Item - Check Item
a42b9419-05b3-4ae7-b9f9-ff5fadcfbf47 | checkpoint | 3 - Areas to be Cleared and Grubbed
4938c2dd-33b2-58b8-89f7-6c0aca0a1293 | note | ○ Clearing and Grubbing shall be limitted to the extent of those areas required to construct the works plus an additional width of no more than the distance stated in cl 1.1 of annexure MRTS4.1 or 3m where not so stated and/or meet the specified visibility requirements.
68960655-fc1c-553a-ad93-ef0d87145bdf | note | *Maximum additional width for clearing and grubbing - The lesser of 1.0m from the extent of earthworks or ground treatment areas or the property boundary.
82418f24-d061-5fd4-b7bd-954eb84e4018 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
81c4123c-81b1-540c-ab31-a8fcfa069623 | note | Check Item - Check Item
895dd8d3-6b31-50d5-ada1-afd99c3f90cb | note | Reference - Cl 7.2.1 MRTS04, Cl 1.1 MRTS04.1
63f57bf9-caa4-4af4-bd16-55603915806f | checkpoint | 4 - Limitations on Clearing Operations
fee349b1-d63d-52ff-8d6d-26174f43b6a2 | note | ○ Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked out by the contractor prior to clearing operations.
2e846ff4-b4e4-5a21-8ec9-8aa7cf4c5d89 | note | Acceptance Criteria & Frequency (Project Specific) - Verify
7ff21a96-0e97-563e-91f6-3123d77cd607 | note | Check Item - HOLD POINT
93d96d77-5fbd-5a0d-bbfe-65a27378605c | note | Reference - Cl 7.2.1 MRTS04
3d7b77ca-4a85-4c85-9e19-5326519a9d27 | signoff | HOLD POINT
da618f26-d67e-4ee7-a2d6-830f05396023 | checkpoint | 5 - Trees Required by the Administrator
a9adb572-ea97-59e4-88dd-404303ceab99 | note | ○ Any trees required by the principal for use as marketable timber detailed in cl 2.3 MRTS04.1. Handling procedure shall be in a manner avoiding damages to the trunk and branches shall be trimmed appropriately. *None*
06916171-b6a6-51ef-b068-14948fbf2afe | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
ad43ca8d-98cb-53a8-9f03-4f83f21c3d66 | note | Check Item - HOLD POINT
2a3d013e-f497-55dd-9972-8ee77099d717 | note | Reference - Cl 7.2.3 MRTS04
cbdc6cb8-b7af-45a2-a2ff-738c169bdfea | signoff | HOLD POINT
ba1b9f8e-d47a-4dff-8c0f-7bb5c3bd788a | checkpoint | 6 - Additional Requirements
c9dbfc93-b75a-5c3f-8ac1-c9f804db1b3b | note | ○ Contractor shall mark the extent of clearing on the ground and agreed with the administrator prior to any clearing and grubbing activities. After completion of works, contractor shall give 5 days notice to the administrator and principal's RPEQ geotechnical enginner to inspect and confirm in writing that the clearing and grubbing works are complete before proceeding to the other works on same surface.
9fe5e689-daaa-537a-9580-f532dab85e09 | note | Acceptance Criteria & Frequency (Project Specific) - Verify
7cb1d0a6-c065-54a8-a30d-a34c0088ecc5 | note | Check Item - Hold Point
fd14f159-1cd9-5cda-a11c-dd2ce0e065f8 | note | Reference - Cl 7.2.8 MRTS04, Cl 1.4 MRTS04.1
855d6b3b-9e1f-4bd0-af06-98cd7ff08a1b | signoff | HOLD POINT
637ff0cc-1512-4539-8c08-80c4226d1767 | checkpoint | Final Verification
027843e8-a6df-51f0-a20b-30d41287c611 | note | Doval Representative
ee9b6c2d-b6e8-57aa-b45f-d72e1e1a4950 | textbox | Print Name:
b6a575e7-5faa-576f-984c-85152ee860c9 | date | Date:
fa683a18-ed8c-5879-afac-2e508d5696cf | note | Administrator
7f02271c-c09e-57d2-8888-0af59463531e | textbox | Print Name:
1bc63c42-38d6-580c-9bfa-84c91db20f6c | date | Date:
3caac692-6cd9-4b4a-b6b1-44a87aa15af2 | signoff | Signature
768d0fde-f760-45e1-8578-91d07db6ed7a | section | Final Sign Offs (to be completed at closure of Lot)
59e52a86-3982-4cf2-8ebe-14fbe8f6dc1b | checkpoint | Agreed Quantities
0fd34b87-4dc8-4b62-9439-5807c0bfe895 | signoff | Agreed Quantities Sign Off
abab0441-2fc1-4354-a42a-5cc113bb2a36 | checkpoint | Closure of Lot
8003a3e8-0766-4d4b-b1fa-ffb2d77732e5 | signoff | Closure of Lot Sign Off
5bfc3731-4d86-49cc-9b8e-908482410340 | checklist | 03.00 - Concrete | itp | 03.00 - Concrete
eb84198e-ece2-4409-a90d-d698400af80b | section | Concrete
96aac009-218c-43e7-b1e8-1d056253a363 | checkpoint | 1 - Document Submissions
367d186c-53aa-5d50-8097-15c93d629b4c | note | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
02bd6f54-d568-5f35-bb86-4430c3d364a2 | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
fb31e04f-db64-5d99-85c5-57f82d484768 | note | Check Item - Check Item
70225c5e-6a9d-443e-baf1-b508d6839008 | checkpoint | 2 - Traffic and Safety Controls
de2be10a-391d-52c9-a783-5bcdde056fde | note | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
0f7b3fa4-1ac9-5372-a53e-d88b359ae6cb | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
0c360003-2128-5d1d-b90b-500fde732ac9 | note | Check Item - Check Item
90ee9f75-0aa2-4f4d-a046-a7056398add7 | checkpoint | 3 - Submission and Approval of Mix Design
087f8a2d-1ed1-5c01-80c6-3a7f3d32f256 | note | ○ Submit details of the mix design for each specified Class of concrete to the Administrator for approval 6 weeks prior to commencement of concreting operations. The Mix Design shall include the information in Clause 15.1 MRTS70
3707d028-f30f-5a92-83e0-7b4d5a9184e8 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
f64fe23c-c72c-5812-9742-9fcc03a708ac | note | Check Item - HOLD POINT 1
e0d01b94-858c-5162-bbfb-799db857d889 | note | Reference - Clause 9.2 MRTS70, Clause 15.1 MRTS70
7661c22d-d52c-4781-a3e5-ef2473082592 | signoff | HOLD POINT
63839f0e-ab07-422a-8c3d-baca4933fe64 | checkpoint | 4 - Trial Mix
5528294c-0365-5d50-aed7-684a5d330ba7 | note | ○ Minimum volume for trial mix shall be 25% of the rated capacity of the mixer. Each trial mix shall be a witness point with a notice period of 3 days. Shall be tested for slump, workability, and strength. The slump shall meet the allowable range with Table 11(a) Refer Clause 11 MRTS70
edb5fcf0-cc4c-52cb-8263-31149d4da564 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3b2d2467-0f5f-51cf-b635-8b7b31227517 | note | Check Item - WITNESS POINT
ca29752e-4f81-508e-9566-a52c07c291c6 | note | Reference - Clause 15.1.1 MRTS70
53f943eb-35bf-4304-b298-a7b4ab958662 | checkpoint | 6 - Concrete Testing
5b6a3e9b-1159-53a9-b7ba-8e8c1c8591e7 | note | ○ Concrete to be tested and meet the mix design requirements. It shall only be tested at a NATA registered laboratory. Sampling and testing shall be in accordance with AS1012
bc8a1c79-522d-5ee9-a5bf-2b2191738823 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
c205e7ce-4b52-5a8b-88b6-f8e4cd978949 | note | Check Item - Check Item
8a80eee9-cc46-5aeb-8a4e-5e8ac03fdec3 | note | Reference - Clause 12.3 MRTS70
88621a3a-1d37-4722-8194-1332c3d37263 | checkpoint | 7 - Temperature and Evaporation Limits for Operations
55c65877-2423-5d2f-a6e0-e9f2cc11158c | note | ○ The procedure for hot weather concreting shall be submitted at least 2 weeks prior to the first concrete pour
1a204fb9-f900-5174-a7be-e2fc6f536151 | note | Acceptance Criteria & Frequency (Project Specific) - Check
6b9988ef-2013-5f47-a63a-de7353a455dc | note | Check Item - MILESTONE
615d5255-1e2c-5a67-a6b9-6f8232294dfe | note | Reference - Clause 13.1 MRTS70
cbac2665-32fe-40ae-80b8-ed973920cf31 | checkpoint | 8 - Air Temperature Measurements
6bf32416-14a8-52b9-877e-f5d934cfa3a1 | note | ○ Ambient air temperature measured at the point of placement is not to be less than 10ºC or exceeds 35ºC. If the ambient air temperature measured at the point of placement is likely to exceed 35°C during placing and finishing operations, the Contractor shall take practical precautions, approved by the Administrator.
201b8c2b-4dfd-565e-aa7d-e57934dc0bbf | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
7676827f-d767-553e-9582-9836f445a977 | note | Check Item - Check Item
7eb1788e-4925-58c2-9e84-167599f6a076 | note | Reference - Clause 13.1 MRTS70
6770692e-3039-4880-965f-ead2e3b75b31 | checkpoint | 9 - Evaporation Limits
765d3de2-6b07-5514-b65e-ace1954ad90a | note | ○ The predicted evaporation rate during the intended work is not to exceed 0.75kg/m2/hr. If the evaporation rate exceeds 0.75kg/m2/hr then the Contractor shall undertake practical measures described in MRTS70 Cl 13.2 are to be implemented
f4c2a7a0-ac2f-5d3d-a714-691220b66e90 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
8c1e2fb4-849a-52c8-9917-91ebca3dc1a2 | note | Check Item - Check Item
1ba47da7-ac67-5528-9772-89276379799a | note | Reference - Clause 13.2.1 MRTS70
6a05a793-76db-4dd9-9469-0a087902f125 | checkpoint | 10 - False Works
04425893-2a4f-54b4-9d5c-c4a459b122c9 | note | ○ False work shall conform to AS 3610, except otherwise specified. The method of founding or supporting the false work and the time, order and manner of its release shall all require approval of the Administrator. Detailed drawings of such falsework shall be supplied to the Administrator at least 4 weeks prior to commencement of erection.
de20b4f6-61de-57bc-a9bd-60cfc988526f | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
94a96265-b938-55a6-896c-554da3b3f2d7 | note | Check Item - HOLD POINT 2 /MILESTONE
cd500207-cf81-5a02-bd65-f0aa6f32e599 | note | Reference - Clause 15.3 MRTS70
e9c2052b-58e9-40b9-9d51-eaed5968b602 | signoff | HOLD POINT
dd352680-9bb5-4df4-9073-dc772a2b050c | checkpoint | 11 - Formwork, Bar Chairs, and Spacers
166cc467-d33d-5fbb-9c4d-ca8ca879da58 | note | ○ All formwork shall be subject to inspection and approval before the concrete is to be placed. Formwork shall comply with AS 3610 and conform to Class 2 AS 3610 surface finish except as otherwise specified. All forms shall be smooth, mortar tight and have sufficient rigidity to maintain the tolerances specifed when subjected to fresh concrete and other construction loads. Unless otherwise shown in the drawings, all corners shall be provided with 15mm x 15mm chamfers or fillets.
f8c17d93-6ba5-5e5e-8780-2cb086952fda | note | Acceptance Criteria & Frequency (Project Specific) - Approval
ec72311c-7ddb-53ea-9fbc-7d3619d43816 | note | Check Item - HOLD POINT 3
89a61cb5-d760-5e64-89fb-c13e94860411 | note | Reference - Clause 15.4.1 MRTS70
24f844f5-1f35-42e7-ac18-23d572bccc50 | signoff | HOLD POINT
25f22c5a-14af-4f04-af96-ff78f5bdaa0f | checkpoint | Concrete Temperatures:
b18b7796-0197-58ed-aff1-13e5d60f5473 | note | ○ Concrete shall be managed to ensure that at no stage does the concrete temperature during hydration exceed 80°C or the difference in temperature between the geometric centre of the cross section and any adjacent edge location exceed 25°C (see Clause 15.5.3 for location details).
6620f7aa-ac9a-51be-a8c4-12defd7c39d9 | note | ○ If these limits are exceeded, appropriate rectification or rejection of the element shall occur, and additional precautions enacted.
e8c06bf9-df8a-5360-882e-2e309dd888d3 | note | Acceptance Criteria & Frequency (Project Specific) - Nonconformance
f6ba0534-d8eb-5d3e-8ff8-e9c03692d5cd | note | Check Item - Nonconformance
d2a1d353-685a-58cb-bbb6-c4e3ab3e7e61 | note | Reference - Clause 15.5 MRTS70
6ffef8eb-9aea-45c5-a8b3-2b743395ed56 | checkpoint | 12 - Placing and compacting concrete
f4f982f1-f322-515a-a599-8ab2b29e9f49 | note | ○ Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
86ab1127-411f-5246-b136-e7bcb5acf334 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
ed388b2c-8040-54dd-8b61-0a59c5c767fc | note | Check Item - HOLD POINT 4
0d33b095-44f4-5ce2-be6c-322a4b35ba6b | note | Reference - Clause 15.6 MRTS70
95311988-caf1-49bd-b167-9763e18b9206 | signoff | HOLD POINT
ad45487d-b0b0-4c1b-96e8-f4566e62278d | checkpoint | 13 - Placing Concrete - General
64c88265-a817-5f9c-8170-11f8c3551ae4 | note | ○ No concrete shall be placed in the Works until falsework, formwork, reinforcment and stressing materials have been inspected and all foreign material has been removed from the forms and all foreign material completely removed and the compaction equipment and placement procedure has been appoved.
a2e4b782-5943-5e79-80ad-374f419841a4 | note | — Placing operation shall be conducted in the presence of the Administrator and Contractor shall give at leat 24 hours notice
897b09ce-8ba7-5383-89a3-12c91b3a9d5c | note | — Where reinforced concrete is placed on earth or sand foundations, the earth or sand is to be compacted to 95% RDD
fccec0c1-8cb2-512f-9541-7bea9605eb18 | note | ○ If placing operation required a drop of more than 2m, the concrete shall be placed using a flexible tube reaching the base of the formwork.
4dba775d-4a31-51ad-9f1e-9dbd3643a0ea | note | Acceptance Criteria & Frequency (Project Specific) - Approval, Visual
639b58b2-2284-593c-8e3d-30e85341e52a | note | Check Item - HOLD POINT 5/Witness Point 2
38dd7d3d-8da9-5426-ac5e-d16b304cb2d7 | note | Reference - Clause 15.6.1 MRTS70
0da8d06f-4542-459e-ad7e-c1e3f2a22758 | signoff | HOLD POINT
76783e27-b693-42b1-b650-70ae407fd218 | checkpoint | 14 - Sheet Seperator
e52c49eb-29e8-5b51-bafc-2a160692834f | note | ○ Polythene sheet separator of thickness not less than 100µm, and extending at least 300mm beyond the concrete work, to be placed between the ground/bedding and the concrete
cebe9999-9fbc-529b-afee-9e1fc91162d2 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
8538d72d-efde-5ddb-8223-d582fb788d67 | note | Check Item - Check Item
1f848850-dbc0-5057-9923-7f570a337fb9 | note | Reference - Clause 15.6.1 MRTS70
7d932bb5-6c78-4c96-a3aa-2d737bb856b4 | checkpoint | 15 - Concrete Placement Under Water
6a0a9cb1-ee42-5db4-83fb-4ff15659f877 | note | ○ Prior to concrete pouring commences the application procedure shall be submitted 2 weeks prior. Placement of concrete under water shall be carried out in the presence of the administrator and comply to techniques as specified in MRTS70 Clause 15.6.3
e062f03d-4323-5753-89ab-cf77580cfc3c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3d8909c5-1f82-59f2-a79e-c353860ceb18 | note | Check Item - WITNESS POINT
f06a602a-67ed-5517-b5ba-9c372a20f010 | note | Reference - Clause 15.6.3 MRTS70
27d58bca-9483-4678-887e-ed8815e5290a | checkpoint | 16 - Compaction of Concrete
78faeb1f-debf-5809-84d2-606a94391f53 | note | ○ The compaction for concrete other than for concrete to be placed under water and for no-fines concrete shall be deposited in horizontal layers not more than 400mm thick. Compaction of concrete shall commence immediately after deposition by using high frequency internal vibrators supplemented as required by external form vibrators.
3e1db44d-56e3-51e3-9216-7c5cabc01279 | note | Acceptance Criteria & Frequency (Project Specific) - Check
638292d9-ae97-5a1f-8006-c12b7d61dfda | note | Check Item - Check Item
75fc4159-906e-5611-8527-e72e9f411f3a | note | Reference - Clause 15.6.2 MRTS70
2febfe8b-8251-4e3c-a669-a241f3e3c0b7 | checkpoint | 17 - Removal of formwork
150d8660-25da-5e70-8a7c-41fa8c1806bf | note | ○ Forms, falsework and centring shall remain in position until the times stated in Table 15.8 MRTS70 elapsed after completion of concreting.
cf549efa-7a67-5d76-bd5a-b017cbfe7eb6 | note | — — — — — — — — — — — — — — — —
71163278-193a-5c34-b0da-088eb77b6a6f | note | Exposure Classification ¦¦ Minimum Form Retention (hours)
975fac5e-f6d7-52da-81cf-b55ce419a027 | note | — — — — — — — — — — — — — — — —
a25d251f-0b56-57bc-9bb3-fcd590ee2bbf | note | A ¦¦ 48
4bc74034-0da6-5a6c-b269-348253b5d6dc | note | B1, B2 ¦¦ 72
f659da63-0498-5f51-ad98-e653bf5c4937 | note | C1, C2 ¦¦ 120
be4febb8-b3bc-5fcb-9043-9107912b0249 | note | — — — — — — — — — — — — — — — —
75244d68-0e5e-54e3-ae55-0fd27689dd46 | note | ○ For structural concrete 70% has been reached of the 28 day strength characteristic and 7 days no loading should applied
1fc4a5c1-9c42-5998-a799-88617dab315b | note | Acceptance Criteria & Frequency (Project Specific) - Approval
bd4eab32-ab59-5aa5-9f2f-a665cf9f6550 | note | Check Item - HOLD POINT 6
a0b84f67-e984-5f7b-934c-61f7b9749ad6 | note | Reference - Clause 15.8 MRTS70
d9bc63fd-bd35-4d53-a5ff-d46ff4fcca86 | signoff | HOLD POINT
132100e4-d425-42bf-8b74-3486742dbdde | checkpoint | 19 - Early loading
dc6e8c24-709d-5ffa-967a-9f69b940a84d | note | ○ Concrete shall not be loaded until seven days has elapsed from placement of all elements within the load path, including foundations.
97dfc3ee-00c2-5df0-8d92-8fc4bfef4a16 | note | Acceptance Criteria & Frequency (Project Specific) - Check
9ceddc9d-4eb5-58ed-8729-fae7d2f34342 | note | Check Item - Check Item
cc620c8b-6ba3-59bb-ba4a-6b308814ded5 | note | Reference - Clause 15.9 MRTS70
3094783a-8e75-4468-a8fd-e7add9852140 | checkpoint | 20 - Concrete Curing
0b2c3532-b545-5cfc-a554-7acf3462d116 | note | ○ Contractor shall submit to the Administrator curing procedures 2 weeks prior to the first concrete pour. Curing shall continue for a minimum period of seven days. If forms are removed in less than seven days, curing of the formed surface shall commence within one hour of stripping, unless otherwise specified in Clause 15.12.
7ad1edcf-e91c-5ae8-955c-a788ef5680c9 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
21937581-1064-5613-a0e8-98368273917d | note | Check Item - MILESTONE
429c3bb2-f66a-5ba4-a674-1e2b2e2b94fc | note | Reference - Clause 15.11.1 MRTS70
f9339d38-29f8-442a-8fb3-862a6a485dfd | checkpoint | 21 - Rectification of non-compliant surfaces
4720b5fc-b60c-5c4a-aeea-486a72a7ff20 | note | Where surfaces fail to meet the requirements of Clause 15.12, the following actions shall be undertaken:
20a838fc-db17-57a8-99e7-ddd04dc6c71a | note | a) All pockets or honeycombed areas shall be cleaned out to sound concrete.
a54afd13-d89e-585b-b479-25acb4cfad05 | note | b) Small voids, not more than 150 mm in lateral dimensions or 20 mm deep, shall be filled with a registered repair mortar, vibrated as necessary. The surface of the patches shall be finished flush with the adjacent formed surface.
24fa9c30-9a49-5b82-b3bd-ffa8f8239f17 | note | c) Large voids shall be formed and filled with vibrated concrete of the same mix design. An effective bonding agent in the mix and on the interface shall be used.
91905680-f68b-5c99-a1f9-f83160bcceea | note | d) The repaired area shall be cured in accordance with Clause 15.11
16b1d737-e915-5de8-aac4-e3441e0d7ef3 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
9b7b9a61-7d76-5a43-adae-bf2c53ae93b7 | note | Check Item - WITNESS POINT
09f0daff-c16f-54a3-bbf5-d2360226047c | note | Reference - Clause 15.12.2 MRTS70
96eb4db6-db27-4a92-a144-1d3668ae8f7a | checkpoint | 22 - Surface Dressing of Concrete
3c1f9676-535a-55c9-b858-a75567d17ec4 | note | ○ Procedures shall be established for surface dressing of concrete and shall comply to the standards established as per MRTS70
1a806dc3-f8da-56cf-9172-8f72f36f0b7f | note | Acceptance Criteria & Frequency (Project Specific) - Check
7a1c2ce1-c0ad-5ad4-8402-30840c623f7f | note | Check Item - Check Item
dfe6d86a-643d-5562-9b90-a533ca4c8a1b | note | Reference - Clause 15.12 MRTS70
d4d63741-afb0-4d21-9bed-e79896c8c6c2 | checkpoint | 23 - Construction Joints
718a11e2-44f5-5c70-bd71-97d7c36d5bf2 | note | ○ Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
56b86e50-bbd3-50d2-bf5f-8a690c2477f2 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
704785a5-9e54-5fdf-9afd-87f74ddf6e05 | note | Check Item - HOLD POINT 7
0c4eacbb-d40f-5489-a50c-42f9eaa226f4 | note | Reference - Clause 15.13 MRTS70
cd3eb7b8-27af-4cc9-b707-37f9c2fcde33 | signoff | HOLD POINT
20398e77-0fa8-4d38-ae71-c4c5fb2f2306 | section | Requirements for precast and precast prestressed concrete
910f5acb-e54b-4b89-b09b-3b1cd7fddf8f | checkpoint | 24 - Placing and compacting concrete
5de5136a-c47f-541d-aedb-aecf739fffba | note | No concrete shall be placed in the Works until:
a721053b-6d8a-51c1-9766-167d8dc133ac | note | a) the mix design has been approved by the Administrator,
0b7593e6-86cc-59a4-8764-58308dfe1b10 | note | b) the registration status of the precaster has been confirmed, and
33cc7e9b-b916-51e0-8831-969dbb8509e4 | note | c) any project-specific requirements have been addressed regarding placement and curing.
539f39da-bb04-50a4-a485-c97af440ae36 | note | Acceptance Criteria & Frequency (Project Specific) - Approval See HOLD POINT 5
0554ef36-edc4-5e14-b09b-257e1655b30a | note | Check Item - HOLD POINT 8
f93b3356-24df-5421-ac9c-481a93582c4a | note | Reference - Clause 16.5.1 MRTS70
50370197-5692-43ba-8c04-1c60aef2858e | signoff | HOLD POINT
4b666054-6902-481b-955f-bc55b2d1fd19 | checkpoint | 25 - Rectification of non-compliant surfaces
ba99826f-4217-5c93-b61f-f5f6d57e5337 | note | Where surfaces fail to meet the requirements of Clause 16.8, the following actions shall be undertaken:
8ee3ab35-179c-5dab-a0ea-ed88e16d37cb | note | a) All pockets or honeycombed areas shall be cleaned out to sound concrete.
3780e1bb-379a-58b5-a6e5-68f639ed4c3c | note | b) Small voids, not more than 150 mm in lateral dimensions or 20 mm deep, shall be filled with a registered repair mortar, vibrated as necessary. The surface of the patches shall be finished flush with the adjacent formed surface.
8f515339-bbfa-5c5c-b76e-ca71f5b1e8fd | note | c) Large voids shall be formed and filled with vibrated concrete of the same mix design. An effective bonding agent in the mix and on the interface shall be used.
108d8834-01f7-5e91-9724-a018f9e92663 | note | d) The repaired area shall be cured in accordance with Clause 16.7
8a4890cf-f43f-5c9f-bc38-123988aa8a54 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
794e1de1-4c28-595e-a114-4c15a871eae4 | note | Check Item - WITNESS POINT
fac719c6-8568-506e-8ac2-70e11c43ae7b | note | Reference - Clause 16.8.2 MRTS70
5b556131-585c-44f4-8341-bb6f70759fb0 | checkpoint | 26 - Construction Joints
a9d5d1ed-43b7-5870-81be-b2ba61808aa3 | note | ○ Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
0c41f357-4e6b-5c26-85cf-fa8a0a546882 | note | Acceptance Criteria & Frequency (Project Specific) - Approval See HOLD POINT 7
d12511de-0ce1-5231-9194-39d1c7b760f1 | note | Check Item - HOLD POINT 9
0a8a19f4-d6ed-533b-a9c5-482c83e0e341 | note | Reference - Clause 16.9 MRTS70
8bced314-6af1-47eb-8cfe-d14fbdf6cbc5 | signoff | HOLD POINT
8c378245-14e6-424e-92b2-0bee4705199d | section | Normal Class Concrete
3524b8d2-8795-44de-bbd9-c4b7edd096a7 | checkpoint | 27 - Long distance travel and extended placement times
316af968-26e0-5b61-b7c2-2b74fd3834c6 | note | ○ Where travel times are, by necessity, longer than 90 min as listed in AS 1379 Clause 4.2.5, a procedure for long-distance travel or extended placement times shall be submitted to the Administrator for approval six weeks before concreting begins.
ddfeacdc-2a2e-5749-aff0-8e33892e53c1 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
c03b163a-7b19-58ea-a8fc-f3f5bcf662e6 | note | Check Item - MILESTONE
b9fd2785-951f-5451-803a-d851bd64aa87 | note | Reference - Clause 17.6.1 MRTS70
624a4f2b-76e4-4c84-8dad-31516280e0f9 | checkpoint | 28 - Falsework
0d47dcf1-702d-50ed-9e38-24500991a57a | note | ○ Falsework shall conform to AS 3610. The design and erection of falsework, the method of founding or supporting the falsework and the time, order and manner of its release shall all require approval of the Administrator.
83074b78-f6c2-5dfb-9c3f-2801611e8fc5 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
a5d63938-0709-507a-af4a-7a5d7190c49a | note | Check Item - HOLD POINT 10
5a96d64f-8be8-5951-928c-a01a766b7ce1 | note | Reference - Clause 17.10 MRTS70
4a0dc349-89fe-4e05-a4f9-6f40ad74b2e2 | signoff | HOLD POINT
10bf4cf8-56a7-46f2-ab0d-9c86889c2b11 | checkpoint | 29 - Formwork
edc623f5-56c5-56d0-b9aa-b0de2e24a65f | note | ○ All formwork shall be subject to inspection and approval by the Administrator. Formwork shall conform to AS 3610 and provide a Class 2 AS 3610 surface finish, except as otherwise specified.
f8b641ee-6af8-55f6-a171-96891f58a3cd | note | Acceptance Criteria & Frequency (Project Specific) - Approval
afa3015d-6fe3-58fd-ba8a-1a2995c60925 | note | Check Item - HOLD POINT 11
5cbf436b-e4b1-5499-9ea2-3589ea84ec98 | note | Reference - Clause 17.11 MRTS70
a3817e73-1409-4569-8159-76927e34de5b | signoff | HOLD POINT
bfab2529-c135-46a8-98fa-7b5ff6904653 | checkpoint | 30 - Placing and compacting concrete - General
c0059d6b-bbec-521d-8702-94f5c8a585ca | note | No concrete shall be placed in the Works until:
6566852b-df6f-5fe2-9c78-c0814fe5c7a8 | note | a) the formwork and reinforcement have been inspected, and
67e7b8bb-f570-55b0-9316-271c71578c92 | note | b) all foreign material has been completely removed from the forms.
6c9f1e4e-bd4e-52c2-9996-8b586737aee5 | note | ○ The Administrator may revert this Hold Point to a Witness Point.
57a450e8-20e7-5fdb-86a9-bcae80d7fb99 | note | ○ The placing operation shall be conducted in the presence of the Administrator Witness and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
e4406d87-f5d6-56ef-bb89-933d61913297 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
708bda7d-991f-5502-b90b-906e971c4841 | note | Check Item - HOLD POINT 12 / WITNESS POINT
a719d48c-b22b-542a-a8f5-af09ff4a74c3 | note | Reference - Clause 17.12.1 MRTS70
e94e8f40-1158-4df5-9a52-a6ce0b52a979 | signoff | HOLD POINT
0c9901cd-b965-4775-b432-f7b1ebc58d19 | checkpoint | 31 - Removal of formwork
99e83cb8-9209-5c83-ae5d-b7af7448042e | note | ○ For cast-in-situ concrete, forms, falsework and centring shall remain in position until 72 hours has elapsed. Precast concrete shall not be removed from the formwork or formwork stripped until 40% of f’c is attained
fc5d764d-ccf8-5ec6-95e0-0c4968e660e8 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
aa538c56-d740-56eb-a2c9-7adaaf1e7c85 | note | Check Item - HOLD POINT 13
3b1f04d6-1432-58bf-8eaf-b3b8f36766b7 | note | Reference - Clause 17.17 MRTS70
f312018d-a436-4e0c-a934-1c2668dd66ab | signoff | HOLD POINT
edc39730-70e8-4c5b-b974-cb21180ef023 | checkpoint | 32 - Formed surfaces exposed to view
9512d478-6d28-5dc7-9ceb-8ecdf6385fa8 | note | Following the removal of formwork the following operations shall be carried out to the standard approved by the Administrator:
0938180e-6699-543a-87cb-ea06f75d26ff | note | a) all fins and other unwanted projections shall be ground off to provide a smooth surface.
5038e72e-ceee-597b-af87-70ea41b5e1da | note | b) where specified in the Drawings, surfaces shall achieve the required surface finish to AS 3610.
61f6118d-e4a5-5fa0-ad5b-7be9b80ab7e8 | note | c) where surface finish is not specified in the Drawings, a Class 2 surface finish to AS 3610 is required. Repairs shall be a Witness Point
cc118314-e79b-533c-9b5f-48fe4564806b | note | Acceptance Criteria & Frequency (Project Specific) - Approval
b09f93a8-fad6-5be4-acf0-3dc0792c3dc4 | note | Check Item - WITNESS POINT
68ad1bd4-597b-567b-b8cc-8f30f5d303b3 | note | Reference - Clause 17.18.1 MRTS70
377388e3-6b4b-424a-8076-4616840821ba | checkpoint | Final Verification
32e158d2-7f07-5d3b-83ad-14f8db728f80 | note | Doval Representative
79aa249e-27d4-5b0b-b866-03d3cdb9b3ec | textbox | Print Name:
053c2a2e-84b9-58ca-aaba-716488658acd | date | Date:
a5fc378b-0263-5886-8c39-191b0719a87e | note | Administrator
442787ed-6744-5337-b1a1-9049c33407a7 | textbox | Print Name:
8a47ffc0-2404-56a0-b2e5-408839044e8e | date | Date:
fb5bd097-7d95-41f4-9084-abda047d7fee | signoff | Signature
1ad9903b-e643-4809-b270-3115f1ca3e9b | section | Final Sign Offs (to be completed at closure of Lot)
ecc46e64-ed23-49d3-9552-fad419b2870e | checkpoint | Agreed Quantities
f5b3617b-71e4-4504-9508-efc16ae44d6d | signoff | Agreed Quantities Sign Off
6618284f-4ba0-49da-9b82-7f87dbc6e310 | checkpoint | Closure of Lot
817f28a5-dfb8-4ee0-8a10-1a1080f5a43a | signoff | Closure of Lot Sign Off
db35c1ff-4e0c-4184-97d7-64f4d0a742d3 | checklist | 04.00 - Back Fill | itp | 04.00 - Back Fill
88297046-b7bc-4e47-bf87-8dae7572416b | section | Details
0f77cc19-467a-454b-9a45-99bd94dff940 | checkpoint | 1 - Document Submission
63f755d0-917d-5b2d-8f5e-67343a1f66be | note | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
9ad566fb-2d45-5ce0-9d5b-cbaa81a92b2b | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
3da081c8-46ad-5247-a23d-cdf36d567ad9 | note | Check Item - Check Item
d5c2c9ed-17d6-43f4-83bf-abb446bc4b8e | checkpoint | 2 - Traffic and Safety Controls
ba168bc8-5fe0-59f6-a893-036212c3431c | note | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
dbb0a5d5-cc46-5b58-99f0-a3fed55ddd0e | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
6c238796-74ef-53f0-96bb-458dfd430956 | note | Check Item - Check Item
a1f24e89-ef78-4d81-9f92-d0d712228307 | checkpoint | 3 - Material Conformance:
91dd6297-af84-5b66-bc68-460f512f2bf1 | note | ○ Prior to incorporating any backfill material into the works, the contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrates the source meets the specified material requirements.
418527b4-5f8c-54b1-98a9-d3f88b2a6415 | note | Check Item - Hold Point
563d5da7-6910-5275-80a3-566ac17b1f43 | note | Reference - Clause 19.1 MRTS04
61e0f2bf-85f1-4033-abf7-3fc2ce326acd | signoff | HOLD POINT
95a9a712-e781-428f-845e-f727807d4a66 | checkpoint | 4 - Earth Fill Material
c0ed3dbe-0e15-5a8d-a5f9-6d257f45b9f4 | note | ○ Earth backfill material shall comply with the requirements of earth fill material Class A1, Class A2 or Class B specified in cl 14.2.2 except that 100% of the material shall pass 25.0mm test sieve.
8fccecac-f394-5b2b-9879-d1614c6b42d5 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
4eb6ce88-6e7d-5c61-996b-4b58db41d798 | note | Check Item - Check Item
71ceb1b4-74eb-5238-ac71-6f83a4a00cf6 | note | Reference - Clause 19.2.2 MRTS04
b578780b-3de2-4eb5-a161-1dbf7b1cdc1c | checkpoint | 5 - Select Backfill Material
76f7fcbb-ff94-5a76-9944-887abc2224bb | note | ○ Select backfill material shall be gravel or loam and shall have material properties as specified in Table 19.2.3
126e494b-01a1-53d2-9264-960a6675dfab | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
7a2204e4-74fd-54ce-b84c-562d2305fd34 | note | Check Item - Check Item
4ce45c43-1c1d-5769-9441-35856d2725b2 | note | Reference - Clause 19.2.3 MRTS04
e0a6c974-6620-4aa6-b159-88cae765a2cb | checkpoint | 6 - Geotextile
9b6f1e38-e024-5c32-9cb1-2f7c2e065ac7 | note | ○ Geotextile shall be a material of the appropriate strength class and filtration class complying with the requirements of MRTS27 Geotextiles.
e26d06e8-ae1c-51b0-b7de-d06bc47a48b0 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
970dc26b-a48a-50ea-8988-a684f361e6d2 | note | Check Item - Check Item
4fe69293-1d9f-5ae2-aae0-fc309a94a54b | note | Reference - Clause 14.2.6 MRTS04
0f6b193c-94a0-47d2-a952-aae7fa4e562a | checkpoint | 7 - Construction General
1a9ecf96-935b-51c7-a6c7-194b8bb17928 | note | Check the following requirements;
d5be0be5-2c52-5143-b0ae-b109bd698533 | note | ○ Embankment is constructed to the shapes, zones and other requirements shown on the drawings or otherwise as specified. (Refer to Clause 9.3 of Annexure MRTS04.1) Fill material shall be placed in zones as shown in Figure 14.3.1
b421b5c2-b916-5145-88b3-69e6a191b785 | note | ○ Earth fill material is to be placed so that it is homogeneous.
f533c0e2-d450-588b-8dd7-b602374152c5 | note | ○ Embankment fill material shall be either earth fill material or rock fill.
89cabb33-5e89-5400-8289-f81bb982ef2f | note | ○ Care shall is taken when sourcing fill material so that sufficient Class A and Class B materials are available to complete the embankment in accordance with the requirements of this standard.
525e663b-e890-50af-a689-73af32bebb80 | note | ○ The method of construction employed shall be the compacted layer method for suitable material placed in an embankment within a height 600mm below subgrade level.
b1197f86-0fcc-5b00-8fe2-e12d38f85131 | note | ○ Compaction Standard shall be as specified in Clause 15.
278c7a33-bb94-57b3-95be-39c40052625f | note | ○ Permanent embankment batters shall be finished in accordance with Clause 16
e6bf3bde-4d24-5a90-9032-5de5cfb86ed3 | note | Acceptance Criteria & Frequency (Project Specific) - Check
9e1f5511-d97b-5a96-a567-20cd81327aec | note | Check Item - Check Item
43dde034-d8bf-56c5-83f5-df290e80ee4a | note | Reference - Clause 14.3.1 MRTS04
0d46e099-c569-4da0-a2b3-511a4811cd21 | checkpoint | 8 - Earth Fill Homegenous and Zoned Embankments
baf13289-8fa3-5b32-b356-2e1eb70c5b04 | note | ○ Cover for zoned embankments, depened on embankmnet height to subgrade level and rainfall zone. Unless shown otherwise in Clause 9.4 of MRTS04.1, the requirements shall be given in Tabe 14.3.1. Zone definitions for the cross section and rainfall are shown in Figure 14.3.1 and Table 15.3(c)
c5895b07-9ad1-52d0-a65a-fb902b35672c | note | Acceptance Criteria & Frequency (Project Specific) - Check
517a2129-3bec-5e20-85bd-74ec8ebfa859 | note | Check Item - Check Item
e6c9f5ca-329e-5e9c-b1db-62e030134062 | note | Reference - Clause 14.3.1 MRTS04
8504e194-8bd8-452e-af47-45a435aea5bb | checkpoint | 9 - Geotextile at changes in material type
59541fe5-4fb7-5839-a9cd-681adf37fdfc | note | ○ Geotextiles requirement shall comply with MRTS27 Geotextiles (Seperation and Filtration) shall be installed at the interface where fill material changes from mechanical interlock to compacted layer method.
ca727175-d48c-5df0-864f-dd4df10e6907 | note | Acceptance Criteria & Frequency (Project Specific) - Check
2fe7baab-0422-5f53-8c3b-f0fa3feac466 | note | Check Item - Check Item
e19b4b8d-fe55-5f01-8af4-b8742af37145 | note | Reference - Clause 14.3.2 MRTS04
7e1854b1-ec79-454e-bf7f-ac0cb332be1a | checkpoint | Final Verification
3a871e73-4552-5ec8-b4a6-6c924d376fdd | note | Doval Representative
2daec67d-2b53-55e0-b779-dfaab7653459 | textbox | Print Name:
9fb1708c-afe1-5431-89ef-7e90dac4c03f | date | Date:
7d66a61c-9c75-5abb-bb14-37ff0bc017f3 | note | Administrator
97bf8aa7-e8f6-5db8-a004-352a667db7c9 | textbox | Print Name:
314faae9-3911-5a84-a7e2-909a45842e7f | date | Date:
a769c2b4-a187-4764-a2bd-37bd1a6bc054 | signoff | Signature
173b3588-c58b-41ad-bf68-ed825d8e5ea3 | section | Final Sign Offs (to be completed at closure of Lot)
6c3e8faa-3fb4-4bf4-a7fb-4d286780b9b7 | checkpoint | Agreed Quantities
f6117e55-38ad-47bd-9ee0-1cd40b8cae85 | signoff | Agreed Quantities Sign Off
db118dfc-5e79-458a-8225-ae3a5a406a23 | checkpoint | Closure of Lot
d0754a43-e4e6-4dd5-a9b5-3aa44df47918 | signoff | Closure of Lot Sign Off
ea9c97c8-187a-491a-bc49-42afdaa0076e | checklist | 05.00 - General Excavations | itp | 05.00 - General Excavations
cb72db25-a391-43e6-8431-dcda1eab0616 | section | Details
1b47c937-7fd7-4bf8-a50b-12cf689876e2 | checkpoint | 1 - Survey Set Out
0b7c3f41-2d7b-59eb-8b6b-19bf7096425e | note | ○ Survey setout complete. Surveyor has setup reference points for width and depth of excavations.
6308686e-42f2-5430-87b6-d7bb1a283f58 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
9af8f6f4-bb57-5632-9c30-fbf467cb8fd4 | note | Check Item - Check Item
2daed9ac-4288-47af-a709-fd3e6718dc90 | checkpoint | 2 - All Excavations
d710a6c6-a53b-5a2e-acf6-a39ee248ebfd | note | ○ General Excavation and earthworks activities shall be completed in accordance with MRTS04 General Earthworks
9a6b378b-f517-5ea9-b30d-dd4e8f2eea51 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d45d0466-ffd3-5b4f-913e-6b8fba4c5703 | note | Check Item - Check Item
1fb42067-84d6-5185-aab4-b6ca4d0b4a5f | note | Reference - Clause 13 MRTS04
58318e44-7c07-4f4c-b26c-02a81f08fafc | checkpoint | 3 - Construction requirements
6f560b7a-0b37-5dd1-98c7-dc6bba31b9fe | note | ○ It shall be the sole responsibility of the Contractor to prove that material is Unsuitable Material as defined in Clause 9.2.
1e1afe84-963c-5449-9f8a-efc243858aee | note | ○ Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim.
9486dd38-d7ad-5a95-9407-8bd86a456f7d | note | ○ Within 24 hours of the above notification, the Administrator will advise the Contractor of the required treatment, if any, and the extent of such treatment.
d20183f5-8193-5bb9-8309-c4f3a7908400 | note | ○ Methods of excavation of Unsuitable Material shall be in accordance with the requirements of Clause 13. Excavated material shall be used or disposed of in accordance with Clause 11.
e3a5808c-9297-55c9-a8a3-6ce41150ea20 | note | Acceptance Criteria & Frequency (Project Specific) - Notify
1b27f0c7-7281-5371-9bd2-ddb0330ae829 | note | Check Item - HOLD POINT 3
610fff6d-ac7c-5e97-8df3-3ff3aaf5dc89 | note | Reference - Clause 9.4 MRTS04
26dae34d-966e-43f7-8798-233fed29a625 | signoff | HOLD POINT
a8701d87-7ae0-43f3-8a44-f5b1d10107cb | checkpoint | 4 - Testing and reporting of acid sulfate soils
cedcc135-2cbc-594d-b7e5-f737e5596c5d | note | ○ Testing for acid sulfate potential and reporting of test results shall be carried out on all excavated material and exposed cuttings on the site which could reasonably be expected to have a possible acid sulfate potential.
138f3e0c-f69d-5339-aefa-a5babb69dc87 | note | ○ The testing frequency and reporting shall be as detailed below:
ab1b0db4-4917-566e-9a13-c9a79e507a5e | note | ○ Visual testing undertaken by trained personnel shall be continuous throughout the earthworks phase of the Contract and shall be applied to all such areas on which work is performed including Borrow Areas.
96bbd42d-9966-5cb0-bab8-b28204bca4c2 | note | b) Field pH testing for both actual and potential Acid Sulfate Soils shall be carried out (on the same soil sample) on all Borrow Material to be imported to the Works and all material excavated or exposed in the Works in areas specified as having acid sulfate potential. A minimum of one test per soil type shall be carried out. The results shall be documented and reported to the Administrator prior to such materials being used on the Site. Hold Point 5
0fd99d6a-d04d-50fc-8edc-d8d31708c55b | note | c) Where materials test positive to actual or potential acid sulfate contamination in the field, the Administrator shall be notified immediately. Such soils shall not be used on the Site until the results of subsequent quantitative laboratory testing negates the results of the field testing. Quantitative laboratory testing shall be in accordance with the National Acid Sulfate Soils
55bd69f5-ae62-5ab7-b3b1-255e02a3df5f | note | ○ Guidance: National acid sulfate soils identification and laboratory methods manua
aa71c875-b29c-5387-b83d-ea76c1b01199 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d5c80f43-4d59-5f42-98a4-7218af8df785 | note | Check Item - Hold Point
ef9bf497-56ff-5e31-a1ca-a482366d0b5c | note | Reference - Cl 10.4 MRTS04
5ed47dc4-a7f7-4f20-9e80-f75f7a205b1e | signoff | HOLD POINT
5a638671-3358-4153-a87e-ed11d1046fdc | checkpoint | 5 - Unsuitable Material below the lines of cuttings:
cfb271b4-07df-579a-bbd3-5ac9f5d774b1 | note | ○ Material which deemed unsuitable as per cl 9.2 below the finished lines and levels of cuttings, shall be removed and disposed of in accordance with the provisions of cl 9.4. backfill material to be finished surface level with appropriate fill with reference to cl 18 & 19
9fb8028f-f939-5075-ad08-da078ddc2cec | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
9c2f156d-393d-554b-b4ff-48f87ecf114f | note | Check Item - Check Item
bf56b330-a376-52f7-9b10-ab9fd57d4355 | note | Reference - Cl 13.3.2.2 MRTS04
21901da9-dd0f-4b0f-837f-85fc5c7d39e0 | checkpoint | 6 - Bottom of Excavation:
d7afbbe3-2de2-54ce-80bc-002b4edf6cb9 | note | ○ When the level of excavation has reached subgrade level, contractor shall carry out the provisions of cl 18.3.3 and cease excavation until the subgrade treatment type has been determined with cl 18.3.3
f437ee55-feda-5a20-adf6-86a25fe372da | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
db334e10-8f83-5c92-b7c7-ba99e0fdadcc | note | Check Item - Check Item
7e7e694d-2e2d-54e8-9223-2ad9419c89e1 | note | Reference - Cl 13.3.2.1 MRTS04
f77db365-d0a2-434f-b640-88d362b54909 | checkpoint | 7 - Pre-Splitting:
bf689e21-6ce0-5222-ab19-2b4738b959d1 | note | ○ Batters specified in cl 8 of annexure MRTS04.1 and batters of rock cuttings with a slope of 2V to 1H or steeper shall be pre-split prior to burden blasts to ensure protection. Spacing of pre-split dill holes shall not exceed 1000m c/c
3389787a-4b71-5097-b618-3f7ff9a2bc89 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
eabb02fa-9c63-57bd-ba62-1235f1bb42c8 | note | Check Item - Check Item
37f3e64e-2d1b-55f0-ae8b-63678e3c6106 | note | Reference - Cl 13.3.2.3 MRTS04
6dd9109e-c131-43eb-be3a-2ea06118937f | checkpoint | 8 - Berm Drains
9601f49b-ecff-5af7-8531-eccf6a3158e5 | note | ○ Berm drains shall be constructed where shown on the drawings. Unless shown otherwise, berm drains shall have a nominal depth of 100mm and shall be two metres wide. Berm drains shall be concrete lined in accordance with MRTS03.
d9ec9687-128c-5910-a10f-b184d64f7543 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
ea6bcf95-9545-512c-b50b-d2cff6891564 | note | Check Item - Check Item
fe77a056-b19d-5b3b-86c3-c713641676d3 | note | Reference - Clause 13.3.2.5
92f165e1-27fc-446b-90d0-7452796dc6a9 | checkpoint | 9 - Confined Excavation:
81bb0538-a118-5798-af1f-7eb7e6f2e78f | note | ○ Protection of Excavations.
6be49373-9c21-55a2-a2c3-ee8223250d18 | note | ○ Contractor shall take necessary precautions to protect an excavation and all personnel and equipment in or about an excavation.
15dbfe08-ccb1-5854-8d83-218b87c91809 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
04e8c4ff-0442-5e39-a137-8772cf5a2647 | note | Check Item - Check Item
ad63f091-c99d-57b5-bc2c-dae05ca16998 | note | Reference - Clause 13.3.3.3 MRTS04
d712e85f-9d37-4fbc-85a9-f4e8dd98ff63 | checkpoint | 10 - Confined Excavation: - Bottom of Excavation
208531ab-f2ce-564f-86a0-8a1d1cddb3f7 | note | ○ The material in the bottom of confined excavations shall comply with the density requirements of Clause 15. Where the insitu material does not comply, it shall be compacted to a depth of at least 150 mm in accordance with the requirements of Clause 15.
e9e38037-96dd-55b0-a95a-457996d4ad6f | note | ○ Where precast concrete items (end structures, walls, kerbs, kerb and channels etc) are to be placed in excavation, a 50 mm layer of bedding material complying with the requirements of Clause 19.2.6 shall be placed and compacted to provide continuous, even support to the structure.
90c9cb2f-3405-56f2-b679-bc684e4a49d9 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
94004793-f1d5-5df1-b74c-d886852a3525 | note | Check Item - Check Item
71572a6c-69f5-507d-8693-c58e150dcca0 | note | Reference - Clause 13.3.3.4 MRTS04
00c0a38d-ea92-4a94-b8df-03442035e03a | checkpoint | 11 - Excavation for Load Bearing Footings
a7a988c1-b4cb-5376-b10f-eaa723775633 | note | ○ Excavation for foundations of structures shall be carried out to the dimensions and depths shown on the drawings.
064b903a-f6f7-5fd3-b2c6-eb963677b05d | note | ○ When adequate material has been reached at or below the depth shown on the drawings, the foundation surface shall be trimmed toa horizontal plane or horizontal steps, completely dewatered and presented for final inspection by the Contractor's RPEQ Geotechnical Engineer. No work which will cover the surface foundation shall proceed until the Contractor RPEQ and Administrator approval. The Contractor shall give the Administrator 3 days notice of such inspection.
d268b329-918e-5879-80bb-b7bb0ff35ba2 | note | ○ If the foundation surface has deteriorated since the time the foundation was approved and before blinding concrete or backfill material has been placed, additional material shall be removed until competent material is reached as described above and then Hold Point 6 shall be re-released
4e527ba7-6ff6-5ab0-8b9a-6f8d267447e1 | note | Acceptance Criteria & Frequency (Project Specific) - Notify
9c8abce6-b27d-5a52-890f-3b2e95e94206 | note | Check Item - HOLD POINT 6 / WITNESS POINT
38e07703-eefd-5ce0-8f29-84f78b3fe942 | note | Reference - Clause 13.3.4.1 MRTS04
f10571f2-e5f3-42c3-8a90-101eaae92330 | signoff | HOLD POINT
cd46f7f4-4fc6-4b6d-8ad2-1e35cc11e6d6 | checkpoint | 12 - Excavation for Pile Caps - Excavationf or pile caps shall be caried out to the dimensions and levels shown on the drawings.
98d8a97c-f9da-5e12-be5e-028341c36b82 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
849542b3-9eb5-5bcf-aec3-f74034291c1d | note | Check Item - Check Item
8e2a4651-fdac-5134-8242-1419e96031aa | note | Reference - Clause 13.3.4.2 MRTS04
039ee47e-e68b-4d50-9134-a851abb85966 | checkpoint | 13 - Special Requirements for Culverts
643ecb0c-cbd9-5f63-b191-7e4ec1230751 | note | ○ Widths excavation for culverts shall not be greater than those specified in SD1359
9231b85c-59a5-57e9-9e0f-4b73688edb34 | note | ○ The base material shall comply with the density requirements of Clause 15. If it is not complying the insitu
9bafcb07-d57c-5706-a362-f6e131ef371a | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
cfe23040-4835-562a-846f-6ee8b2d3c6d1 | note | Check Item - Check Item
c9478e06-198f-56b4-9107-a68a8f783fc4 | note | Reference - Clause 13.3.6 MRTS04
c3f51885-4334-41fe-a6a1-1d9e194a7c49 | checkpoint | 14 - Dewatering Excavation - Shall be carried in respect to the Environmental Management Plan. Under no circumstances shall water be disposed of to sanitary sewers.
650475cb-5463-5d4b-9ae5-92639c3f7945 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
c08dca30-3028-56ef-8a3a-805677410969 | note | Check Item - Check Item
3cfa802c-3029-55c9-80c6-c91d6553f898 | note | Reference - Clause 13.3.8 MRTS04
049a317d-ed37-456d-ba4a-fdda394b1efe | checkpoint | 15 - Supplementary Requirements:
1bb8f441-959d-5cd3-b28b-1514f596c788 | note | Where specified in the drawings the following work operations shall be completed in accordance with cl 13.1 of annexure MRTS04.1.
cdaf53ed-602f-5a50-a090-8720e6a4ca6f | note | — Trimming batters, removal and disposal of any material including boulders,
1331c628-bc43-57a0-8219-99146de51a95 | note | — Excavation, remmoval and disposal of any existing retaining structures,
454cc5f0-cf3e-587c-8687-c1241ca7a94c | note | — Removal and disposal of loosened material as a result of scaling shall be completed.
c9448d6b-a363-5a5f-94a6-9b2322cbf830 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
ac85c23c-f8ad-5ff1-9f44-0d83f8ed1020 | note | Check Item - Check Item
12fedb86-3be5-55d5-934c-6946b54d0b34 | note | Reference - Clause 13.1 MRTS04.1
92f1e3ba-dcf7-467e-9d09-e160bd87873a | checkpoint | Final Verification
5b7e48b9-5f00-5c4e-a12b-1c6888c04695 | note | Doval Representative
1d093617-53e4-5cb9-8b8f-2d0809db115f | textbox | Print Name:
bf5fb316-865d-5a08-b35d-093890714a4e | date | Date:
6219c079-f150-5dad-a93a-340d05acab81 | note | Administrator
c6c1f465-083e-5a80-acbd-e7f60bedcb2d | textbox | Print Name:
0d83f0d8-3ac5-5f1a-9081-58194ef1b7c9 | date | Date:
a20de1a0-9c80-4c84-9581-284a26e4c923 | signoff | Signature
a51cc506-d8b5-4a4a-af05-61a12c53d916 | section | Final Sign Offs (to be completed at closure of Lot)
14890005-5ae1-44b4-b290-458900a91277 | checkpoint | Agreed Quantities
a266f8f9-ef18-4493-9f04-6d9263298c15 | signoff | Agreed Quantities Sign Off
5380c808-cd32-4c01-b30c-13353a7b3968 | checkpoint | Closure of Lot
0f3cf220-1abf-4fd3-925b-3b846e412638 | signoff | Closure of Lot Sign Off
75df9de8-5002-4eac-9b07-c5979a00fe6a | checklist | 06.00 - Stripping of Topsoil | itp | 06.00 - Stripping of Topsoil
e675b2de-ef0c-46df-84fb-4ef791c2a977 | section | Details
67a109f9-ffd4-4348-9da1-3653f5937bf0 | checkpoint | 1 - Survey Set Out
b35d5a55-f5e2-526e-b034-52192e2ec876 | note | ○ Survey setout complete. Surveyor has setup reference points for width and depth of excavations.
eec263b5-f058-535a-b927-02e6aa189077 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
a262c4f9-0f93-5b2d-af73-bde0675de2d1 | note | Check Item - Check Item
020dfb8c-1cea-4879-8154-cacff6599b9d | checkpoint | 2 - Topsoil stripping dimensions
283dd317-f7e0-5290-9ad5-84c8664f84de | note | ○ Where Site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped from the Site at a 75 mm (± 25mm) depth, or from areas and depths as specified in Clause 2 of Annexure MRTS04.1.
22ed649a-2761-5bfe-be89-16db76362c14 | note | ○ Average depth - 300mm
f28cf168-e7f0-5728-8d3f-d712101cfa09 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
38ccbff1-f193-5c83-a2b9-e6b0895dfb40 | note | Check Item - Check Item
3485b847-6280-5bb5-86c0-8272438cd3a4 | note | Reference - Clause 8.2 MRTS04 Clause 2 MRTS04.1
dedf9211-85a8-4619-84e6-d7b5f20542df | checkpoint | 3 - Material considered suitable for use as topsoil
604a2690-6724-5542-b9a0-9d8697b2620c | note | ○ Soil stripped from the Site which is considered suitable for use as manufactured site topsoil shall be tested and ameliorated in accordance with in MRTS16 Landscape and Revegetation Works.
a80b2b17-092c-5a64-8e1f-3ce440f9d271 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
1e2ee643-96db-51b4-b064-6a60d2734803 | note | Check Item - Check Item
bccebfd0-8135-5153-ae15-701843c5bc88 | note | Reference - Clause 8.3
2511a398-e30c-47e1-a75f-2d8628646bac | checkpoint | 4 - Stripping to stockpile
d37e4149-db11-50d7-8623-688c851862c7 | note | ○ Material considered suitable for use as topsoil in accordance with Clause 8.3 shall be stripped from the Site in a separate operation to any other clearing and/or stripping operation. Stripped material shall be stockpiled in the locations shown on the drawings, as stated in Clause 2.2 of Annexure MRTS04.1. Material shall not be stockpiled within the drip lines of existing plants to be retained.
ec840604-3185-5739-b229-248fb5838292 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
814fda48-107f-522c-b4b9-cf38426c35c9 | note | Check Item - Check Item
e6a43a01-41fd-5e2a-b1c3-31ff8de410f2 | note | Reference - Clause 8.4.1
51e9b082-cb61-4800-aaee-d06654c7b336 | checkpoint | 5 - Surplus material
33486404-e58a-557e-9fd4-f9278792b48e | note | ○ Surplus material and material considered to be not suitable for use as topsoil in accordance with Clause 8.3 shall be assessed for use as fill or deemed to be Unsuitable Material and disposed of in accordance with Clause 11.
4872fa81-3a5e-5fb9-94f1-91e2afd33466 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
7da564c6-8311-5c94-af8d-f2cdbdfe9bac | note | Check Item - Check Item
32bb7ae7-4a87-51a9-9396-2476ca108d07 | note | Reference - Clause 8.4.2 MRTS04
92e63c1b-18bc-4741-a17b-f12f94c6a697 | checkpoint | 6 - Stripping limitations
45157821-67be-5db0-9381-e8f1a28eec5c | note | ○ Material shall not be removed from within drip lines of existing plants to be retained except where this would otherwise result in Unsuitable Material being left beneath embankments. The root systems of existing plants to be retained shall be preserved wherever practical.
c5c6795b-9829-536b-8476-203540fde267 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
75395837-7f75-512b-a466-358ef9fc74e8 | note | Check Item - Check Item
b3dd4f4f-6c76-5e5f-a18d-959640231274 | note | Reference - Clause 8.4.3 MRTS04
4df1ede3-a567-43ae-a88f-1ceeddd33d24 | checkpoint | 7 - Stockpiling of topsoil
34c0a17b-5620-5e50-acd8-876ccc03ceaf | note | Wherever practical, topsoil shall be transferred directly to placement as planting media. Where stockpiling of topsoil is required, it shall be carried out in a manner which ensures that the properties of the topsoil are not permitted to degrade such that it becomes unsuitable as topsoil.
b7cd94b7-5863-5f4b-b46c-2531ecb14d9a | note | To assist preservation of topsoil, the Contractor shall include the following provisions in the management of topsoil stockpiles:
cf63b783-d5cb-5b28-8afe-c16f9ca03999 | note | a) limiting the height of stockpiles to three metres
dbe9b799-e033-5d15-9385-8b7457d7385c | note | b) limiting the width of the base of stockpiles to 10m
a677c324-25e8-5478-96ea-6f95ca966772 | note | c) adopting batter slopes, protective covers and drainage which reduce potential for erosion and / or segregation
114674bd-d35b-5ac0-8b7a-c8de8e2b4ceb | note | d) limiting the period of stockpiling to a minimum practical time
ca244db7-ad2a-536d-8350-053f39178d97 | note | e) where stockpiling for greater that 12 months, the stockpile shall be revegetated with grass to provide erosion and preserve the physical and chemical properties of the topsoil, and
0be403c3-d20f-533d-94c2-fb92929f7183 | note | f) carrying out herbicide spraying or other treatment of the stockpile at intervals required to prevent weed growth and ensure the stockpile faces are weed-free prior to use.
03ba1dbf-6a81-512f-ad53-da403d82d08a | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
1f319401-6c9b-5ed0-af5b-9079619ee70c | note | Check Item - Check Item
ff58118d-3586-5cfe-bf48-c35154767b8d | note | Reference - Clause 8.4.4 MRTS04
d770679d-cf4d-4ecb-a138-a714963fa0f0 | checkpoint | Final Verification
b1a8d7c6-b7d8-5d3c-a442-cd6c6762dd1d | note | Doval Representative
79bcdcc8-3919-5a2c-89ae-9f4798c1d886 | textbox | Print Name:
48ec6ec5-2062-54f7-ac6f-f288a4dee164 | date | Date:
b57d10e6-f134-5b10-91be-78f98b1f6cfe | note | Administrator
8e13487c-ffef-56e8-97fd-720411aa7589 | textbox | Print Name:
f77a57b7-28e8-55b7-8dfb-3eb6fcb2de8d | date | Date:
5d30d6c9-f7a7-4bc7-860b-29f48ff9cebb | signoff | Signature
be8fe2c6-285c-466a-90c0-cb74fff3b695 | section | Final Sign Offs (to be completed at closure of Lot)
df930a86-528b-48af-afbb-cf10b98067a9 | checkpoint | Agreed Quantities
ae54d66a-4a96-465c-9da1-6b1d014dd7a8 | signoff | Agreed Quantities Sign Off
9ddb190c-f45e-4444-b97c-ddb536582476 | checkpoint | Closure of Lot
f0bd575a-bf1e-4202-875b-ce437de66905 | signoff | Closure of Lot Sign Off
4fb66e21-12fe-4fcb-8b41-244dce2b8252 | checklist | 10.00 - Unbound Pavements | itp | 10.00 - Unbound Pavements
393cb92c-9171-46aa-aad0-0130d0cdf9af | section | Details
67710e1b-33c4-465b-aecb-64fc01d1f805 | checkpoint | 1 - Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and "A single continuous layer completed in one day's production" for construction
e42870ba-c1ab-5973-b172-620911bf3b08 | note | Acceptance Criteria & Frequency (Project Specific) - Qty per lot
55f99711-0dc8-5688-9705-28d15d7584b8 | note | Check Item - Milestone
45011fe3-cf20-54c0-870e-2011b8449041 | note | Reference - MRTS05.1 Table A1
2c6b0e00-0ac5-4db4-b22b-f19c185cc4b3 | checkpoint | 2 - Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
5aadd16d-d7a9-588e-af36-fa3d7bd2be79 | note | Acceptance Criteria & Frequency (Project Specific) - Submission of Registration Certificate per quarry
e7390fb3-4f94-5bba-8a7e-5cf0458576a0 | note | Check Item - Milestone
2ae42492-a0b4-5d52-b97f-35a95fbaa196 | note | Reference - MRTS05 Cl.6.2 & 6.3
417986e1-c85b-47ca-a864-b3dd0c6eccc9 | checkpoint | 3 - Acceptance of construction procedure for unbound pavement works
6d4ecde3-f690-5117-9838-26f664b4c540 | note | Acceptance Criteria & Frequency (Project Specific) - Approval of procedure by from the Administrator
036ffa73-cc9f-530c-8159-015fee42deed | note | Check Item - Hold Point 1
b9fa1c8e-e321-5aca-873b-1b0f0ec1e256 | note | Reference - MRTS05 Cl 5.2.1
f00633ea-9027-43f6-8be9-a1470e8087f9 | signoff | HOLD POINT
5871c371-567a-4bd0-8679-e46f9f30304b | checkpoint | 4 - The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works
2014d645-6036-56bd-874e-77b063469c25 | note | Acceptance Criteria & Frequency (Project Specific) - Written Permission from Administrator
af83a78a-3414-5d15-8822-3e16a789b111 | note | Check Item - Hold Point 2
d9469c6d-2a69-5300-8eac-a15bda81c89e | note | Reference - MRTS05 Cl.6.1
ffd1ccb7-2421-4a38-9c35-27fb8abfaf53 | signoff | HOLD POINT
6245af6a-3dfa-41b0-a5cb-1469fe8deafa | checkpoint | 5 - If more than 1 grading envelope is specified in clause 2.1 of Annexure MRTS05.1 for a single location, the contractor shall notify in writing, at least two days before the commencement of the production of materials for the works, which of the grading envelopes will be used.
c6ab9f8e-86c3-52d1-b8f1-5c76b85310a3 | note | Acceptance Criteria & Frequency (Project Specific) - Submission of test results per material type
cba0413f-e7d8-5d68-84f3-a4d3efa11523 | note | Check Item - Hold Point 3
55f92e90-814d-5099-8833-a2c3d3a283d4 | note | Reference - MRTS05 Cl7.2.4
d7e95177-fb78-4056-b930-80fb22c73c02 | signoff | HOLD POINT
be9dc719-36e0-4f73-b186-bdcd0a7c3ff5 | checkpoint | 6 - Layer Thickness between 75mm and 250mm
a93d878a-20bb-5cb4-a9de-442f36f10b55 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9e66471b-2be2-5e67-88af-d5c0c7738c0a | note | ○ Layer Thickness: 75mm - 250mm
263c79d7-70cf-5a3f-ac02-d48c31170b5d | note | Check Item - Check Item
0f3b9563-aea3-51ba-ac8a-e3b6f01892cc | note | Reference - MRTS05 Table 8.3.3
38a2daa0-68d0-435e-90f0-f5c414833bce | checkpoint | 7 - Relative Dry Density Requirements - C.V of RDD >= 100% for Type 2/3/4 Materials
63bda048-3bc3-5d06-b47a-61e2eae3dc24 | note | Acceptance Criteria & Frequency (Project Specific) - C.V of RDD >= 100% (1 test / 500m2, min 1 / prouction day)
26e49ebf-d925-5d9e-a87e-2e38da2f6059 | note | Check Item - Check Item
e6a6f775-ac15-5469-a8f7-c6f3d9c5cdd9 | note | Reference - MRTS05 Table 8.3.3
603edde0-d69f-4a8e-a4be-475b648720a6 | checkpoint | 8 - Moisture content such that the degree of saturation is less than 65%
ee3bf80b-4e98-5e14-bd83-b47c0c516f00 | note | Acceptance Criteria & Frequency (Project Specific) - S < 65% (1 test / 1000m2, min 4 / lot)
e2ac8142-35be-51d4-b32a-c5bc62abfb4c | note | Check Item - Check Item
2dc62ff2-3d7d-5459-b0a9-59bf588ebd1d | note | Reference - MRTS05 Table 8.2.4.1
f2aebe4e-381e-4f1f-b93c-835dc9e8282a | checkpoint | 9 - No visible segregation of material. Partical Size Distribution Q103A.
7ceb1d8c-299c-5aad-b030-ad7e3493816f | note | Acceptance Criteria & Frequency (Project Specific) - As directed by the Administrator
b01321a6-64ec-523a-9d6f-9b0dadd50c45 | note | Check Item - Check Item
35400996-e4da-5968-ae2d-c6d69bac7ffa | note | Reference - MRTS05 Table A3
775b55dd-805e-44cf-9b8a-66e57afb0287 | checkpoint | 10 - Geometric Tolerances: Vertical tolerance of ±15 mm
7d52cbc1-d678-56bf-a921-c56c29bab06b | note | Acceptance Criteria & Frequency (Project Specific) - ±10mm when covered by AC
c051767e-f2bf-5601-9356-ccdf413fcf5b | note | ○ ±15 mm in all other cases (1 test / 25m)
ad520d73-8c49-559f-bcdf-676f2616786f | note | Check Item - Check Item
b4545c18-4ae1-5297-836b-0f3240068f01 | note | Reference - MRTS05.1 Cl.8.4.4.3
251f2c89-cb8d-409d-b0cb-8882f4bbd857 | checkpoint | 11 - Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
3b76d25b-a206-53cd-9a01-b1416d2f266e | note | Acceptance Criteria & Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
da309da9-f0ab-5472-86c7-08dfca1235c0 | note | Check Item - Check Item
3e75cce6-3885-531c-bec3-4f2d1497f610 | note | Reference - MRTS05 Cl.8.4.4.2
8916375e-78bf-452f-8223-b5188e25a8d1 | checkpoint | 12 - Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
fbc7b735-710f-565e-9e78-9adf8c645c97 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, Continuous testing
04fd211f-f02b-51cf-9c48-fa3b11bd59ba | note | Check Item - Witness Point
e1310be4-98a8-59d8-8665-141a92861cf4 | note | Reference - MRTS05 Cl.9.4.7
622aeb72-5d48-4e23-95f5-5af43de5d5b0 | checkpoint | 13 - Additional Geometrics (final layer only) - The maximum deviation from a straight-edge on any layer shall be 5mm.
970996cd-6ade-58db-94f7-0bdc261ec824 | note | Acceptance Criteria & Frequency (Project Specific) - 5mm deviation from straight edge (1 test / 10m L&R)
bf96c49c-2eef-5d9a-8acb-22e70e15715c | note | Check Item - Check Item
2cb6261f-c3da-5202-a856-8d3d5fd45b3e | note | Reference - MRTS05 Cl.8.4.5
b8c2d94a-136c-4f16-8c30-24ea3351b57f | checkpoint | 14 - Additional Geometrics (final layer only) - The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
660fc88b-968c-5f39-8bed-75fecacb5b39 | note | Acceptance Criteria & Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
d58221fc-0f4d-56e5-a91d-5c43a16978d0 | note | Check Item - Check Item
bba30e82-e094-5e88-9f1e-5e0981c9c5f8 | note | Reference - MRTS05 Cl.8.4.4.4
cb41acb9-a06a-4f87-818a-e3982cd6aea0 | checkpoint | Acceptance of lots
1b756a14-cf30-50da-b9c3-b213c7e847e6 | note | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6:
1675a150-53dc-5c6d-8f4c-5d6c2d3b655f | note | a) all testing has been completed
cabd42b2-3a83-5b83-9db0-be4c81759137 | note | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
a58fa2e3-1b3d-54e3-abb6-b65eef57bddc | note | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
be79ed8e-9120-5a7d-ba5d-9b76904ab889 | note | d) the layer has been presented to the Administrator for inspection, and
31d9b242-bf0c-51b3-bb06-166cdec0cb64 | note | e) the As Constructed Survey requirements of the lot have been met, as specified in MRTS56 Construction Surveying and notice of such Works has been provided to the Administrator.
88e99339-e888-5839-a3df-0c15700db244 | note | Acceptance Criteria & Frequency (Project Specific) - Check & verify
98c175fa-016d-5000-8fcb-e4af54b253c3 | note | Check Item - Hold Point 6
f195b8e8-5ca4-54f2-b062-5a0829a4e39b | note | Reference - MRTS05 Cl.9.5.1
338654f8-1e0e-4546-9057-37a983e52e54 | signoff | HOLD POINT
4bfe1b97-11f0-4bc2-8402-eae72d82386c | checkpoint | 15 - The finished surface of any unbound pavement layer shall: - be hard and homogenous in apperance
3887a544-b0a0-54dd-bc95-06b262529237 | note | — not have any loose, segregated or contaminated areas
2503b43c-70c6-50f0-861f-a704854857d6 | note | — have the coarse particles slightly exposed
bb3f4027-7937-58c2-ba41-41ebac0be9ad | note | — not be affected by delamination, and
317ae72f-ee75-56e2-80f5-7f56f0769cf6 | note | — not visibly deflect under load when proof rolled in accordance with Cl 9.4.6
494ec26d-137c-5693-8ec4-8192b9c6add0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6d74a4d3-62d2-5c8d-8840-468d3d66bdaf | note | Check Item - Check Item
082d7e5c-582b-5114-933f-467e1588d4e0 | note | Reference - MRTS05 Cl.9.1.3
beda9b35-5493-4a85-b401-e1b1f75fa3c8 | checkpoint | Final Verification
c400ca61-18f3-586d-9e17-2ed816c0e80e | note | Responsible Officer
31c3b4dd-5bbf-5246-a4c7-1af07f2a2e24 | textbox | Print Name:
f29cce5d-5151-5bbe-a7b0-da0b6f57b9da | date | Date:
dc7ec00a-af91-53cb-927f-24c50d0cbbda | note | Verifying Authority
fc089d3d-4b59-5929-8498-bd2c3fbe368d | textbox | Print Name:
bf7506e7-f5e9-5956-bf44-917921ea1b82 | date | Date:
1de4d9d8-1d51-441d-9ec5-1b192ef7be29 | signoff | Signature
507ac5e4-7926-42f2-927a-cccd55403fb4 | section | Final Sign Offs (to be completed at closure of Lot)
3a79e4eb-b9a3-41ea-8544-8c8c3bc8b411 | checkpoint | Agreed Quantities
8e86257c-9db4-4856-a501-2d13a67e627a | signoff | Agreed Quantities Sign Off
864258c2-4258-4c29-bde5-7259438ea4aa | checkpoint | Closure of Lot
da4ff486-9450-46b5-a1f4-d5a8200d509c | signoff | Closure of Lot Sign Off
1d3bae17-136e-434d-8c19-e75d3c9c8b51 | checklist | 12.00 - Hand Place Concrete Paving | itp | 12.00 - Hand Place Concrete Paving
fbc98ffe-cb11-4982-81e0-8cb9696bd98f | section | Details
973d96a7-812e-4eed-b836-f1b87828fbc9 | checkpoint | 1 - Material Requirements
32222586-65cf-50fa-8284-80f3c3527a9d | note | ○ Concrete shall comply with Clause 6.1 of MRTS03
b2242294-3b52-5fdc-992a-e274a971a98d | note | ○ Concrete to be pattern finished shall have course aggregate of size not greater than 20mm
666c9cf8-d021-5204-8bea-5d1e58cfb3b5 | note | ○ Colouring agent shall be a colour curing compound from a suitable manufacturer
9c315c1c-343c-5a91-be79-ea370886df5d | note | ○ Compressible packing shall be bitumen impregnated fibre board or other suitable packing
54e0bd61-f231-5cdc-aa8b-9cb66c3c8f10 | note | Acceptance Criteria & Frequency (Project Specific) - Check
cdf6c5f7-2ef3-5921-b87f-fce46bb34851 | note | Check Item - Check Item
2c8e3b3a-39ca-55a6-8b17-b7ebe1624239 | note | Reference - Clause 30.2 MRTS03
9bdaab39-ec9d-42fc-9443-6f711bfd1437 | checkpoint | 2 - Construction
5fdcd95f-d09f-5373-87a0-a158018486db | note | ○ Hand placed material shall be in accordance with specified drawings
9bfaa779-ac9c-59d9-804b-74b61a5c5ffd | note | ○ If material other than rock on or against paving shall be compacted in accordance with MRTS04
3b08ab69-b437-5895-8dde-8787d11e5dee | note | ○ Concrete paving shall not be constructed before ducting, pits, stormwater drainage and any bases for traffic materials.
9cc68aa8-3101-5c68-af6a-0849e53d4e5e | note | ○ Expansion joints to be at regular intervals of 20m longitudinally and 6mm thickness compressible packing
c4d92e19-057a-523d-ba2f-ca51147c285c | note | ○ Contraction joints shall be installed at intervals not exceeding 5m longitudinally and transversely by forming 40mm deep grooves and not more than 6mm wide
2d509da7-03f7-513f-b822-ed794944644e | note | ○ Concrete shall be cured for a period of 7 days before commencement of further operations
8dbfa2b0-ee96-5083-8e4a-0608db3c5342 | note | Acceptance Criteria & Frequency (Project Specific) - Check
c9c27b00-650f-5513-ba60-5357ed4bee29 | note | Check Item - Check Item
bd1b843b-fd68-5bd7-99ff-4223daa5aa87 | note | Reference - Clause 30.3 MRTS03
f1db2a83-6792-46ac-845b-31d040c08e1a | checkpoint | 3 - Colouring and Finishing
5ae0dcee-404c-52ea-87d1-8519597076b1 | note | ○ Where specified, concrete paving shall be coloured. The surface shall be uniform in colour
ea1cba85-b9e2-5f19-bb90-46c282b24bed | note | ○ Where specified, the surfaces of concrete paving shall be pattern finished. Areas not to be patterned finished shall be lightly broomed to produce uniform non-slip surfaces
332ba8e8-635c-53de-ad1b-f0aa0bb3373e | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
fc5f5d11-e60c-5f2b-9788-cf79d110cfb3 | note | Check Item - Check Item
3dde4906-e649-5537-b3ca-7a13021679fc | note | Reference - Clause 30.4 MRTS03
244ead7e-fa65-4f12-a918-5be24ce7017e | checkpoint | 4 - Vertical Tolerances
f4cc9f75-e0b7-500f-98c7-b3a22b1a638d | note | ○ A neat joint shall be made neatly to adjacent work.
88872861-53eb-562c-bc6a-b9927bb230a5 | note | ○ The finished height levels shall not vary from the drawings with more than ± 10 mm
bbe6d55d-1535-55e3-9337-cf441796ade4 | note | ○ Gaps under straight edges shall be placed 3m long anywhere on finished surface and shall not exceed 5mm.
c60b376d-d529-5554-be41-d97c6759172b | note | Acceptance Criteria & Frequency (Project Specific) - Check
cc2a128a-fca7-5dba-946c-526c2ba50ddf | note | Check Item - Check Item
bb3f3cd7-e60a-5337-a34e-ffe5db5ff19d | note | Reference - Clause 30.5 MRTS03
96970f03-f6bb-431a-a05b-6f2ee16673ab | checkpoint | Final Verification
adeeeb16-e0fd-58c7-9ce9-7cb099bdbe6f | note | Responsible Officer
811e13cc-8c4f-5f9d-a154-212610f9f9a3 | textbox | Print Name:
b62f8fc6-92f4-55d5-9cf5-91294706fed4 | date | Date:
f6f96a0d-2c14-5076-81be-e710815846d0 | note | Verifying Authority
14c041e8-d174-5066-9169-49ddc5a3d703 | textbox | Print Name:
7fc9f4b7-312e-5eb6-92c5-8a6f3ad13217 | date | Date:
2503263c-9171-4968-995c-1ad38e73384c | signoff | Signature
8fd2f25c-f697-4ff3-9303-68860a100d0a | section | Final Sign Offs (to be completed at closure of Lot)
a8f42a2a-4fc3-4b19-bb90-8ee1fcb1b742 | checkpoint | Agreed Quantities
25da7af9-23ac-4584-9410-fb2bbb6aeb0b | signoff | Agreed Quantities Sign Off
df6e506c-4ae5-4d3e-8254-f1118aa3b32c | checkpoint | Closure of Lot
98d2ae5a-86ae-480c-80dd-d8c10c3750dc | signoff | Closure of Lot Sign Off
2b7d2a03-7aa5-4162-8bd2-31f47e4158e8 | checklist | 13.00 - Removal/Demolition of Culvert End Structures | itp | 13.00 - Removal/Demolition of Culvert End Structures
c1f60e22-41ab-4667-a43d-1981c543756b | section | Details
815c6985-e2cb-474e-bfa5-6547578de4ac | checkpoint | 1 - General - Where culverts are to be removed or demolished are to be under contract
0076fe79-7a2a-5d1c-8d8d-9fe921b51eaf | note | Acceptance Criteria & Frequency (Project Specific) - Check
41ea65d6-82f7-54a8-93dc-0a10e1e91645 | note | Check Item - Check Item
a7440161-a55b-5a87-bc3d-42c3eaeaf3d9 | note | Reference - Clause 9.1 MRTS03
f4c87bb4-8c38-477f-884c-039d56954bb9 | checkpoint | 2 - Description
09b31928-7a67-5baf-b462-cebfd663fe45 | note | ○ Culverts and culvert end structures shall be removed or demolished where specified in the drawings
9651b4e9-55cf-5a69-a879-1f989575414d | note | ○ If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components
bec8398b-b68a-5f19-a2df-b1372b9df462 | note | ○ Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed of
1fcc2502-9727-5ba7-a87e-33606026cdf5 | note | ○ Components listed in clause 2.1 of annexure MRTS03.1 are to be salvaged intact and delivered and stored as per Clause 2.2 of Annexure MRTS03.1
a11fedb9-d629-52be-aa25-9228613c4b6b | note | ○ Backfilling of culvert and end structure is to be reinstated the area to a safe and free draining state.
84ce15c7-3304-5c66-b577-691148ddfa37 | note | Acceptance Criteria & Frequency (Project Specific) - Check
182da17c-9484-54b7-9c46-4435ab7cb3aa | note | Check Item - Check Item
3cb04c2e-d94a-5e3f-aae4-3abeb70202af | note | Reference - Clause 9.2 MRTS03
821abe56-9f39-4ce5-8a43-d59aae42b517 | checkpoint | Final Verification
a622e5a1-753d-5b49-ac69-a16dd4437127 | note | Responsible Officer
123ecc70-2087-59df-8384-98469d78f5d3 | textbox | Print Name:
78cc80fb-f65d-5571-ae88-f1ff53fd57e2 | date | Date:
4e760a1a-4887-513d-ab16-fb20a7850077 | note | Verifying Authority
d05506f0-d41a-573b-b2b9-111f274b0671 | textbox | Print Name:
baf70085-cdaa-5346-85c2-e516a850f335 | date | Date:
fb37c997-a8cf-419f-a59b-3d1fbb1288f1 | signoff | Signature
9864c1c9-1e5e-4600-be48-191b0fb6e639 | section | Final Sign Offs (to be completed at closure of Lot)
6f09a485-b535-4c01-b840-924526ab729e | checkpoint | Agreed Quantities
fab63412-2e58-414e-921e-48c3115c5906 | signoff | Agreed Quantities Sign Off
99404a0c-6948-4b81-a5fb-7c90f3cda11c | checkpoint | Closure of Lot
baa5778d-a36e-4644-b94d-b4b66dbd6a39 | signoff | Closure of Lot Sign Off
6102c553-1755-4d68-b9e6-2e658ea0cf1f | checklist | 14.00 - End Structures to Culverts including Grouted rock pitching | itp | 14.00 - End Structures to Culverts including Grouted rock pitching
12c82f9f-b44a-494e-8149-44faa2e6f604 | section | Details
aceb8ae0-bad1-4a4a-8c03-ed89b9676af7 | checkpoint | 1 - Cast Insitu Material Requirements
442e34a4-e647-5b96-88b5-8ef6dba20aad | note | ○ Concrete shall comply with Clause 6.1
f87369e7-45c5-5179-89c1-6a7e72ccab64 | note | ○ Steel reinforcement shall comply with MRTS71
15a74d47-355f-5b8a-9723-4790951f2743 | note | ○ Rock masonry material shall comply with Clause 39
2d7448f5-343a-57ab-8d08-f0d11d9b5464 | note | ○ Concrete masonry shall comply with Clause 51
fab42382-f46f-56eb-a4a7-e1d07cab788f | note | ○ Grouted rock pitching shall comply with Clause 40
8d5115d2-a852-5b08-a131-fed58f9792b0 | note | ○ Steel Wire mattress material shall comply with Clause 43
9abeab9b-4746-553c-bbf7-bdebe8580164 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
05261bd8-de5b-5b1f-bf95-028ead11d073 | note | Check Item - Check Item
7ce75d63-577b-5d47-bca7-033b7637f58c | note | Reference - Clause 15.2 MRTS03
b51a29f0-81e5-452b-861d-e32dc194aae5 | checkpoint | 2 - Cast Insitu Construction
87edb5da-f1ef-5438-99ca-5d2be42cd7c9 | note | ○ Cast insitu end structures such as headwalls, wingwalls, aprons, and kerbs to culverts shall be provided in the locations specified in the drawings. Unless otherwise specified in the drawings, cast insitu concrete end structures to culverts shall comply with the details shown on Standard Drawings 1304, 1305 for pipe culverts and 1240, 1250 and 1260 for box culverts as applicable.
26e42b19-51c6-5a21-93d2-ae9208b8c2a0 | note | ○ Where insitu material on or against which structures are to be constructed is other than rock, the material shall be compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks.
bc6951a3-607f-5b3b-afd5-342e8ce9415e | note | ○ Concrete shall be constructed to comply with Clause 6.1.
3d134828-a518-5466-99f0-db576917d982 | note | ○ Endwalls, wingwalls and concrete aprons may be constructed without foundation bedding if specified on the drawings. Endwalls and wingwalls shall be separated with expansion gap unless otherwise as specified on the drawings. Construction of aprons shall include the integral cut-off walls
331fef8a-860f-59c4-9b5e-95ed626001f3 | note | Acceptance Criteria & Frequency (Project Specific) - Check
b6bd1d79-122b-5384-ba27-22875ca93884 | note | Check Item - Check Item
213bfc4a-c713-526b-866a-9339f19bb533 | note | Reference - Clause 15.3 MRTS03
17676236-5382-4c53-b19e-1688ce250e8e | checkpoint | 3 - Grouted rock pitching Material Requirements
7988d693-9164-52a2-8219-147c38d6419c | note | ○ Rock (other than smaller-size rock required for wedging) shall be of size not less than 150 mm and not greater than 250 mm. Where rock pitching is constructed for batter protection, the toe rocks shall be of size not less than 250 mm and not greater than 350 mm.
3008246a-bc2a-5e67-91cc-eb178127071b | note | ○ The rock shall be sound rock which does not disintegrate in water and which has been selected to match the existing rock pitching where appropriate.
e3b37d2f-193e-5ca2-b950-8ac06d8cad2f | note | ○ Cement mortar for bedding shall consist of one part by volume of Type GP cement to three parts by volume of clean fine sand with only sufficient water added to achieve a plastic-like texture. Hydrated lime may be incorporated into the cement mortar to the extent of one part hydrated lime to 10 parts of Type GP cement (loose volume). Hydrated lime shall be an addition to, and not a replacement for, the cement. The mortar shall be able to retain its shape and not flow like a liquid. Materials shall comply with MRS70.
64725cb9-4837-5fc0-a64f-d358d16fbc21 | note | ○ Sand bedding shall comply with Clause 19 of MRTS04 General Earthworks.
90447526-04d0-5e2d-aea6-53ff533cc7c3 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b328f73e-25b9-508e-9b36-52ebd7a239cf | note | Check Item - Check Item
8d95a27e-3cd7-5e77-b055-a544c586f9cf | note | Reference - Clause 35.2 MRTS03
ebff026a-e170-41f0-86a1-f2902f998e60 | checkpoint | 4 - Grouted rock pitching Construction
a470419d-1efc-585f-81ca-b8809cf497be | note | ○ Grouted rock pitching shall be constructed in the locations specified by and in accordance with the drawings.
b3a9bbb7-b20b-5e8a-a249-7279792a1c89 | note | ○ Where insitu material on or against which the grouted rock pitching is to be constructed is other than rock, the material shall be compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks.
b8f31381-9899-52a1-9a73-8eccbae146ea | note | ○ The first row of rocks shall be placed on a sand bedding of minimum thickness 50 mm
d9c80b6c-4ef9-55ab-be99-e88a59e52038 | note | ○ Rocks shall be placed so as to form irregular joints. All rocks shall be interlocked and wedged with smaller-size rock, as necessary, so that no single rock may be easily dislodged, and no large voids remain between rocks. All rock pitched faces shall be stable prior to grouting with mortar.
76339c27-aeb7-5ce5-aabf-3a56617c8dd7 | note | ○ The voids between rocks at the exposed surface shall be filled with cement mortar. The mortar shall be used within one hour of mixing and shall not be re-tempered.
c521608d-0cba-56b2-9ef4-522795fcd60a | note | ○ Exposed surfaces shall have a relatively smooth, even, neat appearance. Where rock pitching is to be trafficable, care shall be taken to provide a smooth running surface.
59ea2d1d-506a-550f-a990-4b09b8e3b026 | note | ○ Rock surfaces shall be cleaned free of any coating of cement mortar exposing the faces of the rocks.
a99b3c86-9b4b-525f-b928-0392bda679a5 | note | Acceptance Criteria & Frequency (Project Specific) - Check
b968e19b-fbae-5635-b9c3-bfd30613a83b | note | Check Item - Check Item
f018116c-dd00-5339-8297-a02dd80dd84b | note | Reference - Clause 35.3 MRTS03
f036dbf0-6130-47f7-8dfc-670b7d81d398 | checkpoint | Final Verification
c2603a0d-f025-51ef-a1a2-0d026ba94a10 | note | Responsible Officer
f766c8a6-6c0d-568d-95ef-22c873b4e9b4 | textbox | Print Name:
a8e68bdd-f765-5cf9-82bc-46558a0e50b2 | date | Date:
15ba7d6c-d6d2-55fe-b89c-7696314f43ac | note | Verifying Authority
da46d373-bad3-59e5-b76d-9845e19786e9 | textbox | Print Name:
83dd0e3c-2deb-5c94-a1aa-040f4e3fdf83 | date | Date:
8879dd3b-9c4c-4e5c-925b-9e756408aa28 | signoff | Signature
5e6fd576-0bb4-44af-84cb-7aecccf8daf2 | section | Final Sign Offs (to be completed at closure of Lot)
dac72bb4-ae5e-4cc5-ad00-9886187982c5 | checkpoint | Agreed Quantities
92758740-82ff-47b7-b186-4a33861731c8 | signoff | Agreed Quantities Sign Off
3d10b134-9836-41bf-814a-2391a61c28ac | checkpoint | Closure of Lot
0e9ce44b-b31b-4549-b151-61c5cb7972c0 | signoff | Closure of Lot Sign Off
6c82bfee-6fe1-4589-ad2f-3d534d61bee7 | checklist | 15.00 - Supply, Installation of precast and preformed culvert components | itp | 15.00 - Supply, Installation of precast and preformed culvert components
378c0952-8917-476c-8e66-ad098cc3d02e | section | Details
1abd6001-8c20-408b-b8e4-c9d07f9e0a71 | checkpoint | 1 - Material Requirements
1745dfe9-2dd2-592b-a032-59a69d84ce9b | note | ○ All material supplied shall be proprietary products and comply with all requirements of Clause 11.2. Concrete box culvert components and spanning slabs shall comply with MRTS24 Manufacture of Precast Concrete Culverts.
c8015d29-71d5-5b82-a88e-0cd7c3b58fca | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
1d59e9c6-d2b2-5054-a1be-d3a378cf62d4 | note | Check Item - HOLD POINT 1
c2da7ed6-a276-5c67-9c12-23dd18486790 | note | Reference - Clause 11.2 MRTS03 MRTS24
319af09e-5e92-45a4-86a1-717529d1777c | signoff | HOLD POINT
aee25b7c-cd58-4077-a72b-335723757f15 | checkpoint | 3 - Construction Proceedure
a1142e88-3b9a-5e26-a366-89751fe63869 | note | ○ At least 14 days prior to construction, the Contractor shall submit their procedure for excavation, installation and backfilling
53821cf6-73a6-532b-a78b-713502b82610 | note | ○ This procedure shall include:
6d8e7bec-eda0-5f3e-8f19-6fd9c24c53d8 | note | a) Earthworks Construction Procedure (refer Clause 5 of MRTS04 General Earthworks).
df369e58-f202-5e77-9098-bab93e06efdc | note | b) Procedure for lifting and installing culvert elements.
91e210c9-ed85-5d34-b08a-1939f591695f | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f11ffd34-d46e-5f0f-9eb4-134b42949e22 | note | Check Item - HOLD POINT 2
1c265d16-e494-5c00-8a94-068a92eeee62 | note | Reference - Clause 11.3.1 MRTS24
b4b5a0b3-1583-4eb6-add3-8a8da3a18dc8 | signoff | HOLD POINT
4e595eaf-00aa-49de-95ba-ce41e60260df | checkpoint | 3 - Precast Culvert Construction and Conformance
8bff4694-8fc6-5ce2-ba27-81d81a9a31aa | note | ○ All Precast culverts shall be constucted and conform to MRTS24. All relevant documents in relation ot the constuction process shall be reviewed and verified prior to installation.
a8e10651-b3ae-5ccc-8b26-00a918398025 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
9fbec820-b9c4-5527-a55d-36c0f2b0983e | note | Check Item - HOLD POINT 3
3a84653e-bc18-5920-b640-d656f98c8639 | note | Reference - Clause 4.2 MRTS24
d3473a51-f83e-4a93-8344-1a47a7734e99 | signoff | HOLD POINT
66d0b74b-2586-4564-9a3a-357777fdd077 | checkpoint | 5 - General Constructions
2b6f0c1a-fad8-521b-ae81-69d265336d70 | note | ○ The construction of culverts shall not commence until the check of the construction procedure has been carried out. The construction loads on the culvert shall be determined.
0710acbb-b03d-57a3-85db-157fd3ed48f8 | note | ○ Precast and/or preformed culvert components shall be installed in the locations and in accordance with the details shown in the drawings.
53b342cb-1662-51c8-89e8-a7212d2a2b7f | note | ○ All drainage structures shall be marked with indelible ink on the inside face with the name of the Manufacturer and month and year of manufacture.
bf980a0b-9a4b-5a8d-988e-b2b6759c355b | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
a6475f73-c0a8-53db-959d-75bba469b19a | note | Check Item - HOLD POINT 4
83d58d74-3202-5c74-ba95-449dc7ebaa69 | note | Reference - Clause 11.3.1 MRTS03
98012e04-b7d4-4aa3-ab59-51fbd1a360cb | signoff | HOLD POINT
8301d946-d08d-4a25-a32f-d667d3396aa2 | checkpoint | 6 - Excavation - Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks
e2928402-6bb7-52f4-8276-b1abb8e61d21 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
437072b3-e30d-5e10-ada7-7df62af2be51 | note | Check Item - Check Item
eb7af481-4907-57a7-861a-5a6d85d74b10 | note | Reference - Clause 11.3.1 MRTS03
0aa588f1-f3a2-45d2-ad5a-9d544ac22eae | checkpoint | 7 - Bedding of Culverts
d6e8c76b-ad64-5cb2-838c-f5bf052b2402 | note | ○ Foundation bedding and haunch zone materials shall be placed in accordance with Clause 19 of MRTS04 General Earthworks.
84417dcb-c943-5acb-bc45-da171d3e07db | note | ○ The foundation bedding shall provide continuous, even support to the culvert components.
cd5e14b1-2364-5201-8f6c-43d9e438108a | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
805ade1a-51d7-5816-a168-941fa1207b01 | note | Check Item - Check Item
56922944-5450-53a1-b482-8b3d69bde4a3 | note | Reference - Clause 11.3.2 MRTS03
9be62abc-0b5b-43ac-bb81-14838755c178 | checkpoint | 8 - Laying and jointing culvert components
61c5d277-e716-5e76-8192-b95c19308884 | note | ○ Where possible, laying of culvert components shall commence at the outlet end of the culvert and progress to the inlet end.
162c0656-af95-59dd-bb39-64f3aa4dc780 | note | ○ Components shall be selected and arranged to give best fit.
0ffc17dc-1750-5d76-a288-c3c62b28306e | note | ○ The ends of components shall be free of any foreign matter at the time of jointing.
42c37f2d-591f-531c-b047-a068488a2cbe | note | ○ In butt and flush joints, the culvert components shall abut one another, and a bandage cover shall be installed on the outer surfaces to seal the joints.
ac72a1e4-b942-5e58-996f-fb15afbd21c0 | note | ○ The bandage cover shall consist of:
904469f5-4b33-524b-8c31-0b4c706266b6 | note | a) one layer of non-woven fabric
f0a6588a-6df1-539a-9d99-4663c5993554 | note | b) three layers of woven fabric, or
c6df3382-5d4a-596d-8cbe-48e7893715f4 | note | c) a plastic or natural rubber band.
c5cebe0e-aa6d-5f19-b709-bc688353b0bb | note | ○ Fabric covers shall have a width sufficient to overlap adjacent components by not less than 45 mm, and shall not be applied until the ambient temperature exceeds 15°C. Fabric covers shall not be wrinkled and shall adhere to the outer surfaces of the adjacent components. The ends of the fabric in the covers shall be secured in accordance with the manufacturer’s recommendations.
6b6feba7-6bc9-5594-8429-2a8f5b5ebf9a | note | ○ Plastic or natural rubber covers shall be installed in accordance with the manufacturer’s recommendations.
069d9def-a1c2-5208-b3a3-a0486e0582bc | note | Acceptance Criteria & Frequency (Project Specific) - Check
f3243da7-d5f2-57c1-962d-94b7019d18b5 | note | Check Item - Check Item
04653110-1433-5b24-9473-a7505329310f | note | Reference - Clause 11.3.5 MRTS03
d63bda43-1f7b-4d2f-893c-9413e90d0f6d | checkpoint | 9 - Special Requirements for Concrete Box Culvert Components
3ef2c9a0-7b30-500c-9d97-9d8bbf145274 | note | ○ Box culvert components shall generally be installed in accordance with the details shown on Standard Drawings 1250 and 1260 or project drawings.
58fa9f6a-8c61-5470-8af2-7a0ff801fd22 | note | ○ U-shaped units laid in the ‘legs down’ position on cast in place concrete bases shall be seated on to the bases using continuous cement mortar pads.
9f591468-3615-5b1d-bdbe-faac3ed53dfc | note | ○ Holding down anchors shall also be installed to retain the units in position in accordance with the details shown on Standard Drawings 1250 and 1260 or project drawings
01fa619e-5bee-527f-8e02-c25044e47e9e | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
97379388-6cfa-52e9-8a6b-d3367d3dd9f6 | note | Check Item - Check Item
8b2c1fb9-6a8b-5d03-b7d0-f9904509087d | note | Reference - Clause 11.3.6 MRTS03
31761cd6-30a2-4ad6-bf76-0d0b90fcafd3 | checkpoint | 10 - Cutting culvert components
f08c7ad4-84ca-5732-83a6-18e86930efc8 | note | ○ Cutting operations shall provide neat end surfaces.
beef0aa5-19df-555f-985c-8461a671c797 | note | ○ The cut surfaces of reinforced concrete culvert components shall be given two coats of a surface tolerant epoxy.
de529ccd-f0ec-53e3-ae44-f57949cae3df | note | ○ The cut surfaces of steel culvert components shall be given two coats of zinc-rich organic priming paint as specified in AS 3750.9. The coats shall have a combined thickness at least equivalent to the thickness of the galvanised coating. Each coat shall overlap the adjacent uncut surfaces by not less than 25 mm.
88687486-033c-52b7-9ae7-44208cc4d879 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
0d03b923-0eb6-5002-912b-35f9eb1cd78d | note | Check Item - Check Item
98642c1c-0415-580a-9a9d-a184c084f9ce | note | Reference - Clause 11.3.9 MRTS03
10d37701-53dd-49d0-b2e0-a1e9ec5563d2 | checkpoint | 10 - Backfilling of Culverts
4eb03155-581d-5610-aba5-0f624d75445b | note | ○ Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04 General Earthworks. To determine testing lots for compaction, a change in compaction equipment or methodology shall necessitate a division of lots.
bbbaa1f2-1b8a-5b08-896e-2df4c8562bc6 | note | ○ Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator.
8560fc9c-9b70-52a9-9220-280a4edeaec6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1a8b0ac8-1432-5271-8981-ddcc025f8c47 | note | Check Item - HOLD POINT 5
9f8b1421-92e0-5a95-9d6d-d88efa2045ea | note | Reference - Clause 11.3.10 MRTS03
6414a628-7f7c-4d2d-ae9f-5c6278c057f5 | signoff | HOLD POINT
07e0cf7a-f641-4b1f-a30d-d5b8e4886f14 | checkpoint | Final Verification
508663e4-0187-5d79-9b1d-529adc4f14a3 | note | Doval Representative
a6f9b3ce-395a-5f13-8344-844d6cb8a1b5 | textbox | Print Name:
c2b42626-e730-5399-83c4-9f1258f89777 | date | Date:
047be524-a4ee-52e1-a157-12d8feb170b3 | note | Administrator
93ec38f7-7046-5cfa-b9d2-a32ea7771206 | textbox | Print Name:
2fad6daa-9446-5b67-93de-0fa3e6410a91 | date | Date:
240d3af1-4a84-414d-bd3b-5e4f758796ac | signoff | Signature
ea2127bb-4512-4cb4-aaa4-1298a7a710e1 | section | Final Sign Offs (to be completed at closure of Lot)
7c3198bf-5342-432c-9caa-e06a61f5e21c | checkpoint | Agreed Quantities
56a1b948-9464-4381-88c9-f93f47507174 | signoff | Agreed Quantities Sign Off
5cb46b82-d06d-4720-bff1-7c27be948c37 | checkpoint | Closure of Lot
b608c94f-7ebb-4c4c-82a8-a671e42bb0bc | signoff | Closure of Lot Sign Off
5a213fb9-a67a-4cf5-a0e2-cc315465b595 | checklist | 17.00 - Subsoil Drains | itp | 17.00 - Subsoil Drains
2486028c-d5b6-493b-bd71-4dad3bb4b12e | section | Details
e6653c49-f818-495f-bfa0-52f4fa2442ed | checkpoint | 1 - General
228faf26-274c-5a91-883e-3589484c7c05 | note | ○ Clause 22 applies to the provision of subsoil drains. The types and locations of subsoil drains to be used shall be shown on the drawings and consist of one of the following types and shown in Figure 22.1.
0de89a06-2fae-581a-a0e6-ef2e6f326fb5 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
e7962f03-0def-521f-acff-22d3f93efc90 | note | Check Item - Check Item
d6c8fe09-67fe-5051-8e83-c9c5fda766ba | note | Reference - Clause 22.1 MRTS03
5b534ec1-326f-49fd-a746-df7fd1fbf4fd | checkpoint | 2 - Material requirements
1c419ac6-b530-5e56-b94e-7cfd452dcefb | note | ○ Perforated drainage pipes used in Type B subsoil drains and associated fittings and jointing procedures shall comply with AS 2439.1. The pipe shall have a minimum diameter of 100 mm.
5fb4ec2f-8189-5cbd-954c-5b700bc0003c | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
622e46f3-19dd-5bc7-8952-96e9b4e41d5b | note | Check Item - Check Item
0da6a281-a1fc-5502-a57f-a18c33f12ad1 | note | Reference - Clause 27.2.2 MRTS03
a986c56c-e583-4109-82d4-dc3458649e4a | checkpoint | 3 - Construction
46cfb5ab-838a-5953-8cde-028e403e6f5d | note | ○ Where type cross-sections for subsoil drains are not included in the drawings, dimensions shall be in accordance with the requirements detailed in Figure 22.1.
27479bf5-a5eb-5868-8119-720fe680166a | note | ○ Subsoil drains shall be installed to the grades specified in the drawings. Where the grades are not specified on the drawings the minimum grades of 0.5% shall apply.
067920ca-61ce-5b96-aad6-605b1af4d3f2 | note | ○ The bottom of trenches shall be trimmed to provide constant longitudinal fall towards outlets. Drains shall be installed with a constant fall and shall not rise and fall within the trench.
3bcc1109-4f49-5497-9567-7f95dfc1e2f5 | note | ○ Subsoil drains shall be joined in accordance with the manufacturer’s recommendations.
b04bfc6b-ca66-5bda-99f8-54538e38e7f5 | note | ○ Where subsoil drains are constructed within the subgrade, they shall extend to the underside of the lowest pavement layer unless specified otherwise in the drawings.
50cd4479-a7cf-5c51-bc02-23051dfb08ac | note | ○ Where subsoil drains are constructed outside the subgrade edge point, the trench backfill material shall be placed to approximately 150 mm of the ground or finished surface and the remaining 150 mm filled with impervious material compacted as for embankment material in accordance with MRTS04 General Earthworks.
9812ae19-ce4a-542b-b9ac-9fd7b9c794fc | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
5b7e7b06-ee28-5d33-97fb-0d5026b59595 | note | Check Item - Check Item
9e09eb9d-0519-5c7d-b919-d2335cf63779 | note | Reference - Clause 22.3 MRTS03
4e5701de-e9e8-4cc6-9cf3-8af883bf39dd | checkpoint | 4 - Cleanout and outlet pipes
2356bdd9-5894-5ef2-83dd-588204ea2af1 | note | ○ Unperforated cleanout and outlet pipes and associated fittings and jointing procedures shall comply with AS/NZS 1254. The pipe shall have a minimum diameter of 100 mm.
825bccd4-3034-526e-b097-f3b5b7df4e0d | note | ○ Clean-outs shall be located at the heads of all subsoil drains and at subsequent spacings not exceeding 60 m for Type B subsoil drains. Clean-outs shall be constructed in accordance with the details shown on Standard Drawing 1116.
ea5a0ba3-97d7-576a-8a5f-885c065c742c | note | ○ Clean-out pipes shall be joined to the subsoil drains using oblique tee or other proprietary connections.
84321340-643b-5a6a-a250-743497e5b38c | note | ○ All cleanouts shall have caps installed.
37c8ce2d-282b-5608-ad68-ecfde6dc4f04 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
486dea06-4dc4-5a45-8698-ca8bcfe68456 | note | Check Item - Check Item
2e516efc-d623-50d1-959c-3fb1925bfbca | note | Reference - Clause 22.2.2 & Clause 22.3 MRTS03
1f2379f5-2360-42a8-a8bf-4beaf214efe7 | checkpoint | 5 - Geotextiles
a110cdfc-b286-521f-9df7-11e2117b5aff | note | ○ Geotextiles used to surround backfill or wrap drains shall comply with MRTS27 Geotextiles (Separation and Filtration).
8cc09c18-b25b-5969-8acf-5c58e5ca54c6 | note | ○ Where an outlet, inlet, or clean-out pipe passes through the filter fabric, a separate piece of fabric of sufficient size shall be wrapped around the pipe and flared against the main fabric to provide an effective seal.
05980731-c7b5-5fb2-aa0d-3301b4315667 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
0b119e73-6ab6-5c06-8b97-3f8978df056c | note | Check Item - Check Item
ad4807f7-1e08-52d9-ad08-2c710d053ecb | note | Reference - Clause 22.2.4 & Clause 22.3 MRTS03
7683f4ff-ad1f-4f44-b6ba-f2c501b34853 | checkpoint | 6 - Trench backfill
6f9a300f-3439-5461-b2bf-5aa61e8f6067 | note | — For Type B subsoil drains, backfill material shall be one of the followings:
70a84513-9797-528b-a780-28ae2490169d | note | ○ 20 mm or 10 mm nominal size drainage aggregate that conforms to MRTS04 General Earthworks, or
e6275b05-29c2-564a-9e1a-c304cfd64092 | note | ○ 20 mm nominal size no fines concrete that conforms to MRTS70 Concrete.
a607d38c-8dd8-5fae-992e-eb12cbfa65d4 | note | — Trench backfill material shall be damp when placed in the trench. The material shall be carefully placed in layers not exceeding 200 mm loose thickness.
20988d84-d30b-54d4-8796-d6a12a3186e1 | note | — Trench backfill material shall be compacted to achieve effective mechanical interlock between particles.
bb2d32bb-334d-5374-b3d1-95f6854090c8 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
b171b8e9-a1bb-593b-9a86-63540e0d491e | note | Check Item - Check Item
6f93a1c2-0e89-5337-8378-443d11d2cc50 | note | Reference - Clause 22.2.5 & Clause 22.3 MRTS03
5589a314-bc06-4fd4-8a91-c79a20ab4e52 | checkpoint | 7 - Flushing - Once all items above have been completed, where directed by the Administrator, after the drains are constructed, they shall be flushed. Flushing shall continue until the outlet water is clean and flows consistently.
a52ed35e-c9a9-5e64-bca2-e8df5d0c178e | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
6fb0275d-b5b8-5c49-89e3-a259b0860c56 | note | Check Item - WITNESS POINT
50a70007-b4fa-5d83-9fce-99d64bd87e53 | note | Reference - Clause 27.2.2 MRTS03
18d7ba8e-2571-477f-9678-e1adb0430270 | checkpoint | Final Verification
812aa526-57d1-51c7-91c0-ffa13222c1b7 | note | Doval Representative
6311168b-421a-58c7-8746-8dc9615ada11 | textbox | Print Name:
fbf3149d-152c-539b-8a14-959269cb5f3c | date | Date:
c7976fb6-5c2a-5036-a5c8-cc312fa3d46b | note | Administrator
be62e8de-8a4f-5f85-aaeb-a8ce3a740ea7 | textbox | Print Name:
8a00277b-497a-54be-9890-6d42b98ecdac | date | Date:
3cdfa2d6-ec1c-45a0-9687-138d9318c479 | signoff | Signature
a7a78932-fd33-4cfe-849f-259966ab10f7 | section | Final Sign Offs (to be completed at closure of Lot)
71c3b176-37dd-45be-b4f9-9ccc9f8c9b34 | checkpoint | Agreed Quantities
8115e69a-4765-48d0-b32c-ef0911bf1d06 | signoff | Agreed Quantities Sign Off
1baf2d4b-0972-47bc-a8b3-580d3971694f | checkpoint | Closure of Lot
8dda05a9-55b2-439d-9b02-1da342eefb29 | signoff | Closure of Lot Sign Off
538efc3b-05ac-488b-a60e-60836d427052 | checklist | 18.00 - Removal/Demolition of Kerbs Channel & Concrete Slabs | itp | 18.00 - Removal/Demolition of Kerbs Channel & Concrete Slabs
48d35d1f-9694-4403-9b74-b589521dc0aa | section | Details
340e30f6-0717-47c2-b4a8-a07ebf6dadb5 | checkpoint | 1 - Scope of Works
ea3d54e4-e83a-52d1-b295-eb269ad7d9b9 | note | ○ Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the Drawing.
252e55a5-1c63-50cb-80cd-239f0065e4cf | note | Acceptance Criteria & Frequency (Project Specific) - Check
4af8aa37-6d3f-50a5-a4b5-5adb5cc8962c | note | Check Item - Check Item
2844755b-09db-53a8-a0c9-402e2ffe6053 | note | Reference - Clause 9.2 MRTS03
f3b57579-8154-4646-a9cb-a885028c455d | checkpoint | 2 - Damage to Adjacent Work
da70a3f0-88a7-5801-bcd4-1dc9143e3a91 | note | ○ No damage shall result to adjacent work
43e491c7-02f2-58ae-920f-394c4c586e5a | note | Acceptance Criteria & Frequency (Project Specific) - Check
a36bd167-5d43-5857-b1f9-036647cbd444 | note | Check Item - Check Item
2ecf8aa6-eba1-5d26-9547-c43a4a8570a4 | note | Reference - Clause 9.2 MRTS03
baf14155-1633-4cd6-b01c-27c240755672 | checkpoint | 3 - Joint to Existing
e29244a9-09a5-5277-83f5-2438bf9eb63e | note | ○ Where part only of kerb, channel or slab is to be removed or where it joins existing has been either terminated at a joint or sawn to provide a clean joint. Any resulting excavations shall be backfilled to the surface finish level.
b00715b0-5297-5bea-a751-1e11f5511b60 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d6f43851-76ce-5ff5-8341-08302e7f79a2 | note | Check Item - Check Item
cf61272d-ce0b-53ab-894a-9882d1cc2e69 | note | Reference - Clause 9.2 MRTS03
9879e56d-97b9-40e3-a3a1-4cb8e12774a1 | checkpoint | Final Verification
82e20c4d-7d41-5384-b75a-a3c558452465 | note | Responsible Officer
9dc14126-4486-525a-ae49-ff87913ef71b | textbox | Print Name:
7f54e82a-5c7e-5299-9152-300448515a4e | date | Date:
6e19c451-067f-56f9-9b64-20515320821a | note | Verifying Authority
f1ef08e3-557c-5f34-b70a-f48f524eb1fc | textbox | Print Name:
28fbf149-e282-5a9c-892f-dafbc38c579e | date | Date:
82698427-af89-4575-b831-077e8deace3e | signoff | Signature
14a791d5-ddb8-4483-9e90-40c485183505 | section | Final Sign Offs (to be completed at closure of Lot)
62ff260a-bed0-43aa-ad27-bdfbb9ff2c6c | checkpoint | Agreed Quantities
28fc3dc9-717b-44b2-b9bd-402ccad76ee7 | signoff | Agreed Quantities Sign Off
8bb2fa9c-a76a-4ad0-9f3c-b69da0e31ee8 | checkpoint | Closure of Lot
a5259101-0664-4244-a18b-2ba523174108 | signoff | Closure of Lot Sign Off
ad50a621-7f86-4e59-9dc2-c565358ffb1a | checklist | 19.00 - Cast insitu concrete kerb, channel, and kerb and channel | itp | 19.00 - Cast insitu concrete kerb, channel, and kerb and channel
08f916f1-f50d-42c9-9d18-b53359f0fd20 | section | Details
d345447b-1417-4849-8c07-11deb024970e | checkpoint | 1 - General - Concrete
967e18af-aa5d-5ecd-8225-12591aa45858 | note | ○ All insitu concrete kerb, channel, kerb and channel are provided in the locations specified in the IFC drawings.
e2afc48b-3629-57d5-83b5-8a83bc73bea1 | note | ○ This does not apply to kerbs cast integrally with structures.
2b7bf358-ca73-54c3-9901-becca31935fb | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
df5e59ad-4142-5f7f-b50b-b87bfda8d3df | note | Check Item - Check Item
f0f31f3a-dab5-56dd-a95c-023808fd2802 | note | Reference - Clause 3.1 & Clause 18.1 MRTS03
642e8bb8-8c1d-4f7b-a5d0-1fcecf5a34f0 | checkpoint | 2 - General material and construction requirements
136c0a49-13b0-5d35-a6d6-f84071c30288 | note | ○ The concrete strength grade and concrete class shall be as specified in the IFC drawings.
70ffec80-c69e-5791-917a-f0d4a79142a2 | note | ○ Construction joints shall be provided only as specified in the drawings and no construction joint specified in the drawings shall be omitted.
b724e7cd-9ca1-5b8e-9d98-907446f7a8e9 | note | ○ Concrete mix designs are to be approved prior to any concrete works.
bf922e34-9cdb-53af-a962-6db4ca39738e | note | Acceptance Criteria & Frequency (Project Specific) - Check
20a39803-fba9-5ba9-9ade-a29abbe26ef2 | note | Check Item - Check Item
75fbd3c4-b704-5748-b066-a046926251b2 | note | Reference - Clause 20.3 MRTS03
e069a145-0b32-45b0-a431-e8923cf9cd66 | checkpoint | 3 - Construction
77deae25-18f0-534e-9788-82ae4839561d | note | ○ Where insitu material on or against which kerbs or channels are to be constructed is other than rock, the material has been compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks. The ground surface shall be moistened just prior to placing concrete. Manually-placed concrete shall be in accordance with Clause 6.1. Exposed surfaces shall have a steel-trowelled finish.
6c86a6de-3e89-5828-b602-e2fd7d501061 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
3577a6f3-943b-5ac2-88ce-363901183e73 | note | Check Item - Check Item
bd3b4755-03db-5d83-a00b-e99fb74b2996 | note | Reference - Clause 18.3 MRTS03
a39e90f7-0018-496f-b653-a448ba3c8ed6 | checkpoint | 2 - Set out & Excavation
5da4a832-4463-5a5e-acfe-35a487c55feb | note | ○ All kerb areas shall be set out by a surveyor in accordance with the IFC Drawings.
1cb91490-290c-5ab7-9022-f10048c3fa9a | note | ○ Excavations shall be constructed to the shapes, lines, dimensions and other requirements shown on the IFC drawings.
1417bc12-9af9-5265-ad38-d11e595215d6 | note | ○ The bottom of excavations shall be trimmed to the tolerances specified in MRTS03 Clause 6 and any loose material removed from the surface.
506d648d-4cfe-5c69-812a-a58bd68de1b1 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
a6ef8121-e918-5c54-bf49-21a3e067daf2 | note | Check Item - Check Item
4405bf89-4417-5264-80da-4c9a86fb665c | note | Reference - Clause 18.3 MRTS03
4ebebe61-bc84-465b-aaa1-78d34b92b348 | checkpoint | 3 - Compaction of Bottom of Excavation
407ed44d-b83c-571e-968d-aa92708b0a06 | note | ○ All Earth Fill Material shall be placed uniformly in layers. The allowable loose layer thickness for material compacted using the compacted layer between 150mm to 300mm (Table15.3(a)) and shall be compacted to a 95% Standard Compaction (Table 15.3(b)).
6963ade5-89e3-5bd9-92b2-6dadce527b19 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
99749b65-c1af-5654-9529-e3e936e67447 | note | Check Item - HOLD POINT
2e2dbc76-0aa9-59fe-b5db-5d08fa7cc1d5 | note | Reference - Clause 15.3 MRTS04
c66b9407-79c4-4795-b316-f46f2819ed16 | signoff | HOLD POINT
a4164a39-0251-4377-8211-4a4f99d7c276 | checkpoint | 2 - Subgrade
5a360cdf-f508-53a9-8f07-817494623a14 | note | ○ The Subgrade shall be constructed and tested to Subgrade Level in accordance with the requirements of MRTS04.
6ddb4683-ab4e-5aee-8961-8f6c0fbc4bdf | note | ○ Subgrage layers shall be in accordance with the IFC Drawings
412e72fd-503e-5f81-aad4-721df6d6fe48 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
4bdcf915-5aa1-5de7-91f6-84e08559d06c | note | Check Item - Witness Point
a8d97a61-3b80-5c49-a631-be6c29f8a2f8 | note | Reference - MRTS04 Clause 18.3.1
6417cbd0-2afa-4d66-84ca-3f0beabc026d | checkpoint | 3 - Compaction of Subgrade - All subgrade materialsl shall be compacted and tested, a 97% Standard Compaction (Table 15.3(b)) is required
debe6e6d-fedd-5727-bd6c-7e72ebd37a30 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
1e48a3a3-97d3-5889-8e06-b4be4662c489 | note | Check Item - HOLD POINT
c3525705-df9c-5882-be6a-5ab44b76b489 | note | Reference - MRTS 04 Clause 15.3
bbfd501e-d8d3-43e7-a9c1-2df958d186d2 | signoff | HOLD POINT
663bf716-9c41-4bca-83f8-e573764fc142 | checkpoint | 4 - Formwork
ec45e14e-d080-5001-8743-b77a353d78c7 | note | ○ All forms shall be set and maintained to line and level such that the finished concrete shall conform within the specified dimensional tolerances, and to the proper dimensions and contours as shown in the IFC Drawings .
481c047e-e15a-5a03-b152-c94b4f2fa083 | note | ○ All forms shall be cleaned and coated with the lightest practical coating of release agent prior to pour.
c13e5935-1b1f-5c75-8b38-784f84e928bd | note | Acceptance Criteria & Frequency (Project Specific) - Check
45b775b4-cc95-5807-affa-5977247cadb0 | note | Check Item - HOLD POINT
3a1d2faa-3563-5065-8efa-98b15610fae6 | note | Reference - Clause 20.4 MRTS03
cff14660-28a9-487c-be28-9f25c1e09bcd | signoff | HOLD POINT
697b2847-f0c1-4bee-a8e6-b2e0fe116f7e | checkpoint | 5 - Pre Wetting - Wet the bedding material immediately before laying concrete without resulting in free water remaining on the surface.
7b301c62-995d-5d4a-810e-e50f0024038d | note | Acceptance Criteria & Frequency (Project Specific) - Check
b8e2408b-d5c2-5996-a339-5567240df959 | note | Check Item - WITNESS POINT
ec88b2fe-5b37-5220-82c9-1c771357f1fb | note | Reference - Clause 20.5 MRTS03
2b247587-9ec0-4d59-93ba-e970522d1b7d | checkpoint | 4 - Concrete Pour
3f2eac84-e92b-5d48-8b20-08684924ae1f | note | ○ Manually-placed concrete shall be in accordance with MRTS03 Clause 6.1.
640d3cee-0b70-5a15-be0d-fcb5b7e9a39c | note | ○ Concrete strength grade and concrete class shall be as specified in the IFC drawings (N32/10).
f741199f-2407-5a79-b2e4-4b310a4db46d | note | ○ All concrete shall be tested in accordace with MRTS70
471e1347-c7db-573a-8a57-c1aa99b57bb7 | note | ○ Slump as per Table 11.3(a)
4636fea6-4af6-5640-afbe-df11e7417339 | note | ○ The temperature of the concrete is less than 10°C or exceeds 35°C
99803737-618b-574e-bad1-f9b7474ebc65 | note | ○ Concrete shall be placed and compacted within the times in MRTS70 Table 10.5 from the charging of the mixer.
1440ed9b-0f78-584a-a1a2-d907b47cdc1c | note | ○ All Exposed surfaces shall have a steel-trowelled finish.
f686e58e-da7e-5e47-9228-1001831e212d | note | ○ The finished kerb, channel and/or kerb and channel shall be well compacted and shall have exposed surfaces free from voids and honeycombing
f80ce4b1-a608-522b-bf6f-d886f4ba7228 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
c9f6d56a-92da-59d4-9e43-ab5099f02ffe | note | Check Item - Witness Point
53b7ce48-5e28-5e2c-8213-26165a91e40f | note | Reference - MRTS 03 Clause 6.1, MRTS70 Clause 11
b5587200-a4c2-4335-bf94-909d206df4c9 | checkpoint | 5 - Expansion at Joints
4dec485d-3fd7-5aa7-a833-6c7e7c5e19f0 | note | ○ Expansion joints shall be installed at regular intervals not exceeding 20 m. The joints shall be constructed by installing 6 mm maximum thickness compressible packing in the full cross-section. Where relevant, joints shall be located to line up with expansion joints in adjacent structures.
09415660-2f10-50ba-80a9-04628da0c263 | note | ○ Compressible packing shall be bitumen impregnated fibre board
8e7c5126-686b-5459-a100-2541d384f02e | note | Acceptance Criteria & Frequency (Project Specific) - Check
ccdf0b13-18f2-5697-b5c6-d3208f95f465 | note | Check Item - Check Item
b0ec9bdd-b4bd-5ccc-b901-7f01d5772a48 | note | Reference - Clause 18.3 MRTS03
07b0fc66-f2fa-4279-b35a-5bddf6321ae7 | checkpoint | 4 - Contraction Joints
2350c4cd-e282-596a-89de-f352e64a99be | note | ○ Contraction joints between expansion joints shall be installed at regular intervals not exceeding 5 m. The joints shall be constructed by forming grooves 40 mm deep and not more than 6 mm wide in all exposed surfaces of the kerb, channel and/or kerb and channel. All grooves shall be normal to the top surface and square to the alignments of the kerb, channel and/or kerb and channel.
b4cbbcb6-706a-5d6a-8f19-88cb7f56dbc2 | note | Acceptance Criteria & Frequency (Project Specific) - Check
2d6ee8ed-b718-5ffa-9d61-3655991bb6b7 | note | Check Item - Check Item
bb0ff29f-7d03-5622-94bc-80031d7e834e | note | Reference - Clause 18.3 MRTS03
725afcb1-abf8-4343-b684-a1f19f4e5d9e | checkpoint | 5 - Curing
303395e9-c8e3-58fc-8206-8fed090e8714 | note | ○ Concrete shall be cured for a period not less than seven days before any other roadworks operations are carried out adjacent to the kerb, channel or kerb and channel.
7e4ea61d-9af5-5831-93ed-73d56b8fc26b | note | ○ The curing compound shall be applied using a fine spray at the rate stated on the certificate of compliance, or at a rate of 0.2 L/m² per coat, and two coats shall be applied at the full rate.
fc8f4cbc-e912-5169-9283-aeebb2600995 | note | ○ The time between the first and second coat shall be in accordance with the manufacturer’s recommendation
86cae6b4-a925-5a0f-ab34-b36ce4834337 | note | Acceptance Criteria & Frequency (Project Specific) - Check
aa38714d-3aa0-5cb2-b02b-c35d3d5dc86e | note | Check Item - Check Item
07eda2d9-c4ba-5007-bf50-59ed6df8b4bb | note | Reference - Clause 15.11 MRTS 70
1007ca5e-d40d-4cec-9468-f84c1961e8ce | checkpoint | 4 - Tolerances
1e73c48a-c876-5a0e-9b0b-92b7eb6ee927 | note | ○ The horizontal and vertical alignments shall vary by no than ± 10 mm from those specified. Alignments shall have smooth lines. The overall dimensions shall nowhere be less than that specified in the drawings and controlled by means of a sensor working to a control line.
cccb13cb-dea0-54de-ac48-e72a023875ec | note | Acceptance Criteria & Frequency (Project Specific) - Check
3eb58f56-fa14-5a67-a466-35fd77da0b4a | note | Check Item - Check Item
f35e1055-1f56-5ab6-a7ab-b148205ab2de | note | Reference - Clause 18.4 MRTS03
168a0ac1-6a83-4cd9-9141-99516c35918a | checkpoint | 5 - Water Test
ff4139c0-20a7-57d1-a50c-e040977922e4 | note | ○ Where the longitudinal grade of channels <1%, a test shall be carried out by discharging water into the channel to check uniformity of flow along the channel. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel. The test shall be carried out as soon as possible after the concrete in the channel has hardened
8a1d375c-033a-5bb2-8b52-71128928bc12 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
cb31032e-d7d4-5f87-b1fd-95c5c1472ba3 | note | Check Item - WITNESS POINT
0eceb7f8-870f-5f8a-aaf2-e4a546915d80 | note | Reference - Clause 18.5 MRTS03
fa1d5f87-2ebe-4647-a698-6c2933f38908 | checkpoint | Final Verification
e05f5065-da45-56c5-8a4a-9d2fe0ad75f9 | note | Responsible Officer
940918a1-f2ae-5aa7-83ca-44257b58bb77 | textbox | Print Name:
ae27bf2e-b339-57c0-81e5-464a20c39b8b | date | Date:
ff8e8787-2a4d-580b-b880-f7d69b3e4807 | note | Verifying Authority
02ba4c9c-5342-52a1-80ca-a0781402f6b0 | textbox | Print Name:
38364d62-52a0-5d76-88a6-c5aadf852a56 | date | Date:
179d9887-f5c2-455d-a699-a9025b3b38bf | signoff | Signature
22e53fe1-b5e1-464b-88eb-223ab3b1ddf1 | section | Final Sign Offs (to be completed at closure of Lot)
4d4447f5-6305-436c-89da-f9093117a7ce | checkpoint | Agreed Quantities
e5af6c82-be91-438c-b077-79468d8bbc89 | signoff | Agreed Quantities Sign Off
483824cc-343d-462e-a8b2-49bc4c0b1ffd | checkpoint | Closure of Lot
6912a45c-0214-493d-9ec5-af6ef318b2eb | signoff | Closure of Lot Sign Off
b6b4f751-183d-4d04-a71c-9e411262916e | checklist | 23.00 - Road Furniture | itp | 23.00 - Road Furniture
df0564a3-2331-478c-8e8b-8ba4f83e3a68 | section | Details
4c2d3742-7e8a-4d19-ac66-07ea739ccccd | checkpoint | 1 - Demolition List
aec591ff-c9c0-521e-9a86-a60b6e9b7406 | note | ○ The items of road furniture to be demolished and disposed of are listed in Clause 3 of Annexure MRTS14.1
51c724d3-60a9-5db8-9bfa-39e6b0af97d9 | note | Acceptance Criteria & Frequency (Project Specific) - Check
1def0b86-a6d0-5b78-98a9-04a6e0bfa65e | note | Check Item - Check Item
a81df349-d8d8-5638-aea3-73aa2147f101 | note | Reference - Clause 7.2 MRTS14
d31dd830-5bda-498f-983f-933f9afdee9b | checkpoint | 2 - Removal of Furniture / Footings
910cf380-49c5-54da-b64c-b56afd21d85e | note | ○ Existing road furniture shall be demolished and removed in a manner which avoids damaging any adjacent work. All existing footings shall be removed.
0517eca8-d2ff-579a-96d2-5fc2e2972f7b | note | ○ Resulting excavations shall be backfilled and finished so as to reinstate the area to a safe and free-drainingstate. Backfilling shall be carried out in accordance with the requirements of MRTS04 General Earthworks.
56e39b32-f7f4-541c-ba40-d978d2ce8729 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
c4adde4c-8262-551e-951f-96d2321c54bd | note | Check Item - Check Item
c3191ace-501d-5ded-bd25-d3f0240489f5 | note | Reference - Clause 7.3 MRTS14
468af5d9-8838-490a-99ad-82e87fcfbc4e | checkpoint | 7 - Sign Substrate Material Requirements
b48d3ad2-6dce-5cd2-ba33-6b19100d1c80 | note | ○ As Required Sign substrate shall be manufactured from aluminium except for Regulatory Parking Sign which shall be manufactured in reference to Clause 13.3.1.6 and Temporary Sign in reference to Clause 13.3.1.7
7ae247dc-e529-57fb-83f9-3c53945abf91 | note | ○ Other materials may be considered but evidence of the full approval to be provided to the administrator.
55eabcb1-4dc1-5a8f-8363-17f85398efbd | note | Acceptance Criteria & Frequency (Project Specific) - Approval
1d3e85e8-bf19-5e5e-b2f8-848c5d52a1df | note | Check Item - HOLD POINT 3
4ebc7b53-712c-5abe-bbda-e0a712694c96 | note | Reference - Clause 13.3.1 MRTS14
c12a0ca3-edad-43a8-aa35-e916dbfb3641 | signoff | HOLD POINT
67db7226-d2aa-4609-8325-76ea4773a07e | checkpoint | 8 - Coatings
1dbdd8db-e269-5eed-ba9c-5d04f9881ba9 | note | ○ The class of sign material for the legend and the background shall comply with Table 13.3.3.2.1 (Class 400)
d099f1cb-dbdc-5b09-a408-f59a705336f6 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
65a16f66-5ffc-5aa4-aae0-b539a9ce62ee | note | Check Item - Check Item
243ab517-f3b2-584e-85b4-d578bab3e5d6 | note | Reference - Clause 13.3.3 MRTS14
a0d658de-52fb-44ab-8976-35bcf7c58f69 | checkpoint | 9 - Construction Footings for Road Sign Posts
8fdb917e-a482-5247-8608-c1cc8d64d307 | note | ○ Posts for road signs shall generally be circular hollow section or rectangular hollow section in accordance with the details shown on Standard Drawing 1363
fd4ca681-74dd-5a85-9dde-0b446c1a36c7 | note | ○ Holes to be excavated to minimum size
b0acf97a-9741-5263-a459-729ab74510e2 | note | ○ Anchor bolts for cantilever and gantry signs shall be assembled into the positioning template which shall be held firmly in place during placement of the concrete
70a476c2-d531-5bf0-8588-1796aa7f4f4c | note | ○ Concrete shall comply to MRTS 70
72c11f8d-1bff-5834-98a0-daa61fd0eb25 | note | ○ Unreinforced concrete shall not be less than normal class 20/20 and reinforced concrete shall not be less than S32/20
5d5509e3-dc49-5819-bae8-890e190dd5bc | note | ○ For fragile support posts, TMR approved proprietary bagged concrete with 28 day compressive strength of not less than 40MPa may be applied.
db142149-a5b2-55c8-9756-5a393c348dab | note | ○ Steel reinforcing shall comply with MRTS 71
5e9ed377-ac7d-54d3-a51a-21bb7aabf394 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
293249ed-e01f-5cdf-9f33-5cc8be84fb51 | note | Check Item - Check Item
76ad338c-aef3-58b2-88b1-3d9db5c0784a | note | Reference - Clause 14.3 MRTS14
8f59a735-4db9-4bf3-a1cb-0f17cf2de315 | checkpoint | 10 - Project Signs
62820138-48d3-5270-8653-5a8b5b7518e8 | note | ○ Installation, maintenance and removal of project signs will be in accordance with Clause 15.
f6736851-4cc0-55be-abb8-24cb3101f8bc | note | Acceptance Criteria & Frequency (Project Specific) - Check
c866895e-eb33-5e03-8224-97e9e6056a15 | note | Check Item - Check Item
0b36b459-c9e1-521e-8a9b-b7050983f7bf | note | Reference - Clause 15 MRTS14
b4b774f4-f5ec-4208-bbac-8ba705ef959b | checkpoint | 11 - Erection of Signs
9174910c-aeac-594e-855b-281e97b6dcbc | note | ○ Signs shall be erected at the locations in the design documents or where not indicated according to the Manual of Uniform Traffic Control Devices.
f776aeb1-fd4e-54be-8674-f31e74ff0df0 | note | ○ Orientation of sign shall be in accordance with Clause 1.12.5.3 part 1 of the Manual of Uniform Traffic Control Devices.
bdee2aa1-6b52-5d85-bfac-6ff4d28b5dba | note | Acceptance Criteria & Frequency (Project Specific) - Check, Verify & Visual
d19b8af8-2bb1-5b5d-98ef-47ef5f96b5b8 | note | Check Item - WITNESS POINT
71d905e7-514b-5e83-93fd-faa546f02733 | note | Reference - Clause 14.4.1 MRTS14
54d2e9e4-f6e4-4c45-b88f-a087879955ea | checkpoint | 12 - Contractor's information signs
834bc4ce-d8d6-52ec-9a2a-bca577845bca | note | ○ The location, number and legends of these signs shall comply with TMR policy. Details of signs shall be submitted to the administrator at least 14 days prior to commencement of manufacture.
0d1fd898-65ef-50fe-9eeb-cb10035dc58f | note | ○ Information signs shall not be manufactured until expiration of the 14-day period.
8889f71e-7001-5c3c-85cd-3b4dac564323 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
0d9dd6b9-83be-5af1-b899-2537314aee04 | note | Check Item - MILESTONE/HOLD POINT
5fa717ce-15b5-5a8d-a2df-987d397706e2 | note | Reference - Clause 20.4 MRTS03
f049d5ff-3a63-47f3-b6a8-4ffae2bd6db4 | signoff | HOLD POINT
f0a0d368-40e0-47ed-a9bd-b61af13e5b90 | checkpoint | Final Verification
84c9740d-318f-53b8-9c3e-2d56247af497 | note | Doval Representative
9a8dab4f-8b85-55ce-8ec1-4b4235fe65c6 | textbox | Print Name:
15440b8d-1aa6-5fca-8cfd-b5d98eb1d3bb | date | Date:
e2ddd91c-3579-535b-9103-26059171c32d | note | Administrator
cafd70ba-0c4c-52a2-bc3c-15e104676dba | textbox | Print Name:
64eb41e4-0f95-5641-a631-2e6fc678a8cb | date | Date:
80f2d46e-09d9-436c-95ab-13a919a92e36 | signoff | Signature
4558dd96-2fdd-4492-a930-f3b2138839a8 | section | Final Sign Offs (to be completed at closure of Lot)
eaa897fe-4b6d-4adc-accf-32eed1f43d4c | checkpoint | Agreed Quantities
6a6926e0-8697-4091-b8ea-e5f0ebd6095c | signoff | Agreed Quantities Sign Off
5f236489-d17b-474b-9761-9e64b3982aad | checkpoint | Closure of Lot
e00b8d5b-c7ee-4a1e-a170-681ee0bb30ce | signoff | Closure of Lot Sign Off
68fd1f5a-8889-407f-9dd8-47be8930f1a0 | checklist | 24.00 - Landscaping & Revegetation Works | itp | 24.00 - Landscaping & Revegetation Works
28dcf6c0-653c-44cf-be50-e3f9585d47eb | section | Details
5fc41171-63ed-45b6-aa8e-9c78a583911e | checkpoint | 1 - Topsoil Requirements
3c4a6ea9-5126-5cb2-8c83-a991416178ce | note | Topsoil may be:
153d7f43-e072-52a6-b273-a2feea54f2c5 | note | a) manufactured site topsoil, or
d0ea98ba-98ee-5be0-a072-598103054795 | note | b) imported topsoil.
57edcfbc-17ad-5f84-98b7-e49bfc2b7c0d | note | Manufactured site topsoil shall:
993f0ce2-3467-5069-820e-b526092cbb83 | note | a) be manufactured from material stripped and stockpiled during clearing and grubbing operations in accordance with MRTS04 General Earthworks
a974f720-c992-5b74-b8de-f3ef84b2cdb4 | note | b) be initially tested in accordance with Clause 8.1.2.1
f7d63370-8f28-5e93-97d1-8311595940e0 | note | c) be manufactured in accordance with Clause 8.1.2.2, and
048168b7-49af-5ff1-97f5-5d24e64bc8ec | note | d) be tested for compliance in accordance with Clause 8.1.2.3.
589c7304-604d-5aa4-8073-6c0a911b5bc5 | note | Imported topsoil shall:
ce52e471-6978-5df4-bef2-f9f579bd6d8d | note | a) be tested in accordance with Clause 8.1.2.1
63f167e5-89c6-55db-a17f-a7d261516059 | note | b) meet the requirements of Form C – Topsoil Testing, and
9b66c0c8-af13-5806-a48d-73a9c24d9ea6 | note | c) be certified weed free.
00062cff-41c7-5d07-8bd0-369232623009 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
5e18cc2a-ee67-571e-b38a-c947787e8f4c | note | Check Item - Check Item
496c6e15-604f-562e-8400-90aa08e955b5 | note | Reference - Clause 7.1.2 MRTS16
ab23b978-ba6b-4ebe-aa8c-a383146fb987 | checkpoint | 2 - Soil Sampling
d27ab9b1-4072-513c-b367-52eee407004e | note | ○ Subsoil Sampling shall be conducted by a soil scientist with qualifications in accordance with Clause 6.2.
04312920-d9bb-54d0-872b-827795fd65dc | note | ○ Where an accredited soil scientist is unavailable in a remote location, soil sampling will be carried out under the direction and supervision of the Administrator.
7d535b59-b52a-5285-9c67-5416a737f8ad | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f24f4ff3-3957-528d-85b6-66a8a45396f5 | note | Check Item - Check Item
15325e63-abf6-576d-93a4-7b96170321d2 | note | Reference - Clause 8.1.1.1 MRTS16
201873e2-cb4d-4bbb-9ce1-56b13bc37e36 | checkpoint | 3 - Weed Control
b4cb9efe-83ba-518d-9d99-0155b16bee91 | note | ○ Prior to the commencement of other ground preparation operations, the site shall be in a weed free condition. A list of weed control procedures is stated in the clause.Weed removal is to be undertaken in accordance with the EMP-C in reference to Clause 3.1.2 Annexure MRTS16.1
2fc38251-cbc1-5f73-b9d3-e67d08886662 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3614ff57-63f8-5217-8cf2-8a2d908056d8 | note | Check Item - WITNESS POINT
70c427ab-e4ff-5ae3-945a-f4baae2a12ad | note | Reference - Clause 8.3 MRTS16
c142c89f-19ff-4e52-8e01-0e7da1648751 | checkpoint | 4 - Amelioration Agents
d207f087-af92-56cf-90b6-0326d30cd66a | note | Soil wetting and water holding agents
c7ed9cee-4232-558b-a343-2e1c3485dbe2 | note | Soil wetting agents (surfactants) shall:
5ce399b3-082e-5cd7-9f64-1c095dafaa8d | note | a) have a life of at least three months from the time of application
4e4d7818-6d4f-55b9-9557-246b62185231 | note | b) reduce soil water repellence / hydrophobicity
daa8a606-af89-5598-a544-94606eec66c9 | note | c) reduce surface tension of soil particles
c9479b67-1ae4-5e5f-ba1e-87556b34e16d | note | d) increase water penetration to soil, and
113c0153-b4e0-5f39-b44f-5a60bc7a6cdf | note | e) be free from matter toxic to plant growth.
88f0eab9-3170-5bc8-9435-827f2da955eb | note | Water holding agents shall:
24a8f95b-adde-535d-92f5-d7b9680efaf4 | note | a) have a life of at least six months from the time of installation
ce6db0e0-bc96-5b6b-b9fc-563171de22d8 | note | b) hold water equal to at least 200 times their own mass
212e4b8c-8ed6-5afa-8d2b-8417c21e076b | note | c) be hydrated / activated prior to installation, and
fc5b6491-8e67-5091-8e69-c36b574a9508 | note | d) be free from matter toxic to plant growth.
11df0b34-4819-524b-8d29-5b2e6e5a9f09 | note | ○ Water holding agents shall be incorporated into the topsoil
8f747b91-ea23-5d47-a013-94d7abd54743 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0a4f2f40-3975-5004-bae6-7484b718bacb | note | Check Item - WITNESS POINT
4f794bdc-0ce2-5c71-a45c-bf48084084d5 | note | Reference - Clause 7.2.5 MRTS16
8148776f-db92-45b3-b7e8-a017daa34b1b | checkpoint | 5 - Imported Turf
09e0619e-7870-5c55-972b-8610fcbf29a3 | note | Turf shall:
79f0b203-6aa0-5139-8b8a-4efcc5a91cc9 | note | a) have a minimum 30 mm depth of sod
91cdac72-b0a0-5445-a2c3-f6d97ed35cd1 | note | b) be in a healthy condition
7791844d-81d7-528d-9d2b-2cbb74cabd8a | note | c) be free from prohibited or restricted biosecurity matter, pests, diseases and matter toxic to plant growth
0f231ebe-c3f6-5c52-8fd3-58e97fc9948a | note | d) show signs of active growth
1a352a59-209d-527f-9204-6a1e3dbbb609 | note | ○ Turf species, turf grade and roll width shall be specified in Clause 3.3.1 of the Annexure MRTS16.1
77b61ebc-d145-54ed-9dfd-cb1e660fee79 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ea2fb339-b3fa-5899-bcff-833260e7a760 | note | Check Item - WITNESS POINT
c4cae202-6e8e-5476-bf35-811f24977fba | note | Reference - Clause 7.5.2 MRTS16
51cb14b8-2ba8-4308-b5f3-bfb9228a9150 | checkpoint | 6 - Application of Amelioration Agents
5b07426f-4eb7-5b87-aa72-971996e64ffc | note | ○ Amelioration agents, shall be spread over the subsoil surface at the specified rates prior to subsoil operations.
5b5023df-767c-59f0-a4cc-3e9d12756705 | note | ○ Ground preparation operations shall occur immediately after the application of amelioration agents
641ee82c-dbe5-5438-aa9f-c7ca04da8939 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
acb0a5dd-9b55-5c3c-b461-f0b5f87e516e | note | Check Item - WITNESS POINT
752153aa-c8be-5f04-9021-3c85f8460892 | note | Reference - Clause 8.4.1.1 MRTS16
f0af8347-3806-4df6-8285-e1275e2860f6 | checkpoint | 7 - Subsoil Operations: Roughening
45cb3b7b-85f0-5c78-b47d-7ccd993017ce | note | Roughening shall occur immediately after the application of amelioration agents as per Clause 7.2.5
10f2bf80-75ab-57a5-a596-b9d57c981432 | note | Roughening shall:
ff11e4b6-aa56-5469-be1d-2425101fbe5f | note | a) be approximately 50 mm depth
cfb49611-f10c-54c0-90e2-306884a067d6 | note | b) incorporate amelioration agents into the subsoil
0da68426-f042-52f0-82d9-c1a3424b94b6 | note | c) occur when soils are dry enough to roughen / break up / crumb the surface, and
4a033fd4-ccb7-54d5-b003-d43afdddf329 | note | d) be parallel to the contour and form keys in the subsoil to prevent subsequent material slipping down the face of the slop
b749b932-400f-517f-ba5f-750ec03e5b56 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
eeec65f3-a6db-5ddb-bc81-658ef617b93a | note | Check Item - WITNESS POINT
28ed062d-53d3-5943-b731-c12159312394 | note | Reference - Clause 8.4.1.4 MRTS16
55b0339f-7ede-4be9-9d05-27ca4ce2c41b | checkpoint | 8 - Topsoil Installation
c1529427-fc75-5a5b-85f6-183111b6ccd9 | note | ○ Topsoil shall be installed within three days of the subsoil operations.
950e49d1-a048-5054-9307-eacff2b88770 | note | ○ Topsoil shall be spread to the minimum 75 mm depth, and allow for settlement after installation.
7281fc1e-7cef-5a7b-a103-46eb0a71d2e8 | note | ○ The Contractor shall give at least three days notice before installation of topsoil.
99fc6360-da7a-5f9c-9b56-06453a0ba634 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
91c08237-341c-5c32-bc65-e246095896b8 | note | Check Item - WITNESS POINT
4313ea63-7205-589f-9b28-5beaf5fcfc3e | note | Reference - Clause 8.1.2.4 MRTS16
f944cc2c-070c-4750-bef7-e232a75634bf | checkpoint | 9 - Installed Turf Requirements
4f827bab-fb86-52f2-87fd-17f8760040bf | note | ○ Turfing shall be in accordance with Table 8.5.2.
5b5ecbf5-d37d-567c-a0c6-a035276c4a26 | note | ○ Turf shall be installed within two days from the completion of the topsoil operations.
943b9f4d-7162-5380-8228-c437d9bc242b | note | ○ Turf shall be delivered within one day of cutting, and installed within two days of cutting.
a4f70fea-2a9c-5a09-bf67-85df79c93c86 | note | Turf shall be installed:
31234acc-d2a7-5406-a592-7ac2e63d2b3f | note | a) by spreading fertiliser over the topsoil and raking the surface smooth
d07c9fa0-e484-50f5-8805-feda2c31db96 | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
6eb7dfed-087b-51f9-b91e-837166aba5ee | note | c) on the day turf is delivered to site
59d22710-f394-53d6-8098-55e481ea0c5d | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
3f5cdae1-4492-5dab-bc61-251985ef0f79 | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
68afaf2b-0651-5ed7-9663-57db133696bc | note | ○ Turf in high profile areas shall be top-dressed to ensure there are no gaps between rolls and to correct any uneven areas. Top-dressing shall be washed and graded sand specifically produced for the horticultural industry.
e348fa56-0e99-56ed-a99c-b5e201790d97 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b04b9166-6166-5b6c-a3e9-d71d1b916de1 | note | Check Item - Check Item
f4f8be8c-b686-5d9b-952a-24e946d7ce92 | note | Reference - Clause 7.5.1 MRTS16
c69ec4ec-5a2d-47ee-97f4-8ddf2758e867 | checkpoint | 10 - Establishment Period Watering Frequency
45bc1f0a-2485-5f98-a43b-fff3767789ed | note | During the Establishment Period watering shall:
06651cb4-4dd8-5125-a520-93e2bb429eb7 | note | a) be ‘misted’ or conducted in a manner that does not cause damage, run-off or subsequent erosion or displacement of treated areas
5e1665f5-12cf-545d-b270-3b0705f571aa | note | b) not spray onto, flow across or pond on paved areas including roadways, bikeways and footpaths, and
5e24a600-d247-57d2-a636-199ef3ad7b60 | note | c) be in accordance with the minimum watering schedule and watering rates of Table 9.1.1.1(a) and Table 9.1.1.1(b), unless otherwise specified in Clause 4.1 of the Annexure MRTS16.1.
951ab717-049d-5602-8fa3-1712b80b9894 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b2584960-6038-563f-8a43-3d04e1c7018d | note | Check Item - Check Item
b36f19dd-c783-5006-b4b1-80ca78f222eb | note | Reference - Claue 9.1.1.1 MRTS16
9eafff49-83ca-4b4a-8446-258302f44d47 | checkpoint | 11 - Interim evaluation
83506ed6-a334-5561-ba80-f2adc4f0bf0b | note | ○ After four weeks from installation, treatments shall be evaluated against the following criteria to determine if it is on track to meet the completion criteria
6c9a366b-962c-5a56-a37b-408212c117f4 | note | ○ Turfing treatments - Turfing treatments shall have a healthy grass cover and show signs of growth.
b8d5e4c7-a22e-5c09-9f15-f799c4bec483 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
97fa748b-c761-5399-af00-f5b3b3f720b8 | note | Check Item - Check Item
c2568bc9-9c1c-59b0-9b55-22195c617d46 | note | Reference - Claue 9.1.1.6 MRTS16
c60700e8-318a-41ff-bf00-097e14adf787 | checkpoint | 12 - Establishment Period completion criteria
35a07c6f-9f1c-5044-aed5-ade6596a2f80 | note | The Establishment Period shall be completed when the lot has met the following completion criteria:
5204fa00-ec36-5b55-9f46-c9acf8cd3d27 | note | a) the area is weed free in accordance with Clause 9.1.1.3
cb870712-4796-51e8-81a7-7f3a90c2b7a0 | note | b) seeding treatments meet the completion criteria of Clause 9.1.2.1
0633ae65-756d-5c2f-b860-6e567ae29f3d | note | c) turfing treatments meet the completion criteria of Clause 9.1.2.2,
5d2eceb4-ceb3-5eb3-8c2a-4936f2e20abc | note | d) planting treatments meet the completion criteria of Clause 9.1.2.3, and
f7633610-1441-5130-82bb-b84af42be9e9 | note | e) the lot has been established for a minimum 90 day duration.
02d70a54-3170-5229-bd62-61bc108946ad | note | ○ At the completion of the Establishment Period a Certificate of Completion of the Establishment Period shall be issued by the Administrator.
7ffe5799-1c5a-58b8-a98b-004ed5069c64 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
cc80bb39-5342-5c57-94c0-3caf79a76e17 | note | Check Item - HOLD POINT
55b2e932-a8c9-5644-9aa2-1008310d6ac2 | note | Reference - Clause 9.2 MRTS16
38bccb74-8fc7-4efb-bb8e-ab363a40b396 | signoff | HOLD POINT
a078d1d9-1c5e-4d17-976b-41b1668c7eeb | checkpoint | 13 - Monitoring Period
246c8e09-bf7d-53db-8b79-7878789646ed | note | The Monitoring Period for each Lot shall:
d87412c9-f740-5fbc-9b1d-0ad10b8dfaf0 | note | a) be a minimum duration of 90 days, from the date of Certificate of the Commencement of the Monitoring Period, and
9ff4ee05-c7c1-51a6-ac50-fbca3fa29538 | note | b) continue until all vegetation treatments / Lots meet the completion criteria of Clause 9.2.2.
b8e91383-7d6a-5ff2-9688-9262cce500f8 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
5ccf10dc-b4ca-52d0-97df-0135ae9761cc | note | Check Item - HOLD POINT
f5454b82-aa1b-505a-bbb6-faca458c4b59 | note | Reference - Clause 9.2 MRTS16
dd7f7001-6fba-4be6-9bf7-d1ff8ce41ede | signoff | HOLD POINT
38b3a4c4-45d5-4f49-82df-f316b2ac66a1 | checkpoint | 14 - Monitoring Period operations
872d0ee5-8524-59a2-a14b-7159182388b4 | note | ○ The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.2.2.
352f8c4d-53eb-5f31-97ca-1ca7e1dd0b6a | note | Monitoring Period operations include:
1d590f2e-7aea-57b4-9c3f-a0e3d839213c | note | a) watering Clause 9.2.1.1
35b1951d-d466-5b3e-8dec-48b746d561b3 | note | b) fertilising Clause 9.2.1.2
0b4e24a4-f073-562d-8e43-bcb26ae555fd | note | c) weed control Clause 9.2.1.3
78f6dd7a-6eb8-52e5-aea5-890ec4ca3c2e | note | d) pest and disease control Clause 9.2.1.4
de1cb9a0-bf38-5359-8325-f0867072f4f9 | note | e) repair or re-installation of failed treatments Clause 9.2.1.5
3860cfb1-4430-51bd-828c-7887f004b695 | note | f) mowing, slashing and brush cutting Clause 9.2.1.6
3e576443-96e7-5752-87ed-2fddc87a0f05 | note | g) monthly program and inspection reporting Clause 9.2.1.12
5ca7dc69-43bc-510d-9a8e-e91da6a5fb0a | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b31b350d-f530-583b-a633-491beda98b78 | note | Check Item - Check Item
1eacf247-10bc-5997-969e-77a0e1a5420e | note | Reference - Clause 9.1.2 MRTS16
0f579b8f-9869-4d39-a3a8-e01b8f680968 | checkpoint | 15 - Monitoring Period completion criteria
b92857da-7a73-5f9a-ab11-1202b5189aab | note | The Monitoring Period shall be completed when the lot has met the following completion criteria:
b76dac3e-6b38-56b1-8a42-73b353a13373 | note | a) the area is weed free in accordance with Clause 9.2.1.3
0943e00b-1830-57f7-966f-5c56bfc4afd8 | note | b) seeding treatments meet the criteria of Clause 9.2.2.1
88fada67-fc92-51e2-b1a7-68825ec1a589 | note | c) turfing treatments meet the criteria of Clause 9.2.2.2
fc64854f-ee78-5313-a441-abc30be5ae2b | note | d) planting treatments meet the criteria of Clause 9.2.2.3, and
eac5cc9c-5468-5729-9080-8c79e7c6ce43 | note | e) the lot has been monitored for a minimum 90 day duration, or as otherwise specified in Clause 4.1 of the Annexure MRTS16.1 or the Contract.
8d9e568f-28ba-5029-a9de-f3375ea666fb | note | ○ Upon successful completion of the Monitoring Period the Certificate of Completion of the Monitoring Period shall be issued by the Client.
27dafbcc-9bcc-5971-be73-aa9899e10377 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0cd6fa67-4230-5e06-8393-aa459b72b866 | note | Check Item - MILESTONE
932b3c5e-d45f-550a-bee5-f238b84460cf | note | Reference - Clause 9.2.2 MRTS16
f6c32818-6e31-4edb-b1f3-371cd9d68b91 | checkpoint | Final Verification
9ba951ac-7ac6-5bd9-bd69-e2ee1bfc7946 | note | Responsible Officer
19cccad5-35d7-5c7e-880c-b2cadf974530 | textbox | Print Name:
b933fc35-ea81-533c-9b32-4970703ccc8b | date | Date:
79298242-aec0-51cf-b01a-2e80131b1926 | note | Verifying Authority
5e9cbe82-3e59-5fbf-a5b4-8e22c8c46fc8 | textbox | Print Name:
4b381a73-9978-5719-a729-e69b2e0ed9ce | date | Date:
7014dd94-080a-429a-ba39-e854e258ec34 | signoff | Signature
1e6e8570-98b8-4369-93d4-ede09031d899 | section | Final Sign Offs (to be completed at closure of Lot)
5a2ad86f-8455-46db-a630-80cff948054e | checkpoint | Agreed Quantities
48e43353-5143-4aa0-a14d-d6c803c323a3 | signoff | Agreed Quantities Sign Off
0b05ef0f-165b-485f-9ee1-624017d81b65 | checkpoint | Closure of Lot
8253f73a-627a-489d-8cf8-818312ff898b | signoff | Closure of Lot Sign Off
63f4134f-8d1a-4fe5-b78b-5045a51ce9a2 | checklist | 26.00 - Contractor's Site Establishment | itp | 26.00 - Contractor's Site Establishment
aed28049-08f6-4bf1-969b-a02436b886bc | section | Details
3c6a0115-c124-4ef1-a5c8-6c9deddf9e4b | checkpoint | 1 - Document Submission: Site facilities and camp establishment is to be in accordance with MRTS01 and MRTS50.
04f53cee-2f3b-5b45-a960-228d0571f916 | note | Acceptance Criteria & Frequency (Project Specific) - Check that all documentation are in place
a791b0a2-af89-5cb9-8421-c3be3ae3901e | note | Check Item - Check Item
83ffc99a-79c6-4b2f-b62e-418ea227e0a3 | checkpoint | 2 - Location of Site Facilities
39839aa7-fb36-5314-9b8a-92e266b05a38 | note | ○ The areas shown within Clause 1 of Annexure MRTS28.1 are available for the establishment of Contractor’s Site facilities and / or storage of plant and / or materials.
97f55cc5-f6cc-57af-87ac-3fa44f727632 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b9ad1500-9ff7-5ab5-9d7f-5f4052f89945 | note | Check Item - Check Item
ee39de47-7d29-5fca-9655-4385c1bca3da | note | Reference - Clause 4.2 MRTS28
87629fc5-0222-4b3b-9916-bba7b252783a | checkpoint | 3 - General Requirements
1e10e012-713c-5dd9-a27b-a7bacf2cd6cf | note | ○ The Contractor shall supply, equip, service and neatly maintain all necessary buildings, workshops and storage areas for the satisfactory completion of the Work. The Contractor shall provide properly constructed toilets and washing facilities at the Contractor’s site facilities for the use of personnel.
3b65e430-b324-5cad-9b0e-7b54e953e0d5 | note | ○ Appropriate First Aid facilities should be made available at the site facilities and camp.
618d177e-c157-5e47-99eb-33ade2981d14 | note | ○ Erosion and sedimentation control measures shall be implemented during the construction and operation of the Contractor’s site facilities.
50ca6eea-5c95-5580-8acf-bc8c9d81c41e | note | ○ On completion of the Works, all areas disturbed by the Contractor’s construction activities shall be restored to their original condition, or as may be otherwise acceptable to the Administrator.
a402fc03-931b-5c85-b91d-0e9ae77e5354 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
bb174853-c85a-5ea9-af5e-85779288b3dc | note | Check Item - Check Item
90c0078d-7768-5c64-a610-82dd7f509ecf | note | Reference - Clause 4.3 MRTS28
38ce454b-8194-4336-b76a-32cd28d2032e | checkpoint | 4 - QA Facilities and Meeting
ac4a0adf-c809-5da5-8cc3-9279d44f5ccf | note | ○ If stated in Clause 2 of MRTS28.1 Annexure, a facility for QA Auditing and meeting shall be provided. If no indication is given, a facility for meeting requirements related to QA audits and meeting on site shall be provided.
3786afdb-022f-5edb-963b-eaae5ab12a06 | note | ○ Room Dimensions shall not be less than:6m length, 3m width and 2.4 height and be equipped with one 0.75 kW reverse cycle air conditioner,
d097b7f3-2893-58d5-a8fe-8ca7c103e721 | note | ○ The room shall be furnished with two office tables 1.2 m by 0.9 m each and four office chairs.
639fe6bb-f651-50c3-a1e6-d06bc427267b | note | ○ The room shall be equipped with computers (with internet access where possible) and printer (with photocopy facility).
3d7a881f-bd6e-5c9b-92d0-2df11e535c40 | note | Acceptance Criteria & Frequency (Project Specific) - Check
bf5a883c-8c97-5a3f-be61-d0f44d6e24f1 | note | Check Item - Check Item
1e2da18c-80e6-5862-86bf-c4392ef09bf5 | note | Reference - Clause 4.4.1 MRTS28
b20e6604-9cd9-4877-840f-8e00d2f69ba8 | checkpoint | 5 - Documentation for Contractor Site Facilities
51c7410d-8046-54ac-abbe-9530824f81f0 | note | ○ If so stated in Clause 3 of Annexure MRTS28.1, the Contractor shall also provide, Drawings of location and sizes of buildings and plant maintenance areas,waste storage areas,access roads, fuel storage locatons, emergency evacuation plan and assembly point, location of parking area.
e6dfd62c-961f-5bc4-989f-d26e8b6cb79e | note | Acceptance Criteria & Frequency (Project Specific) - Check
451a564d-39af-5e64-b2e8-9978b9c0b137 | note | Check Item - Check Item
d885a61b-b68d-5f17-83ec-0ccff31313e6 | note | Reference - Clause 4.5.1 MRTS28
6484538c-9686-48dd-990a-96ce48c2598e | checkpoint | 6 - Visibility to the public
0bd9b9d1-3e29-5169-a432-3009f47df73a | note | ○ Where so stated in Clause 5 of Annexure MRTS28.1, the site facilities established by the Contractor shall be screened from public view as stated in this clause.
a8fb7565-9f96-519c-8ca0-2b19ebc58778 | note | ○ Site facilities shall be screened using an opaque material which camouflages the facilities from public view and provides an aesthetically pleasing appearance blending into the existing background.
261f9056-96e2-512b-8896-117177ffef72 | note | ○ External lights on the facilities and camps should be positioned or shielded to minimise light overflow onto neighbouring properties.
0996fc0f-c1e3-528c-a55c-843831449aa0 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
fe7f824b-6718-5259-a37b-e00b83922bf6 | note | Check Item - Check Item
263c2e99-ceca-59ce-8250-ef50b6e8c9b0 | note | Reference - Clause 4.5.2 MRTS28
d2c3b1e5-9659-4657-bc5e-b25a1d56a62c | checkpoint | 7 - Noise
b682f6fa-2489-5401-97e6-a740fba201ab | note | ○ The Contractor shall in its best endeavours to sustain the noise generated from the site facilities to a minimum and managed in accordance to MRTS51.
8c73be09-541a-50e3-8d30-a65d941c2083 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
4c68086d-2468-572f-82e9-fe98e6227b11 | note | Check Item - Check Item
17369eec-e265-53ee-bd39-fd840311d506 | note | Reference - Clause 4.5.3 MRTS28
cd64c613-013b-4bc5-879e-462103317904 | checkpoint | 8 - Dust suppression
c3165dc7-1c9a-5748-a593-59fe7ed5cb6e | note | ○ If so stated in Clause 5 of Annexure MRTS28.1, all access roads to and from the Contractor's site facilities and compound areas shall be sealed. A water carts shall be readily available at times to prevent generation of dust.
d5df9c08-bd4a-5485-a1f6-283e8fd843ab | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
7f8888b0-b332-5790-b5fa-d6d9486c027e | note | Check Item - Check Item
b772cd7f-10c3-5384-abf1-e568663589ec | note | Reference - Clause 4.5.4 MRTS28
cefee59a-5520-41ae-a235-dc2a1c8f2089 | checkpoint | 9 - Environmental Management
48df2a6f-490f-5aea-ad89-188bbc6468e4 | note | ○ The Contractor’s Site facilities and camp shall comply with MRTS51 Environmental Management and MRTS52 Erosion and Sediment Control, including addressing the facilities and camp within the project’s Environmental Management Plan (Construction). The Site facilities and camp are taken to be included within the definition of ‘Worksite’ provided in MRTS51.
84162c8c-e3f1-5540-89b4-ca387b217854 | note | Acceptance Criteria & Frequency (Project Specific) - Check
52eceedb-13b4-5c7f-8f05-1a2edd54b009 | note | Check Item - Check Item
7d8fd827-4784-5b16-ac01-c465de454106 | note | Reference - Clause 4.5.7 MRTS28
e22b625f-941a-4bc9-b882-64a9f208e26a | checkpoint | Final Verification
7766f453-4b1b-5b71-8fff-1e58d20e4398 | note | Doval Representative
962c8c3b-03f9-53a7-a713-5dcce9111582 | textbox | Print Name:
e745771c-5e33-58de-9c68-c69694d54f62 | date | Date:
b42860fb-5e7b-5295-b8d0-20934c33292d | note | Administrator
ed7b05e8-c499-5870-9083-80ef12a8e827 | textbox | Print Name:
0ecc503f-6b05-5ed0-a966-590d344569ed | date | Date:
8e8b1cb3-1271-4fc1-8dbe-586a9d96be60 | signoff | Signature
a8b2a2dc-9097-4ed2-97e1-2279bbc886e5 | section | Final Sign Offs (to be completed at closure of Lot)
b3eebef2-bb3a-4670-92a7-a8064347aa35 | checkpoint | Agreed Quantities
952b624b-638d-4385-b28b-c6d3ee754d09 | signoff | Agreed Quantities Sign Off
d0f9b127-2a8a-4e21-bb52-68632552015a | checkpoint | Closure of Lot
677ff029-0ec3-4493-8e47-2888bff270bb | signoff | Closure of Lot Sign Off
4a95b95e-b2d5-4cb9-be3f-14a1ab6f97ab | checklist | 28.00 - Road Surface Delineations | itp | 28.00 - Road Surface Delineations
5d2749d4-25cb-4e3f-8065-a27e2bce9734 | section | Details
64516e0b-50a5-43b9-a405-1ecc22923252 | checkpoint | 1 - Construction Procedures
bebfaafd-5918-5579-b916-1eef9cb1f157 | note | ○ The Contractor shall prepare documented procedures for the application of pavement markings with reference to Clause 5 MRTS50 Specific Quality System Requirements.
e9ff4a06-a153-594c-a09b-26b503cb7a67 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
a1a3be8f-0088-58ac-b48b-5c34e7640f1e | note | Check Item - Check Item
91a9f4c2-1641-50f7-a447-0b856dd753d8 | note | Reference - Clause 5.2 MRTS45
d59b88a8-f635-42d8-84fd-e23e18119cf5 | checkpoint | 2 - Testing Frequency
2a0fdd31-86be-5915-beb6-17cbd4e8d031 | note | ○ The method of testing shall follow the requirements detailed in AS4049.4 and may be varied by the testing frequencies nominated in Clause 1 of Annexure MRTS45.1. Measurements of the retroreflectivity shall be in accordance with the procedure define in AS 4049.4
0f169a18-8362-5cee-953f-f519a4534efa | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
32ad7a95-2c9d-5e49-97f3-311cc99ef3f1 | note | Check Item - Check Item
d15136ec-dc9b-55e9-ac5b-8316ccf33b15 | note | Reference - Clause 5.3 MRTS45
c7c72ed6-08f0-4e8c-943d-10040e32d3df | checkpoint | 3 - Material Requirements
43cad651-0ad0-53f2-b6f8-9493ef518a8b | note | ○ Performance Criteria: The retro reflectivity of new pavement markings shall be measured at 20 days of wear aaverage of all the readings (a minimum of 350 mcd/lux/m2) is required. Refer Clause 1 of Annexure
f4f9440b-1e18-52f7-b558-8d32a614ad4c | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
484aaace-54ae-5cb2-870d-0eb93ce8c9f4 | note | Check Item - Check Item
e5f648c1-9281-5023-a11b-f55795ee4311 | note | Reference - Clause 6.1.1 MRTS45
eb7ca263-006e-42b0-b2de-250d44a3a8fd | checkpoint | 4 - Material Requirements
fb45009f-87e5-5628-9441-8c21fc588d5d | note | ○ Paint: Is to be suitable for use on roads surfaced with a sprayed sealed, hot and cold mixed asphalt and concrete. Table 6.1.2 of MRTS45 detailed the paint colour designation and in accordance with AS2700.
396b3048-84b4-5666-9afe-4a4c80b712bc | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
e6bc896c-8189-543c-abc6-fc5ffec7981e | note | Check Item - Check Item
8ee3a8d1-9d3f-5116-96b9-4d79f3abaf71 | note | Reference - Clause 6.1.2 MRTS45
a2c22252-a85a-4382-9b19-515800cf6d3b | checkpoint | 5 - Material Requirements
c55e890b-4acc-575c-b388-88a095a3ed02 | note | ○ Reflective Glass Beads: To be of Type B, B-HR, C, D or D-HR conforming with AS2009 and AP-S0042. The type to be used shall be as stated in Clause 3 of Annexure MRTS45.1
11764ab7-d10d-5acb-99db-e88e09a749d7 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
f2b97a51-92f7-512e-8b27-539dad21432e | note | Check Item - Check Item
61fc72e9-b626-5760-9c0e-a22a519b2cf3 | note | Reference - Clause 6.1.3 MRTS45
3bafd32e-5568-4e57-8d82-518cc31672e5 | checkpoint | 6 - Material Requirements
c3920b03-2147-5d4d-8c4c-89d25e1fb215 | note | ○ Skid resistance for transverse line marking: shall have a skid resistance conforming to Table 6.1.4 MRTS45. The test method and frequency shall be as AS 4049.4. and varied as stated in Clause 1 of Annexure MRTS45.1
b75bf622-975e-5335-ae93-45ecec0510e9 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
ad252fdc-0c28-5ce1-be8b-6ec80053e35d | note | Check Item - Check Item
f363a26a-e7cd-5526-a436-5b6c7815b782 | note | Reference - Clause 6.1.4 MRTS45
014c8700-057c-4787-bd0a-9858f8541878 | checkpoint | 7 - Material Requirements
719e79ee-a00a-5c80-8eb3-9a7e0af6ca16 | note | ○ Thermoplastic materials: Shall comply with AS 4049.2 and be an approved product from the 'Asutralian Paint Approval Scheme - Specification AP-S0041/4'
7ccbf51c-0ec7-5548-ba65-d72b69dafdc0 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
9736296b-eb4c-5fc5-9048-6e6ba105d6bc | note | Check Item - Check Item
65441764-f139-502d-9a4d-b1ffd44fd314 | note | Reference - Clause 6.1.5 MRTS45
528e9c7e-f207-47af-b3e0-39174a035128 | checkpoint | 8 - Material Requirements
f63de203-08f2-5041-bcec-5c9bf5437e1b | note | ○ Cold applied plastic materials: Shall comply with AS 4049.4 and Clause 3 of Annexure MRTS45.1 and be an approved product from the 'Australian Paint Approval Scheme - Specification AP-S0041/3)
9083384c-87a7-5ae0-beba-0044be8fb9bf | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
a2c8048f-4ba7-5b10-b7ec-d0f87bb453f1 | note | Check Item - Check Item
9bc85e99-3319-50f1-908e-c0a9de186721 | note | Reference - Clause 6.1.6 MRTS45
c5cfc3d4-c2d5-4e52-9e55-5e66a8a62a65 | checkpoint | 9 - Material Requirements
f640810f-e18d-5374-b8ac-d054263bf107 | note | ○ Raised retroreflective pavement markers: Shall comply with AS 1906.3 and be Type A1 either uni-directional or bi-directional. For uni-directional, the pavement markers shall be white, red, green or yellow. Whilst for bi-directional pavement markers, it shall be white or yellow.
9b05291e-4d85-5260-b3d4-749569dbc1b2 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
5837d155-6516-5768-874e-944bf4fb8fd3 | note | Check Item - Check Item
362ee0f6-c33f-59a8-9f94-1efd0617948c | note | Reference - Clause 6.2 MRTS45
3f2bf01a-7aec-4cd2-beb3-b925be8c6b93 | checkpoint | 10 - Material Requirements
39f98964-c3b8-5d3d-8c39-36fed5d2d544 | note | ○ Non-retroreflective raised pavement markers: Shall conform with the requirements of AS 1906.3 and shall be Type B. It shall be circular, approx 100mm in diameter, and 15mm high and white in colour.
ef839fc8-8fc8-5649-9ea6-f94d587d7fbd | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
9b334d10-c606-5105-a2e3-477e5c8a9162 | note | Check Item - Check Item
1aef4c10-1be1-5932-8daa-1d74c01451ee | note | Reference - Clause 6.3 MRTS45
a476a2b8-b902-4ffb-9c95-2d73adf39f88 | checkpoint | 11 - Material Requirements
c3de7d6b-3bc3-5f51-aff6-0af73ebeba5e | note | ○ Temporary raised pavement markers: Shall conform with the requirements of AS 1906.3
81c8efcf-634d-5649-b1cc-aec90d85c8ec | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
a9e3b34f-9d5f-5276-aa6a-953df63e969b | note | Check Item - Check Item
ce9f4996-4061-5f34-8a19-329ea13b6754 | note | Reference - Clause 6.4 MRTS45
a3b75480-538f-4a9e-96f2-d9f5daeef8e9 | checkpoint | 12 - Material Requirements
d5603d33-b0b9-5bba-a8df-90ef4b093add | note | ○ Pavement Bars: Be manufactured in accordance with details shown on the design document, or if not shown it shall be manufactured from concrete and painted white.
93f3bcc2-8d5e-5539-891f-f174d4377ed3 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
c04bff0c-a01e-5280-baa7-ebb429afe6ac | note | Check Item - Check Item
c72b00c3-b15d-588e-985d-1747c080eb1a | note | Reference - Clause 6.5 MRTS45
32cb1218-c510-4a09-9f7b-bfff8afbf3b2 | checkpoint | 13 - Material Requirements
758fb0be-0046-544d-bd25-654aba989fa3 | note | ○ Adhesives for raised pavement markers: Adhesive to install raised pavement markers shall comply with the manufacturer specification. If not available, the requirements of AS 3554.
6453287a-a461-5d19-8402-2aa2335787b7 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
e4ce104a-b9cf-59bd-8fd9-24a8ca1a4b98 | note | Check Item - Check Item
0b546344-798c-5d8d-8db4-d8218023eb3a | note | Reference - Clause 6.6 MRTS45
e0499d6f-ccef-45c8-8411-c2fe6180d2ab | checkpoint | 14 - Setting out of pavement markings
27ce6345-93a0-5edd-8de1-127d23722066 | note | ○ The Contractor shall ensure sufficient set out is carried out to establish satisfactory alignment of pavement markings, within the specified tolerances.
cf477e9c-5bcb-57e8-a54c-41bfcc0492c9 | note | ○ Spotting on reseals and asphalt overlay, the control line shall be installed at 20m intervals.
daf3f751-2e2c-565a-8601-c71e3fa5291e | note | Acceptance Criteria & Frequency (Project Specific) - Check
b04ac0c2-82ac-5697-8043-b078c45e03d5 | note | Check Item - Check Item
68053382-b662-59d9-93e4-26bc2f627cb4 | note | Reference - Clause 7.1 MRTS45
90a04796-86b1-4b18-9ee9-941db88ae7c8 | checkpoint | 15 - Weather Conditions
bb8eb267-70c9-52e1-a5fa-f6a97b82903c | note | ○ Pavement markings shall not be applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set. The surface shall be dry.
ac1616a8-2228-5595-8c29-6315ab84c7e5 | note | — Air Temperature > 15°C
6a14b567-1553-5680-ac7d-8d014e68b5f3 | note | — Relative humidity < 70%
1f00d918-c40f-5d33-95a3-388b6b7e45c9 | note | — Air movement > 10 km/h
f260ab14-c8be-53be-b2c9-306e88f30ed8 | note | — Adequate protection of lines from traffic during the drying process,
a03fb1b4-0e8f-55fa-a2dc-86c23f1a18d0 | note | ○ Waterborne paint must not be applied when relative humidity is above 85% and when air or pavement temperatures are below 10°C
de1d2fd2-0c4c-5514-997e-18ad75da6e22 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
c4e37542-6919-5495-8f2d-82b6a9a6d715 | note | Check Item - Check Item
dbd8ad1d-cc38-5c8e-86df-bd96383e8475 | note | Reference - Clause 7.2 MRTS45
249e859d-e28e-4dc7-bf3f-7ca87bd6c427 | checkpoint | 16 - Surface Preparation
31261228-59b2-57c6-9ce3-82892ca7fb76 | note | ○ The surface area in which pavement markings are to be installed must be dry, free of dirt, gravel, flaking pavement marking material and other loose or foreign material.
1c4a1ae0-3b64-5fe6-90fc-968607381bc0 | note | ○ Further, for new bitumen sealed surfaces which are to receive new pavement markings shall be free of volatile material and solvents. Clause 7.3 of MRTS45 defines the conditons under which the pavement marking work shall not proceed.
1eb6cb4f-0f3a-576b-bcd3-9f3d048e0ec6 | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
97873cc5-a5ab-5acb-a026-686db9d84c8f | note | Check Item - HOLD POINT
61f7ff94-25dc-5700-bb0e-0ee4ff172a9e | note | Reference - Clause 7.3 MRTS45
a690b8aa-f482-4a9c-8047-2cfe5f314e32 | signoff | HOLD POINT
e4e0128b-b4ab-48a2-834a-f23e92c3349d | checkpoint | 17 - Spotting
de0919de-3e59-543e-b585-98c496bcabf1 | note | Spotting approval shall be obtained prior to the application of pavement markings. It shall consist of spots approximately 30mm wide and 150mm long.
c672bf12-3c37-55c7-8a69-9f3d86141eac | note | — Longitudinal Lines: 5m intervals with 3m intervals on curves less than 50m radius
d33bbe6c-0330-574c-a321-a3babab52104 | note | — Transverse Markings: To be carried out as shown on the design documents
e65b5f42-ead0-5cbb-8f1f-80f5f73a2a80 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
8876058e-f43a-5847-b14d-53c332a00b34 | note | Check Item - HOLD POINT
e119a5de-ae21-5c32-9dd4-8c92c0cf8e79 | note | Reference - Clause 7.4 MRTS45
5c6fa51a-7c05-486f-9f21-632b71256a01 | signoff | HOLD POINT
f6795b9a-8189-4181-be64-bb915af5fcf4 | checkpoint | 18 - Application of paint and glass beads to new pavement surface
f3f93513-2189-5e11-87fb-e26e2624518f | note | It shall be of uniform thickness and intensity.
5d1a540e-7224-5002-9d7e-20012e4a2845 | note | — Waterborne paint shall not be heated to temperature greater than 65°C.
a7413490-65ba-5842-9876-e179d713d87b | note | — Two coats of paint and glass beads shall be applied on longitudinal lines to new surfaces
bd8992be-fe69-5e26-b5d4-943f63b0220e | note | — Each coat of paint for any longitudinal lines group, including glass beads, shall be applied in one pass.
9a306413-722c-5b64-949f-fb0a7dce5308 | note | — The first coat of paint shall be applied using Type B-HR glass beads and the second coat using the gass beads as specified in Clause 2 of Annexure MRTS45.1
99ef7797-163e-5f94-8ae9-6806d09cb1a1 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
c4b2bdda-92c9-5101-9155-d3c8a9f20c78 | note | Check Item - Check Item
c23351b3-9d0f-5c57-8160-f20964a5639f | note | Reference - Clause 7.5.2.3 MRTS45
8f7eb019-aa8e-438d-b37d-6e14f4561806 | checkpoint | 19 - Application Rates
bcb14668-f0ff-5dc8-a1f4-3d933bb4fb1c | note | ○ Table 7.5.2.4 details the minimum application rates for the paint and glass beads.
839e8a35-a399-54e8-b631-154c20edea1e | note | Acceptance Criteria & Frequency (Project Specific) - Check
dafed9a8-eae5-5e8c-a048-382c4087031a | note | Check Item - Check Item
b62cde5a-8d16-556c-9504-61773032fe42 | note | Reference - Clause 7.5.2.4 MRTS45
27ea8823-bb61-448c-a05b-fd63ad6065fc | checkpoint | 20 - Application of thermoplastic material
f8a86b42-91a9-5fcb-907d-8f64e794dc6b | note | ○ Thermoplastic material shall be applied to the pavement at a temperature between 180°C and 200°C unless differ from the manufacturer recommendations.
1f28d25e-0d00-5c01-9acb-1aaaf01443dd | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
dbf34a3d-c043-5c45-8d94-796258ed0d21 | note | Check Item - Check Item
74736024-fe7d-520d-8c3c-139f487e076c | note | Reference - Clause 7.5.3.2 MRTS45
43ec12d6-5f5a-402b-bad2-147e344dfda4 | checkpoint | 21 - Application of retro reflective pavement markers
62aeac27-6758-50f2-bc44-a09aede91442 | note | ○ Shall be in accordance with Clause 5.6.2 of Part 2 of the MUTCD
897fba0b-12d8-55be-970d-57e5b5a2dd3c | note | Acceptance Criteria & Frequency (Project Specific) - Check
7c886974-2668-5f67-8264-060f0a6664d6 | note | Check Item - Check Item
6bc20d7d-7d7b-5154-b85b-1a0834b8898d | note | Reference - Clause 7.6.1 MRTS45
727f32d7-8634-4eb8-bedc-eb5d27fed1f9 | checkpoint | 22 - Protection of the Work
0cf4a58f-ad99-5fc0-ac44-ee4b9abd4e5d | note | ○ Newly placed pavement markings shall be protected from damage by traffic or other causes, using acceptable traffic management procedures; until paint is dry (no pick up condition) or thermoplastic material has hardened sufficiently to prevent such damage.
52d3563e-6007-5a7a-8c69-8254604d8083 | note | Acceptance Criteria & Frequency (Project Specific) - Check
b8ff9d41-fafd-5a06-9432-6dac6bf9d8ea | note | Check Item - Check Item
ecf465f8-f339-5fa7-8961-a573b53964a5 | note | Reference - Clause 7.8 MRTS45
b132b6cb-6b02-413b-898d-92955bb8dfde | checkpoint | 23 - Tolerances
081fd4a4-4a54-5d49-9944-7772fa7ff757 | note | Completed pavement markings shall:
cb581fb0-5eb7-5c39-94da-4e22659a2126 | note | a) be uniform
9a56910c-aaa5-5abd-b5e2-b5a02ba36f4c | note | b) have clean and well-defined edges without running or deformation, and
bd91e935-fbc7-55c9-a6b5-05ef8a816886 | note | c) conform to the dimensions shown on the design documents or in the Manual of Uniform Traffic Control Devices (Qld).
97e76e81-195d-5885-823e-579611743ec1 | note | ○ Longitudinal lines shall be straight on straight alignment and shall be on a true arc on curved alignment.
e1e2a859-56dc-596a-9d9d-a7077490ef32 | note | Acceptance Criteria & Frequency (Project Specific) - Check
de2481fb-6faf-5036-9c56-b05f5f88c777 | note | Check Item - Check Item
63d90732-e418-5718-92c2-05456593f410 | note | Reference - Clause 7.9.1 MRTS45
a95c3d08-b9c0-4e29-98a0-f0c113cd807b | checkpoint | 24 - Removal of Existing Pavement Markings
3e1b6c70-ebd3-5d48-8ca1-a8f28414109d | note | ○ Where required under the Contract, existing pavement markings shall be removed by the appropriate method stated in Table 7.10. Where a method is stated in Clause 1 of Annexure MRTS45.1, that method shall be used.
400d461e-fd18-5b71-aa0f-e3582379abc0 | note | Acceptance Criteria & Frequency (Project Specific) - Check
4c667aa2-8e7a-5263-8d58-6cf8c7b74459 | note | Check Item - Check Item
2d605a94-48c0-5616-a0c6-c0091388ce81 | note | Reference - Clause 7.10 MRTS45
65c542d6-fa3c-4e08-94e1-e7027aabae72 | checkpoint | Final Verification
0c411a32-cc5e-5440-8980-0bef5ad89aea | note | Responsible Officer
69ca5a05-db4d-577e-96df-771d35d1a43f | textbox | Print Name:
c39029f5-6835-52c6-9bd1-2ccd83ec1d61 | date | Date:
41aee832-6ae5-5967-b1d8-b4e532361369 | note | Verifying Authority
fa340cda-3918-5fe1-bc67-e039c181a915 | textbox | Print Name:
db15b636-7d25-54ff-8b34-f8627390d0cf | date | Date:
9e810ab8-b4c9-458a-8b39-df180e7f2962 | signoff | Signature
293f3775-c68f-4ec1-8ce8-b16761c3253d | section | Final Sign Offs (to be completed at closure of Lot)
4d76b39b-2261-4d4b-9c8a-da17c7289ffe | checkpoint | Agreed Quantities
94f299b5-9ed3-4d66-be8a-39b7d6ad2b26 | signoff | Agreed Quantities Sign Off
ac9786dd-4f0a-4b18-9431-4f26bb4d099d | checkpoint | Closure of Lot
d656f7a1-9765-4b10-ac5a-3426a94d4ac7 | signoff | Closure of Lot Sign Off
83ee89de-d9ef-4d81-bce5-c420723be9dc | checklist | 29.00 - Environmental Management | itp | 29.00 - Environmental Management
7be36e8d-5b25-4196-8ea0-1e020bb6ff32 | section | Details
03fa1d7a-e3e1-4938-b37d-36deec193fb4 | checkpoint | 1 - Document Submission
dee21171-f5dd-59a3-92cc-c114d50abd76 | note | ○ As per Doval Safety Plan and Doval Environmental Plan
fbf1089f-955e-52b2-8f01-ab594b87621e | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety and environmental procedures and controls are in place.
dc8687c2-6411-52ca-800c-e58461780b0c | note | Check Item - Check Item
d4bb64b9-84f3-4849-80a2-9f5dafd325b9 | checkpoint | 2 - Environmental Management Plan (Construction)
f267b726-9010-54d0-8c57-4e182075ec3d | note | ○ For the duration of the Contract, the Contractor shall develop, implement and maintain an Environmental Management Plan – Construction (EMP(C)) that meets the requirements of the Contract.
4400216a-a3b4-5bd8-a40a-023d5a90ca7c | note | ○ The Contractor may, with the Administrator’s deemed suitability, substitute environmental Management Measures included in this Technical Specification with other environmental Management Measures which achieve the same, or better, environmental outcomes. These Management Measures shall be documented in the EMP(C).
dac0b590-a011-5fa6-9b9a-64d24c7d2e07 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
dbd2e01b-a935-59bd-bf7a-84cf1f9a29bc | note | Check Item - HOLD POINT 1 / MILESTONE
c86ebb83-dcf9-5b55-8112-fd47f1aebfe8 | note | Reference - Clause 6.3 MRTS50
0ccd8e8b-98bb-4f14-9efc-37aff5a20089 | signoff | HOLD POINT
1e9655cf-5acc-486d-892e-3b93b114e7aa | checkpoint | 3 - EMP (C) Updates
3b3bf95f-bbe7-5eea-bd23-60bccd10562b | note | ○ Updates to the EMP(C) shall be undertaken by the Contractor to address changes on Site, Works under the Contract and to address corrective actions following non-conformances or Environment and Cultural Heritage Incidents. Where undertaken, updates to the EMP(C) shall be submitted to the Administrator as part of the Contractor’s Monthly Environmental Report, for deemed suitability.
f91fb3a4-6528-50b2-b019-e50734a696b4 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
e92a9efd-cb6b-508c-9cbd-faa71671213a | note | Check Item - HOLD POINT 2 / MILESTONE
a7feb2dd-e6d9-5115-b7f3-624f229ff145 | note | Reference - Clause 6.4 MRTS50
5558179d-6e77-4704-aeb4-fa5c8b7f215c | signoff | HOLD POINT
e9096f2e-5859-42c1-b8ec-591d55fa33aa | checkpoint | 3 - Notification Visits by administering authorities
a4bf23ba-2b76-5eaf-9015-b915e55fa025 | note | ○ Contractor must notify the Administrator within 24hrs of any inspections, site visits and meetings from any administering authority
91d23fce-b136-5930-85c4-d67e248b20fc | note | Acceptance Criteria & Frequency (Project Specific) - Notify
243a5054-b167-5c07-ad22-00d1cf633286 | note | Check Item - Check Item
4e6ddd12-7a49-5678-9f79-f7b74a30e49f | note | Reference - Clause 7.2 MRTS51
10e559a5-9a81-459b-af40-ebe95c0fabdd | checkpoint | 4 - Environmental Weekly Site Inspection
a2714777-ce4b-5597-9522-ee7b9255e94e | note | ○ Contractor shall undertake and document daily site inspections for the purpose of verifying compliance with the EMP(C), licences, permits and approvals and the other environmental performance requirements specified within the Contract. Inspection records shall be made available within 48hours of a request for a specific Weekly Side Inspection Report.
3ff6f5a5-ce25-5bae-a45f-05a74eb57576 | note | ○ An environmental representative must be nominated. The nominated person shall undertake the inspections
44cd6987-e36c-5943-a9ab-ae7ea63e681f | note | Acceptance Criteria & Frequency (Project Specific) - Check
c90f1f0b-dcb9-56b0-a179-a0f375436809 | note | Check Item - Check Item
711e3c35-753a-5c7f-9257-4d3afdae38c1 | note | Reference - Clause 7.1 MRTS51
9c396e6d-6bb2-433b-ae87-3188e0a88a3e | checkpoint | 5 - Environmental Monitoring
6cc82163-204a-5387-9dc7-5ce07ef3cfbd | note | ○ Contractor shall contain procedure for undertaking the various types of Monitoring including specific locations, emthod, timing, frequency, duration, parameter to be monitored, and objective / criteria measured against. Reporting shall be submitted to the Administrator within 5 business days of the end of each month.
a8326d51-d2c9-5341-a79a-b5ea42ff4860 | note | Acceptance Criteria & Frequency (Project Specific) - Reporting
de262529-abaa-536f-b06e-745482c46d8e | note | Check Item - Check Item
e6e2d215-d60a-540c-81f6-03e36fa47e13 | note | Reference - Clause 7.5 & Clause 7.6 MRTS51
e5389717-aab0-4a4d-908e-4d36212535c1 | checkpoint | 6 - Notification and management of environmental incidents
7d26b086-1471-55a0-b739-a7a93073d199 | note | ○ Notify the Administrator of incidents involving material or serious environmental harm shall be reported on a monthly basis. Reporting requirements as per the Environmental Protection Act.
6ad324b7-c35d-5417-91c5-cfa4ea9a91b7 | note | Acceptance Criteria & Frequency (Project Specific) - Reporting
edf09158-fa9c-5cce-b51a-076dec322e35 | note | Check Item - Check Item
7bd12845-da19-54dd-b4b4-cbef2575d6e3 | note | Reference - Clause 7.7 MRTS51
fa689bb6-88de-4d99-bc96-729825f28de1 | checkpoint | 7 - Records and registers:
10f027dd-6e41-598b-a6fd-dd506ab7d978 | note | ○ Environmental records are to be included in the Quality Records under the Contract. Table 7.8 of this
c910e521-fdbc-5274-b4b0-22323e108f2d | note | ○ Technical Specification identifies environmental record requirements. Records and registers shall be made available to the Administrator upon request. Hold Point 3 Milestone
18e61d57-fd10-5ccb-b764-e5e92b953c7a | note | ○ The environmental records listed in Table 7.8 shall be submitted to the Administrator (electronically unless agreed to by the Contract Administrator) prior to Practical Completion.
6ea52249-16f1-5b9d-8e9e-3871db546b48 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
4932078e-b280-5ee6-869a-e897691d9fd2 | note | Check Item - HOLD POINT 3 / MILESTONE
a44b2144-c040-5f2d-a6a3-7072216f4d3a | note | Reference - Clause 7.8MRTS51
25911309-8094-4393-ba65-d071a47bb4f4 | signoff | HOLD POINT
2dbc7e03-a771-4f47-8bca-966a3a379ac5 | checkpoint | 8 - Noise
91ad7db9-aaa7-5687-a383-e643e9b77eb8 | note | ○ The Contractor is responsible for the management of construction noise generated from Work under the Contract. The requirements of this Technical Specification do not include management of noise in relation to noise exposure within the Workplace occupational noise). This Technical Specification does not address noise impacts on native fauna unless specified in the Annexure MRTS51.1.
a230e534-77b5-5e83-b8c6-7a630f6d6601 | note | ○ In the event of a noice complaint refer to Annexure 51.1 CL 4.4
2a281390-9bec-534d-90a7-42abf9daf191 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
6823d4ee-e736-5973-a9d0-93a8564443f6 | note | Check Item - Check Item
50b27c0b-6119-5aff-adcb-7a9dc4f872fe | note | Reference - Clause 8.5.1 MRTS51
82e8f05d-3c4a-4912-8073-98c92a74169c | checkpoint | 9 - Vibration
c9f70db7-592c-579a-b20e-b961a6ab35c0 | note | ○ Contractor shall undertake a risk assessment of the potential damage cause by vibration to nearby premises, building and structures or cause environmental nuisance/harm prior to commencing any work activity. The Contractor is to prepare a condition survey of the premises, buildings and structures (including those listed in Clause 4.1 of Annexure MRTS51.1) that may be impacted by noise vibration.
a2a45ff3-b754-5d8c-bf00-8d6d43977a51 | note | ○ Unless stated in Clause 4.2 of Annexure MRTS51.1, a registered structural engineer (RPEQ) shall carry out the condition survey.
ab3c32a1-2b4a-5033-ab4d-731b76fe722f | note | ○ At least 5 working days before any work activty that cause vibration start, a copy of the condition survey shall be given to the Administrator.
a7c30476-23e5-537f-9a02-f258f0cde10c | note | ○ Identified vibration sensitive receptors are detailed in Clause 4.3 of Annexure MRTS51.1
42209f49-00bd-5643-95bd-b10e07c71740 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Reporting
9e794c21-99a9-5ffc-9cb4-795baa14b849 | note | Check Item - Check Item
dae71f5c-d305-57f1-a2fd-b8299837dda6 | note | Reference - Clause 8.6 MRTS51
79719189-a86f-426a-bbab-897195f43d64 | checkpoint | 10 - Air Quality
6f47eea0-d216-5c82-8785-13ae505e3978 | note | The Contractor shall manage construction activities as such to mitigate air quality impacts that cause environmental nuissance or harm. The following management strategies shall be implemented, but not limited to:
ee711de5-ebf3-53e2-a534-fbb830f250c7 | note | — regular watering or temporary sealing of the site and access roads.
8aee9043-2e90-5f57-9a92-8ecd96e102c0 | note | — avoiding works (e.g. stripping, excavation, etc.) during dry and windy conditions.
7be5044e-f2e9-5e3e-a268-a36413b7604f | note | — fitting equipment with dust collection/suppression devices
59367674-9c5a-558e-ab50-6e725d16bb13 | note | — stabilising/covering all stockpiled material for longer than one month
3d919475-19ef-5044-ad8b-4d9f8e40c483 | note | — covering loads
cd847df7-1497-5305-8790-e5470803dad8 | note | — maintaining clean roadways to and from worksite
04575fbe-a438-52b6-a716-25a80dc55bf5 | note | ○ If stated in Clause 5.1 of Annexure MRTS51.1, burning of material shall not be permitted.
661dc6eb-c013-536e-9a61-a114745bd372 | note | ○ Clause 5.3 of Annexure MRTS51.1 specifies the air quality monitoring requirements for compliance. Unless stated otheriwse, air quality monitoring shall be undertaken in accordance with the Air Quality Sampling Manual, EPA, 1997.
f4503ce3-c98d-5058-8ae2-dd12ec8116d9 | note | ○ Construction related air quality complaints shall be managed in accordance with Chapter 7 of the Road Traffic Air Quality Management Manual.
df4aaf04-6439-5d9e-90b4-ce7785963dff | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d14254ac-59b6-552b-90bd-3b72cfff06e1 | note | Check Item - Check Item
841755dc-884d-553e-828e-6fd46c653c0e | note | Reference - Clause 8.7 MRTS51
b08c2280-9068-4e4f-b8f3-5a5fdabf9463 | checkpoint | 11 - Acid Sulphate Soils
73bc2a33-92ca-540f-8e9c-faed1da27f76 | note | ○ The Contractor shall be responsible for the management of actual or potential acid sulfate soils within the Site. The Contractor's EMP(C) shall address the requirements of MRTS04 General Earthworks including the requirements concerning the management of actual and potential acid sulfate soils.
8725270d-4ad4-5710-9fef-ea462186545d | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
dac41eed-a32b-5aa2-85fe-94eacf965a20 | note | Check Item - Check Item
c8577382-9622-518a-b880-73235d9916b9 | note | Reference - Clause 8.8 MRTS51
a02a9b5a-4fb9-4b26-b5f1-76c44bd43f50 | checkpoint | 12 - Contaminated Sites
1ca50a6a-2a78-5782-9018-f0f4ad1430e1 | note | ○ The Contractor shall be responsible for the management of contaminated sites (e.g. contaminated soil, waste dumps, unexploded ordinances) within the worksite.
783dd772-6fe5-5672-adab-d17225c210dd | note | ○ Clause 6.1 details a lists of known contaminated site within the worksite and associated management requirements.
5a422f46-9b61-568b-988b-87b17659d783 | note | ○ The Contractor shall manage known contaminated sites in accordance with statuary requirements and any additional requirements stated in Clause 6.2 MRTS51.1
94a307d9-3b10-569a-846b-9bbd40b04127 | note | Acceptance Criteria & Frequency (Project Specific) - Check
92878619-afe1-5e0e-92ad-71d0478faa85 | note | Check Item - Check Item
9b94123e-f2c4-55b0-84df-a200e558b20d | note | Reference - Clause 8.9 MRTS51
97cc8105-634e-4189-aab8-d278ee20dd51 | checkpoint | 13 - Fauna
e8e5ed2b-0446-5dbe-b730-1d88c169623d | note | ○ Duty of care shall be taken to not harm native fauna. A list of fauna management to which the Contractor shall followed is described in Clause 8.10
4ebe29ec-d547-5426-800e-33c05b7d56f5 | note | ○ The Contractor shall be responsible for the assessment, management and compliance of temporary Waterway Barrier Works undertaken as part of this Contract unless otherwise stipulated in Clause 1 of Annexure MRTS51.1. Principal identified Queensland Waterways for Waterway Barrier Works, as mapped by DAF13, are identified in Clause 8.1 of Annexure MRTS51.1.
07aebdab-2cd4-5fc5-84c9-a187e3f1c0f3 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
2d1c0a99-45e8-5fc2-8c86-ccff01ea0ceb | note | Check Item - Check Item
1799ea47-ce19-5e83-90d7-4434d9b91a0a | note | Reference - Clause 8.10 MRTS51
6ede4a49-9fc0-43d8-8976-6247bf8fef04 | checkpoint | 14 - Vegetation
a3659684-a4c9-5da3-be70-9f84a7de724b | note | ○ The Contractor shall ensure a vegetation management plan within the worksite is establish. As stated in Clause 8 of Annexure MRTS51.1, a list of significant areas of vegetation and associated management requirements has been highlighted within work site. The Contractor shall ensure they implement a vegetation management strategies listed in Clause 10.10.1 MRTS51 in their management plan.
2b5b8cfe-97c1-53c3-9531-ab1bb57b8456 | note | Acceptance Criteria & Frequency (Project Specific) - Check
e926228a-59dc-55ff-a609-658bd609e7fa | note | Check Item - Check Item
1d7109dd-a151-57a8-b39b-7208413b69e2 | note | Reference - Clause 8.11 MRTS51
6edf955c-a6b7-4e1c-ab2d-2b52b2570ed9 | checkpoint | 15 - Fauna Monitoring
d8978050-6b0b-599d-b917-bd0187b7a033 | note | ○ Monitoring in accordance with Section 8.10.2 of the Technical specification (MRTS 51 – Environmental Management) must be undertaken if the requirements of the Environmental Approval for Tampering with Animal Breeding Places of Least Concern Species (SMP-low risk) and Colonial breeding species (SMP) are triggered.
c1e73041-9659-5183-b966-2e54f41db7aa | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
287c3ebb-540b-5def-a251-86f7e60c210d | note | Check Item - Check Item
9522d95b-58fb-5a68-a20b-2d5af24533cb | note | Reference - Clause 8.10.3 MRTS51
b36ad732-a02f-4725-8eb9-25349c7a864b | checkpoint | 16 - Biosecurity Management (Pest Management)
5abc250b-831e-5a8f-a919-4af4b796e1fb | note | ○ The Contractor shall ensure they consider in their management plant the lists of biosecurity management strategies nominated in Clause 8.12 MRTS51. The Contractor shall control the movement of all biosecurity matters (including invasive animals and plants) preventing their spread on and off site. Detail in Clause 10.1 - 10.3 of Annexure MRTS51.1, a lists of known biosecurity matters within the worksite and asssociated management requirements has been highlighted.
198c0090-45cd-510f-a2a3-779f5f88110a | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
775bf8c7-b249-57ea-98e3-2ada379ea126 | note | Check Item - Check Item
583c3f5e-bac5-57b1-999c-735da473da37 | note | Reference - Clause 8.12 MRTS51
fee971c2-4b7b-4296-8636-d40eecb5e1bd | checkpoint | 17 - Waste Management
1512ced8-8196-5a7c-a21d-d3a1c6d79414 | note | ○ A waste management strategies/plan must be developed to control wastes generated during construction, inclusive of but not limited to waste avoidance, waste reuse, waste recycling, energy recovery from waste and waste disposal. The Contractor shall ensure compliance with the Waste Reduction and Recycling Act, 2011 at all times.
e1a2b385-6533-53e6-a7bb-7005ee7671c5 | note | ○ The implemented EMP must accomodate the documents and/or diagram listed in Clause 10.12.4 MRTS51
a2031903-f494-5308-b5e8-ad1d66380bee | note | Acceptance Criteria & Frequency (Project Specific) - Check
1294ff0a-eedc-5bfd-b635-8caf92cb7f4f | note | Check Item - Check Item
ae288ef2-98d2-5616-b0e9-237e3340bdd7 | note | Reference - Clause 8.13 MRTS51
a21f294c-cd70-432c-8484-81ef5cabd053 | checkpoint | 18 - Chemical and Fuels Management
4a8fc5bc-ca30-5c79-945e-a807cdbc2c9f | note | ○ The Contractor shall be responsible for the management of all chemicals and fuels within the worksite so as to prevent environmental nuisance or harm.
dce1f663-50d9-58c0-9343-1aedadc17317 | note | ○ Further to the compliance with the requirements of the Environmental Protection (Water) Policy, hazardous substances or dangerous goods, the Contractor shall comply with AS 1940 and the Work Health and Safety Act.
16e3c68b-35ba-5a35-b27c-c12ad7f46452 | note | Acceptance Criteria & Frequency (Project Specific) - Check
f85db6df-88c1-5034-bb54-6dee753fd28e | note | Check Item - Check Item
30ff5595-fa5d-5bcc-a9b2-70bd667ecf55 | note | Reference - Clause 8.14 MRTS51
f23bf612-c9f0-4854-b3c9-a4bc3f555c9a | checkpoint | Final Verification
477931b5-9ca8-5233-8b66-c15724f98a09 | note | Doval Representative
63ad7609-0d18-576b-8087-464d9c1c608d | textbox | Print Name:
ef29aec5-8c96-52b8-b3a2-0b3a6ac87516 | date | Date:
b4735d17-21e2-5fe4-968f-426928904433 | note | Administrator
8fe7bd2e-cc77-5275-abdd-8ef85128bcb6 | textbox | Print Name:
4b081f44-e9ba-571d-9bdc-4329da54ec7d | date | Date:
30ff69f3-13fd-49d8-b61c-1aa01e134236 | signoff | Signature
183a83da-214d-4e57-8e25-d83acdef5d3b | section | Final Sign Offs (to be completed at closure of Lot)
ccdcb154-94e9-44c5-ad70-2ac496d83b6f | checkpoint | Agreed Quantities
bf4945a4-2a7e-4c3d-9612-1b7e1801893f | signoff | Agreed Quantities Sign Off
33c8f7b9-9ad8-453f-926d-44636137ca20 | checkpoint | Closure of Lot
63bc908c-5354-47f9-9591-0b72575c7759 | signoff | Closure of Lot Sign Off
730f35b2-3255-4ec2-b570-3e8b9c90b2dd | checklist | 30.00 - Erosion and Sediment Control | itp | 30.00 - Erosion and Sediment Control
b6f026c2-8c38-4d70-8c9a-70f5e1c6aa60 | section | Details
6903fc40-3250-4c34-9352-c4775ba29716 | checkpoint | 1 - Document Submission
f2f6d398-b355-5646-9675-17d96f023c06 | note | ○ Submission of the Erosion and Sediment Control Plan (ESCP). It shall incorporated areas of disturbance such as stockpile and storage area, temporary waterway crossing etc…
c7563dad-3482-5aab-857b-a1b9b547cdbd | note | ○ Clearing and Grubbing shall not start until the ESCP for that section until deemed suitable by the Administrator.
4ce9f048-d17f-5600-8371-1c084dc5272b | note | ○ Timeline for assessment os suitability of ESCP shall be as per Conditons of Contract.
c8564b45-b531-5821-b77a-b68693a4c610 | note | ○ Any changes to the drainage flow or sediment treatment locations shall be updated on the ESCP accordingly and submitted to the Administrator for suitability.
60be8af5-083a-505c-a03b-8e722337969b | note | Acceptance Criteria & Frequency (Project Specific) - Approval
d428ddbf-0e77-56dd-aa8c-806b5e1e5537 | note | Check Item - HOLD POINT 1
4a9ed994-be32-56f4-8e22-56b0e42d2440 | note | Reference - Clause 6.1 MRTS52
b54d160b-de63-4850-9e33-0bd55e840bf2 | signoff | HOLD POINT
8dc96a4e-5dad-4d63-843e-79832d20e4c1 | checkpoint | 2 - ESCP Plan Requirements
8ce80ef7-d3c4-5d17-a339-8d3e6ceb49c5 | note | ○ ESCP has been developed in accordance of the principles of Clause 1.4 and the requirements of Clause 6.2
7666f544-36d3-5fc9-b480-cff44493a6f6 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
27e6ff05-4981-53e8-bfb8-241c3534dace | note | Check Item - Check Item
a18820ee-c4f7-5eae-a6f2-fde63d1dc142 | note | Reference - Clause 6.2 MRTS52
20024413-440e-4d54-ae5c-fadf0c4ff2ed | checkpoint | 3 - Personnel Plan Development
c8392165-79df-5518-a025-15572f742cdc | note | ○ The Erosion and Sediment Control Plan shall be prepared and updated by personnel who have the requisite level of training and experience outlined in Table 6.3, or as modified by Clause 5 of Annexure MRTS52.
6c6285f5-73ab-53d3-b01c-ac183d6bb47e | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
32fa81a3-3067-5e6c-ba9a-df7eb150bb8c | note | Check Item - Check Item
61e5431f-e164-5eda-83ca-bafdaeae0d25 | note | Reference - Clause 6.3 MRTS52
c5a50ba1-ec1c-4462-93d1-a6d56137356e | checkpoint | 4 - Installation
616bd4d5-48ed-5b96-bc1c-bae023e1dd59 | note | ○ Erosion and sediment controls have been installed as soon as practicale and prior to initial earthwork for the section of the works (Includes rock check, catch banks, traps and diversion drains) The completion of these activity shall be approved before any earthworks can proceed.
6e4e1160-1d95-56de-9e0d-65641cd630c1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Check
90efc330-da35-5c3d-bb04-da453429fd39 | note | Check Item - HOLD POINT 2
c1363403-71d1-57b7-90e5-ebec91d58c71 | note | Reference - Clause 7.1 MRTS52
4fc4ac88-7fef-4b78-87dd-be43f81055de | signoff | HOLD POINT
26c4dfd2-35b4-4f3d-8c4a-e170f91bcee6 | checkpoint | 5 - Operation and Maintenance
df98afdc-dc0c-514f-bcb8-a4d3bb0ba510 | note | ○ Erosion and Sediment Control is to be maintained in effective working order throughout the works
768ed45a-f02d-5d0e-bd0d-cc76cddd34d9 | note | Acceptance Criteria & Frequency (Project Specific) - Check
c24705a5-d8fa-5edc-b9e9-df9955d5622b | note | Check Item - Check Item
bc7fe90b-b165-59a3-ab77-55c1cc4a8b5b | note | Reference - Clause 7.2 MRTS52
a3f6ecb2-670c-4fe2-8b3d-7eb1d0ef4f98 | checkpoint | 6 - Decommissioning and Removal
4d5a3cee-1a58-517c-ae4a-54f9d72e8f79 | note | ○ All temporary sedimentation control shall be removed in areas where permanent measures are in place and/or site stabilisation has occurred prior to the Final Certificate. The removal of these erosion and sediment control devices shall occur prior to the end of the Defects Liability Period or the end of the Landscape and Revegetation Works Monitoring Period whicever is the later.
a0256e16-ee54-5bf2-8c7a-b9f7b4f69da8 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b2bfa220-0b69-5d65-8c51-91c6937f3fca | note | Check Item - Check Item
d76b977e-4742-5b1f-9406-d2322b91a782 | note | Reference - Clause 7.3 MRTS52
64b00cd1-2f07-4a07-a301-81b77aca039f | checkpoint | 8 - Waterways - Offsite Impact
97063f04-97a6-5877-ba9c-6008375c3a61 | note | ○ Erosion and sediment captured within the work site shall not cause environmental nuisance or harm outside the worksite, or to permanent water bodies.
39c04cb3-a75e-5e43-a8fc-fd4252872a97 | note | ○ Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated in the ESCP and as deemed acceptable by the Administrator.
98e046e1-d2c9-5a90-8168-97ccd203ecef | note | Acceptance Criteria & Frequency (Project Specific) - Check & Report
22333dd2-26b7-5092-87c7-6b70111dc548 | note | Check Item - Check Item
8f10ad2f-8cb6-5adf-a9da-6f3c0edbc647 | note | Reference - Clause 8.1. MRTS52
1cca1cee-98f2-491f-8653-6fe1e90f8891 | checkpoint | 9 - Contractor Inspection and Audits
bef2be8c-046f-5bc3-88d8-d0bd65956acd | note | ○ Inspection shall be documented daily for verifying compliance with the EMP. Inspection shall include visual assessment of erosion and sediment control structures,
bbd7e26f-5f43-5be1-86d6-65dd662dcd6b | note | Acceptance Criteria & Frequency (Project Specific) - Visual Check & Reporting
2525faf4-5b3c-550e-bc34-196c854fdb8a | note | Check Item - Check Item
855713f1-2deb-5420-be83-2f2f5b1152ad | note | Reference - Clause 9. MRTS52
f6ade8cb-d870-46a3-8753-1c3b57ef703b | checkpoint | Final Verification
9995f6cb-a757-594f-a8ec-54d5781e0c5a | note | Doval Representative
1f25172f-e8a7-5e42-a74b-3b78eaa8ac25 | textbox | Print Name:
e979d5c7-68d0-5051-b92b-7784d03e9312 | date | Date:
b6392323-1a9f-5c5f-b6de-d4cee16fc01d | note | Administrator
9724a29d-de2e-5655-847d-b6fc9d9525ef | textbox | Print Name:
d176375a-e2b7-52f4-80cf-0a98f340c713 | date | Date:
162d1636-9dfe-4db8-aca1-f6d982d0985f | signoff | Signature
cc02f0ea-6cfb-425b-b2d9-39e58c96b1f1 | section | Final Sign Offs (to be completed at closure of Lot)
1611aaa3-eff8-442d-abc3-f16e513de07d | checkpoint | Agreed Quantities
16b5c5f4-1ec8-415c-af8b-bab66bc6e2ed | signoff | Agreed Quantities Sign Off
c33406c3-630d-4fdb-b608-31417a9a3d1f | checkpoint | Closure of Lot
e80abde8-e470-4314-b966-3818054352f3 | signoff | Closure of Lot Sign Off
e6db5c5e-ffd4-4bd3-a9d0-99cd398e5ef2 | checklist | 31.00 - Reinforcing Steel | itp | 31.00 - Reinforcing Steel
b354a7ca-1d5c-4a40-80bd-742b4796a910 | section | Details
ccbafc2c-7a7f-4d9e-b3dc-07b67a5d0500 | checkpoint | 1 - Document Submission
648e490f-0e89-53f9-a294-93377ede37d8 | note | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
f9abc7cb-8cd4-5d98-bd39-d0ac54cba2cd | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
eb762536-098f-5a46-84dc-92a599bd93bd | note | Check Item - Check Item
6f0efdfc-54f9-4913-aab8-99af645b2bf2 | checkpoint | 2 - Traffic and Safety Controls
f964c86f-29bc-5d1f-b1ec-cbb203962b66 | note | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
3488e6ef-2840-5baf-9629-c4c828b0c6da | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
8fe95d03-3edb-5795-8cd5-f391ebf3e360 | note | Check Item - Check Item
cca1ed88-9c93-4088-95b7-e3645ec751e5 | checkpoint | 3 - Supplier Approval
e032a02f-7fb6-557f-99f7-49f21057dcec | note | ○ At least 3 days before steel reinforcing is supplied, the Contractor shall submit to the Administrator the identity and address of the proposed supplier and evidence of conformance.
565617a1-62ec-54a1-80a9-95ce0d41ab31 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
8003d5ce-6b99-55d6-b9f2-af85fba407ee | note | Check Item - MILESTONE
12883382-083b-5bdf-ad1d-7b36028ef5e8 | note | Reference - Clause 6.1 MRTS71
02fcce38-97f1-4e88-981e-11935f0541c8 | checkpoint | 4 - Delivery of Reinforcing
cb461629-f192-5978-999d-a6b1f0ccdecf | note | ○ Steel reinforcing shall not be delivered to the Site until written acceptance of the proposed supplier has been obtained from the Administrator.
d049fdab-892c-57e8-be23-351165a29b0c | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
4e9f0873-37f3-5c6a-8086-2645dad5553b | note | Check Item - HOLD POINT 1
fd1449ce-04b1-532d-b8fe-9292f050fe17 | note | Reference - Clause 6.1 MRTS71
0a5d29ed-7dd1-469d-979f-e230b3a16f02 | signoff | HOLD POINT
3efce14a-f55a-487d-8315-980cea968f02 | checkpoint | 5 - Registered Manufacturer
45bcc348-b940-52a8-b646-69be3d0399c9 | note | ○ Steel reinforcement manufacture shall be certified by ACRS or a TMR approved product (Refer to Clause 1). If any reason the supplier cannot gain independent certification may be granted if compliant to Clause 6.1.2
01d23b25-1629-5577-b54a-364d34627298 | note | Acceptance Criteria & Frequency (Project Specific) - Check
a95348ec-21e7-519a-8e7f-0d891ade9dd4 | note | Check Item - Check Item
057815ec-6898-5950-93d7-43d7161526d4 | note | Reference - Clause 6.1.1 MRTS71
76b5e160-cae1-41eb-a604-4976d7782acc | checkpoint | 6 - Hot bending of steel
a4f9ed76-889b-5c50-9d69-74f90e5fc4a6 | note | ○ Authorisation is requires where specified for the bending of steel reinforced bars on site
17e6b3ac-0885-5015-a41b-26c8877f175d | note | Acceptance Criteria & Frequency (Project Specific) - Approval
6b3e4929-3537-53fb-ac38-88ae65db9578 | note | Check Item - HOLD POINT 2
22fd79d4-eed7-518f-89f7-69c60d876309 | note | Reference - Clause 8.2 MRTS71
ef9fadde-db78-4419-be5a-2dd10eff2319 | signoff | HOLD POINT
2be7bf1c-eb6c-4b1e-9ad5-881c4e392f68 | checkpoint | 7 - Placing and Fixing
540c5dbd-7252-5d8f-933e-9fcfa12a6e75 | note | ○ Where the bars will be tied together, the reinforcement must be tied by wiring at each intersection, using annealed wire not less than 1.6 mm in diameter. Where the bar spacing is 300 mm or less, alternate intersections only need to be tied.
2156fc93-8642-5f12-aadb-7d77acdaa37a | note | ○ All steel reinforcement in position shall be inspected and approved before placement of concrete commences.
eff5c9cd-8f60-576a-8925-221447969405 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
87b02674-9567-5196-acd1-01f483c821c8 | note | Check Item - HOLD POINT 3
d28a32cd-ad9e-510a-917b-109da0070500 | note | Reference - Clause 7 MRTS71, Clause 7 ATS 5310
f84f3e87-47ed-40b0-918d-43810e0cc70f | checkpoint | 10 - Substitution
bee77d7b-2d75-5487-8e41-44c62f6e9241 | note | ○ Substitution of different size, grades or ductility class of steel reinforcement so that shown on the drawings shall not be made unless approve in writing by the Administrator. The application shall be forwarded 3 weeks prior of steel placement.
557be0bb-bc3f-58eb-9a08-25f9b8d42902 | note | ○ Substitution shall not proceed until the Administrator has approve the change.
8b25b26d-44cf-5211-a0d9-4ffbd1bad14d | note | Acceptance Criteria & Frequency (Project Specific) - Approval
ad69a650-bd70-5e0c-a9e8-33d34f9b027b | note | Check Item - MILESTONE/HOLD POINT 4
8395fc29-eadd-5639-a3ee-9ba9fda9de95 | note | Reference - Clause 13 MRTS71
e8c080d6-bb8a-4b2c-8f60-53bf0c7c8270 | signoff | HOLD POINT
725b52b1-20b5-45a9-a25a-5e6e8c0d9352 | checkpoint | 13 - Prefabricated reinforcing cages
2ab6517e-a53b-5a83-a072-bb28a165db74 | note | All prefabricated reinforcing cages must be identified with the following information, either by tagging or a combination of labels, schedules and drawings:
3d182bd6-5800-5627-8dc9-fe2027f58519 | note | a) the fabricator’s name;
0e4ebf01-7c5c-51b7-8ae0-70591b854374 | note | b) date of manufacture;
29d05dd9-ab31-5950-8ffc-6e4085c12da0 | note | c) drawing reference;
7f81efd1-8d54-5a92-ad9e-29383a4611a2 | note | d) traceability of reinforcement as required by this Specification;
4c9190ab-583b-53b3-b734-411a5f760d1b | note | e) the mass of the cage; and
8670e77d-f29d-5b6b-a59f-cfeedc6f1f4e | note | f) the colour and location of dedicated lifting points.
9a89f56e-a8e5-5fd5-8e6c-cade2fea23c9 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
6ff619fc-00ba-5572-9f7c-5dca45717453 | note | Check Item - HOLD POINT 5
8616a2ee-2f9f-5130-bf2b-3c58635ad8ae | note | Reference - Clause 15.1 MRTS71
f5b921c5-ee97-4ced-a778-791bfd9d2276 | signoff | HOLD POINT
9ffd0369-d1ba-479d-94e2-002d87514c24 | checkpoint | 13 - Provision for lifting of cages
28f1ecc2-ad44-5896-8385-192a07c93348 | note | ○ Prior before lifting of large cage an RPEQ engineer needs to certify lifting points and their capacity. These must be submitted to the administrator prior to lifting
1c657c54-d3a6-5c74-bcf7-3f2c438a5074 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
070bb622-b03e-5b2f-8a42-7b9f3e848327 | note | Check Item - HOLD POINT 6
842c6e80-e61c-5200-bce2-031733a7b1a1 | note | Reference - Clause 15.1 MRTS71
5dad6531-2da4-4b58-a7c2-f7be81399080 | signoff | HOLD POINT
88a1e1fb-fd91-4783-96bc-4d8b25879045 | checkpoint | 14 - Inspection of Cage fabricated outside Australia
4b188b82-e423-592c-9c0b-42c005b763db | note | ○ Shall be visually inspected by the Administrator prior to any steel placement
a63e3443-9422-526b-bbac-293dcf588abf | note | Acceptance Criteria & Frequency (Project Specific) - Visual
42aa3137-20ac-5ba7-9dec-558ce67fd1da | note | Check Item - HOLD POINT 7
b9c9fb9e-9a29-50a3-9d45-ee1147fc5c27 | note | Reference - Clause 7.1 ATS 5310
e2c97573-b15d-4c38-ac9b-617168005d85 | signoff | HOLD POINT
11017829-4e2a-4f0c-8880-f1fdd61b5e14 | checkpoint | Final Verification
6493faf9-ecfb-5801-aeaf-9f38a1c7ec6e | note | Doval Representative
64719a07-c926-56ed-bec5-5b83a328196d | textbox | Print Name:
96d8f6e9-9f57-50f1-805c-6589789d9131 | date | Date:
6eb977d7-b35a-5fd6-a5b3-63ad3684b2f0 | note | Administrator
784c6e6d-e89c-521b-92ef-f549d808d98a | textbox | Print Name:
263c9ca0-f67e-5ea8-ace1-f3c06e79da6c | date | Date:
46d5a36b-f48d-483b-bf4b-4367fbfe8458 | signoff | Signature
f9114e18-0b70-424b-a4c5-2619512a448f | section | Final Sign Offs (to be completed at closure of Lot)
6f269f96-586d-4d68-8d47-68e1e6e94a85 | checkpoint | Agreed Quantities
2104b754-54e3-40cf-9539-1f9adc9f4835 | signoff | Agreed Quantities Sign Off
d57f5c6c-e730-414a-8a04-d64826e340b7 | checkpoint | Closure of Lot
15e194db-e1da-4b51-8919-e15ff90d14ef | signoff | Closure of Lot Sign Off
dd6da29a-3c66-41cc-a0d8-388852ab35ed | checklist | 32.00 - Specific Quality System Requirements | itp | 32.00 - Specific Quality System Requirements
cbaaf57a-68e5-46ba-850e-5a8e3e1ecefd | section | Details
43c372d7-e505-494c-a009-b3b92c28c454 | checkpoint | 1 - Document Submission
7c8b9c12-d930-59d8-9a75-4ba6591139c0 | note | ○ As per Doval Quality Management Plan
b730f60a-c523-58cd-a81a-e70253dee4ca | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper quality procedures and controls are in place.
b15da9d3-d5f3-56ba-bce7-019e91bdee89 | note | Check Item - MILESTONE
9260ca2a-c3bd-4de8-820c-9701951fe5c4 | checkpoint | 2 - Construction Procedure
2dbff12d-b68f-57c9-9d86-3792ad5bc109 | note | ○ Procedures shall be prepared for all constructions procedures, including statement of equipment utilisation. Construction procedures shall be submitted at least 14 days prior to commencement of construction procedure.
2185d912-138d-56b2-b32d-8a28daba941d | note | Acceptance Criteria & Frequency (Project Specific) - Check
15d81cf7-9ac6-5b7e-97c3-ef940944763d | note | Check Item - Check Item
d7a94bb4-2474-5254-9d01-0593d3b31a8c | note | Reference - Clause 6 MRTS50
8d54f583-52db-43c8-9938-9dcbe9b618b7 | checkpoint | 3 - Lot identification and traceability
6a1fc53a-2d6f-5fdd-8ff3-4bf95c8158b9 | note | ○ Works shall be divided into lots for adequate identification, monitoring, submission of works to the administrator, rejection of works and possible bonus provisions for each specific item.
77e5d28b-f789-5980-9ee5-690a6b104a59 | note | ○ Lots shall be chosen taking into account any restrictions included in the contract.
5e6fe86f-d3fc-53d0-a22c-b8412adbb2a6 | note | Acceptance Criteria & Frequency (Project Specific) - Check
4f1c703d-8bc0-5cdc-8369-cf5848f8c252 | note | Check Item - Check Item
fb8287a9-d162-5793-8c7c-72d9d47f6f48 | note | Reference - Clause 7.1 MRTS50
69083ad6-d98c-44e8-b79e-15f04ee00d51 | checkpoint | 4 - Inspection and Testing
0fc71f60-e362-5692-a214-5043209e7eaf | note | ○ Inspection and test procedures shall be included in an inspection and test plan and shall comply with clause 8.2 of MRTS 50 and to ensure compliance with the contract requirements.
4121331b-23cc-5e8a-af2e-4fc2447f701d | note | Acceptance Criteria & Frequency (Project Specific) - Check
e3ba419a-6ce2-5767-b712-5ee8964d0f21 | note | Check Item - Check Item
cb8ac5ac-3591-5faf-812c-0e2dd0791de3 | note | Reference - Clause 8.2 MRTS50
e532a9e3-4dbb-42a4-a46c-405f64998f78 | checkpoint | Final Verification
1c806b55-274f-5a79-bcad-f0aac6f11569 | note | Responsible Officer
5ce606a2-985f-55e9-a8d1-c06dc3c3cb72 | textbox | Print Name:
72b0743d-daf2-5edc-8448-0a922c80c32d | date | Date:
87077c81-24b8-5df6-ac1e-072770a01fae | note | Verifying Authority
bb1adbf5-636e-53fa-849d-2db4d55cddd8 | textbox | Print Name:
34745124-6605-5d35-9ea5-54d4a57ecc32 | date | Date:
8b10679c-25d9-441d-9ea8-7ca5cb5ed7b1 | signoff | Signature
9150a635-893c-486d-acf6-cbd51d9a9f7a | section | Final Sign Offs (to be completed at closure of Lot)
24da735c-1818-4528-9ca6-e59239daccb9 | checkpoint | Agreed Quantities
3f20bdab-3fbb-4f17-9317-d5235f73b219 | signoff | Agreed Quantities Sign Off
78cbce79-78d2-4241-a3f6-937c2a1268ce | checkpoint | Closure of Lot
088dec7b-6b68-4455-a651-d3b2de8dc293 | signoff | Closure of Lot Sign Off
898ac97e-4f13-4f76-ab90-efe85df4f648 | checklist | 33.00 - Signage Installation | itp | 33.00 - Signage Installation
c8f5aa08-ea09-458b-b343-14892fcfdac9 | section | Details
a79655cc-3301-4ef5-9826-c945d4cdb416 | checkpoint | 1 - Document Submission
5cd8c60c-b21d-5f9a-9c03-b100c5facc65 | note | ○ Has Doval’s Traffic and Safety Management Plan been submitted and approved for use by the Principal at least 14days before commencement of its implementation (as nominated in Clause 2 of Annexure MRTS02.1)
0aea147f-0bc5-5620-8dc8-47150ecd3b72 | note | Acceptance Criteria & Frequency (Project Specific) - Document Submission
9ee7bd1f-604a-5e72-9dc3-bdcf9ac243c1 | note | ○ Has Doval’s Traffic and Safety Management Plan been submitted and approved for use by the Principal at least 14days before commencement of its implementation (as nominated in Clause 2 of Annexure MRTS02.1)
b3be7ff7-18fd-59a8-8297-12e05d6b5444 | note | Check Item - Check Item
19bd3a10-ff5b-4925-9219-691dd80fb088 | checkpoint | 2 - Traffic and safety controls
1d9c8e2c-2190-5da8-8fc5-fb694db092ae | note | ○ Are safety controls are in place (eg. PPE, daily plant check)
a7b77693-fbfe-531c-89db-00902bf5d379 | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
2869659c-8ee3-568a-b115-4d5dedcc3ab3 | note | Check Item - Check Item
bdd7f71b-00cb-4e0c-aa04-204e6ac386b7 | checkpoint | 3 - Traffic Management Process
d2c4f75d-f29a-555b-97b7-64fb2b2b747a | note | ○ All traffic control signs, devices and measures in accordance to the TGS shall be applied in order to warn traffic in advance. Refer to Clause 2.2.4 of MUTCD Part 3
aa3a7a6c-d5ca-5579-ab96-5cfcd78d0336 | note | ○ TGS shall be prepared has been prepared by a suitability qualified and experienced persons and has been submitted to the Administrator for a direction as to its suitability at least 7days as per Clause 2 of Annexure MRTS02.1
bd2bbe63-73c9-5c2a-be6a-c6658ebb7695 | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
d811fb7d-a2ac-5a2c-b81b-1227c53a683b | note | Check Item - Check Item
4505c959-bfde-5d8b-800e-b7e496d6ee89 | note | Reference - TGS
743520b6-2f51-4cb6-a03d-424dfa46ceb9 | checkpoint | 4 - Risk Management
32525499-e51d-56b5-be41-877a59d71fdc | note | ○ The Risk Management shall foresee all safety risks likely to arise during works on road when preparing standardised plan, SWMS and the TGS
a6c72dea-eab4-5a51-b94d-0660c17a43ee | note | Acceptance Criteria & Frequency (Project Specific) - Check
9db10fbe-4bf6-58ed-a077-e3b1d3648f67 | note | Check Item - Check Item
80de430a-1a44-5d73-871a-1cc81b8df526 | note | Reference - Clause 2.2.3 MUTCD
96d0fe59-884c-49e1-9f6a-b3bb650dd207 | checkpoint | 5 - Temporary Footpaths and Pedestrian Crossings
29885fbe-7b7e-5681-8a46-6e688a1867d2 | note | ○ Where footpaths or pedestrian crossings have been partially closed or temporarily relocated, has provision been made for temporary access in accordance with Clause 2.3.8 of the MUTCD Part 3?
19efe961-a54e-5ffc-83b7-83b568a24149 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
2e6461b7-4ccf-582a-9e51-74e8409e6d68 | note | Check Item - Check Item
6cca98bf-ae6f-52c2-96f3-26716fdb7390 | note | Reference - Clause 2.3.8 MUTCD
82f8898d-00e8-4c0f-9057-9699f6f7492b | checkpoint | 6 - Traffic Management
8c52a8c6-8291-52f0-a043-ab8bab858f80 | note | Traffic Management will be developed in accordance with the TMP and satisfy the following Clauses:
09a54583-6a8b-55dd-83a0-d84bf731edd8 | note | — Safety & Convenience Clause 2.3.2
6faf5142-fb45-599e-99b9-7ffc07c4bc71 | note | — Traffic through the work area Clause 2.3.3
1b73fa4c-4a6b-5a3e-a2e0-78a38882a28f | note | — Traffic past the work area Clause 2.3.4
5f011d4c-4339-5380-92c6-bef68c7482c0 | note | — Traffic around the work area Clause 2.3.5
15baf332-ad8f-538c-9b3d-4a8d7cf944e8 | note | — Night Conditions Clause 2.3.6
eb8b2bc9-58d6-57ae-aa20-2ffd7e0105aa | note | — Provision for Pedestrian and Bicycles Clause 2.3.7
98d712c9-0bc3-56a1-a4ff-90a1924e5739 | note | — Temporary Footpath and Pedestrian
37b1b627-c1d9-5b4f-a2f2-274b6b138e06 | note | Acceptance Criteria & Frequency (Project Specific) - Check
0e07e00f-cc1a-5afa-9fe9-ea84719b9afe | note | Check Item - Check Item
52a19aac-d69a-57cb-812e-be947cd07234 | note | Reference - Clause 2.3 MUTCD
ef79e7d6-a3a3-4c0f-b3bd-a0a205d45371 | checkpoint | 7 - Delineation
b7308fa2-391b-57e9-bb3e-a95198929dca | note | ○ Appropriate delineation shall be established and illustrated which part of the roadway is available to road users or the path traffic is required to follow under all conditions. Long range or short range delineation shall be installed accordingly
8bf58f65-ef8e-5bb4-bc6f-53635bc4afd9 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
902d11b3-6dcd-5b54-ae32-2acdf7ff7329 | note | Check Item - Check Item
a0fc9522-dc00-5d36-8854-521304f604d4 | note | Reference - Clause 2.4.2 MUTCD
efbfd0e0-1054-469a-9d21-09883569af12 | checkpoint | 8 - Night Conditions
66e3bd22-b1a6-5c2e-9a3f-ac69c83b0741 | note | ○ Flashing Lamps may be used to draw attention to certain advance sign (Refer to Clause 3.11) Pavement marking through the work shall be retroflective. Delineating devices shall comprise or incorporate retroflectors. Barriers may require floodlighting to make them more conspicuous.
96556457-9ad8-59f2-bfab-496d59dc6236 | note | Acceptance Criteria & Frequency (Project Specific) - Check
7286b2e2-aa73-5fb4-8532-74d008226a9f | note | Check Item - Check Item
561c3c20-f320-5924-922d-2c9c4d727e8e | note | Reference - Clause 2.4.3 MUTCD
9552a1cd-5306-4bc1-993c-43d42d66cc21 | checkpoint | 9 - Safety Barriers
946e7948-b520-580c-bef1-1688072fc739 | note | Shall be installed in place where it is deemed to have:
f878b65c-4806-51ef-a9c3-ba5f043a931d | note | — Inadequate safety clearance between moving traffic and workers and plant on site
ffafeeef-0978-5bff-86ec-b72f11edca2d | note | — Hazardous traffic conflicts
e0219f21-f85b-551d-9174-08aaa16934c7 | note | — Collisions with hazardous fixed objects, construction works or falls into excavation closed to the travelled path.
b8aa5937-1ce7-5186-b4c5-53598d853c57 | note | — Inadequate separation of temporary footpath, shared path or bicycle paths
ff99f7a9-6a09-5f22-a063-6e97b9e4442d | note | Acceptance Criteria & Frequency (Project Specific) - Check
4cfc66b2-d854-5ae5-b98e-fbe36a551273 | note | Check Item - Check Item
d8392ab7-3ea2-57b0-a0d0-df5d6efb7d2a | note | Reference - Clause 2.4.5 MUTCD
bee9d655-4081-4e6a-8994-532b7c04885b | checkpoint | 10 - Vehicle Size and Load Restrictions
4e577f9e-1b77-5fe5-a366-75f10301741c | note | ○ Informed appropriate authority about alternating width, height or load carrying capacity of the roadway
9e33e4f2-6b4a-5566-a9d5-c2e9bb8c7bfe | note | Acceptance Criteria & Frequency (Project Specific) - Notify
5e8e00d1-5f2c-5fe3-9b18-98ee90462510 | note | Check Item - MILESTONE
d8a74e6e-8805-45b4-9dfc-7f344af6a70e | checkpoint | 11 - Condition of devices
c385a93a-ff9c-5c14-aa22-971095f2268d | note | Check that signs and devices are examined before installation to ensure that they are in good condition and their performance is not impaired. The following checks are required:
70980618-4482-581b-97e4-2c46a606134e | note | (a) Mechanical condition
8a3b71b2-b4e1-5587-bbaa-2e1fc3e2396c | note | (b) Cleanliness
2caa076d-caca-5368-be4b-4d988d740723 | note | (c) Colour of fluorescent signs
7878d8f3-0aca-5b54-a14f-eb0a9e84bac1 | note | (d) Night-time visibility
57f67da9-b49e-5178-bc39-b29794b93642 | note | ○ Functional inspections are also required, see Clause 2.5.5.
50a54ae3-a9d2-581a-a805-36dac1a8bd9b | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
663300ce-c9fb-5d6c-8eab-10d71edfef8c | note | Check Item - Check Item
8eb96572-b653-52d7-a3f5-29e6fd548c0b | note | Reference - Clause 2.5.1 MUTCD
64e36c59-6a76-4893-9237-80ac00291077 | checkpoint | 12 - Positioning of Devices
0cd66ed6-c7ed-52cd-b55c-f24053d8384b | note | Check that signs and devices should be positioned and erected so that-
83248c0b-fb40-5933-9e52-cb8f99b977ce | note | (a) they are properly displayed and securely mounted (see Clause 3.3);
7b1f5550-7353-5389-8100-7d44a90a5f5c | note | (b) they are within the line of sight of the intended road user;
22966193-2622-58e0-9a7d-e64291d2026e | note | (c) they cannot be obscured from view
31ba85bc-1424-5c3c-8e85-a936c8753bb2 | note | (d) they do not obscure other devices from the line of sight of the intended road user;
194e9073-c4d9-57e7-a87d-819213e9ffa0 | note | (e) they do not become a possible hazard to workers, pedestrians or vehicles
76e8509b-b81a-552e-bcd8-fe1de1266939 | note | (f) they do not deflect traffic into an undesirable path.
a64b3224-8ea0-5e23-882d-8eaac35829f7 | note | (g) they do not restrict sight distance for drivers entering from side roads or streets, or private driveways; and
398a6362-cf1a-5265-8adf-59dc2f9be4ec | note | (h) they are not installed using supports that could be a hazard if struck by a vehicle.
0a88495e-7ca6-5343-8dd4-f0d972fae09c | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f6bc1ab5-6c08-5436-9563-42db5d504bdc | note | Check Item - Check Item
5f0cddc9-c38c-573c-bb92-1b61e6208ddf | note | Reference - Clause 2.5.2 MUTCD
c631ee8a-a852-4c1a-b1f6-410f0180c9a3 | checkpoint | 13 - Positioning of Devices
3e6c064e-6c4c-5077-bb38-5dc5236272f6 | note | ○ On kerbed roads in built-up areas where signs are mounted on posts adjacent to a footpath, or where vehicle parking may occur, they should be erected a minimum of 2.2 m above the level of the kerb or footpath to the underside of the sign, to reduce interference from parked vehicles.
2d98120b-b482-506a-baf0-796abb57db9f | note | ○ Where neither pedestrians nor parked vehicles have to be considered, e.g. on a traffic island or median, a mounting height of 1.5 m may be more appropriate.
9191d174-e932-5576-9aff-7fb4e393d373 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b1a228c9-23fc-5ee2-a4bb-67c74dfcec99 | note | Check Item - Check Item
6e9c26ed-4b7f-5c26-a930-afcfe90dddbf | note | Reference - Clause 2.5.2 MUTCD
40fa86f4-bde9-4033-9a5f-a0d2c9a47c86 | checkpoint | 14 - Setting out and recovery of devices
3d6728ca-5c79-5b39-a9be-28941be23036 | note | Check that before work commences devices at the approaches to and within the work area should be set out in accordance with the traffic guidance scheme in the following sequence:
f68cc816-4400-5251-9b20-2859c2322e98 | note | (a) Advance warning and regulatory signs.
25f27aba-ceef-5b22-ac2e-3de113cff0e5 | note | (b) All intermediate advance warning and regulatory signs and devices required in advance of the taper or start of the work area.
620dbbd2-7bbf-536c-a2d3-ed8dbc84b7ad | note | (c) All delineating devices required to form the taper including the illuminated flashing arrow sign at the end of the taper where required.
e16ded0e-1d4c-51e4-8d53-dce7f482cae2 | note | (d) Delineation of the work area or side track.
9e123ef4-8474-50a8-9235-25d4ac814790 | note | (e) All other required warning and regulatory signs including termination and end of temporary speed zone signs. This operation
d032e438-771e-5dd8-ba9a-3a3bdae72859 | note | Acceptance Criteria & Frequency (Project Specific) - Check
4da3a68e-e09f-5863-846d-995a4f1fc521 | note | Check Item - Check Item
5a6f4e2d-def5-5a8d-91c3-77548cc3ea2e | note | Reference - Clause 2.5.3 MUTCD
9d63d85f-d2f8-4d73-80d5-6c91c2763aa1 | checkpoint | 15 - Orientation of sign
22c341bc-8a8f-5e70-a334-ccebed4bc8aa | note | ○ Sign should face towards approaching traffic approximately at right angles to the line of sight from the driver to the sign.
fd799e0f-6294-5bd1-8d00-d573dd7fb709 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f4f21e19-f62a-5370-b69e-9f17546106cb | note | Check Item - Check Item
cf347fa7-b266-5494-b813-ef4a70a26f13 | note | Reference - Clause 2.5.4 MUTCD
38b7349f-e36f-4a6b-b0f8-6e2670ca298d | checkpoint | 16 - Inspection
3c4f19cd-dbe2-5d80-9f7d-5b9d0a468b2d | note | ○ Inspection of signs and devices shall be carried out before and after opening traffic. This inspection should be carried out along the travelled path, and past all of the signs and devices. Night inspection is to be undertaken similarly with headlights on low beam. If arrangement is confusing or unsatisfactory it shall be adjusted and reinspected.
7606f2df-4ab9-565b-b117-e783a86cc05f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
67e2ecbf-6d58-5340-ae44-a7d98df0d043 | note | Check Item - Check Item
9fc70811-ffb7-5c8a-9da8-b0ad13c68af6 | note | Reference - Clause 2.5.5 MUTCD
7f0aeea4-2a91-4949-b7f5-ebc7f5274311 | checkpoint | 17 - Publicity
d49058c3-3f61-5622-8107-0519efc546fe | note | ○ May be necessary to erect special signs to inform the public of the traffic guidance scheme depending on the complexity of the traffic guidance scheme.
551763d7-b722-5208-b8fc-d81311962a17 | note | Acceptance Criteria & Frequency (Project Specific) - Check
a1f70278-5762-5616-a3f7-bb9a60d1f52b | note | Check Item - Check Item
f0a65a19-be4a-5a80-b37c-476d143f46fb | note | Reference - Clause 2.5.6 MUTCD
a6e0d63d-b30f-4b6f-866b-1f7b9ead863a | checkpoint | 18 - Removal
db43cb46-cee8-5b50-86a0-b53911158912 | note | ○ Relevant signs and devices are to be removed or concealed as soon the activity has been completed or a hazard ceases to exist. When all work is complete, sign and devices should be dismantled in reverse order to Clause 2.5.3
0095f5fc-05c1-501d-be28-fc4cc2074b58 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
7f2309cc-2228-5429-a935-3a689e559661 | note | Check Item - Check Item
e79acb25-1909-5a3e-a445-4791ca8820aa | note | Reference - Clause 2.5.7 MUTCD
4710b744-c27b-466e-93ea-cb202f8c681f | checkpoint | 19 - Operation
004d4628-6b00-5a44-8d17-138f602f9b89 | note | Appropriate measures shall be implemented throughout operations of the project, this will include:
2c723301-d6e3-5a2c-ba38-faf7982a5b6e | note | — Daily routine and worksite records
b6174ccd-b6ce-5ca2-8b28-51acda2bbcc4 | note | — High visibility clothing
f00376d7-1183-56f4-a31b-be61e1063a71 | note | — Closure & Delays
735ce8b6-2582-5c15-93bd-fc957dea41c4 | note | — Safety audits
394d9d0b-a33d-5dfd-95a7-3b87d7352022 | note | — Device maintenance
15f13206-9fa1-5ed9-91f4-71d6719e4fcd | note | — Layout variation
8c455c44-f45a-5571-834d-c924701d2759 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
7a2e2b87-83af-5a8f-8ba0-eba56c8d892f | note | Check Item - Check Item
fb739fa2-6f2f-51d6-a4c5-d490ba63af29 | note | Reference - Clause 2.6 MUTCD
9c61b701-4a66-4f72-9908-feca3afc6357 | checkpoint | 20 - Emergency and Unplanned Works
04782580-c3a0-57a9-8f5c-05bedcc18615 | note | ○ In an event of an emergency, procedures for the safe control of traffic and the safety of road authority shall be in accordance of Appendix H. FIGURE H1 illustrates different scenarios to manage traffic throughout an incident.
65afe5af-5a77-5584-9841-fb83bab8719b | note | Acceptance Criteria & Frequency (Project Specific) - Check
b274b739-ff20-5807-afae-74f798ad2088 | note | Check Item - Check Item
6f0e4bfa-ac39-5b62-b647-081b0df1e3cc | note | Reference - Clause 2.7 MUTCD
930c553d-4066-4572-8f8d-5ee158353099 | checkpoint | Final Verification
95f50efd-bd83-53a9-9705-6d233a935a38 | note | Responsible Officer
20a2441e-1750-521d-85a7-7abbbed1010e | textbox | Print Name:
ca628cee-d162-5aad-9071-dacdfa8804ec | date | Date:
ae13b796-4b62-5430-ae93-83107ee7630e | note | Verifying Authority
e5fce47d-ffe1-5841-a380-0608767b3643 | textbox | Print Name:
72aaa6f6-54a2-516a-abb3-04c0989afa18 | date | Date:
543426fe-00cb-4b23-b7ef-39a17c839357 | signoff | Signature
4ec000ad-9295-4310-80db-4fa270dfa774 | section | Final Sign Offs (to be completed at closure of Lot)
61f392e5-6f6d-4a33-8661-841e33fb1033 | checkpoint | Agreed Quantities
db93872a-5286-422e-857d-22ef8a3537f4 | signoff | Agreed Quantities Sign Off
7a4a372b-fcc2-4c89-a04a-871b5c5ec2d3 | checkpoint | Closure of Lot
7820fc11-e514-4254-8842-ba72ed2e1584 | signoff | Closure of Lot Sign Off
cd3637e1-68d2-4c2d-a19d-067b06b7d455 | checklist | 35.00 - Cast-in-Place Piles | itp | 35.00 - Cast-in-Place Piles
a5226773-ce9b-42c9-b933-d146e6c4fa87 | section | Details
b5bdd1c8-9bd1-42c9-9f95-36771ff8eb42 | checkpoint | 1 - Document Submission
f527045d-9716-5a60-b275-d3b244286f52 | note | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
93bf7dea-f37b-533e-b6f6-ccc39e641bc9 | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
2264f8ec-6795-5ebb-a7e4-34b67ef26547 | note | Check Item - Check Item
0a96c877-861d-4bf6-9c89-ad4928c8b10f | checkpoint | 2 - Traffic and Safety Controls
6f224f59-c182-5c21-b649-7ee513f63b80 | note | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
a28ed8fa-6e51-5299-baf3-0eef67062455 | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
27c87ebf-7d88-50e2-bddc-a705dcc1e1cf | note | Check Item - Check Item
dafb778e-a3ae-4ef1-8a04-6d0fc2199bed | checkpoint | 3 - Construction Procedures
feeec324-dd89-5ef4-952c-705e2e33543e | note | ○ At least 28 days prior to the date for sinking of pile shafts a detailed construction procedure has been submitted to the Administrator for review.
5904ae69-b8e9-5a3e-9584-4492ad2bcc78 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
a0cb2515-d5e1-5d3c-852d-6fe51cbac6bd | note | Check Item - MILESTONE
bb566c6f-d038-55d3-92c3-5ad4410bb0c9 | note | Reference - Clause 6.2 & 7 MRTS63
abafd4a5-9512-470c-abc7-ad271248efbd | checkpoint | 4 - Construction Procedures
134ad26f-b669-5e7b-83e4-d98a2e3bfdab | note | ○ Approval of procedure for construction, excavation, inspection, certification and concreting of piles.
53b00e11-e57d-5492-b081-91e46097f93c | note | Acceptance Criteria & Frequency (Project Specific) - Approval
1feb547e-2e41-562a-8278-0818937c0fb1 | note | Check Item - HOLD POINT 1
5a162894-ed41-540d-a510-c1144888f29a | note | Reference - Clause 6.2 MRTS63
24cf2b8f-ce7a-48e3-8306-b7b09dff3fb7 | signoff | HOLD POINT
b2a273fc-8cd7-40de-82e2-de23e1dcff72 | checkpoint | 5 - Fabrication of liners
47249bb5-05cb-56ed-8626-e1b4b33730bc | note | ○ Welding shall be carried out in accordance with the provisions of AS/NZS 1554.1. A Weld Procedure Sheet shall be submitted to the Administrator for approval prior to welding liners.
29d713f8-d9fc-5b4f-a341-8ed0e00d0e6c | note | Acceptance Criteria & Frequency (Project Specific) - Approval
6db815a0-dd84-51c3-a7da-3cc79e591a9e | note | Check Item - HOLD POINT 2
be448606-b6e4-559e-ad5c-7b1476341e11 | note | Reference - Clause 7 MRTS63
8664efb0-ba44-4c5e-b41b-773630781f7e | signoff | HOLD POINT
be3cef03-4e52-420f-9bfa-30cd4b3f487e | checkpoint | 6 - Liners driven fom top
23658857-3f61-544a-92dd-b3d25213722b | note | ○ Liners shall be driven (hammered, oscillated or rotated), open-ended using a driving rig capable of achieving penetration of the liner to the founding level.
484f8f51-8b2b-57d7-9b12-209a679c069a | note | Acceptance Criteria & Frequency (Project Specific) - Check
42f86b14-8d15-52b7-ba56-913180ce9cd6 | note | Check Item - Check Item
a10604a4-8bbe-56a7-b781-85c7af9ed5bd | note | Reference - Clause 8.2 MRTS63
ff8b7bd5-fbb7-40b4-86bb-c430eec61e70 | checkpoint | 7 - Construction Limitation
1128c588-3af6-528f-8919-b5c04b74def4 | note | ○ A pile which is located within 2.5 m clear distance from a newly concreted pile shall not be bored or driven until 18 hours after completion of concreting in the adjacent pile. A pile which is located between 2.5 m and 9 m clear distance from a newly concreted pile shall not be driven in the period between initial set and 12 hours after casting is completed.
572dda6f-c97e-5010-81f8-43eb345d5709 | note | ○ The top of a newly concreted pile shall not be in contact with the driving platform while another pile is being prebored or driven from that platform.
d89cf5bc-0767-524c-ba1b-faeac91cf4ad | note | Acceptance Criteria & Frequency (Project Specific) - Check
bb295d26-5e2c-5eb0-bef6-ca744c2fc3d8 | note | Check Item - Check Item
2ebe042b-df35-56d5-907e-099d7d0b271f | note | Reference - Clause 8.5 MRTS63
a45b5fba-62b4-48d3-a4ed-e3d50d836f75 | checkpoint | 8 - Tolerances
d339ce0f-9f84-5b72-9e97-28ac2fc8cf86 | note | The completed pile shall be located as shown on the Standard Drawings within the following tolerances:
de1f57dd-3687-5ea4-9656-2c902d0878d5 | note | a) Top of pile, in plan 75 mm in any direction
d73b566f-e5d9-5b3f-95ab-2e13f3e2c01d | note | b) Top of pile, vertically 5 mm in height
c55c8f91-511c-55b0-a2cc-073c70810f81 | note | c) Variation from vertical or designated rake 20 mm per metre
a241bbc7-b62f-5b1f-afa8-ee88433869ae | note | d) Bow of pile 1% of length of pile in any direction, and
a973f5e6-0abe-53d8-949d-118f4d9c41e3 | note | e) Diameter of liner and socket - 0, + 5% of nominal diameter at any position.
e07410a1-c12e-59a3-b997-a963ec1732f9 | note | Acceptance Criteria & Frequency (Project Specific) - Check
6fd4f981-def9-58a5-a697-bf256338ea47 | note | Check Item - Check Item
42db62d9-66a3-5050-92d3-6544d8d1cd4d | note | Reference - Clause 9 MRTS63
a22e076b-b1c1-45bd-bf1e-c90602b9f5d1 | checkpoint | 9 - Excavation of cast-in-place piles
55241857-2162-56ea-aa1f-87c0d7c365d6 | note | ○ When a pile is to terminate above the design level, the concurrence for this change must be obtained from the Designer, it is not just a geotechnical decision.
529d0e6b-e9fe-5644-8bc4-44d574d5eec4 | note | Acceptance Criteria & Frequency (Project Specific) - Check
e73b5b16-1e10-5eaf-b7d1-3684736585d4 | note | Check Item - Check Item
f75adb3c-16a0-569e-8085-f814390c104c | note | Reference - Clause 10.1 MRTS63
a9e3fe4a-a3fb-451f-abb1-f19a129196c0 | checkpoint | 10 - Excavation of cast-in-place piles
4d418ae2-4b5f-5118-b01c-e93c29ddb877 | note | ○ Temporary safety shields shall be used where manual work is carried out in unlined holes and sockets as required by the Workplace Health and Safety Act.
db4bfa94-6b27-51fb-a3b3-4cbe67809ead | note | Acceptance Criteria & Frequency (Project Specific) - Check
7eba1d21-0678-54f0-8803-f9fd32f6ea92 | note | Check Item - Check Item
1c2066a2-13f7-5d09-b9c9-9d3645cfe26d | note | Reference - Clause 10.1 MRTS71
288e7b98-0302-4baa-8094-c227b85b9f3d | checkpoint | 11 - Pile Sockets
7ae73556-7811-59a5-b5a3-aef3f77fbf57 | note | ○ The walls shall be clean and free of smeared material. Smeared walls shall be cleaned and roughened prior to certification and subsequent concreting.
bb4b66bf-d621-5a0b-9558-31d80f98e478 | note | Acceptance Criteria & Frequency (Project Specific) - Check
3b9dfcf7-aca8-57f7-aadf-b1c56d6391e1 | note | Check Item - Check Item
5f953b37-4c4f-5e20-b210-2b38199c697c | note | Reference - Clause 10.3 MRTS63
4420d146-969e-4a02-89ce-bb339bbe8d60 | checkpoint | 12 - Geotechnical Certification
dd47a663-2a87-5db4-ab93-1e11d23d52a1 | note | ○ The Contractor shall forward a copy of the geotechnical certification of the foundation to the Administrator prior to concreting. Insertion of reinforcement and concreting of the pile shall not proceed prior to the Administrator's approval.
394fb7e9-d689-57d0-a47d-f8ec336c8237 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
956123b3-99c2-5f6e-9aa4-f19b88400907 | note | Check Item - HOLD POINT 3
5fbab347-0125-5392-94a3-9ff7867df728 | note | Reference - Clause 11.1 MRTS63
4439c599-5cd7-4021-891b-1342c30b22eb | signoff | HOLD POINT
f35c69c9-3408-4e7e-89a1-e3aa2f3646d3 | checkpoint | 13 - Steel Reinforcing
94e0a74b-4442-55fb-90ac-5f2d9cade0f6 | note | ○ Steel reinforcing shall be supplied and placed in accordance with the requirements of MRTS71 Reinforcing Steel and MRTS71A Stainless Steel Reinforcing. Steel reinforcing shall be assembled as detailed on the Standard Drawings to form a rigid cage capable of being lowered into the excavation without any disintegration occurring.
a00c4caa-b812-55fd-be8c-fb1f38b51e92 | note | Acceptance Criteria & Frequency (Project Specific) - Check
d5024538-0931-59d0-8de5-2600e2b8809b | note | Check Item - Check Item
38b29b2a-afcc-5359-8c89-5e6191ee5444 | note | Reference - See Steel Reinforcing ITP
52475380-ef78-4000-b200-0c4508c87278 | checkpoint | 14 - Inspection For inspection purposes, supply of a suitable camera for inspection.
7a1a6471-a1c8-582a-8d40-c5d778f6ad2c | note | Acceptance Criteria & Frequency (Project Specific) - Approval
e9f1520e-e770-5d8c-b274-82fc7896ec01 | note | Check Item - MILESTONE
8dc7ec7d-7ba3-5357-8985-ce324d19e601 | note | Reference - Clause 11.9.3
90e2d856-7d9e-4a68-933d-464db195e6c1 | checkpoint | 15 - Concreting
8fc3b7f3-1aa8-5ecc-ae54-1e5ede11f1f3 | note | ○ All concrete shall be placed in accordance with MRTS70 Concrete except as otherwise specified in Clauses 13.2 to 13.4. The Contractor shall observe all relevant Milestones and Hold Points in MRTS70 Concrete.
727daab7-4b1f-5ba9-aad8-3ea0258eb967 | note | Acceptance Criteria & Frequency (Project Specific) - Check
c1e0b991-a600-5177-829f-e9818814acf8 | note | Check Item - Check Item
1ac2b470-69c1-55c6-a642-f09869b1f62c | note | Reference - See Concreting ITP
0fd3ec5b-53ff-4c3e-85c1-e3090a1013dd | checkpoint | 16 - Concreting
7a95873e-33b5-51d3-9f34-38c4627c86c4 | note | ○ Where there has been a delay of more than 24 hours between certification and when the Contractor is ready to start concreting or when the foundation has been observed to deteriorate significantly, the foundation shall be re-cleaned (if required) and re-certified.
b92b98f7-00a4-5414-92fa-a133d02f4c60 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
271ee039-ce18-549e-927e-bedad60b2674 | note | Check Item - HOLD POINT 4
8d53bd2a-c339-5a7c-9e4a-38d980ace8b7 | note | Reference - Clause 13.1 MRTS63
b3a90290-abc8-4969-9807-1676673e4709 | signoff | HOLD POINT
ccaec426-f1cd-4928-80bb-d6872b420634 | checkpoint | 17 - Concreting
b655a6cd-510d-5fe4-b265-7c570597e80b | note | ○ All concrete shall be placed in accordance with MRTS70 Concrete except as otherwise specified in Clauses 13.2 to 13.4. The Contractor shall observe all relevant milestones and hold points in MRTS70 Concrete. Placement of concrete underwater shall only commence after the tremie and the placing procedure have been accepted for use by the Administrator.
846f5e7a-f0d5-5392-ae59-b72a32f33177 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
d7cb74e0-03f1-553c-bdef-55327fbfcd06 | note | Check Item - HOLD POINT 5
e17d9452-86bc-5e9a-b739-88c0a814db31 | note | Reference - Clause 13.1 MRTS63
b5c0fb7c-caba-4f00-b187-132a6b9a847d | signoff | HOLD POINT
dd495d8b-f03a-4b58-891f-7c7cc2e68d8f | checkpoint | 18 - Concreting
224c5fc4-d9f9-536a-8de7-31a05865c0ac | note | The target slump of concrete shall be selected from the range below:
6f574771-0d87-5e12-befc-aa59a1e3c75c | note | a) for concrete placed in dry conditions 150 mm to 180 mm
5750925a-2426-56d1-ba9a-1e6aac4f790e | note | b) for concrete placed by tremie underwater 180 mm
c24e017b-a70e-5029-a328-031667811998 | note | ○ Slump tests on delivery shall conform to the target slump and the tolerances given in AS 1379.
ebba77cf-976e-510a-8210-113d8c5b39c2 | note | Acceptance Criteria & Frequency (Project Specific) - Check
54f9bdd4-1e29-5ba9-9cee-69369f53790b | note | Check Item - Check Item
1f91c3f6-2198-5b11-beb6-728aedca2713 | note | Reference - Clause 13.3 MRTS63
2d62773c-df89-4913-9280-68ef797f988d | checkpoint | 19 - Concreting
17a7368d-ac3f-5751-b5b1-90f6f8f277d7 | note | ○ Prior to commencement of concreting the length of the pile from the base to the top of the liner shall be measured and the socket walls and pile base checked for cleanliness.
39cff14b-cc41-5b63-a953-794a73bab16b | note | Acceptance Criteria & Frequency (Project Specific) - Check
1b9e41c8-1434-5bec-bf21-0d8e413be2dc | note | Check Item - Check Item
c815badc-ea3a-5c94-aba3-92947c84998f | note | Reference - Clause 13.4.1 MRTS63
e374dd7c-ef48-4530-b6f7-31f927ca1ae2 | checkpoint | 20 - Concreting
103cece2-2b5e-5ad1-ac66-ad34fef331c3 | note | ○ To assist compaction by hydraulic head, the rate of placing the concrete shall not be less than 10 metres of pile length per hour.
c556d3b3-5a2e-52f2-bd01-8d1c2669a348 | note | ○ Concrete supply shall be effectively continuous with delays between concrete delivery trucks of 15 minutes or less, unless an approved specific retarded mix design has been developed to allow for longer delays, as in remote areas.
672a9851-0751-558c-9ab3-02aceb0f10ad | note | Acceptance Criteria & Frequency (Project Specific) - Check
71961d5a-97c6-5a25-8d59-f927bf1cdc78 | note | Check Item - Check Item
893cd15c-a9a3-5c53-aef3-8d5286c3c269 | note | Reference - Clause 13.4.1 MRTS63
19cc6030-478e-4819-a836-c75f9d04e2e9 | checkpoint | 21 - Concreting
2be1d0ca-f0fb-586b-85c9-3897eeb7f9fc | note | ○ The base of the pile shall be clean and all water removed immediately prior to placing concrete. This shall be confirmed by direct observation or by using a camera. The method of placement shall allow the following:
109b8d17-646f-51d6-8543-5f539e27d810 | note | a) delivery hose or pipe to 2 m above the pile base, and
03506adb-1b4d-5ee4-8a99-438e032ff00b | note | b) ability to lift and/or shorten the delivery hose / pipe quickly with delays no longer than 10 minutes.
69b9ac36-acce-5e82-ab46-1c237ba365a4 | note | ○ Concrete shall be dropped 2 to 3 m from the end of the delivery hose / pipe onto the concrete surface to provide compaction or shall be compacted using vibration. The delivery hose / pipe shall be positioned so that the concrete does not fall onto the reinforcement cage. For raked piles, the Contractor shall detail in the procedure for construction of piles the method of delivering concrete down the piles that minimises the risk of segregation. [Refer to Hold Point 1] The top 3 m of concrete shall be well compacted with a concrete vibrator with a minimum diameter of 50 mm.
cd8c5c62-b729-510f-821d-da0e9c9e6278 | note | Acceptance Criteria & Frequency (Project Specific) - Check
2143eb48-fd16-5462-baca-8af92ba476d2 | note | Check Item - Check Item
19c59ac5-9dc2-5273-80d3-5b2eb0d7f478 | note | Reference - Clause 13.4.2 MRTS63
700cee60-c8cc-4b93-8ec0-43073ec3fe6c | checkpoint | Final Verification
e3e603e0-60cb-54ef-83c0-2def8d9defa3 | note | Doval Representative
ff1f60f4-00ce-5070-9d6b-42415fe95ec6 | textbox | Print Name:
4ed01e34-b81b-58f2-b599-c3d4d6a61199 | date | Date:
06c66fe6-2f07-50a2-9140-fd0a61338703 | note | Administrator
522d63a3-7555-51dd-a348-18070eb08255 | textbox | Print Name:
c640ab89-18a4-5318-bce8-d419cdc51431 | date | Date:
b9c7ed72-cb6a-4a09-ab75-abf4159d4c9b | signoff | Signature
304f9e06-f74b-4143-99cc-0a738de6ef0a | section | Final Sign Offs (to be completed at closure of Lot)
9b1772e5-49f4-4c18-8675-031e938da7c7 | checkpoint | Agreed Quantities
db0ec70e-0fb4-4e23-aa86-47196a987b99 | signoff | Agreed Quantities Sign Off
431c004a-0f9d-4409-a75a-52f962e9c383 | checkpoint | Closure of Lot
6ae2605e-a9d7-4a6f-8c88-c0b39083defe | signoff | Closure of Lot Sign Off
793a242a-3d74-4e7f-8bff-43bc16c8834b | checklist | 36.00 - MRTS92 Traffic Signal and Road Lighting Footings | itp | 36.00 - MRTS92 Traffic Signal and Road Lighting Footings
27cfe624-22aa-4caa-bf2a-1a60c0ab8e28 | section | Pre-Construction
6f7561d9-882e-4d29-b773-38bbeeab76c5 | checkpoint | 1.1 - Construction procedure submitted to the Client.
f7ad80a3-4b11-5ef6-ad60-e52751713108 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f9cf970d-ef60-5966-bfbf-3c3bcf5e74d2 | note | Check Item - Check Item
14fd280e-9633-5b1f-8d86-e4d7decb1ea1 | note | Reference - MRTS91 Cl.5.2
c3717430-d608-4710-8804-8c72adf7ae90 | checkpoint | 1.2 - Asbestos presence assessment
6ef117c2-d142-5a4a-aa4d-d377d7bae137 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
1ce578be-1d92-5dbf-a793-a8735accdd98 | note | Check Item - Check Item
08cf10af-d6c1-5076-bee8-33a645dde92f | note | Reference - MRTS91 Cl 6.1
23f60d31-8488-4aa3-ab4b-3f252d6be664 | checkpoint | 1.3 - Material certifications submitted to the Client.
8984a6eb-db5d-5a0d-90e8-84dd0bfdc063 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
8154c07c-3c69-5f23-9c71-7bf914705060 | note | Check Item - Check Item
dfa5ee1f-6edc-5f7c-935a-9ea55ab28d10 | note | Reference - MRTS91 Cl.7.1
4195346a-f6d3-4431-8870-3608a73d89a4 | checkpoint | 1.4 - Drawing versions correct.
23e6e9f5-8224-50cd-9e4c-da8e686e886a | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
eb4ec47b-dde3-54e3-a591-7c76c5d6a9aa | note | Check Item - Check Item
ffd7b635-e966-56f6-bc8f-2235bb15cd09 | note | Reference - IFC
b116bd97-d3e9-4a99-87e1-0031673f8c43 | checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
469b64b5-aaf8-5d97-bcf4-932bf5d2da08 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
8bf24a5f-a4f5-58a0-beaa-5f8832a11cd2 | note | Check Item - Check Item
d0463360-1877-55e6-a7cf-3227f6977ab9 | note | Reference - WCS34
a1abc3fd-2b2f-4017-9834-a879bd72f320 | checkpoint | 1.6 - Form 15 for footing design completed
bea908be-4b67-5dd7-9e92-52920fc32e61 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
cc6773aa-b6d4-5637-bcb8-c3a7ee2f7691 | note | Check Item - Check Item
61c193f7-f65c-52ef-b747-ad35b059f9b5 | note | Reference - Clause 2.4.2 MUTCD
088fdaef-5865-4ba7-b804-33beb123ccbb | checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
78ee04d0-b240-59b8-9eda-ad7802733b00 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
5ce94ecf-05c4-54fa-abf9-c8b533620b44 | note | Check Item - Hold Point
a4c1a83d-0cce-54fb-9517-772ba4e65d7f | note | Reference - Clause 2.4.3 MUTCD
d9cd2e43-e244-4a6e-bf02-24486206735a | signoff | HOLD POINT
4f9ffd5f-76ee-4023-830a-6bac4179ceba | section | Conduit Installation
69a281b4-25c2-4289-ad3a-4df9eef83ed3 | checkpoint | 2.1 - Bottom of trench compacted to form a firm uniform surface free from loose material.
04f78d54-ce8a-50d7-93f0-24bbedf18e56 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
5d71695a-17ab-5a53-89ac-e4d7844a7114 | note | Check Item - Witness Point
c08a3ae0-b5b1-50fe-a48c-d440f838ce3f | note | Reference - MRTS91 Cl.9.1
ec75b041-a57a-44ad-ae1d-4fb4ddd98410 | checkpoint | 2.2 - Boring/Jacking Contractor and equipment approved by the SI and works are carried out by experienced operators.
339ce04e-6d32-5501-92d9-ba825aa9455d | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
5e05694e-7c2c-5940-8616-c24527c9236a | note | Check Item - Hold Point
00399d99-073e-5dbf-8c98-9b7ab7c1d7b4 | note | Reference - MRTS91 Cl.8.7
ed0f1597-f0ec-4660-8272-0812e1bba5fc | signoff | HOLD POINT
8c40aae2-3b32-4506-868d-15317f433cee | checkpoint | 2.3 - Conduit installation approved by Superintendent and conduit will properly drain, contains no blockages and is not lower than pits that they are connected to.
6a8098ba-0576-538d-a0f8-b37a6cbdf45e | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d171b5dd-0a51-59ae-906a-fb67d4525870 | note | Check Item - Check Item
ba7c8800-8356-5635-bd1b-aa59bdaa57ff | note | Reference - MRTS91 Cl.9.1
a737c548-5473-46c4-9a65-510a8c45192c | checkpoint | 2.4 - Conduits in roadway backfill:
fcb02d2b-8e1e-58a2-889b-0287d767687d | note | ○ TMR/GCCC/Energex - lean mix BCC – Unbound Pavement or Lean Mix to match existing permeability
749b0880-e1c5-50b1-aaf8-1983766ca65d | note | ○ Passing Test Result: TMR - 95% RDD
da80f8c1-af37-54c7-b0b6-6fa72d493de2 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
c3139444-bd71-56c8-a6d0-a5bb6f2adbd8 | note | Check Item - Check Item
c224a9b9-7e2b-52f5-bd03-86483b8fcac1 | note | Reference - MRTS91 Cl.13.2
84ddc954-8db5-4d6d-b1ab-fe503372d0c8 | checkpoint | 2.5 - Conduits in footpath backfilled with insitu material, else MRS11.05 Type 2 material where insitu cannot be compacted.
7c002d63-a7aa-5ad4-8f49-76e95390d80e | note | ○ Passing Test Result: TMR - 90% RDD
367dbad9-b9a5-5eec-8476-e47babb90240 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
30ade3e9-6a4a-52f0-ae61-25f8221125bc | note | Check Item - Check Item
acc076c7-a4d0-565e-aff1-2c4364f35b4d | note | Reference - MRTS91 Cl.13.2
2766be1b-7aa9-4ece-b539-f26eb6bea084 | checkpoint | 2.6 - Conduit and conduit fittings proved by drawing a mandrel of following size:
121eda63-2bbc-5a82-8102-a0f9ee77387c | note | ○ TMR – 95% of ID and 95% of ID in length
b446e955-cea6-5bf8-aefd-e14c67dc2477 | note | ○ Energex:- 6mm less than ID and 100mm in length
f9774da3-9acf-5c83-9994-6d1e6360c919 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
17b24d01-0dc9-534e-bee5-d892355f8ac0 | note | Check Item - Hold Point
95136d5c-e81e-5421-9802-c5ab5c128835 | note | Reference - MRTS91 Cl 9.1
cdcaf171-9416-4c34-b625-89394bb09bef | signoff | HOLD POINT
4bf49605-705d-42e3-95a6-094546ec85e7 | checkpoint | 2.7 - Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
e8858f42-cf5f-579f-9cd8-e1e68a978250 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
3f76dd05-a710-5cc5-ad37-a1c6321f969f | note | Check Item - Witness Point
79666611-614d-5ea3-a15d-fd2c233aa80c | note | Reference - MRTS91 Cl 9.13
3d5ad1e5-706f-4d90-bf97-df9c9aecd81c | checkpoint | 2.8 - Vermin proofing of conduits with unspecified sealing system.
9263484b-8599-5879-9aee-2eb6a060de94 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f368561b-fb8c-50f9-9fdd-640dcacd3e6a | note | Check Item - Check Item
d18d93c8-9fa4-5bd1-881d-06b89e99c88b | note | Reference - MRTS91 Cl 10.9
0180cf35-12f1-4f8f-b4c8-46ac5d209567 | section | Pit Installation
651d41dc-7d98-4213-b538-1a9da88a5246 | checkpoint | 3.1 - Soil under pit compacted to 95% RDD
55542baf-6c22-59ab-89ee-d2c53ded76b6 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
72d1d2f2-4c3b-5ab2-bc4b-fbd8980c8f6d | note | Check Item - Witness Point
71c1df1b-0e85-570f-b524-a4ab5a262487 | note | Reference - MRTS91 Cl.10.4
fa894375-0874-472c-a70d-44b9a45c01ec | checkpoint | 3.2 - Compact bedding material to density index 60.
9e44e73c-2ba9-5135-bb5c-5b8d60846099 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
2fe6427e-f67c-55c1-b777-c2828c633281 | note | Check Item - Check Item
0c70241d-bfcc-5281-ac63-514f0fac910b | note | Reference - MRTS91 Cl.10.4
74c3eb56-4267-4a91-9939-39a92776cc81 | checkpoint | 3.3 - Lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level
8f642f57-5d8e-545a-a6f7-57d4d757bc07 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
baec7a8f-29ab-5b71-9177-6e4693ff989f | note | Check Item - Witness Point
caa4f26e-3b91-55fb-ac4d-5996cdbefa73 | note | Reference - MRTS91 Cl.10.10
c6495ea3-9d7f-497e-baf0-bcea79f9fa9c | section | Footing and slab Installation
35478b6c-3f36-419e-bed6-f4eb99ff5175 | checkpoint | 4.1 - Depth, base and sidewalls of footing’s and slab’s confirmed for each location
97081973-d935-54b1-a50b-e33c7519a587 | note | Acceptance Criteria & Frequency (Project Specific) - Verify & Hold Point
cc53ee20-e10d-55a8-9510-d4a2db83a1c6 | note | Check Item - Hold Point
0576b2db-5215-457f-8cd4-7aa50e3cc3b7 | signoff | HOLD POINT
fcd7a771-eb84-47e0-9704-1bdbf9da6992 | checkpoint | 4.2 - Ragbolt/reinforcement assembly inspected prior to concrete pour.
02c98a23-f3e3-5bd8-be7b-fce07dd856d5 | note | ○ Concrete poured in accordance with MRTS70.
654dcaf7-a3ad-5733-bbd6-5406df435b4a | note | ○ Concrete inspected to ensure correct vibration, monitor placing time and check that material is placed to avoid segregation. Check surface finish.
a699c88a-7383-50aa-9525-46aa2b142008 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
1a865cf2-2fd1-5f96-97a0-674620aa6cf9 | note | Check Item - Check Item
41f193d8-357d-553f-af1b-7281b41892a3 | note | Reference - MRTS92 Cl.8.3.7, MRTS70
c5db398b-45ca-4de9-925c-33842ad5ec25 | checkpoint | 4.3 - Concrete tested for slump and compressive strength by NATA laboratory
6555a7ae-bd59-5655-98ee-0820999dee6b | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
68b64015-54a7-5c35-80e3-0e7ee8438af9 | note | Check Item - Check Item
d79f9cc6-8a22-50ae-9c45-00f16275498b | note | Reference - MRTS70
48c90899-ca9d-4657-986b-1df50205b46e | checkpoint | 4.4 - Form 16 provided to client verifying footing construction completed in accordance with drawings
011bef9e-cdb5-55fe-9923-45d7902aeadb | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
43e8ac3d-408b-5781-86c2-7203baec5d02 | note | Check Item - Check Item
1f4f7fce-b19f-595d-8021-df89e696d2f5 | note | Reference - Project Specific
a23e97e4-2f45-47be-83fd-695b4185e691 | section | Energex Concrete Insitu Pits
fb53d40f-3a78-4841-a768-eab3c7a59dd7 | checkpoint | 5.1 - Form 15 provided by Pit Designer
3e0880c4-40c9-5e60-b525-38ee824b2b98 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
849fb6c4-907a-5341-bb0e-cd0698a276d0 | note | Check Item - Check Item
078f35df-d316-4615-a17d-0cb9bc28f4ff | checkpoint | 5.2 - Form 16 provided to client verifying pit construction completed in accordance with drawing
0c23aeff-e53a-5d33-9385-71d76e35d827 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
79285298-fd12-5577-977b-9b0be6cce3d1 | note | Check Item - Check Item
df7f6774-1436-436f-b685-6d0b9039690c | section | Completion Works
a35c8a23-baf2-406b-ba88-b0a8e4135e95 | checkpoint | 6.1 - Submission of certification package to Energex including:
fcfba0ee-2e31-5fa1-8bb8-a6cf943064af | note | — Certificate of Test
85f9a7b1-2b61-505d-9716-8ec66471e819 | note | — As-Con Drawings
e8886f09-1b1d-5920-a018-c88d0c1accb4 | note | — Product Audit
4f903763-bc19-5e20-8f2f-b92eff857286 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
e8a4b939-d5b1-5e0a-869a-2f07d825aedf | note | Check Item - Check Item
cb7d67c0-6485-4b87-8fa2-39fa1333eafc | checkpoint | Final Verification
0f1e3c35-aec3-541b-b6c9-f97850868fd8 | note | Responsible Officer
6bd166c8-2bb1-58e1-abff-ee08154a3bb0 | textbox | Print Name:
d2fcd7b7-cb71-5ab1-befa-89e69a669226 | date | Date:
83c56e33-4242-513a-97de-eba749f8f9ef | note | Verifying Authority
9d661d04-0ed7-525a-a3d8-861d32e03884 | textbox | Print Name:
972156cf-dc8f-5018-8224-fc0faa63321d | date | Date:
aa4e452f-aefc-4d2e-a416-0ff5e00a1e70 | signoff | Signature
b2ac977f-9b96-4254-b740-350b7fcf28b6 | section | Final Sign Offs (to be completed at closure of Lot)
b26a828d-9d99-4770-ad60-f085ffc53edf | checkpoint | Agreed Quantities
2b24dd90-5c5d-4b11-a582-ee608e272ac8 | signoff | Agreed Quantities Sign Off
49261f15-a3b3-4320-b1ee-a73f891afb3f | checkpoint | Closure of Lot
d96120d3-2999-48b2-8425-2c16eb043627 | signoff | Closure of Lot Sign Off
8aacb646-5f29-44ad-8c80-a4bf257241c6 | checklist | 36.01 - Conduits | itp | 36.01 - Conduits
17370d8a-18b6-4e73-b321-7f0b61b21707 | section | Pre-Construction
a27af043-b2ae-4b65-a013-e3009d5a1243 | checkpoint | 1.1 - Construction procedure submitted to the Client.
fe4abb6d-7d31-5a86-a132-f331efb8e0ac | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
490bba4c-033e-55ee-819f-28c92469cddd | note | Check Item - Check Item
74654608-7794-5843-a9dc-b0b467af3cdf | note | Reference - MRTS91 Cl.5.2
078334a5-61ef-4fc8-8293-d5b3291589e4 | checkpoint | 1.2 - Asbestos presence assessment
bfe55d56-46b8-5285-ad36-6e1723775e22 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
683416c5-b782-5c24-95ab-4ab44cc7b7ae | note | Check Item - Check Item
7a2b39e1-b382-5884-bbb5-94488425189d | note | Reference - MRTS91 Cl 6.1
cef677ab-4f8f-49da-a7a3-a1cffd3ccdf4 | checkpoint | 1.3 - Material certifications submitted to the Client.
5ea5b7e2-5fc0-57a3-b03a-5231a9246a74 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
1db08658-ea02-59ba-a892-e179808afd98 | note | Check Item - Check Item
7fd4cf60-7703-54f3-ba9f-b4b62f67e2d6 | note | Reference - MRTS91 Cl.7.1
0f58da8b-ebfd-4662-a416-677cb1e1bd1b | checkpoint | 1.4 - Drawing versions correct.
6c186eaa-99e1-5c4d-9b6e-805805f33c4d | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
da7ae308-ff13-59e8-a05d-af93dac46c81 | note | Check Item - Check Item
ef4a20be-4e17-5df5-ac5c-c27b00993347 | note | Reference - IFC
f4c20081-e9da-4e88-b12e-0255a09d31e9 | checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
af08b38a-45ad-5427-9dff-80ea0808c472 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
6530627f-ee4c-5d15-b784-6169e9fcc559 | note | Check Item - Check Item
8ba1e625-28ad-50b4-a8e0-869ad6d52f1c | note | Reference - WCS34
d5b86ef3-c76f-4505-b410-9338c995da35 | checkpoint | 1.6 - Form 15 for footing design completed
20c74d90-b56c-5480-aba7-e33fc1d24305 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
3859107c-9462-5f64-a55d-94f591d82bb5 | note | Check Item - Check Item
d02f71a0-3f5a-5e69-86c2-0c9f5cbf2010 | note | Reference - Clause 2.4.2 MUTCD
1a3673ac-e3fe-41c6-8dd9-09c1b3b16255 | checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
d0932042-6b39-59a1-a5dd-4f6292eb9dd0 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b56828e6-ee78-5aaf-8500-98fb21b311cb | note | Check Item - Hold Point
5ebd7f75-93d1-5ace-8e16-e6c0ac00c8b4 | note | Reference - Clause 2.4.3 MUTCD
0d19a510-4b0f-45c6-a292-daf82723400f | signoff | HOLD POINT
34267e9d-e7d0-4ee4-a4af-3d21b8e5c0cd | section | Conduit Installation
b873689d-a094-478f-8200-6ef57557ec1a | checkpoint | 2.1 - Bottom of trench compacted to form a firm uniform surface free from loose material.
cc05ccdb-8f4b-5442-958d-697f5f17b820 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
24874a2a-1525-5143-8ba0-97aeeb097fb4 | note | Check Item - Witness Point
a796f977-986c-5f2e-93ed-2d33af61a846 | note | Reference - MRTS91 Cl.9.1
8699bf78-f65e-47cd-95f4-e1747b96f4f9 | checkpoint | 2.2 - Boring/Jacking Contractor and equipment approved by the SI and works are carried out by experienced operators.
4a86285a-d672-57aa-980a-b531bb000c52 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
900851a6-60ab-5893-b523-e228b6185a09 | note | Check Item - Hold Point
0dc2d507-87ee-5319-9d9e-b4d3ddb1a20b | note | Reference - MRTS91 Cl.8.7
f2d0683e-e4d6-44e5-9fec-35dd94d4a3ff | signoff | HOLD POINT
5064fbd2-4f6b-4a2b-8c16-4d223bd5ca6f | checkpoint | 2.3 - Conduit installation approved by Superintendent and conduit will properly drain, contains no blockages and is not lower than pits that they are connected to.
700bccbf-b4ea-565f-bd47-7768aa9fff83 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
2f0418ba-c5d5-5f8d-93ef-f5e3637c7a3c | note | Check Item - Check Item
60a2bc09-cc60-5239-bb4b-aafd9e3e79bb | note | Reference - MRTS91 Cl.9.1
50ed04de-31c0-42c1-b1a2-8806efe2d82f | checkpoint | 2.4 - Conduits in roadway backfill:
92aaa135-0f90-51f7-8297-de0994cd966f | note | ○ TMR/GCCC/Energex - lean mix BCC – Unbound Pavement or Lean Mix to match existing permeability
c6230ded-a256-5c61-be6f-26a21a3ea6a8 | note | ○ Passing Test Result: TMR - 95% RDD
babbe15e-f74d-57e4-a7b2-364ee67d4cd5 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
e8d1a019-8219-59d5-b38b-5cb53d7c88c9 | note | Check Item - Check Item
a8380660-db25-54e5-a92f-0fcbe06e9d08 | note | Reference - MRTS91 Cl.13.2
6956979e-fea0-4071-85b4-9f0d1cf9f6f8 | checkpoint | 2.5 - Conduits in footpath backfilled with insitu material, else MRS11.05 Type 2 material where insitu cannot be compacted.
76530e05-4380-57e3-ba76-cff1609ea30c | note | ○ Passing Test Result: TMR - 90% RDD
01479f5b-baa6-5b9e-9df8-53ba3ef67f7c | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f5c033a1-c2ea-5341-8f53-eb857000dd87 | note | Check Item - Check Item
3b3cd70a-cb4f-5738-ab3a-b36448304954 | note | Reference - MRTS91 Cl.13.2
656862d3-ca89-4fce-ad5a-4b4a82bb1c57 | checkpoint | 2.6 - Conduit and conduit fittings proved by drawing a mandrel of following size:
b21544e5-9fc6-5816-9a00-a435beacfcca | note | ○ TMR – 95% of ID and 95% of ID in length
723b32c0-e0ff-59b9-9ef8-916a29de963e | note | ○ Energex:- 6mm less than ID and 100mm in length
0d1a93cb-3652-5c41-8ad4-298bbcee14e1 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
dc31cd59-55ee-5f54-b257-012cc310b234 | note | Check Item - Hold Point
8372b930-023a-5168-8764-25e38e414b45 | note | Reference - MRTS91 Cl 9.1
b33f8ff7-26bd-4570-8140-6fe341cfb470 | signoff | HOLD POINT
0d57fa1f-18ba-4a47-b81c-72b405a269c1 | checkpoint | 2.7 - Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
d51f7a14-b7d9-5843-9a7b-3847ed2d8af3 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
366360f5-f312-59d2-a995-9aeb068764f0 | note | Check Item - Witness Point
66bce3e5-cde3-5663-b8bb-d2b756bb961a | note | Reference - MRTS91 Cl 9.13
cfb99ae8-1355-47df-944e-781b70fc817d | checkpoint | 2.8 - Vermin proofing of conduits with unspecified sealing system.
1cef017a-2ea4-55bf-874b-39d92ba5fba5 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
901bd5c1-6c4e-5e99-8d4a-3921bd1496d4 | note | Check Item - Check Item
c600925d-492c-55ce-b53c-ee85e5575815 | note | Reference - MRTS91 Cl 10.9
0fab0058-f686-4c38-acf1-8927343ad00f | section | Completion Works
cae59dc6-9e5c-407c-8012-eb699ee60433 | checkpoint | 3.1 - Submission of certification package to Energex including:
3bb60cee-8f73-5693-9340-e00be9a23067 | note | ○ Certificate of Test
258ca34d-7d46-584d-b696-1cd32fc8e324 | note | ○ As-Con Drawings
95814fc3-e241-5e51-beea-50a4560777b0 | note | ○ Product Audit
221fe8dc-7f43-5440-b467-9d19a3df5ac1 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
e79ef1a8-ce72-585d-b682-f73adff52707 | note | Check Item - Check Item
ccb20195-181c-41dc-9063-7d738bca0c1a | checkpoint | Final Verification
23590f36-24ec-5298-8393-aafa69c31173 | note | Responsible Officer
03e79c5a-395b-5873-bc7c-3a56d018cbea | textbox | Print Name:
9d1a4fe6-a98d-542c-8783-3d106c72ee6d | date | Date:
028faefe-a817-5f5d-9f4d-34f62e43773e | note | Verifying Authority
022f3db0-794b-572d-99f3-4ab2fe0cb7f7 | textbox | Print Name:
c4b810fe-cb44-5e48-bbe8-36e62c1a9914 | date | Date:
ed2088b0-82b8-4915-b8b1-4d7cec5969c0 | signoff | Signature
b6672e7f-57c3-48e9-b2f7-bd6768819948 | section | Final Sign Offs (to be completed at closure of Lot)
ce646402-af3f-4e45-8e75-175398e72b0c | checkpoint | Agreed Quantities
f0f8368d-58d3-4235-b5f8-1e18b93e87f3 | signoff | Agreed Quantities Sign Off
4d7a9f0b-75ed-4344-91a4-185ca7fab45a | checkpoint | Closure of Lot
641c2b78-39e5-45b5-8141-b3fc99e5b89e | signoff | Closure of Lot Sign Off
e940ee06-9247-4dcb-8aa3-2c8eac4f711a | checklist | 36.02 - Pits | itp | 36.02 - Pits
514e1db2-aedb-481e-a292-24c80c143169 | section | Pre-Construction
6828873a-f074-4c08-bba5-f622436e1652 | checkpoint | 1.1 - Construction procedure submitted to the Client.
3106c421-88eb-5404-8cd5-b2bb51371093 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d21aed70-efce-59e9-8785-acc2a770c6c4 | note | Check Item - Check Item
cbeccac4-384b-5836-80fd-520a38870dcd | note | Reference - MRTS91 Cl.5.2
b17ab348-34b1-431e-8cb9-e188e97f5aa2 | checkpoint | 1.2 - Asbestos presence assessment
bb5c6234-ca73-50f3-995c-9fd6be2c1809 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
c5ff984b-a268-555d-9103-f052d4a0d148 | note | Check Item - Check Item
e317aab4-b352-55d1-b4c6-9f6c8331de20 | note | Reference - MRTS91 Cl 6.1
6ed239dc-ea74-41fc-90e2-2ef8bc034015 | checkpoint | 1.3 - Material certifications submitted to the Client.
bf83c0fb-8e2b-513c-9351-f12382ea064e | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
11f351f1-72f8-5a70-9a89-4e713ca6689e | note | Check Item - Check Item
28598fdb-011e-5d7d-9897-fa4f881946d3 | note | Reference - MRTS91 Cl.7.1
ffa4f848-d943-4a76-a5ce-5d0503c10e0b | checkpoint | 1.4 - Drawing versions correct.
fe0ea22d-578f-5f9f-bc59-be0e30eae814 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d6dfaca4-6bce-50f7-953c-f0af52efd1c4 | note | Check Item - Check Item
3c3a15f6-1ece-5f88-907b-2260389739e2 | note | Reference - IFC
eeb62fd4-13e7-49d1-9c4a-34897977c517 | checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
9e352660-7bd9-50e0-8c5d-d2525e0f6dc2 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b498d87b-4e4d-51cb-9cb4-32448dcd95a4 | note | Check Item - Check Item
7b4c093a-ff98-56a0-8f39-765faf0a845c | note | Reference - WCS34
7433fa04-8006-4d94-a97b-7d1b24cbfde7 | checkpoint | 1.6 - Form 15 for footing design completed
4b87d398-ced8-59c9-8e7b-a1e0bc7067d9 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
7fbed408-d6ea-5fc3-a896-162435b4c110 | note | Check Item - Check Item
34519c4f-f093-5f12-8f9a-d80fe71f5824 | note | Reference - Clause 2.4.2 MUTCD
cf76b0ae-f095-4c03-be2d-022121ab7394 | checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
acaac6d4-67ba-5664-a2e9-d0b7696c119f | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
c771a213-d607-5f40-9021-38cf545a4a1b | note | Check Item - Hold Point
2253c70f-b691-5ce7-a53f-ff0038103053 | note | Reference - Clause 2.4.3 MUTCD
ac34ef53-eb5e-48fa-9eb4-3a4870cb0d56 | signoff | HOLD POINT
9b16c85e-3c30-4389-b28f-f4c275af19a8 | section | Pit Installation
3541ae00-0290-4581-91c5-a00d8c3839ce | checkpoint | 2.1 - Soil under pit compacted to 95% RDD
c3f1a13a-92d5-5aeb-a68c-43bbcf4b3f30 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
30d8dda2-050a-5e70-a186-fc0f44f45cd7 | note | Check Item - Witness Point
65aa2e12-4bfd-5da1-95d5-3c8ee513192d | note | Reference - MRTS91 Cl.10.4
bbd5c4a9-d176-491b-9b37-c8feb2b1b48f | checkpoint | 2.2 - Compact bedding material to density index 60.
bfc88573-911a-5ffd-9f45-e283179715b0 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
97824d21-add1-5ec0-abab-463c1de7c214 | note | Check Item - Check Item
de925b81-f862-5d05-a203-07dd25635e03 | note | Reference - MRTS91 Cl.10.4
de2deb94-735b-49c7-bf4d-1fcf07790768 | checkpoint | 2.3 - Lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level
8f2b310e-7aa3-52d7-b9a4-ccd26e0f227d | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
22cf8fca-dec4-51ef-acc6-5c33c25ea8b7 | note | Check Item - Witness Point
ca64aee5-a41c-584e-900c-3e2ab4f568e8 | note | Reference - MRTS91 Cl.10.10
12be2b61-6d6d-4b94-9a13-9bad2e51c93a | section | Completion Works
481077c1-3f93-4e51-a531-8f1971d6c2af | checkpoint | 3.1 - Submission of certification package to Energex including:
56529b8c-6016-58e6-968b-857d81fe8362 | note | ○ Certificate of Test
2e499075-68c8-58aa-a8e9-f2de318f93e8 | note | ○ As-Con Drawings
83fb9be2-cb81-5ed6-bf0e-407195e4bc92 | note | ○ Product Audit
d5390c3f-fb29-5d82-82be-a2fc9edf5be7 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
39e038a3-1902-59e6-bf7f-d61ff8c54360 | note | Check Item - Check Item
81b8cf1c-26f0-4b45-8d01-ffff00d36ed9 | checkpoint | Final Verification
c4485361-5747-55af-bcac-16e6d049db28 | note | Responsible Officer
26f9f155-1345-5cd4-bfc7-249ea6737e31 | textbox | Print Name:
d5153935-d113-5d30-b9d1-2f6f9a57e9bf | date | Date:
2dc4904a-0520-52f9-99ca-695346b86d9d | note | Verifying Authority
453306a4-cef4-5b76-b2a6-01df6b5a0ef9 | textbox | Print Name:
f80ad0f8-8e6f-57d2-a2ad-2a18378b38c8 | date | Date:
dda97e01-bf93-42ad-880c-0007d2c5d046 | signoff | Signature
b2ec8614-4aec-479e-b10b-4b3da2247bbd | section | Final Sign Offs (to be completed at closure of Lot)
479e069e-da16-4bc4-95e8-dd9339deddd8 | checkpoint | Agreed Quantities
0facffd5-0a88-46a0-bc6f-d6e504e6d65b | signoff | Agreed Quantities Sign Off
94fab4e1-9690-419a-a7dc-14fa0591e0ab | checkpoint | Closure of Lot
8277d5e3-d66e-4a6f-9bd7-e6e5ccb1a1d6 | signoff | Closure of Lot Sign Off
9d2e1c3d-95b0-47d1-a367-6b1fa766e3f1 | checklist | 36.03 - Footing and Slabs | itp | 36.03 - Footing and Slabs
b6bd779b-d50a-42f3-aeab-6f42213c1aab | section | Pre-Construction
73b8a859-361c-4c90-b6ef-31a5d39a6ebb | checkpoint | 1.1 - Construction procedure submitted to the Client.
96db3821-70e8-5e8b-9185-b1ed87685649 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d98261be-c1bd-55c4-825d-4db47afe742e | note | Check Item - Check Item
55f0dd5e-3cb4-52d9-8310-97a887afd301 | note | Reference - MRTS91 Cl.5.2
da04114d-b003-4f98-bbe2-f6ac0722023d | checkpoint | 1.2 - Asbestos presence assessment
c53bb363-edf7-5b7b-8cf0-72c66ef3126a | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
a52d9c38-0a9e-5cee-8dea-d4a51f283b86 | note | Check Item - Check Item
910beaef-e8c0-5746-8bdb-41f7a3fa8b9c | note | Reference - MRTS91 Cl 6.1
86004cbd-796a-46ed-a301-99e394725697 | checkpoint | 1.3 - Material certifications submitted to the Client.
4b87f62d-79cc-5ba9-889d-b630359401a9 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d33fc22d-ea0e-5851-a934-9792e23cdd45 | note | Check Item - Check Item
910d00bc-d3f1-5b9c-a053-6da516d5046f | note | Reference - MRTS91 Cl.7.1
bf199701-bfbd-4676-8406-82326f23f650 | checkpoint | 1.4 - Drawing versions correct.
fb7474b5-6ac9-54b4-b9bd-c52084a50cba | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
13887e73-f981-514c-8301-f5ef79f21b88 | note | Check Item - Check Item
dd3b08d4-23f0-50e2-9784-4df20ff22f79 | note | Reference - IFC
d718a065-90f5-411b-9087-fa95cfb2dc18 | checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
45dac9f8-fb71-5ee9-9e4a-266465ac2ba6 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
dbd40c5a-9bef-5621-b393-e76ca35707fb | note | Check Item - Check Item
f5634338-ecff-5271-839e-49b2cfc4963c | note | Reference - WCS34
dbce0495-c097-4f36-a6cb-04f8ca2da74f | checkpoint | 1.6 - Form 15 for footing design completed
8f34222c-ca3d-54e4-90a4-1a14671184b6 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
bb09e6b3-0295-5326-9f2c-389ee0f8fe41 | note | Check Item - Check Item
11092770-3300-58fa-b748-d47b2e74cfaa | note | Reference - Clause 2.4.2 MUTCD
f4389bce-8e55-430b-88aa-7b75b137ebb5 | checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
9694a851-6672-50df-ae13-5a29134e2a51 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
a869479f-5617-5946-83d0-9e2df6ac9c71 | note | Check Item - Hold Point
4d0ad550-447a-5d4f-94cb-fbf7ac6d59ae | note | Reference - Clause 2.4.3 MUTCD
4de12ded-d946-4e97-9d4c-ace26d329667 | signoff | HOLD POINT
e8e6b8e7-c588-4de0-80a6-83a9a07a762a | section | Footing and slab Installation
9ce30119-aeb1-481a-a386-14647c7fa118 | checkpoint | 2.1 - Depth, base and sidewalls of footing’s and slab’s confirmed for each location
708f2297-6f79-5c53-8d66-ffd7139bbee6 | note | Acceptance Criteria & Frequency (Project Specific) - Verify & Hold Point
2f527fad-4923-5f97-9745-16fc3084a3b0 | note | Check Item - Hold Point
b80c33b5-fecb-4ba9-ae7e-dce27a00e1ae | signoff | HOLD POINT
e0a969b8-56b9-44a9-bcb3-37cd2788542b | checkpoint | 2.2 - Ragbolt/reinforcement assembly inspected prior to concrete pour. Concrete poured in accordance with MRTS70. Concrete inspected to ensure correct vibration, monitor placing time and check that material is placed to avoid segregation. Check surface finish.
81956973-c0a0-5810-a8ce-b3d076d69b6a | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
5d9bed7f-5f43-5a5c-a040-04a17b592a0d | note | Check Item - Check Item
d422d5b3-3fc5-52d9-9cd2-a6719dab0f4d | note | Reference - MRTS92 Cl.8.3.7, MRTS70
2c3b1db2-0a4d-4faf-ba19-975a07a9ee10 | checkpoint | 2.3 - Concrete tested for slump and compressive strength by NATA laboratory
73a9b437-04e8-5fcc-82ba-a8e88752170e | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
3d88175e-a3ad-5574-bd63-22d5cb2cee93 | note | Check Item - Check Item
15716346-ea3c-5d98-bc38-e046841b7a6d | note | Reference - MRTS70
43f22c9c-fe0c-4eef-b2d8-4789d3e8ef5d | checkpoint | 2.4 - Form 16 provided to client verifying footing construction completed in accordance with drawings
3bf5361e-fa48-5183-a572-556d5732f0ed | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d977c258-9f35-5fd4-9e95-c452776b9de3 | note | Check Item - Check Item
2dd38ad7-a346-5e66-8c4d-8bdae94810fd | note | Reference - Project Specific
9d929450-f54e-415a-9d75-ae6df2e36f81 | section | Completion Works
2e230048-c753-4917-aa66-c1eab85fbf51 | checkpoint | 3.1 - Submission of certification package to Energex including:
5312ba5b-13ba-56ea-ab0c-c39c1545eff6 | note | ○ Certificate of Test
ba0434a7-565f-5fb9-8fa4-d7058256d2dd | note | ○ As-Con Drawings
774442e7-daa0-5699-a5c1-49e8c8bbe991 | note | ○ Product Audit
b41bcd5e-9434-5ab7-bd6a-48f76685cf68 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d6f8b893-4650-522c-a927-bfc0908a5bde | note | Check Item - Check Item
ffa3a613-f0ea-4db0-9c86-60fe31e637f8 | checkpoint | Final Verification
d7dde1f9-21f1-50b6-873a-1ad9f3d65f5c | note | Responsible Officer
8a1e17b8-1a58-5640-9af7-602ece0ecb76 | textbox | Print Name:
2d743990-2131-5302-a13f-4f796d1d9c51 | date | Date:
0be3920b-50ad-5fb2-832a-1fcfd1d8dd5e | note | Verifying Authority
583bcb08-3729-51ef-bfe4-f63a04d914a9 | textbox | Print Name:
b4a955ce-a86f-5b5a-982f-80f816ee5e16 | date | Date:
e8bffc6f-45a8-459d-9443-4c842d0b803d | signoff | Signature
a5a15ffa-b53a-49f2-be64-e3a7874878f0 | section | Final Sign Offs (to be completed at closure of Lot)
e8bf3437-97df-4cfb-b7e4-6f85bac0522a | checkpoint | Agreed Quantities
829d297d-03f2-4d34-b9e0-dc9b9f497be8 | signoff | Agreed Quantities Sign Off
30ed7b85-ddad-455e-bbec-d652fefe45f6 | checkpoint | Closure of Lot
eaaab772-0012-4919-8de0-eb0a88d11632 | signoff | Closure of Lot Sign Off
b08179d7-7e5d-4e6f-99dc-e6f7670c64a9 | checklist | 40.00 - Dense Graded & Open Graded Asphalt | itp | 40.00 - Dense Graded & Open Graded Asphalt
b639edee-f6d0-43d9-9989-4c4e0625d47e | section | Details
90054201-4525-4006-b48a-c420042f6474 | checkpoint | 1 - Document Submission
d59535e7-d7d4-57f6-bf8c-11b61a8a963b | note | ○ As per Doval Safety Plan, Doval Environmental Management Plan and Traffic Management Plan
c377774c-9a65-5d45-bfc9-32f98b591174 | note | Acceptance Criteria & Frequency (Project Specific) - Check that proper safety procedures are being followed and environmental controls are in place, including traffic management
6ecfc226-d207-5dd3-a0a9-cd79ad2373dd | note | Check Item - Check Item
a6ea0ac6-8313-4ae1-b277-63a9487ecfb9 | checkpoint | 2 - Traffic and Safety Controls
4b2fb477-95c5-5b0b-b9a1-c7ab293cf98b | note | ○ Traffic and safety controls are in place (eg. PPE, daily plant check)
8d95f92c-26a7-56e5-b71b-5a6a9074de36 | note | Acceptance Criteria & Frequency (Project Specific) - Check traffic & safety controls have been implemented as per plan
82c609e3-bd1c-509e-8f10-f13d026532a9 | note | Check Item - Check Item
56c7c052-6bec-48f4-99e9-4f066537edfd | checkpoint | 3 - Asphalt Quality Plan
b2e22556-3940-5c84-aa6f-73cbe28af75c | note | ○ The Contractor must develop an Asphalt Quality Plan (AQP). The AQP must be submitted to the Administrator for consideration at least seven days prior to work commencing and must be implemented.
3ba16975-94eb-5a1d-a971-66e22cf860e7 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
8bfa0066-823c-503a-a64d-c5b352745906 | note | Check Item - MILESTONE
4f7811f5-2f2c-5a61-8af0-e9c7f02567f7 | note | Reference - Clause 5.2 MRTS30
76866be6-fea0-4a83-a4b2-2013694bf5e6 | checkpoint | 4 - Compliance Testing
6f936f41-cdee-52b4-9666-dedd50a396d2 | note | ○ Compliance Testing shall be carried out for each lot. The Testing Frequencies shall not be less than those listed in Tables 5.4.1-A, 5.4.1-B and 5.4.1-D
5c13c971-7c49-53af-b2c9-48d40ccb2bb9 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
05506a8e-d704-5dcd-a353-008cb19511ef | note | Check Item - Check Item
fe970c1c-c376-5ca9-98bd-51b673b6d4ee | note | Reference - Clause 5.4.1 MRTS30
f2fd4a8f-9f18-4893-8c59-3ddb48f99ab6 | checkpoint | 5 - Binder Class
190e0ac7-8be7-5ff7-8d1e-61b67da8fcf9 | note | ○ Contractor shall provide evidence of the binder conformance and compliance with MRTS17 Bitumen or MRTS18 Polymer Modified Binder
3d39df11-b169-5ef1-9fbe-8939bc727304 | note | ○ The Binder Class are specified in Clause 1 of Annexure MRTS30.1 and are:
865f4001-e6aa-568d-bed6-88b282123630 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b06da018-f7c2-5b1f-a034-7c662c34469f | note | Check Item - Check Item
50b90bcd-78c5-5e27-81e3-18e0aac25ef6 | note | Reference - Clause 7.1.6 MRTS30
6bc3640a-e9da-4885-8e8a-04b23a7340c7 | checkpoint | 6 - Moisture Sensitivity
87431088-83af-511a-b907-36fe82435a50 | note | ○ For dense graded asphalt, the tensile strength ratio (TSR) must be ≥ 80% and the average tensile strength of the freeze/thaw group must be 500 kPa for polymer modified binders and 600kPa for mixes containing all other binders.
a3bac242-f366-5499-9df2-c76903a4789a | note | ○ Table 7.2.5 is a list of accepted non-conformance strength ratio for 70% ≥
ee024322-4f8b-5dd9-bc32-e44bae40a5a5 | note | ○ Where a Hold Point is required to be observed, the Contractor shall investigate the causes of the nonconformance and propose corrective action to prevent recurrence of the nonconformance. The Contractor shall submit:
f619b937-fa5a-5a31-9f50-afba9d99bd42 | note | a) test results covering the same Lot for insitu air voids and all characteristics specified in Clause 9.2, and
f046c71f-933d-5b21-a92e-d18637dbc846 | note | b) the proposed corrective action to achieve conformance.
d8f0eb10-efba-55c9-a6a6-b9632591b7f4 | note | ○ The Administrator shall consider the submitted documents prior to authorising the release of the Hold Point allowing recommencement of asphalt production.
30d3c548-d877-52b9-965e-9e0cc569e394 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
e6cbc1a6-449d-5637-8a10-7a5dc356c500 | note | Check Item - HOLD POINT
f89b1b08-5e3a-52c3-a405-d3329422c4dc | note | Reference - Clause 7.2.5 MRTS30
365d5a88-37fd-437e-9bda-2a32236c432d | signoff | HOLD POINT
33ff5864-26ce-4535-81b9-fa9f535404f1 | checkpoint | 7 - Asphalt Contractor Prequalification & Operation Procedures
f1725308-e528-57ae-b498-9ce66554d5c1 | note | ○ At least 7days before asphalt is incorporated the Contractor shall notify the Administrator in writing of the identify and address of the PAC (Prequalified Asphalt Contractor) and their operation procedures.
2ec31d1a-5d83-5701-891e-6490de9a4c38 | note | Operation procedures
91c70564-c0d8-5ef0-94e3-b8df97f45cd4 | note | a) laying program and rolling pattern
1960539d-1a9f-5979-861f-8b419356a79e | note | b) details of any required placement trial and Technical Standard, MRTS30 Dense Graded and Open Graded Asphalt Main Roads Specifications and Technical Standards
c2cacc4f-a78f-563c-9854-8c5a4c1362d6 | note | c) Inspection and test plan.
7d00ef4e-e3a0-55cb-a864-48b993c36158 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
69115ae3-138b-5362-a541-288453114e57 | note | Check Item - Check Item
2ef40898-f179-5220-b844-634ea61bb0c2 | note | Reference - Clause 6 MRTS30
a97c365f-2a46-4108-b7c3-650539ab395f | checkpoint | 8 - Mix Design Submission
96be1a2b-a07d-5d40-a1d9-30d32f8ec2a8 | note | ○ At least seven days before asphalt is to be incorporated into the Works, the Contractor shall submit to the Administrator a copy of the mix design certificate(s) for each nominal size and type of asphalt mix to be incorporated into the Works.
94198b4a-5043-532e-8c2f-20711b33c018 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
71ae15a5-dd8b-597b-aff4-56d3706eb208 | note | Check Item - MILESTONE
92adeea4-f9bf-515c-bd42-b2035e2ae280 | note | Reference - Clause 7.3.3 MRTS30
110b864b-fac3-4613-9430-4f09e8c5eb96 | checkpoint | 9 - Asphalt Mix Design Registrar
9a651955-3d0f-5481-8698-9abb149423a8 | note | ○ The process is written in Technical note 148 Asphalt Mix Design Registration. The certificate shall be sign the Contractor mix designer certifying the mix complies with MRTS30 and shall be submitted 28days prior to asphalt being incorporated.
737ad8e6-a698-5ffe-a5d1-d39ddd9a6860 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
7ade57b8-dc42-57bc-98da-b5c961f25afe | note | Check Item - Check Item
f487eb65-c6a1-5da8-affe-20e4962276dd | note | Reference - Clause 7.3.2 MRTS30
6f39d184-eb34-4c75-afd4-fa4b712a6705 | checkpoint | 10 - Asphalt Mix Design Acceptance
a1266280-29fe-5888-9564-947a20a17aae | note | Asphalt shall be produced by a registered asphalt manufacturer from the nominated asphalt plant in accordance with the nominated mix design for the Works. Asphalt shall not be incorporated into the Works until the Contractor has demonstrated to the Administrator that the underlying lots conform to the specified requirements or have been accepted by the Administrator for utilisation at a reduced level of service, and the following documents have been received and reviewed by the Administrator:
13387217-990c-5214-b656-a64a341b9f7b | note | a) identity of the PAC(s) who will undertake the asphalt production, placement and compaction and the address of the asphalt plant that will produce the asphalt (refer Section 6)
bb62bd3c-bb89-5584-b33e-bf1f7a7939a8 | note | b) the mix design certificate, which holds current registration with TMR, for each conforming mix design to be used in the Works (refer Section 7.3) or conforming revised mix design submissions (where applicable) (refer Clause 7.3.3)
91ecf51a-12c6-57a8-a602-c1cc43999ede | note | c) the Contractor’s AQP (refer Section 5.2)
9a884266-672c-5ed1-bf60-d385453ad2da | note | d) the Contractor’s Aggregate Production Procedure (refer MRTS101), and
e3beb5b8-9cc5-57ff-b8a1-b223e943ac41 | note | e) the Contractor’s RAP Management Plan (where applicable).
857666d1-2d44-5ee3-bd5b-ac8c09338967 | note | ○ These documents shall be submitted to the Administrator not less than seven days prior to the commencement of asphalt being incorporated into the Works.
12a3c344-faa1-571c-88a1-6c53c2750f2e | note | ○ Any subsequent changes to any of the above documents will require re-submission and re-release of the Hold Point.
d96bd0ec-2eb9-5cae-a813-5bb8d52e4ec9 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
d65f824c-34df-5e4e-b4d8-31fbe0d80696 | note | Check Item - HOLD POINT
4dc0091c-14d1-5bf1-8f80-da344d5ba1b2 | note | Reference - Clause 7.4.1 MRTS30
22ca23b3-82aa-4f33-a457-d620d3385d2a | signoff | HOLD POINT
40acff08-6407-49f1-927b-340260ca8a86 | checkpoint | 11 - Nonconforming Mix Design
f60513be-8533-5b99-83b0-d6168f962781 | note | ○ Nonconforming mix designs, that hold current registration with TMR, shall not be incorporated into the Works unless otherwise accepted in writing by the Administrator prior to the commencement of asphalt production.
148c2b1f-afc2-54bd-a05c-b0bf5da983e8 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
04167b25-12b7-5468-a88b-d6cfe9072640 | note | Check Item - HOLD POINT
a3954be5-544d-50f5-995c-72e030ecfaad | note | Reference - Clause 7.4.1 MRTS30
694a738e-e9e8-40eb-bc35-beeff3afccaa | signoff | HOLD POINT
e7c4f1b7-595d-4efd-80ba-0ceae6a2921b | checkpoint | 12 - Preparation of Pavement
0d75aaa4-7c48-53c4-8dd8-cd2bd24aabcf | note | ○ The surface of the pavement base/bridge deck or existing substrate shall not be wet, and shall be thoroughly swept using a rotary broom to remove any loose material or other deleterious material which may be present. Any deleterious material, which still adheres to the surface after sweeping, shall be removed by other means.
b821ec1b-9fc0-51eb-b1e2-403fec8125f2 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
8a066e9d-b7f1-5207-a089-d029a975d52e | note | Check Item - Check Item
6b419805-6042-5182-9f32-0b683b9ab5a9 | note | Reference - Clause 8.2.2 MRTS30
d7f483ea-e776-4806-8008-93afc27d7224 | checkpoint | 13 - Crack Filling
20420634-9f40-5be9-b4c8-a8ca4983c548 | note | ○ In areas shown in the Drawings or stated in Clause 2 of Annexure MRTS30.1, cracks greater than 2 mm wide shall be filled prior to placement of any asphalt. The Contractor shall mark out in the presence of the Administrator, the extent of crack filling to be carried out.
ccceb61c-048a-593e-b9c3-e84825959b31 | note | ○ Cracks shall be filled level with the surrounding surface with a polymer modified sealant approved by the Administrator.
c67b3049-86d2-57f6-a0f0-b5ffcb0d3722 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
60b8ee00-ca9f-589d-be25-6972ec964a7e | note | Check Item - WITNESS POINT
3b51cbf7-7ec6-562e-ac88-c579eea71e43 | note | Reference - Clause 8.2.3 MRTS30
382d5f86-ab9a-47e2-b72e-58d6e892c050 | checkpoint | 14 - Strain Alleviating Fabric Strips
17aa934e-1c1c-5bc7-863c-193d5b293fa0 | note | ○ In the areas shown on the Drawings or stated in Clause 3 of Annexure MRTS30.1, strain alleviating fabric strips shall be applied to existing cracks prior to placement of asphalt or sprayed sealing.
90c73413-12a4-5454-aac7-a6be6da80fce | note | ○ The Contractor shall mark out, in the presence of the Administrator, the extent of the strain alleviating fabric strips to be applied.
b6406c3b-c2e8-56b5-87d2-d76a39749e6e | note | ○ Where directed by the Administrator.
715ebdd5-273e-5ede-9811-aa1f917a3fb6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9352e9e0-bed8-54a3-98ac-f1a574a2ef82 | note | Check Item - WITNESS POINT
990971e1-628d-58b3-8c39-85534e9c55e5 | note | Reference - Clause 8.2.4 MRTS30
aa4fa7e9-5570-4d03-99ee-731033a2f7e4 | checkpoint | 15 - Method of Placement
9c71307f-0dd7-5a8c-b1e4-fdef577157dc | note | ○ A self-propelled paving machine equipped with the ability to be operated with automatic thickness control and automatic joint matching facility must place the asphalt.
afb70782-8054-53a1-9680-d6a0dbcb3dba | note | ○ Hand placement of asphalt is only permitted for minor corrections of the existing surface and in areas where placement with a paving machine is impractical.
9233352b-f1a5-588e-af5e-6cd29ef39a7b | note | Acceptance Criteria & Frequency (Project Specific) - Check
04cc7bf3-72df-51d5-97c9-befdd025add0 | note | Check Item - Check Item
9aa04ff1-d9ff-5860-94e1-ba407b8de37c | note | Reference - Clause 8.3 MRTS30
40e78a14-edce-4fc8-a61d-2257d451e599 | checkpoint | 16 - Nominated Layer Thickness
2caa8f4a-8e56-5ead-b09a-35ef4c9d6178 | note | ○ The binder details are specified in Clause 1 of Annexure MRTS30.
75d31959-e464-5cac-8cbf-89c3f75fe8b9 | note | ○ The nominated thickness of a layer of Asphalt shall be within the limits specified in Table 8.6.1
5f941e21-0093-5edf-ba27-8e2e808910cf | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
53cf8942-4b88-5027-af53-6f7528a16dc6 | note | Check Item - Check Item
170e919d-4ee4-5f93-a556-ae42b0d243c8 | note | Reference - Clause 8.6 MRTS30
838684b7-35eb-470c-b818-cdc81e57eabb | checkpoint | 17 - Tie-ins to Existing Pavement
a66c0faa-0cd1-510d-9eff-43203bf00801 | note | ○ For Tie-ins, the Contractor may be required to a implement a layer thickness that does not conform with Clause 8.6.1. The Contractor shall detail the work methods to be adopted in the AQP.
49d1595a-f4ae-53c0-814a-5749940d26a4 | note | ○ Placement of asphalt in a nonconforming layer thickness shall not occur until Administrator approval.
2fc5b004-52db-5fa8-861b-50a7ab6a9ae4 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
b6547403-aea8-52a1-8d6c-bdeb87dbb9f8 | note | Check Item - HOLD POINT
d687a5c5-4309-57fb-9061-1306762bc9ef | note | Reference - Clause 8.6.2 MRTS30
6a752431-ae40-4036-acbc-23a64b75209d | signoff | HOLD POINT
820cb024-ba71-4551-9030-9fa649943586 | checkpoint | 18 - Pavement Temperature
068ef3ad-b510-5af3-9221-f1090d5f80a3 | note | ○ The pavement surface temperature shall be measured and recorded at the point of asphalt placement on a regular basis during paving operations. The Contractor shall document the method of measuring and recording pavement temperatures in the AQP. Unless otherwise accepted by the Administrator, asphalt placement shall not commence or continue, unless the pavement surface temperature complies with the requirements of MRTS30 Table 8.7.
bb115c4b-2649-5d7d-bd33-ed6641747e3c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
640f6a59-16b2-5f86-b1f4-0e4c1c02972a | note | Check Item - HOLD POINT
23ad615c-bf59-574b-a527-46fb557d6d22 | note | Reference - Clause 8.7 MRTS30
9ce7f181-de19-4af3-9b7d-eaef910cbe31 | signoff | HOLD POINT
89f41ef9-8103-4fe2-a354-f2af5f024b07 | checkpoint | 19 - Paving and Compaction Temperatures
493c2323-7332-58f2-8fcc-19b830afb708 | note | ○ Contractor AQP must document the temperatures at which the asphalt is placed and compacted to achieve the insitu air voids requirements specified in Clause 9.2.1. The contractor shall nominate in the AQP the listed of requirements described in Clause 8.8.
c6c2d32d-b5d6-56d0-9bb2-645c8a612e8f | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
92252a11-21d1-5289-b758-5b94f3c1321d | note | Check Item - Check Item
1d720e24-950b-5e78-a862-4453dba696d8 | note | Reference - Clause 8.8 MRTS30
cccdaa82-0268-44ea-838d-10f77f7dd4c6 | checkpoint | 20 - Tack Coat
5682f7aa-73b0-5348-880c-fd871ab07ce5 | note | ○ Tack coat is to be applied to a clean, dry surface immediately prior to the placement of asphalt. The AQP shall state the bituminous emulsion grade and proposed tack coat.
fd1b6c19-7d16-57d5-82da-be80f3544e86 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Check
ae72cd34-0097-5760-bcbb-7e197a6bbbac | note | Check Item - Check Item
b9c88cd2-08c7-56a8-8ab9-daefedf53aa1 | note | Reference - Clause 8.9 MRTS30
46337fd7-fffb-4861-b63a-b7aef6fd1bd9 | checkpoint | 21 - Joints
b39047bd-5d5c-5960-a337-711c880049e6 | note | ○ Construction of asphalt joints shall be described in the AQP and shall follow the procedures described in Clause 8.10
40092c37-46ee-5ac5-87b8-c423d41aac8f | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
e99a10f9-88b1-528b-a5b3-45c5e8502217 | note | Check Item - Check Item
63058fac-c67d-5ddb-b4cc-a05d1e900750 | note | Reference - Clause 8.10 MRTS30
07a9ce23-2a78-44ec-8319-234969f4a110 | checkpoint | 22 - Placement Trial
5dd2bde8-a03a-572e-9800-d957cbf8a351 | note | ○ If specified in Clause 6 of Annexure MRTS30.1 and prior to commencing work, the plant and personnel proposed for use for the Works must be subjected to a placement trial.
d22875e6-475b-5bcb-adc4-11604a2c3c6a | note | ○ The Contractor shall submit a copy of the completed inspection and test plan and all relevant test results and records from the placement trial. Prior to further placement of the Contractor’s nominated mix(s) in the works, the Administrator shall review the outcomes of the placement trial. No further work shall be undertaken until the Administrator has given approval to proceed. N/A
42751bf0-81ba-5a45-a3c6-10d884dd20a5 | note | Acceptance Criteria & Frequency (Project Specific) - Approval
df191684-33d0-57d4-b98a-187643c9b0da | note | Check Item - HOLD POINT
97e932cf-605d-53d1-9e75-53dbd6217765 | note | Reference - Clause 8.11 MRTS30
3d60f61c-f381-4456-9b5a-2d7c8bdb7b4b | signoff | HOLD POINT
f4b40191-9c57-4ca9-9856-8a8cc1fe075d | checkpoint | Final Verification
ae6abaef-1025-513f-92b4-4bcd84263545 | note | Responsible Officer
382c3c18-5d65-5c6d-af92-6f36e29631e6 | textbox | Print Name:
d2b696d3-32ea-54b1-bead-cb198cc572fd | date | Date:
0c947c23-f4d5-5797-b61a-8b77f642625f | note | Verifying Authority
cf6ffe36-d2d6-5c9c-973e-a70081a338dc | textbox | Print Name:
10d76d4e-cc2e-5bed-920b-c29ccbe9bdd7 | date | Date:
aa95b7c8-4498-4653-90c7-256a3e356aaf | signoff | Signature
acce7b78-2a58-4ace-b26b-17ca70bff7ff | section | Final Sign Offs (to be completed at closure of Lot)
270a164a-b740-4928-beac-3d601415383e | checkpoint | Agreed Quantities
3077e71f-5a2e-48b7-b628-ddb60600397b | signoff | Agreed Quantities Sign Off
f6983056-e9cc-488c-ac5c-36acf3efa366 | checkpoint | Closure of Lot
4bcc647e-475d-4d4b-aba3-f8464fc8ab32 | signoff | Closure of Lot Sign Off
dfd9f321-efb8-4666-9421-83f21de39ceb | checklist | Material Conformance |  | Material Conformance
77bbc0c5-6646-4d00-b9bf-d13e11611256 | section | 1 - General Info
de45a59c-8aa8-4f51-a740-06e4dace7d8e | checkpoint-no-value | General Info
875b0b33-ab91-514f-aa64-2b8f27ad1446 | textbox | Project Name
0f7f8cc9-77d1-5401-a578-f5bd2b4a7656 | textbox | Project Location
799171e4-a751-5572-8fa3-28ab19db95b3 | textbox | Principal Contractor
8754c53d-186e-5d77-9ee5-75466c90bc60 | textbox | MRTS Specification No.
8864f884-ea12-5171-bfc5-63819a66a853 | textbox | Material Type
0eb6b6ef-c89a-5dea-9433-c7b51f8bb978 | textbox | Lot Number
c9b5101f-fe57-5dfd-9dfd-435d896c2ed3 | date | Date of Sampling
77884ef0-1863-5e58-93cb-043ca9463526 | date | Date of Delivery
be235a1d-de4d-511d-9874-cb15675010f6 | textbox | Quantity Supplied
498b554f-2d5c-4ef1-9595-18c78fa0c69c | section | 2 - Supplier Info
24784741-5404-4a16-9c25-38fd6135fdd1 | checkpoint-no-value | Supplier Info
7154ccba-f568-572d-bdfe-f4d2b9b6bdc0 | textbox | Supplier Name
a2aeb609-b60f-5d0a-8c77-61e470a8da0a | textbox | Contact Person
18e1a842-4625-59c8-b5ba-f80830af9f74 | textbox | Contact Phone / Email
530d2082-6385-5192-8bd4-0163db2aadb4 | textbox | Source / Plant Location
ca973671-7851-5721-ba0e-8b8ea4347c23 | textbox | TMR Approved Source ID (if any)
6ac528f0-5921-4fc7-a3d7-fec9286fee90 | section | 3 - Test Summary
6c379aa3-b0a2-46db-b88c-bc7deeb562a8 | checkpoint | Test Summary
282b8ece-3c75-5f08-afad-3cc9c0c7108c | textbox | Test Parameter
9f8bdf04-c551-5e59-9709-3c8892bac2fa | textbox | Test Method
46664d52-ce54-5bcf-a8ce-9ac33efaf82b | textbox | Specified Requirement
03d0fb28-454a-573f-8ae1-155a69030c4f | textbox | Actual Result
f5182a60-b14c-4423-988d-1667f2412c86 | section | 4 - Test Certificates
4531d668-f351-463b-b1be-a5da24666dbd | checkpoint | Test Certificates
8b9451fd-4a14-5217-af71-c24a290e8cf4 | textbox | Certificate Type
31e0c1da-0e6a-5ed6-b6fd-7955ae1de2ea | textbox | Certificate Number
df2bdc13-7592-512c-81ee-3979ec567308 | textbox | Issuing Laboratory
cb41bb2f-54ec-5f95-bc34-b55cac24dd9c | button | NATA Accredited? | Yes,No
570106de-d3c6-4f5a-a711-64b9f00d4af2 | section | 5 - Declaration
fede0ea7-106d-4a84-bda3-7248779d5078 | checkpoint | Conformance Declaration
086df0da-950d-5b88-bab3-dfe189410bcf | textbox | I hereby declare that Lot
73cd8736-4f9a-5070-8b73-be2a3d8a1819 | textbox | complies with all applicable requirements of |  |  | as verified by testing and documentation provided above.
5f98b5d1-e705-4735-a41e-4c756dc1ea92 | signoff | Signoff