## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
8aacb646-5f29-44ad-8c80-a4bf257241c6 | checklist | 36.01 - Conduits | itp | 36.01 - Conduits
17370d8a-18b6-4e73-b321-7f0b61b21707 | section | Pre-Construction
a27af043-b2ae-4b65-a013-e3009d5a1243 | checkpoint | 1.1 - Construction procedure submitted to the Client.
fe4abb6d-7d31-5a86-a132-f331efb8e0ac | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
490bba4c-033e-55ee-819f-28c92469cddd | note | Check Item - Check Item
74654608-7794-5843-a9dc-b0b467af3cdf | note | Reference - MRTS91 Cl.5.2
078334a5-61ef-4fc8-8293-d5b3291589e4 | checkpoint | 1.2 - Asbestos presence assessment
bfe55d56-46b8-5285-ad36-6e1723775e22 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
683416c5-b782-5c24-95ab-4ab44cc7b7ae | note | Check Item - Check Item
7a2b39e1-b382-5884-bbb5-94488425189d | note | Reference - MRTS91 Cl 6.1
cef677ab-4f8f-49da-a7a3-a1cffd3ccdf4 | checkpoint | 1.3 - Material certifications submitted to the Client.
5ea5b7e2-5fc0-57a3-b03a-5231a9246a74 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
1db08658-ea02-59ba-a892-e179808afd98 | note | Check Item - Check Item
7fd4cf60-7703-54f3-ba9f-b4b62f67e2d6 | note | Reference - MRTS91 Cl.7.1
0f58da8b-ebfd-4662-a416-677cb1e1bd1b | checkpoint | 1.4 - Drawing versions correct.
6c186eaa-99e1-5c4d-9b6e-805805f33c4d | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
da7ae308-ff13-59e8-a05d-af93dac46c81 | note | Check Item - Check Item
ef4a20be-4e17-5df5-ac5c-c27b00993347 | note | Reference - IFC
f4c20081-e9da-4e88-b12e-0255a09d31e9 | checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
af08b38a-45ad-5427-9dff-80ea0808c472 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
6530627f-ee4c-5d15-b784-6169e9fcc559 | note | Check Item - Check Item
8ba1e625-28ad-50b4-a8e0-869ad6d52f1c | note | Reference - WCS34
d5b86ef3-c76f-4505-b410-9338c995da35 | checkpoint | 1.6 - Form 15 for footing design completed
20c74d90-b56c-5480-aba7-e33fc1d24305 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
3859107c-9462-5f64-a55d-94f591d82bb5 | note | Check Item - Check Item
d02f71a0-3f5a-5e69-86c2-0c9f5cbf2010 | note | Reference - Clause 2.4.2 MUTCD
1a3673ac-e3fe-41c6-8dd9-09c1b3b16255 | checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
d0932042-6b39-59a1-a5dd-4f6292eb9dd0 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b56828e6-ee78-5aaf-8500-98fb21b311cb | note | Check Item - Hold Point
5ebd7f75-93d1-5ace-8e16-e6c0ac00c8b4 | note | Reference - Clause 2.4.3 MUTCD
0d19a510-4b0f-45c6-a292-daf82723400f | signoff | HOLD POINT
34267e9d-e7d0-4ee4-a4af-3d21b8e5c0cd | section | Conduit Installation
b873689d-a094-478f-8200-6ef57557ec1a | checkpoint | 2.1 - Bottom of trench compacted to form a firm uniform surface free from loose material.
| note | ○ Compaction Passing Test Result: MRTS04 - 95% Standard
cc05ccdb-8f4b-5442-958d-697f5f17b820 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
24874a2a-1525-5143-8ba0-97aeeb097fb4 | note | Check Item - Witness Point
a796f977-986c-5f2e-93ed-2d33af61a846 | note | Reference - MRTS91 Cl.9.1
8699bf78-f65e-47cd-95f4-e1747b96f4f9 | checkpoint | 2.2 - Boring/Jacking Contractor and equipment approved by the SI and works are carried out by experienced operators.
4a86285a-d672-57aa-980a-b531bb000c52 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
900851a6-60ab-5893-b523-e228b6185a09 | note | Check Item - Hold Point
0dc2d507-87ee-5319-9d9e-b4d3ddb1a20b | note | Reference - MRTS91 Cl.8.7
f2d0683e-e4d6-44e5-9fec-35dd94d4a3ff | signoff | HOLD POINT
5064fbd2-4f6b-4a2b-8c16-4d223bd5ca6f | checkpoint | 2.3 - Conduit installation approved by Superintendent and conduit will properly drain, contains no blockages and is not lower than pits that they are connected to.
700bccbf-b4ea-565f-bd47-7768aa9fff83 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
2f0418ba-c5d5-5f8d-93ef-f5e3637c7a3c | note | Check Item - Check Item
60a2bc09-cc60-5239-bb4b-aafd9e3e79bb | note | Reference - MRTS91 Cl.9.1
50ed04de-31c0-42c1-b1a2-8806efe2d82f | checkpoint | 2.4 - Conduits in roadway backfill:
92aaa135-0f90-51f7-8297-de0994cd966f | note | ○ TMR/GCCC/Energex - lean mix BCC – Unbound Pavement or Lean Mix to match existing permeability
c6230ded-a256-5c61-be6f-26a21a3ea6a8 | note | ○ Passing Test Result: TMR - 95% RDD
babbe15e-f74d-57e4-a7b2-364ee67d4cd5 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
e8d1a019-8219-59d5-b38b-5cb53d7c88c9 | note | Check Item - Check Item
a8380660-db25-54e5-a92f-0fcbe06e9d08 | note | Reference - MRTS91 Cl.13.2
6956979e-fea0-4071-85b4-9f0d1cf9f6f8 | checkpoint | 2.5 - Conduits in footpath backfilled:
| note | ○ Energex: Existing Material
| note | ○ Compaction Passing Test Result: Energex UDCM - 90% Modified
| note | ○ TMR: MRTS05 Subtype 2.3 Minimum
| note | ○ Compaction Passing Test Result: MRTS04 - 95% Modified
76530e05-4380-57e3-ba76-cff1609ea30c | note | ○ Passing Test Result: TMR - 90% RDD
01479f5b-baa6-5b9e-9df8-53ba3ef67f7c | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f5c033a1-c2ea-5341-8f53-eb857000dd87 | note | Check Item - Check Item
3b3cd70a-cb4f-5738-ab3a-b36448304954 | note | Reference - MRTS91 Cl.13.2
656862d3-ca89-4fce-ad5a-4b4a82bb1c57 | checkpoint | 2.6 - Conduit and conduit fittings proved by drawing a mandrel of following size:
b21544e5-9fc6-5816-9a00-a435beacfcca | note | ○ TMR – 95% of ID and 95% of ID in length
723b32c0-e0ff-59b9-9ef8-916a29de963e | note | ○ Energex:- 6mm less than ID and 100mm in length
0d1a93cb-3652-5c41-8ad4-298bbcee14e1 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
dc31cd59-55ee-5f54-b257-012cc310b234 | note | Check Item - Hold Point
8372b930-023a-5168-8764-25e38e414b45 | note | Reference - MRTS91 Cl 9.1
b33f8ff7-26bd-4570-8140-6fe341cfb470 | signoff | HOLD POINT
0d57fa1f-18ba-4a47-b81c-72b405a269c1 | checkpoint | 2.7 - Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
d51f7a14-b7d9-5843-9a7b-3847ed2d8af3 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
366360f5-f312-59d2-a995-9aeb068764f0 | note | Check Item - Witness Point
66bce3e5-cde3-5663-b8bb-d2b756bb961a | note | Reference - MRTS91 Cl 9.13
cfb99ae8-1355-47df-944e-781b70fc817d | checkpoint | 2.8 - Vermin proofing of conduits with unspecified sealing system.
1cef017a-2ea4-55bf-874b-39d92ba5fba5 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
901bd5c1-6c4e-5e99-8d4a-3921bd1496d4 | note | Check Item - Check Item
c600925d-492c-55ce-b53c-ee85e5575815 | note | Reference - MRTS91 Cl 10.9
0fab0058-f686-4c38-acf1-8927343ad00f | section | Completion Works
cae59dc6-9e5c-407c-8012-eb699ee60433 | checkpoint | 3.1 - Submission of certification package including:
3bb60cee-8f73-5693-9340-e00be9a23067 | note | ○ Certificate of Test
258ca34d-7d46-584d-b696-1cd32fc8e324 | note | ○ As-Con Drawings
95814fc3-e241-5e51-beea-50a4560777b0 | note | ○ Product Audit
221fe8dc-7f43-5440-b467-9d19a3df5ac1 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
e79ef1a8-ce72-585d-b682-f73adff52707 | note | Check Item - Check Item
ccb20195-181c-41dc-9063-7d738bca0c1a | checkpoint | Final Verification
23590f36-24ec-5298-8393-aafa69c31173 | note | Responsible Officer
03e79c5a-395b-5873-bc7c-3a56d018cbea | textbox | Print Name:
9d1a4fe6-a98d-542c-8783-3d106c72ee6d | date | Date:
028faefe-a817-5f5d-9f4d-34f62e43773e | note | Verifying Authority
022f3db0-794b-572d-99f3-4ab2fe0cb7f7 | textbox | Print Name:
c4b810fe-cb44-5e48-bbe8-36e62c1a9914 | date | Date:
ed2088b0-82b8-4915-b8b1-4d7cec5969c0 | signoff | Signature
b6672e7f-57c3-48e9-b2f7-bd6768819948 | section | Final Sign Offs (to be completed at closure of Lot)
ce646402-af3f-4e45-8e75-175398e72b0c | checkpoint | Agreed Quantities
f0f8368d-58d3-4235-b5f8-1e18b93e87f3 | signoff | Agreed Quantities Sign Off
4d7a9f0b-75ed-4344-91a4-185ca7fab45a | checkpoint | Closure of Lot
641c2b78-39e5-45b5-8141-b3fc99e5b89e | signoff | Closure of Lot Sign Off
e940ee06-9247-4dcb-8aa3-2c8eac4f711a | checklist | 36.02 - Pits | itp | 36.02 - Pits
514e1db2-aedb-481e-a292-24c80c143169 | section | Pre-Construction
6828873a-f074-4c08-bba5-f622436e1652 | checkpoint | 1.1 - Construction procedure submitted to the Client.
3106c421-88eb-5404-8cd5-b2bb51371093 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d21aed70-efce-59e9-8785-acc2a770c6c4 | note | Check Item - Check Item
cbeccac4-384b-5836-80fd-520a38870dcd | note | Reference - MRTS91 Cl.5.2
b17ab348-34b1-431e-8cb9-e188e97f5aa2 | checkpoint | 1.2 - Asbestos presence assessment
bb5c6234-ca73-50f3-995c-9fd6be2c1809 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
c5ff984b-a268-555d-9103-f052d4a0d148 | note | Check Item - Check Item
e317aab4-b352-55d1-b4c6-9f6c8331de20 | note | Reference - MRTS91 Cl 6.1
6ed239dc-ea74-41fc-90e2-2ef8bc034015 | checkpoint | 1.3 - Material certifications submitted to the Client.
bf83c0fb-8e2b-513c-9351-f12382ea064e | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
11f351f1-72f8-5a70-9a89-4e713ca6689e | note | Check Item - Check Item
28598fdb-011e-5d7d-9897-fa4f881946d3 | note | Reference - MRTS91 Cl.7.1
ffa4f848-d943-4a76-a5ce-5d0503c10e0b | checkpoint | 1.4 - Drawing versions correct.
fe0ea22d-578f-5f9f-bc59-be0e30eae814 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d6dfaca4-6bce-50f7-953c-f0af52efd1c4 | note | Check Item - Check Item
3c3a15f6-1ece-5f88-907b-2260389739e2 | note | Reference - IFC
eeb62fd4-13e7-49d1-9c4a-34897977c517 | checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
9e352660-7bd9-50e0-8c5d-d2525e0f6dc2 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
b498d87b-4e4d-51cb-9cb4-32448dcd95a4 | note | Check Item - Check Item
7b4c093a-ff98-56a0-8f39-765faf0a845c | note | Reference - WCS34
7433fa04-8006-4d94-a97b-7d1b24cbfde7 | checkpoint | 1.6 - Form 15 for footing design completed
4b87d398-ced8-59c9-8e7b-a1e0bc7067d9 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
7fbed408-d6ea-5fc3-a896-162435b4c110 | note | Check Item - Check Item
34519c4f-f093-5f12-8f9a-d80fe71f5824 | note | Reference - Clause 2.4.2 MUTCD
cf76b0ae-f095-4c03-be2d-022121ab7394 | checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
acaac6d4-67ba-5664-a2e9-d0b7696c119f | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
c771a213-d607-5f40-9021-38cf545a4a1b | note | Check Item - Hold Point
2253c70f-b691-5ce7-a53f-ff0038103053 | note | Reference - Clause 2.4.3 MUTCD
ac34ef53-eb5e-48fa-9eb4-3a4870cb0d56 | signoff | HOLD POINT
9b16c85e-3c30-4389-b28f-f4c275af19a8 | section | Pit Installation
3541ae00-0290-4581-91c5-a00d8c3839ce | checkpoint | 2.1 - Soil under pit compacted
| note | ○ Compaction Passing Test Result: MRTS04 - 95% Standard
c3f1a13a-92d5-5aeb-a68c-43bbcf4b3f30 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
30d8dda2-050a-5e70-a186-fc0f44f45cd7 | note | Check Item - Witness Point
65aa2e12-4bfd-5da1-95d5-3c8ee513192d | note | Reference - MRTS91 Cl.10.4
bbd5c4a9-d176-491b-9b37-c8feb2b1b48f | checkpoint | 2.2 - Install bedding material
bfc88573-911a-5ffd-9f45-e283179715b0 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
97824d21-add1-5ec0-abab-463c1de7c214 | note | Check Item - Check Item
de925b81-f862-5d05-a203-07dd25635e03 | note | Reference - MRTS91 Cl.10.4
de2deb94-735b-49c7-bf4d-1fcf07790768 | checkpoint | 2.3 - Lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level
8f2b310e-7aa3-52d7-b9a4-ccd26e0f227d | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
22cf8fca-dec4-51ef-acc6-5c33c25ea8b7 | note | Check Item - Witness Point
ca64aee5-a41c-584e-900c-3e2ab4f568e8 | note | Reference - MRTS91 Cl.10.10
| checkpoint | 2.4 - Pit in verge backfilled
| note | ○ Energex: Existing Material
| note | ○ Compaction Passing Test Result: Energex UDCM - 90% Modified
| note | ○ TMR: MRTS05 Subtype 2.3 Minimum
| note | ○ Stabilised Sand or MRTS05 Subtype 2.3 Minimum
| note | ○ Compaction Passing Test Result: MRTS04 - 95% Modified
| note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
| note | Check Item - Witness Point
12be2b61-6d6d-4b94-9a13-9bad2e51c93a | section | Completion Works
481077c1-3f93-4e51-a531-8f1971d6c2af | checkpoint | 3.1 - Submission of certification package to Energex including:
56529b8c-6016-58e6-968b-857d81fe8362 | note | ○ Certificate of Test
2e499075-68c8-58aa-a8e9-f2de318f93e8 | note | ○ As-Con Drawings
83fb9be2-cb81-5ed6-bf0e-407195e4bc92 | note | ○ Product Audit
d5390c3f-fb29-5d82-82be-a2fc9edf5be7 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
39e038a3-1902-59e6-bf7f-d61ff8c54360 | note | Check Item - Check Item
81b8cf1c-26f0-4b45-8d01-ffff00d36ed9 | checkpoint | Final Verification
c4485361-5747-55af-bcac-16e6d049db28 | note | Responsible Officer
26f9f155-1345-5cd4-bfc7-249ea6737e31 | textbox | Print Name:
d5153935-d113-5d30-b9d1-2f6f9a57e9bf | date | Date:
2dc4904a-0520-52f9-99ca-695346b86d9d | note | Verifying Authority
453306a4-cef4-5b76-b2a6-01df6b5a0ef9 | textbox | Print Name:
f80ad0f8-8e6f-57d2-a2ad-2a18378b38c8 | date | Date:
dda97e01-bf93-42ad-880c-0007d2c5d046 | signoff | Signature
b2ec8614-4aec-479e-b10b-4b3da2247bbd | section | Final Sign Offs (to be completed at closure of Lot)
479e069e-da16-4bc4-95e8-dd9339deddd8 | checkpoint | Agreed Quantities
0facffd5-0a88-46a0-bc6f-d6e504e6d65b | signoff | Agreed Quantities Sign Off
94fab4e1-9690-419a-a7dc-14fa0591e0ab | checkpoint | Closure of Lot
8277d5e3-d66e-4a6f-9bd7-e6e5ccb1a1d6 | signoff | Closure of Lot Sign Off