## CRG-FH-ITP-0014
|  |  | Inspection and Test Plan - Installation of Precast Concrete Barriers | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-001A
[11 empty] | Revision : A | Date : 28/05/25
Client: | Department of Transport & Planning |  | Construction Process: | Installation of Traffic Barriers |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  | Specifications: |  |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Structure / Component: |  |  | Position: | Senior Project Engineer | Delivery Manager |  |  | Delivery Manager
|  |  | Location: |  |  | Date : | 2025-05-28 | Date : |  | 2025-05-28 | Date : |  | 2025-05-28
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the Melton Hwy/Leakes Rd site | Site Induction Register | Document review | Site induction signed. | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Work pack briefing |  | Prior to Commencing | All personnel on site have been briefed on the relevant work park relating to scope of works. | WP | Document Review | Work pack signed. | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | Prior to commencing | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Confirm understanding of current Environment Management Plan (CEMP) related to the work area and that all prescribed environemental controls are in place |  | Prior to Commencing | All personnel on site have been inducted and briefed on the requirements of the CEMP. All environmental measures including sediment and erosion control to be implemented as per current CEMP. | CEMP | Document review & Site inspection | Signed ITP | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.5 | Traffic Management |  | Prior to Commencing Work | Approved TMP and MOA in place. Traffic management implentation is inpected and verified to be fit for purpose | Approved MOA | Document review & Site inspection | Approved MOA / Superintendents Correspondence | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.6 | Lift plan |  | Prior to Commencing Work | Ensure that a lift plan has been prepared for the works and covers the lifting capacity required for the barriers | Lift Plan | Document Review | Signed ITP | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.6 | Light towers |  | Prior to Commencing Work | Ensure light towers have been procured and set up to adequately light up the work site at night | WP | Visual Inspection | Signed ITP | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.7 | Availability of water |  | Prior to Commencing Work | Ensure that a watercart or connection to water has been sourced, so that the crash cushions can be filled with water | WP | Visual Inspection | Signed ITP | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.8 | Procurement of barriers |  | Prior to Commencing Work | Ensure that all required concete barriers have been delivered to site and inspected to be in adequate condition | WP | Visual Inspection | Signed ITP | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.9 | Procurement of end treatments |  | Prior to Commencing Work | Ensure that adequate end treatment cushions have been procured, as well as all required fixings and connections | WP | Document Review | Superintendents Correspondence | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.1 | Certificate of Compliance |  | Prior to Fabrication | Manufacturers Certificate of compliance for all precast concrete barriers demonstrating structural adequacy for the specified MASH level and compliance to project specification design requirements by a suitably qualified structural engineer. | WP | Document Review | Certificate of Compliance | IP | Site Engineer / Site Foreman | N/A |  | N/A
2 | Installation
2.1 | Prelifting Check |  | Prior to Work Commencement | Before lifting barriers, inspect that the lifing points for wear, corrosion or cracking | WP | Site inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.2 | Set out of Barriers |  | Prior to Work Commencement | Ensure that the location of the barriers has been marked on site in accordance with the traffic barrier detailed installation design | WP | Site inspection | This ITP Signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.3 | Placing barriers |  | Each Lot | Barrier are placed in correct alignment in position shown on installation drawings. Check the end of each barrier to ensure that they are correctly orientated and secured so that they lock in to place. The coupling on the end of the barriers must already be inserted prior to lowering the abutting barrier | WP | Site Inspection | Survey Markups This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.4 | Confirmation of line and level |  | Each Barrier | Alignment should be adjusted where necessary to provide a smooth and even vertical and horizontal alignment. | WP | Survey Check | Survey Conformance Report | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.5 | Installation of end treatments |  | Each Lot | Ensure that the end treatment crash cushions are installed as per the manufacturers specification, and filled with water | WP | Site Inspection | This ITP signed off | IP | Site Engineer / Site Foreman |  |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent