## CRG-FH-ITP-0017
|  |  | Inspection and Test Plan - Underground Stormwater Drainage | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-001
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Pre-Construction Checklist |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  |  |  |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Specifications: |  |  | Position: | Senior Project Engineer |  | Delivery Manager |  |  | Delivery Manager
Structure / Component:
|  |  | Location: |  |  | Date : | 2025-05-05 | Date : | 2025-05-05 |  | Date : | 2025-05-05
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman GPP Coordinator | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Pre-construction Checklist
1.1 | Communication |  | Prior to Commencing Work | Community and emergency services | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.2 | Communication (2) |  | Prior to Commencing Work | Emergency response plan | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.3 | Approved Construction Documentation |  | Prior to Commencing Work | IFC drawings (PDF, hardcopy) | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.4 | Approved Construction Documentation (2) |  | Prior to Commencing Work | Digital (CAD) files for surveyor | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.5 | Approved Construction Documentation (3) |  | Prior to Commencing Work | Budget / Resource arrangement POs (incl. sub-contract agreements) | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.6 | Approved Construction Documentation (4) |  | Prior to Commencing Work | Quantities / Specifications | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.7 | Dilapidation Report (1) |  | Prior to Commencing Work | Residential (ie: structures, access/gate, letterbox, fence) | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.8 | Dilapidation Report (2) |  | Prior to Commencing Work | Business (ie: structures, access/fence/gate, signs/letterbox) | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.9 | Heritage / Cultural listed areas |  | Prior to Commencing Work | No go zones established | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.1 | Protected Environment |  | Prior to Commencing Work | Protected environment flora & fauna identified and workshopped | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.11 | Underground services - DBYD |  | Prior to Commencing Work | DBYD up to date and stored in file | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.12 | Underground services - Service location |  | Prior to Commencing Work | Assess and arrange for Service location | N/A | Document review & Site inspection | This ITP signed | IP | Engineer | N/A |  | N/A
1.13 | Underground services - Excavation permit |  | Prior to Commencing Work | Excavation permit implemented and all personnel signed on | N/A | Document review & Site inspection | This ITP signed | IP | Engineer | N/A |  | N/A
2 | Precommencement Checklist
2.1 | Traffic Management - VMS Boards |  | Prior to Commencing Work | VMS boards implemented | N/A | Document Review | This ITP signed | HP* | Engineer / Foreman | N/A |  | N/A
2.2 | Traffic Management - TMP |  | Prior to Commencing Work | TGS, TMP and MOA approved | N/A | Document review & Site inspection | This ITP signed | HP* | Engineer / GPP Coordinator | N/A |  | N/A
2.3 | Site Demarcation |  | Prior to Commencing Work | Litmit of works and control points implemented | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
2.4 | Utilites clash assesment |  | Prior to Commencing Work | Clash assessment of all services with construction activities | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
2.5 | Review of SWMS |  | Prior to Commencing Work | SWMS reviewed and communicated with personnel | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
2.6 | Site Access |  | Prior to Commencing Work | Vehicle movement plan implemented | N/A | Document review & Site inspection | This ITP signed | IP | Engineer | N/A |  | N/A
2.7 | Site establishment |  | Prior to Commencing Work | Site compound, site parking, material stockpile areas established | N/A | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent
#